## Cover
Jobber to Google Workspace and QuickBooks Online migration (commercial cleaning)
Work sample: realistic data, built to show how I approach this work.
Scenario | Melbourne commercial cleaning business leaving Jobber before its 15 Feb 2027 renewal: rosters to Google Calendar, files to Google Drive, billing to QBO recurring invoices
Inputs | Jobber clients, properties, recurring jobs, team, visits and invoices; QBO customers, recurring templates and invoices (Aug-Oct 2026)
Outputs | Customer, property and template matching, a rate reconciliation, a 3-month billing check, a calendar build (.ics per cleaner), a Drive plan and gated cutover waves
How to use | Every status, gate and total is a formula. Change a rate, a template or a cleaner on a data tab and Rate Reconciliation, Cutover Waves and Controls update.
Sheets
Dashboard | Headline figures, every one a formula over the tabs below
Data Profile | What the exports look like before any change
Jobber Clients | Jobber client export
Jobber Properties | Jobber property export (notes as exported, codes included)
Jobber Jobs | All recurring jobs with the monthly billing basis and weekly hours as formulas
Jobber Invoices | Jobber invoices Aug-Oct 2026
Jobber Visits | Visit history Aug-Oct 2026
QBO Customers | QBO customers and sub-customers (locations)
QBO Templates | QBO recurring invoice templates, each mapped to its Jobber job by formula
QBO Invoices | QBO invoices Aug-Oct 2026
Customer Match | Each QBO parent customer matched to a Jobber client
Property Match | Each QBO sub-customer matched to a Jobber property
Template Match | Each QBO template matched to a Jobber job
Rate Reconciliation | One row per job (and per QBO-only template): status worked out by formula
Actions | What to do for each status, and who does it
Billing Check | What should have been billed per job per month vs both systems
Roster Clashes | Same cleaner, same day, overlapping times
Cleaner Load | Rostered vs contracted hours
Access Notes | Codes pulled out of property notes; what goes into the calendar
Calendar Build | One Google Calendar recurring event per active job
Drive Folders | Client / location / subfolder plan with sharing
Drive Permissions | Who sees which subfolder
Cutover Waves | Pilot + 4 regional waves, gates G1-G6 counted by formula
Exceptions | Everything that needs a person, with owner and status
Controls | Formula checks, all must PASS
Test Log | Engine regression and scenario tests

## Dashboard
Dashboard (all formulas)
Work sample: realistic data, built to show how I approach this work.
Area | Measure | Value
Scope | Active recurring jobs | 339
Scope | Locations | 252
Scope | Cleaners | 60
Matching | QBO parents matched to a Jobber client | 168
Matching | QBO duplicate parents to merge | 10
Matching | Templates matched to a job | 283
Rates | Jobs matched (move as is) | 195
Rates | Jobs needing a billing fix | 157
Rates | Monthly under-billing to fix (rate + basis) | 2323.02
Billing Aug-Oct | Over-billed (credits owed) | 73774.99
Billing Aug-Oct | Under-billed (to invoice) | 24094.07
Billing Aug-Oct | Of which double-billed by Jobber and QBO | 42156.02
Roster | Roster clashes | 11
Roster | Cleaners over contracted hours | 4
Calendar | Recurring events built | 339
Calendar | Access codes moved out of notes | 66
Calendar | Events with a code in the text | 0
Drive | Folders planned | 1670
Cutover | Gates blocked (all waves) | 20
Cutover | Pilot gates passed (of 6) | 6
Exceptions | Open exceptions | 178
Controls | Controls passed | 32

## Data Profile
Data profile (before any change)
Work sample: realistic data, built to show how I approach this work.
Measure | Value
Jobber clients | 158
Jobber properties (locations) | 252
Jobber recurring jobs | 363
active | 339
archived | 24
weekly / 4-weekly / monthly | 276 / 66 / 21
active jobs invoiced by Jobber | 77
Cleaners | 60
Visits Aug-Oct | 7313
skipped | 145
Jobber invoices Aug-Oct | 231
QBO customers + sub-customers | 420
parents | 168
QBO recurring templates | 289
active templates | 289
QBO invoices Aug-Oct | 884
Property notes holding an access code | 66
Weekly templates on the x4 basis (not 52/12) | 19

## Jobber Clients
Jobber clients (export)
Work sample: realistic data, built to show how I approach this work.
Client ID | Company | Email | Phone | Locations
JC0001 | Oakwood Vet Clinic | accounts@oakwoodvetclinic.example | 03 9846 1248 | 2
JC0002 | Clearwater Dental Pty Ltd | accounts@clearwaterdental.example | 03 9205 5937 | 1
JC0003 | Riverside Insurance Brokers Pty Ltd | accounts@riversideinsuran.example | 03 9441 4979 | 1
JC0004 | Ironbark Pathology Pty Ltd | accounts@ironbarkpatholog.example | 03 9663 1439 | 1
JC0005 | Westend Fitness Pty Ltd | accounts@westendfitness.example | 03 9994 6303 | 1
JC0006 | Redgum Dental | accounts@redgumdental.example | 03 9431 2098 | 2
JC0007 | Elm Street Physiotherapy | accounts@elmstreetphysiot.example | 03 9491 2610 | 2
JC0008 | Wattle Grove Property Group | accounts@wattlegroveprope.example | 03 9997 1472 | 1
JC0009 | Hillcrest Physiotherapy Pty Ltd | accounts@hillcrestphysiot.example | 03 9710 3126 | 2
JC0010 | Kingsley Real Estate | accounts@kingsleyrealesta.example | 03 9488 7364 | 2
JC0011 | Wattle Grove Medical Centre Pty Ltd | accounts@wattlegrovemedic.example | 03 9338 5153 | 1
JC0012 | Bluestone Engineering | accounts@bluestoneenginee.example | 03 9473 7117 | 1
JC0013 | Clearwater Insurance Brokers Pty Ltd | accounts@clearwaterinsura.example | 03 9684 5770 | 1
JC0014 | Redgum Optometrists Pty Ltd | accounts@redgumoptometris.example | 03 9271 3810 | 1
JC0015 | Northside Accountants Pty Ltd | accounts@northsideaccount.example | 03 9294 2950 | 3
JC0016 | Oakwood Accountants Pty Ltd | accounts@oakwoodaccountan.example | 03 9453 5962 | 1
JC0017 | Northside Engineering Pty Ltd | accounts@northsideenginee.example | 03 9781 1302 | 4
JC0018 | Ashwood Early Learning | accounts@ashwoodearlylear.example | 03 9474 3215 | 1
JC0019 | Silverton Pharmacy | accounts@silvertonpharmac.example | 03 9205 1377 | 4
JC0020 | Brightside Podiatry | accounts@brightsidepodiat.example | 03 9669 7410 | 1
JC0021 | Ashwood Optometrists | accounts@ashwoodoptometri.example | 03 9110 1012 | 2
JC0022 | Parkside Accountants | accounts@parksideaccounta.example | 03 9957 6898 | 2
JC0023 | Brightside Motors Pty Ltd | accounts@brightsidemotors.example | 03 9895 8035 | 1
JC0024 | Westend Motors Pty Ltd | accounts@westendmotors.example | 03 9471 6043 | 3
JC0025 | Oakwood Lawyers Pty Ltd | accounts@oakwoodlawyers.example | 03 9708 6656 | 2
JC0026 | Riverside Medical Centre | accounts@riversidemedical.example | 03 9458 7586 | 1
JC0027 | Riverside Motors Pty Ltd | accounts@riversidemotors.example | 03 9363 3269 | 1
JC0028 | Parkside Pathology Pty Ltd | accounts@parksidepatholog.example | 03 9493 6157 | 1
JC0029 | Sunbury Accountants Pty Ltd | accounts@sunburyaccountan.example | 03 9854 9287 | 1
JC0030 | Sunbury Early Learning | accounts@sunburyearlylear.example | 03 9854 6755 | 1
JC0031 | Silverton Lawyers Pty Ltd | accounts@silvertonlawyers.example | 03 9367 6420 | 1
JC0032 | Waverley Accountants Pty Ltd | accounts@waverleyaccounta.example | 03 9801 9174 | 1
JC0033 | Westend Podiatry | accounts@westendpodiatry.example | 03 9884 3084 | 3
JC0034 | Lakeside Engineering Pty Ltd | accounts@lakesideengineer.example | 03 9603 1755 | 2
JC0035 | Kingsley Financial Planning | accounts@kingsleyfinancia.example | 03 9651 3633 | 1
JC0036 | Wattle Grove Physiotherapy | accounts@wattlegrovephysi.example | 03 9281 9478 | 1
JC0037 | Elm Street Fitness Pty Ltd | accounts@elmstreetfitness.example | 03 9280 4249 | 2
JC0038 | Wattle Grove Dental | accounts@wattlegrovedenta.example | 03 9198 2208 | 1
JC0039 | Lakeside Vet Clinic | accounts@lakesidevetclini.example | 03 9715 1531 | 2
JC0040 | Clearwater Property Group Pty Ltd | accounts@clearwaterproper.example | 03 9533 6363 | 2
JC0041 | Eastwood Real Estate Pty Ltd | accounts@eastwoodrealesta.example | 03 9537 4230 | 1
JC0042 | Clearwater Physiotherapy | accounts@clearwaterphysio.example | 03 9991 7951 | 2
JC0043 | Greenway Physiotherapy | accounts@greenwayphysioth.example | 03 9830 5565 | 1
JC0044 | Fairfield Engineering Pty Ltd | accounts@fairfieldenginee.example | 03 9528 3462 | 2
JC0045 | Westend Optometrists Pty Ltd | accounts@westendoptometri.example | 03 9515 7657 | 1
JC0046 | Kingsley Insurance Brokers | accounts@kingsleyinsuranc.example | 03 9554 6293 | 2
JC0047 | Bluestone Learning Centre Pty Ltd | accounts@bluestonelearnin.example | 03 9655 3144 | 1
JC0048 | Oakwood Logistics | accounts@oakwoodlogistics.example | 03 9568 7321 | 4
JC0049 | Banksia Insurance Brokers | accounts@banksiainsurance.example | 03 9139 6535 | 1
JC0050 | Sunbury Lawyers Pty Ltd | accounts@sunburylawyers.example | 03 9882 5338 | 3
JC0051 | Cobblestone Real Estate Pty Ltd | accounts@cobblestonereale.example | 03 9102 2312 | 1
JC0052 | Bayview Engineering Pty Ltd | accounts@bayviewengineeri.example | 03 9914 7545 | 1
JC0053 | Oakwood Financial Planning Pty Ltd | accounts@oakwoodfinancial.example | 03 9660 3453 | 1
JC0054 | Brightside Dental Pty Ltd | accounts@brightsidedental.example | 03 9825 9803 | 2
JC0055 | Ashwood Physiotherapy | accounts@ashwoodphysiothe.example | 03 9185 4295 | 4
JC0056 | Bluestone Dental | accounts@bluestonedental.example | 03 9723 3003 | 4
JC0057 | Kingsley Accountants | accounts@kingsleyaccounta.example | 03 9755 5914 | 1
JC0058 | Clearwater Early Learning Pty Ltd | accounts@clearwaterearlyl.example | 03 9270 3586 | 1
JC0059 | Banksia Pathology Pty Ltd | accounts@banksiapathology.example | 03 9505 5479 | 1
JC0060 | Southgate Financial Planning Pty Ltd | accounts@southgatefinanci.example | 03 9262 4160 | 2
JC0061 | Bluestone Lawyers Pty Ltd | accounts@bluestonelawyers.example | 03 9342 7109 | 1
JC0062 | Riverside Lawyers Pty Ltd | accounts@riversidelawyers.example | 03 9216 9903 | 1
JC0063 | Banksia Accountants | accounts@banksiaaccountan.example | 03 9991 2480 | 3
JC0064 | Ironbark Physiotherapy Pty Ltd | accounts@ironbarkphysioth.example | 03 9151 9406 | 2
JC0065 | Wattle Grove Lawyers Pty Ltd | accounts@wattlegrovelawye.example | 03 9829 7525 | 1
JC0066 | Kingsley Medical Centre Pty Ltd | accounts@kingsleymedicalc.example | 03 9447 6037 | 2
JC0067 | Ashwood Engineering | accounts@ashwoodengineeri.example | 03 9883 7986 | 1
JC0068 | Sunbury Physiotherapy Pty Ltd | accounts@sunburyphysiothe.example | 03 9828 4315 | 3
JC0069 | Eastwood Pathology | accounts@eastwoodpatholog.example | 03 9678 4837 | 1
JC0070 | Waverley Fitness Pty Ltd | accounts@waverleyfitness.example | 03 9215 4171 | 2
JC0071 | Clearwater Logistics | accounts@clearwaterlogist.example | 03 9711 9049 | 1
JC0072 | Wattle Grove Fitness | accounts@wattlegrovefitne.example | 03 9383 6207 | 2
JC0073 | Ashwood Medical Centre | accounts@ashwoodmedicalce.example | 03 9363 6931 | 1
JC0074 | Parkside Vet Clinic | accounts@parksidevetclini.example | 03 9758 8406 | 1
JC0075 | Wattle Grove Architects | accounts@wattlegrovearchi.example | 03 9965 5447 | 1
JC0076 | Bayview Pharmacy Pty Ltd | accounts@bayviewpharmacy.example | 03 9972 5397 | 1
JC0077 | Hillcrest Accountants | accounts@hillcrestaccount.example | 03 9225 8337 | 1
JC0078 | Lakeside Architects | accounts@lakesidearchitec.example | 03 9413 7109 | 2
JC0079 | Ashwood Accountants | accounts@ashwoodaccountan.example | 03 9529 1030 | 1
JC0080 | Westend Property Group | accounts@westendpropertyg.example | 03 9300 2703 | 1
JC0081 | Eastwood Optometrists | accounts@eastwoodoptometr.example | 03 9571 3270 | 2
JC0082 | Westend Medical Centre | accounts@westendmedicalce.example | 03 9315 2534 | 1
JC0083 | Riverside Learning Centre | accounts@riversidelearnin.example | 03 9441 3386 | 3
JC0084 | Silverton Insurance Brokers Pty Ltd | accounts@silvertoninsuran.example | 03 9652 6015 | 3
JC0085 | Greenway Podiatry Pty Ltd | accounts@greenwaypodiatry.example | 03 9701 1094 | 1
JC0086 | Banksia Logistics | accounts@banksialogistics.example | 03 9423 1117 | 3
JC0087 | Sunbury Architects Pty Ltd | accounts@sunburyarchitect.example | 03 9158 5807 | 1
JC0088 | Cobblestone Physiotherapy Pty Ltd | accounts@cobblestonephysi.example | 03 9418 1169 | 1
JC0089 | Banksia Real Estate | accounts@banksiarealestat.example | 03 9169 2295 | 1
JC0090 | Northside Pathology Pty Ltd | accounts@northsidepatholo.example | 03 9395 6478 | 1
JC0091 | Harbourside Lawyers | accounts@harboursidelawye.example | 03 9296 5493 | 1
JC0092 | Kingsley Fitness Pty Ltd | accounts@kingsleyfitness.example | 03 9494 9539 | 1
JC0093 | Lakeside Optometrists | accounts@lakesideoptometr.example | 03 9783 4757 | 1
JC0094 | Southgate Dental | accounts@southgatedental.example | 03 9625 1908 | 1
JC0095 | Sunbury Optometrists | accounts@sunburyoptometri.example | 03 9354 3305 | 1
JC0096 | Bayview Vet Clinic | accounts@bayviewvetclinic.example | 03 9597 4808 | 2
JC0097 | Redgum Pathology Pty Ltd | accounts@redgumpathology.example | 03 9380 9429 | 1
JC0098 | Greenway Medical Centre Pty Ltd | accounts@greenwaymedicalc.example | 03 9643 5022 | 1
JC0099 | Westend Physiotherapy | accounts@westendphysiothe.example | 03 9522 6566 | 1
JC0100 | Riverside Podiatry | accounts@riversidepodiatr.example | 03 9241 2735 | 2
JC0101 | Northside Learning Centre | accounts@northsidelearnin.example | 03 9681 6074 | 1
JC0102 | Harbourside Logistics Pty Ltd | accounts@harboursidelogis.example | 03 9386 7682 | 2
JC0103 | Redgum Podiatry | accounts@redgumpodiatry.example | 03 9194 5182 | 2
JC0104 | Harbourside Chiropractic | accounts@harboursidechiro.example | 03 9986 2025 | 3
JC0105 | Hillcrest Lawyers | accounts@hillcrestlawyers.example | 03 9136 6672 | 2
JC0106 | Silverton Logistics Pty Ltd | accounts@silvertonlogisti.example | 03 9683 3308 | 2
JC0107 | Hillcrest Motors Pty Ltd | accounts@hillcrestmotors.example | 03 9908 9466 | 1
JC0108 | Southgate Pathology | accounts@southgatepatholo.example | 03 9850 7425 | 3
JC0109 | Westend Engineering | accounts@westendengineeri.example | 03 9746 4516 | 2
JC0110 | Lakeside Real Estate Pty Ltd | accounts@lakesiderealesta.example | 03 9311 9802 | 3
JC0111 | Harbourside Pharmacy Pty Ltd | accounts@harboursidepharm.example | 03 9644 3252 | 2
JC0112 | Brightside Early Learning Pty Ltd | accounts@brightsideearlyl.example | 03 9602 4655 | 1
JC0113 | Southgate Engineering | accounts@southgateenginee.example | 03 9699 7202 | 1
JC0114 | Riverside Dental Pty Ltd | accounts@riversidedental.example | 03 9474 4662 | 1
JC0115 | Bayview Early Learning | accounts@bayviewearlylear.example | 03 9487 5443 | 2
JC0116 | Elm Street Financial Planning Pty Ltd | accounts@elmstreetfinanci.example | 03 9790 8547 | 1
JC0117 | Ashwood Property Group | accounts@ashwoodpropertyg.example | 03 9595 2954 | 1
JC0118 | Northside Early Learning Pty Ltd | accounts@northsideearlyle.example | 03 9155 2124 | 1
JC0119 | Brightside Logistics Pty Ltd | accounts@brightsidelogist.example | 03 9376 7697 | 1
JC0120 | Elm Street Early Learning | accounts@elmstreetearlyle.example | 03 9110 7711 | 3
JC0121 | Redgum Financial Planning | accounts@redgumfinancialp.example | 03 9602 5499 | 2
JC0122 | Lakeside Fitness Pty Ltd | accounts@lakesidefitness.example | 03 9385 8997 | 1
JC0123 | Elm Street Logistics Pty Ltd | accounts@elmstreetlogisti.example | 03 9677 7334 | 3
JC0124 | Lakeside Insurance Brokers | accounts@lakesideinsuranc.example | 03 9176 8567 | 1
JC0125 | Elm Street Pathology Pty Ltd | accounts@elmstreetpatholo.example | 03 9625 1712 | 1
JC0126 | Fairfield Accountants Pty Ltd | accounts@fairfieldaccount.example | 03 9186 5545 | 2
JC0127 | Fairfield Dental | accounts@fairfielddental.example | 03 9525 1988 | 1
JC0128 | Oakwood Medical Centre Pty Ltd | accounts@oakwoodmedicalce.example | 03 9869 3101 | 1
JC0129 | Banksia Architects Pty Ltd | accounts@banksiaarchitect.example | 03 9446 5481 | 1
JC0130 | Ironbark Engineering Pty Ltd | accounts@ironbarkengineer.example | 03 9984 6816 | 2
JC0131 | Wattle Grove Financial Planning | accounts@wattlegrovefinan.example | 03 9593 1519 | 1
JC0132 | Parkside Fitness Pty Ltd | accounts@parksidefitness.example | 03 9504 1496 | 2
JC0133 | Greenway Chiropractic Pty Ltd | accounts@greenwaychiropra.example | 03 9102 7631 | 3
JC0134 | Bayview Real Estate Pty Ltd | accounts@bayviewrealestat.example | 03 9781 4705 | 1
JC0135 | Riverside Pharmacy | accounts@riversidepharmac.example | 03 9349 9198 | 2
JC0136 | Elm Street Chiropractic Pty Ltd | accounts@elmstreetchiropr.example | 03 9278 1410 | 2
JC0137 | Ironbark Real Estate Pty Ltd | accounts@ironbarkrealesta.example | 03 9263 1896 | 2
JC0138 | Elm Street Motors | accounts@elmstreetmotors.example | 03 9118 2051 | 2
JC0139 | Sunbury Engineering | accounts@sunburyengineeri.example | 03 9196 1339 | 1
JC0140 | Ashwood Dental Pty Ltd | accounts@ashwooddental.example | 03 9390 9330 | 2
JC0141 | Bluestone Early Learning Pty Ltd | accounts@bluestoneearlyle.example | 03 9659 8895 | 2
JC0142 | Harbourside Property Group | accounts@harboursideprope.example | 03 9228 5917 | 1
JC0143 | Riverside Engineering Pty Ltd | accounts@riversideenginee.example | 03 9692 8820 | 1
JC0144 | Ashwood Lawyers | accounts@ashwoodlawyers.example | 03 9170 9631 | 1
JC0145 | Bayview Fitness Pty Ltd | accounts@bayviewfitness.example | 03 9624 9058 | 1
JC0146 | Ironbark Property Group Pty Ltd | accounts@ironbarkproperty.example | 03 9733 2721 | 2
JC0147 | Oakwood Engineering | accounts@oakwoodengineeri.example | 03 9772 9073 | 1
JC0148 | Waverley Physiotherapy Pty Ltd | accounts@waverleyphysioth.example | 03 9906 7928 | 3
JC0149 | Harbourside Insurance Brokers Pty Ltd | accounts@harboursideinsur.example | 03 9518 9233 | 1
JC0150 | Harbourside Real Estate | accounts@harboursidereale.example | 03 9139 4179 | 2
JC0151 | Eastwood Podiatry | accounts@eastwoodpodiatry.example | 03 9414 1925 | 1
JC0152 | Cityside Real Estate | accounts@citysiderealesta.example | 03 9344 5036 | 2
JC0153 | Parkside Dental | accounts@parksidedental.example | 03 9336 6335 | 1
JC0154 | Parkside Dental Group | accounts@parksidedentalgr2.example | 03 9103 5012 | 1
JC0155 | Northside Physiotherapy | accounts@northsidephysiot.example | 03 9580 3636 | 2
JC0156 | North Side Physiotherapy | accounts@northsidephysiot2.example | 03 9831 8934 | 2
JC0157 | Bayview Accountants | accounts@bayviewaccountan.example | 03 9123 2588 | 1
JC0158 | Bay View Accountants | accounts@bayviewaccountan2.example | 03 9279 4434 | 1

## Jobber Properties
Jobber properties (export; notes as exported)
Work sample: realistic data, built to show how I approach this work.
Property ID | Client ID | Location | Street | Suburb | Region | Notes (as exported) | Code found | Jobs
JP0001 | JC0001 | Main office | 218 High Road | Bentleigh | South | Code for roller door: 239883; Bins out on Tuesday night | 1 | 2
JP0002 | JC0001 | Clinic | 162 Station Parade | Oakleigh | South | Alarm 955049 then press OFF | 1 | 2
JP0003 | JC0002 | Main office | 273 Albert Road | Deer Park | West | Level 3, lift to the left | 0 | 1
JP0004 | JC0003 | Main office | 59 Station Parade | Bundoora | North |  | 0 | 2
JP0005 | JC0004 | Main office | 224 Ballarat Parade | Footscray | West | Park in bay 12 under the building | 0 | 1
JP0006 | JC0005 | Main office | 77 Ballarat Parade | Brighton | South |  | 0 | 1
JP0007 | JC0006 | Main office | 290A Ballarat Highway | Bundoora | North | Level 3, lift to the left | 0 | 1
JP0008 | JC0006 | Clinic | 359 Glenferrie Avenue | Werribee | West |  | 0 | 1
JP0009 | JC0007 | Main office | 315 Park Parade | Oakleigh | South |  | 0 | 1
JP0010 | JC0007 | Clinic | 359 Albert Street | Point Cook | West | Do not use bleach on the timber floor | 0 | 2
JP0011 | JC0008 | Main office | 169 King Street | Hawthorn | East | Call 0400 000 000 if the door is locked | 0 | 2
JP0012 | JC0009 | Main office | 396 Park Highway | Epping | North | Store room on level 1, room 104 | 0 | 1
JP0013 | JC0009 | Clinic | 214A Nepean Parade | Thornbury | North | Store room on level 1, room 104 | 0 | 1
JP0014 | JC0010 | Main office | 208 Main Avenue | Mitcham | East |  | 0 | 1
JP0015 | JC0010 | Clinic | 208 High Avenue | Kew | East | Alarm code 505699#, panel behind reception door | 1 | 1
JP0016 | JC0011 | Main office | 462 Mason Road | Clayton | South | Code for roller door: 715696 | 1 | 1
JP0017 | JC0012 | Main office | 201 Plenty Avenue | Coburg | North | Key safe at side gate, code 412618 | 1 | 1
JP0018 | JC0013 | Main office | 164 Whitehorse Street | Mentone | South | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0019 | JC0014 | Main office | 480 King Avenue | Camberwell | East | Bins out on Tuesday night | 0 | 2
JP0020 | JC0015 | Main office | 426 Mason Street | Cheltenham | South | Sign in at security desk | 0 | 2
JP0021 | JC0015 | Clinic | 351 Burke Road | Oakleigh | South | Vacuum bags in cupboard 2 | 0 | 1
JP0022 | JC0015 | Warehouse | 354 High Street | Clayton | South | Store room on level 1, room 104 | 0 | 1
JP0023 | JC0016 | Main office | 54 Mason Parade | Reservoir | North | Park in bay 12 under the building | 0 | 2
JP0024 | JC0017 | Main office | 430 Victoria Road | St Kilda | South | Alarm 377298 then press OFF; Sign in at security desk | 1 | 2
JP0025 | JC0017 | Clinic | 195/12 Railway Highway | Bentleigh | South | Kitchen: 2 fridges, empty on Fridays | 0 | 2
JP0026 | JC0017 | Warehouse | 10 Queen Highway | Deer Park | West | Do not use bleach on the timber floor | 0 | 1
JP0027 | JC0017 | Showroom | 17 Park Avenue | St Kilda | South | Alarm code 735166#, panel behind reception door; Park in bay 12 under the building | 1 | 1
JP0028 | JC0018 | Main office | 378 Plenty Street | Camberwell | East | Sign in at security desk | 0 | 2
JP0029 | JC0019 | Main office | 266 Union Avenue | Point Cook | West |  | 0 | 1
JP0030 | JC0019 | Clinic | 98 Park Road | Kew | East | Call 0400 000 000 if the door is locked | 0 | 1
JP0031 | JC0019 | Warehouse | 107 Barkly Highway | Bundoora | North | Bins out on Tuesday night | 0 | 1
JP0032 | JC0019 | Showroom | 298 Main Road | Footscray | West | Alarm code 116347#, panel behind reception door | 1 | 2
JP0033 | JC0020 | Main office | 142 Plenty Road | Camberwell | East | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0034 | JC0021 | Main office | 195 Nicholson Road | Ringwood | East | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0035 | JC0021 | Clinic | 245 Ballarat Avenue | Ringwood | East |  | 0 | 2
JP0036 | JC0022 | Main office | 22 Hopkins Road | Bundoora | North | Bins out on Tuesday night | 0 | 1
JP0037 | JC0022 | Clinic | 356 Albert Avenue | Northcote | North | Bins out on Tuesday night | 0 | 2
JP0038 | JC0023 | Main office | 364/12 High Road | Heidelberg | North | Store room on level 1, room 104 | 0 | 1
JP0039 | JC0024 | Main office | 417 Main Road | Sunshine | West | Call 0400 000 000 if the door is locked | 0 | 1
JP0040 | JC0024 | Clinic | 37 Nicholson Highway | Williamstown | West | Lockbox on meter box, 30137; Reception closes 5:30 pm, use the side entry | 1 | 1
JP0041 | JC0024 | Warehouse | 117 Railway Highway | Epping | North | Back door keypad 35089* | 1 | 1
JP0042 | JC0025 | Main office | 453 Plenty Parade | Moorabbin | South |  | 0 | 2
JP0043 | JC0025 | Clinic | 188 Nicholson Road | Essendon | North | Alarm 80204 then press OFF; Vacuum bags in cupboard 2 | 1 | 1
JP0044 | JC0026 | Main office | 300 Sydney Highway | Camberwell | East |  | 0 | 1
JP0045 | JC0027 | Main office | 205 Railway Street | Altona | West | Call 0400 000 000 if the door is locked | 0 | 1
JP0046 | JC0028 | Main office | 359 King Road | Yarraville | West | Park in bay 12 under the building | 0 | 1
JP0047 | JC0029 | Main office | 313A Queen Street | Camberwell | East | Park in bay 12 under the building | 0 | 1
JP0048 | JC0030 | Main office | 386 Nepean Road | Glen Waverley | East | Call 0400 000 000 if the door is locked | 0 | 1
JP0049 | JC0031 | Main office | 255 Glenferrie Parade | Thornbury | North | Alarm code 922787#, panel behind reception door | 1 | 1
JP0050 | JC0032 | Main office | 23A Ballarat Street | Brunswick | North | Bins out on Tuesday night | 0 | 2
JP0051 | JC0033 | Main office | 310 Ballarat Avenue | Brunswick | North | Do not use bleach on the timber floor | 0 | 2
JP0052 | JC0033 | Clinic | 269 Victoria Avenue | Thornbury | North |  | 0 | 2
JP0053 | JC0033 | Warehouse | 332A Glenferrie Parade | Essendon | North | Vacuum bags in cupboard 2 | 0 | 1
JP0054 | JC0034 | Main office | 157 Whitehorse Parade | Deer Park | West |  | 0 | 1
JP0055 | JC0034 | Clinic | 439 Sydney Parade | Maribyrnong | West | Do not use bleach on the timber floor | 0 | 1
JP0056 | JC0035 | Main office | 204 Bridge Highway | Oakleigh | South | Store room on level 1, room 104 | 0 | 1
JP0057 | JC0036 | Main office | 48 Ballarat Parade | Cheltenham | South | Do not use bleach on the timber floor | 0 | 1
JP0058 | JC0037 | Main office | 479 Mason Parade | Hawthorn | East | Back door keypad 411528*; Kitchen: 2 fridges, empty on Fridays | 1 | 2
JP0059 | JC0037 | Clinic | 450 King Road | Doncaster | East | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0060 | JC0038 | Main office | 259 Union Avenue | Hawthorn | East | Alarm 820930 then press OFF; Store room on level 1, room 104 | 1 | 1
JP0061 | JC0039 | Main office | 426 Ballarat Parade | Point Cook | West | Park in bay 12 under the building | 0 | 1
JP0062 | JC0039 | Clinic | 164 Nicholson Street | Laverton | West |  | 0 | 2
JP0063 | JC0040 | Main office | 143/12 Nepean Street | Frankston | South |  | 0 | 3
JP0064 | JC0040 | Clinic | 380 Nepean Parade | Laverton | West | Kitchen: 2 fridges, empty on Fridays | 0 | 2
JP0065 | JC0041 | Main office | 296 Barkly Highway | Hawthorn | East | Park in bay 12 under the building | 0 | 3
JP0066 | JC0042 | Main office | 46 Main Avenue | Bentleigh | South | Bins out on Tuesday night | 0 | 3
JP0067 | JC0042 | Clinic | 211 Union Road | Burwood | East | Code for roller door: 41503 | 1 | 1
JP0068 | JC0043 | Main office | 418 Nicholson Avenue | Burwood | East | Store room on level 1, room 104 | 0 | 1
JP0069 | JC0044 | Main office | 43 Plenty Avenue | Bentleigh | South | Bins out on Tuesday night | 0 | 1
JP0070 | JC0044 | Clinic | 27 Railway Avenue | Cheltenham | South | Lockbox on meter box, 141840 | 1 | 2
JP0071 | JC0045 | Main office | 225/12 Glenferrie Parade | Mentone | South |  | 0 | 1
JP0072 | JC0046 | Main office | 225 Park Avenue | Reservoir | North |  | 0 | 4
JP0073 | JC0046 | Clinic | 410 Burke Highway | Point Cook | West | Back door keypad 445327*; Park in bay 12 under the building | 1 | 2
JP0074 | JC0047 | Main office | 205 Burke Highway | Glen Waverley | East | Bins out on Tuesday night | 0 | 2
JP0075 | JC0048 | Main office | 189 Union Highway | Hawthorn | East | Key safe at side gate, code 582945; Reception closes 5:30 pm, use the side entry | 1 | 2
JP0076 | JC0048 | Clinic | 128 Victoria Road | Blackburn | East | Vacuum bags in cupboard 2 | 0 | 1
JP0077 | JC0048 | Warehouse | 375 Station Highway | Cheltenham | South | Alarm code 686667#, panel behind reception door | 1 | 2
JP0078 | JC0048 | Showroom | 378 Burke Highway | Box Hill | East | Level 3, lift to the left | 0 | 1
JP0079 | JC0049 | Main office | 185 Church Parade | Burwood | East | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0080 | JC0050 | Main office | 115 Nepean Parade | Reservoir | North | Park in bay 12 under the building | 0 | 1
JP0081 | JC0050 | Clinic | 96A Glenferrie Parade | Essendon | North | Back door keypad 706889*; Sign in at security desk | 1 | 2
JP0082 | JC0050 | Warehouse | 158 Station Street | Mentone | South | Store room on level 1, room 104 | 0 | 1
JP0083 | JC0051 | Main office | 476 Sydney Highway | Frankston | South | Do not use bleach on the timber floor | 0 | 1
JP0084 | JC0052 | Main office | 436/12 Nepean Highway | Sunshine | West | Call 0400 000 000 if the door is locked | 0 | 1
JP0085 | JC0053 | Main office | 394 Ballarat Avenue | Brighton | South | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0086 | JC0054 | Main office | 135 Victoria Parade | Dandenong | South | Level 3, lift to the left | 0 | 1
JP0087 | JC0054 | Clinic | 472 Barkly Parade | Moorabbin | South | Reception closes 5:30 pm, use the side entry | 0 | 1
JP0088 | JC0055 | Main office | 151 Nicholson Street | Point Cook | West |  | 0 | 3
JP0089 | JC0055 | Clinic | 4A Gilbert Road | Camberwell | East |  | 0 | 2
JP0090 | JC0055 | Warehouse | 144 Burke Avenue | Coburg | North | Alarm 935781 then press OFF | 1 | 2
JP0091 | JC0055 | Showroom | 182 King Avenue | Footscray | West | Alarm 774460 then press OFF | 1 | 1
JP0092 | JC0056 | Main office | 79/12 Glenferrie Parade | Camberwell | East | Store room on level 1, room 104 | 0 | 1
JP0093 | JC0056 | Clinic | 401 Park Highway | Burwood | East | Store room on level 1, room 104 | 0 | 2
JP0094 | JC0056 | Warehouse | 401 Burke Street | Burwood | East | Call 0400 000 000 if the door is locked | 0 | 1
JP0095 | JC0056 | Showroom | 11 Hopkins Avenue | Ringwood | East | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0096 | JC0057 | Main office | 263 Nepean Highway | Altona | West | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0097 | JC0058 | Main office | 288 Main Highway | Northcote | North |  | 0 | 2
JP0098 | JC0059 | Main office | 459 Park Avenue | Deer Park | West | Level 3, lift to the left | 0 | 1
JP0099 | JC0060 | Main office | 464 Barkly Road | Blackburn | East | Alarm code 37983#, panel behind reception door; Bins out on Tuesday night | 1 | 1
JP0100 | JC0060 | Clinic | 90A Albert Parade | Bentleigh | South | Do not use bleach on the timber floor | 0 | 1
JP0101 | JC0061 | Main office | 29 Burke Parade | Burwood | East |  | 0 | 1
JP0102 | JC0062 | Main office | 23 Station Parade | Glen Waverley | East | Kitchen: 2 fridges, empty on Fridays | 0 | 2
JP0103 | JC0063 | Main office | 251 Union Avenue | Altona | West | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0104 | JC0063 | Clinic | 270 Station Road | Doncaster | East |  | 0 | 2
JP0105 | JC0063 | Warehouse | 463 Gilbert Street | Glen Waverley | East |  | 0 | 1
JP0106 | JC0064 | Main office | 59 King Highway | Point Cook | West | Level 3, lift to the left | 0 | 1
JP0107 | JC0064 | Clinic | 61 Church Street | Point Cook | West | Sign in at security desk | 0 | 2
JP0108 | JC0065 | Main office | 280 Railway Road | Point Cook | West | Do not use bleach on the timber floor | 0 | 2
JP0109 | JC0066 | Main office | 149 Main Road | Point Cook | West | Code for roller door: 142257; Level 3, lift to the left | 1 | 2
JP0110 | JC0066 | Clinic | 313 King Road | Hawthorn | East | Lockbox on meter box, 867918; Vacuum bags in cupboard 2 | 1 | 1
JP0111 | JC0067 | Main office | 155 Hopkins Road | Glen Waverley | East |  | 0 | 1
JP0112 | JC0068 | Main office | 284 Park Parade | Point Cook | West | Code for roller door: 182881; Reception closes 5:30 pm, use the side entry | 1 | 1
JP0113 | JC0068 | Clinic | 85 Nepean Road | Frankston | South | Alarm code 637956#, panel behind reception door; Store room on level 1, room 104 | 1 | 1
JP0114 | JC0068 | Warehouse | 231 Church Highway | Hawthorn | East | Key safe at side gate, code 33491; Park in bay 12 under the building | 1 | 1
JP0115 | JC0069 | Main office | 223A Nicholson Parade | Werribee | West | Alarm 387908 then press OFF | 1 | 2
JP0116 | JC0070 | Main office | 382 Hopkins Street | Footscray | West | Level 3, lift to the left | 0 | 1
JP0117 | JC0070 | Clinic | 443 Station Road | Footscray | West |  | 0 | 1
JP0118 | JC0071 | Main office | 127 Main Highway | Reservoir | North | Code for roller door: 59759; Level 3, lift to the left | 1 | 2
JP0119 | JC0072 | Main office | 68 Church Parade | Essendon | North | Lockbox on meter box, 32434; Sign in at security desk | 1 | 1
JP0120 | JC0072 | Clinic | 102 Union Road | St Kilda | South |  | 0 | 2
JP0121 | JC0073 | Main office | 61 Church Road | Bundoora | North |  | 0 | 2
JP0122 | JC0074 | Main office | 287 Whitehorse Highway | Deer Park | West | Store room on level 1, room 104 | 0 | 1
JP0123 | JC0075 | Main office | 289 Nepean Street | Bentleigh | South | Vacuum bags in cupboard 2 | 0 | 1
JP0124 | JC0076 | Main office | 221 Plenty Avenue | Footscray | West | Sign in at security desk | 0 | 1
JP0125 | JC0077 | Main office | 77 Mason Highway | Mitcham | East |  | 0 | 2
JP0126 | JC0078 | Main office | 170 Railway Highway | Reservoir | North | Do not use bleach on the timber floor | 0 | 1
JP0127 | JC0078 | Clinic | 208 Glenferrie Road | Mitcham | East | Park in bay 12 under the building | 0 | 2
JP0128 | JC0079 | Main office | 212 Sydney Avenue | Yarraville | West | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0129 | JC0080 | Main office | 268 Sydney Road | Heidelberg | North | Back door keypad 595954* | 1 | 2
JP0130 | JC0081 | Main office | 369 Station Road | Burwood | East | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0131 | JC0081 | Clinic | 264 Queen Parade | Mitcham | East | Level 3, lift to the left | 0 | 1
JP0132 | JC0082 | Main office | 130 Barkly Road | Sunshine | West | Level 3, lift to the left | 0 | 1
JP0133 | JC0083 | Main office | 180 Union Avenue | Mentone | South | Do not use bleach on the timber floor | 0 | 1
JP0134 | JC0083 | Clinic | 148 Plenty Street | Cheltenham | South | Park in bay 12 under the building | 0 | 2
JP0135 | JC0083 | Warehouse | 4A Main Highway | Moorabbin | South |  | 0 | 2
JP0136 | JC0084 | Main office | 165 Hopkins Road | Cheltenham | South | Key safe at side gate, code 733532; Sign in at security desk | 1 | 1
JP0137 | JC0084 | Clinic | 245 Victoria Road | Frankston | South |  | 0 | 1
JP0138 | JC0084 | Warehouse | 274 Gilbert Avenue | Glen Waverley | East | Do not use bleach on the timber floor | 0 | 2
JP0139 | JC0085 | Main office | 198 Station Avenue | Burwood | East | Code for roller door: 30177 | 1 | 1
JP0140 | JC0086 | Main office | 387 Burke Parade | Northcote | North | Reception closes 5:30 pm, use the side entry | 0 | 1
JP0141 | JC0086 | Clinic | 467 High Avenue | Northcote | North |  | 0 | 1
JP0142 | JC0086 | Warehouse | 458 Glenferrie Parade | Thornbury | North |  | 0 | 1
JP0143 | JC0087 | Main office | 111A Plenty Street | Epping | North | Lockbox on meter box, 263916 | 1 | 2
JP0144 | JC0088 | Main office | 12 Sydney Road | Bundoora | North | Key safe at side gate, code 250164 | 1 | 1
JP0145 | JC0089 | Main office | 272 Gilbert Street | Maribyrnong | West | Park in bay 12 under the building | 0 | 2
JP0146 | JC0090 | Main office | 416 Park Road | Ringwood | East | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0147 | JC0091 | Main office | 1 Mason Parade | Glen Waverley | East | Store room on level 1, room 104 | 0 | 1
JP0148 | JC0092 | Main office | 460 Sydney Highway | Werribee | West | Lockbox on meter box, 623698 | 1 | 2
JP0149 | JC0093 | Main office | 35 Nepean Avenue | Footscray | West | Store room on level 1, room 104 | 0 | 2
JP0150 | JC0094 | Main office | 271 Victoria Avenue | Hawthorn | East | Code for roller door: 226931 | 1 | 1
JP0151 | JC0095 | Main office | 375 Railway Road | Altona | West |  | 0 | 1
JP0152 | JC0096 | Main office | 186 Sydney Avenue | Coburg | North | Key safe at side gate, code 326061; Vacuum bags in cupboard 2 | 1 | 2
JP0153 | JC0096 | Clinic | 399 Whitehorse Road | Reservoir | North | Vacuum bags in cupboard 2 | 0 | 2
JP0154 | JC0097 | Main office | 453 Railway Parade | Camberwell | East | Back door keypad 64069*; Level 3, lift to the left | 1 | 1
JP0155 | JC0098 | Main office | 326 Main Highway | Glen Waverley | East |  | 0 | 2
JP0156 | JC0099 | Main office | 306 Bridge Road | Glen Waverley | East | Bins out on Tuesday night | 0 | 1
JP0157 | JC0100 | Main office | 79 Ballarat Street | Point Cook | West |  | 0 | 1
JP0158 | JC0100 | Clinic | 145 Church Avenue | Brighton | South | Call 0400 000 000 if the door is locked | 0 | 1
JP0159 | JC0101 | Main office | 190 Nicholson Avenue | Camberwell | East | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0160 | JC0102 | Main office | 387 Barkly Highway | Hawthorn | East | Alarm 702196 then press OFF; Vacuum bags in cupboard 2 | 1 | 1
JP0161 | JC0102 | Clinic | 5 Park Highway | Kew | East | Key safe at side gate, code 63156; Park in bay 12 under the building | 1 | 1
JP0162 | JC0103 | Main office | 204 Mason Parade | Williamstown | West | Level 3, lift to the left | 0 | 2
JP0163 | JC0103 | Clinic | 445 Barkly Avenue | Cheltenham | South | Do not use bleach on the timber floor | 0 | 2
JP0164 | JC0104 | Main office | 151 Glenferrie Highway | Oakleigh | South |  | 0 | 1
JP0165 | JC0104 | Clinic | 284 Mason Highway | Moorabbin | South | Do not use bleach on the timber floor | 0 | 2
JP0166 | JC0104 | Warehouse | 218 Burke Street | St Kilda | South | Park in bay 12 under the building | 0 | 1
JP0167 | JC0105 | Main office | 362 Barkly Avenue | Mentone | South |  | 0 | 1
JP0168 | JC0105 | Clinic | 418 Main Avenue | Northcote | North | Do not use bleach on the timber floor | 0 | 2
JP0169 | JC0106 | Main office | 176 High Highway | Brunswick | North | Back door keypad 306031* | 1 | 2
JP0170 | JC0106 | Clinic | 356 Glenferrie Parade | Frankston | South | Bins out on Tuesday night | 0 | 1
JP0171 | JC0107 | Main office | 64 Glenferrie Parade | Bentleigh | South | Bins out on Tuesday night | 0 | 2
JP0172 | JC0108 | Main office | 433 Mason Parade | Brunswick | North | Alarm 855496 then press OFF; Park in bay 12 under the building | 1 | 1
JP0173 | JC0108 | Clinic | 291 Burke Highway | Hawthorn | East | Alarm code 745388#, panel behind reception door; Bins out on Tuesday night | 1 | 1
JP0174 | JC0108 | Warehouse | 186 Plenty Street | Altona | West | Park in bay 12 under the building | 0 | 2
JP0175 | JC0109 | Main office | 279 Nicholson Avenue | Deer Park | West | Vacuum bags in cupboard 2 | 0 | 1
JP0176 | JC0109 | Clinic | 313 Victoria Road | Reservoir | North | Call 0400 000 000 if the door is locked | 0 | 2
JP0177 | JC0110 | Main office | 44 Nepean Parade | Brunswick | North | Sign in at security desk | 0 | 2
JP0178 | JC0110 | Clinic | 67 Glenferrie Road | Preston | North | Level 3, lift to the left | 0 | 1
JP0179 | JC0110 | Warehouse | 6 Whitehorse Street | Mitcham | East | Lockbox on meter box, 217750 | 1 | 3
JP0180 | JC0111 | Main office | 267 Nepean Street | Yarraville | West | Alarm 749161 then press OFF | 1 | 1
JP0181 | JC0111 | Clinic | 266 Park Road | Williamstown | West | Store room on level 1, room 104 | 0 | 1
JP0182 | JC0112 | Main office | 158 Nepean Avenue | Footscray | West | Level 3, lift to the left | 0 | 1
JP0183 | JC0113 | Main office | 135 Main Avenue | Frankston | South | Alarm 548524 then press OFF | 1 | 1
JP0184 | JC0114 | Main office | 256 Albert Parade | Northcote | North | Do not use bleach on the timber floor | 0 | 2
JP0185 | JC0115 | Main office | 215 Barkly Street | Laverton | West | Key safe at side gate, code 726938 | 1 | 2
JP0186 | JC0115 | Clinic | 329 Station Avenue | Brighton | South | Call 0400 000 000 if the door is locked | 0 | 1
JP0187 | JC0116 | Main office | 462A Victoria Road | Yarraville | West | Reception closes 5:30 pm, use the side entry | 0 | 1
JP0188 | JC0117 | Main office | 248 Sydney Street | Cheltenham | South |  | 0 | 2
JP0189 | JC0118 | Main office | 251 Plenty Highway | Bentleigh | South | Do not use bleach on the timber floor | 0 | 1
JP0190 | JC0119 | Main office | 148 Nepean Street | Bentleigh | South | Alarm 761060 then press OFF; Park in bay 12 under the building | 1 | 1
JP0191 | JC0120 | Main office | 431 Union Avenue | Hawthorn | East | Vacuum bags in cupboard 2 | 0 | 2
JP0192 | JC0120 | Clinic | 356 Main Road | Camberwell | East | Do not use bleach on the timber floor | 0 | 1
JP0193 | JC0120 | Warehouse | 422 Nicholson Parade | Glen Waverley | East | Alarm 676574 then press OFF; Reception closes 5:30 pm, use the side entry | 1 | 3
JP0194 | JC0121 | Main office | 455 Railway Road | Williamstown | West | Level 3, lift to the left | 0 | 1
JP0195 | JC0121 | Clinic | 217 King Street | Epping | North | Park in bay 12 under the building | 0 | 1
JP0196 | JC0122 | Main office | 58 Station Road | Mitcham | East |  | 0 | 1
JP0197 | JC0123 | Main office | 343 Sydney Street | Kew | East | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0198 | JC0123 | Clinic | 399 Plenty Avenue | Ringwood | East | Bins out on Tuesday night | 0 | 1
JP0199 | JC0123 | Warehouse | 256 Station Street | Blackburn | East |  | 0 | 2
JP0200 | JC0124 | Main office | 459 Whitehorse Parade | Sunshine | West | Vacuum bags in cupboard 2 | 0 | 2
JP0201 | JC0125 | Main office | 87 Main Avenue | Maribyrnong | West | Store room on level 1, room 104 | 0 | 2
JP0202 | JC0126 | Main office | 313/12 Union Avenue | Dandenong | South |  | 0 | 1
JP0203 | JC0126 | Clinic | 354 King Avenue | Moorabbin | South |  | 0 | 2
JP0204 | JC0127 | Main office | 122 Main Avenue | Box Hill | East | Sign in at security desk | 0 | 1
JP0205 | JC0128 | Main office | 64 Bridge Street | Coburg | North | Code for roller door: 110533 | 1 | 2
JP0206 | JC0129 | Main office | 213 Church Parade | Frankston | South | Lockbox on meter box, 718011; Do not use bleach on the timber floor | 1 | 1
JP0207 | JC0130 | Main office | 420 Railway Parade | Preston | North | Bins out on Tuesday night | 0 | 1
JP0208 | JC0130 | Clinic | 301 Whitehorse Highway | Thornbury | North |  | 0 | 1
JP0209 | JC0131 | Main office | 294 Victoria Avenue | Northcote | North | Back door keypad 174251*; Store room on level 1, room 104 | 1 | 1
JP0210 | JC0132 | Main office | 81 Nepean Road | Burwood | East | Park in bay 12 under the building | 0 | 1
JP0211 | JC0132 | Clinic | 440 Bridge Street | Maribyrnong | West | Store room on level 1, room 104 | 0 | 2
JP0212 | JC0133 | Main office | 347 High Highway | Ringwood | East | Back door keypad 906773*; Kitchen: 2 fridges, empty on Fridays | 1 | 2
JP0213 | JC0133 | Clinic | 250 Hopkins Highway | Kew | East |  | 0 | 1
JP0214 | JC0133 | Warehouse | 191 Albert Avenue | Burwood | East |  | 0 | 1
JP0215 | JC0134 | Main office | 414 Sydney Avenue | Brighton | South | Reception closes 5:30 pm, use the side entry | 0 | 1
JP0216 | JC0135 | Main office | 472 Hopkins Highway | Box Hill | East | Park in bay 12 under the building | 0 | 1
JP0217 | JC0135 | Clinic | 410 Queen Highway | Glen Waverley | East | Level 3, lift to the left | 0 | 3
JP0218 | JC0136 | Main office | 348 Railway Street | Mentone | South | Park in bay 12 under the building | 0 | 2
JP0219 | JC0136 | Clinic | 4 Sydney Highway | Cheltenham | South | Park in bay 12 under the building | 0 | 3
JP0220 | JC0137 | Main office | 395 Plenty Avenue | Oakleigh | South |  | 0 | 1
JP0221 | JC0137 | Clinic | 32 Park Avenue | Oakleigh | South | Code for roller door: 577595; Level 3, lift to the left | 1 | 1
JP0222 | JC0138 | Main office | 333 Albert Parade | Brighton | South | Call 0400 000 000 if the door is locked | 0 | 1
JP0223 | JC0138 | Clinic | 280 Station Street | Oakleigh | South | Bins out on Tuesday night | 0 | 1
JP0224 | JC0139 | Main office | 87/12 Victoria Road | Point Cook | West | Back door keypad 391094* | 1 | 1
JP0225 | JC0140 | Main office | 241 Mason Road | Northcote | North | Reception closes 5:30 pm, use the side entry | 0 | 1
JP0226 | JC0140 | Clinic | 448 Barkly Avenue | Mentone | South |  | 0 | 1
JP0227 | JC0141 | Main office | 351 High Street | Altona | West | Alarm code 805010#, panel behind reception door; Store room on level 1, room 104 | 1 | 2
JP0228 | JC0141 | Clinic | 477 Hopkins Avenue | Hawthorn | East | Lockbox on meter box, 1172; Do not use bleach on the timber floor | 1 | 3
JP0229 | JC0142 | Main office | 428 Church Parade | Maribyrnong | West | Sign in at security desk | 0 | 3
JP0230 | JC0143 | Main office | 253A Glenferrie Street | Bundoora | North |  | 0 | 1
JP0231 | JC0144 | Main office | 466 Main Street | Werribee | West | Store room on level 1, room 104 | 0 | 1
JP0232 | JC0145 | Main office | 367 Station Parade | Thornbury | North | Lockbox on meter box, 46490; Kitchen: 2 fridges, empty on Fridays | 1 | 1
JP0233 | JC0146 | Main office | 266/12 Albert Avenue | Mitcham | East | Code for roller door: 176058; Bins out on Tuesday night | 1 | 1
JP0234 | JC0146 | Clinic | 479 Burke Road | Reservoir | North | Do not use bleach on the timber floor | 0 | 2
JP0235 | JC0147 | Main office | 216 Plenty Road | Burwood | East | Do not use bleach on the timber floor | 0 | 2
JP0236 | JC0148 | Main office | 42 Queen Avenue | Bentleigh | South |  | 0 | 2
JP0237 | JC0148 | Clinic | 438 Church Highway | Bentleigh | South | Lockbox on meter box, 432357 | 1 | 2
JP0238 | JC0148 | Warehouse | 337 Plenty Parade | St Kilda | South | Do not use bleach on the timber floor | 0 | 1
JP0239 | JC0149 | Main office | 314 Plenty Street | Northcote | North | Bins out on Tuesday night | 0 | 1
JP0240 | JC0150 | Main office | 121 High Parade | Glen Waverley | East |  | 0 | 1
JP0241 | JC0150 | Clinic | 317 Victoria Parade | Clayton | South | Sign in at security desk | 0 | 1
JP0242 | JC0151 | Main office | 273/12 Plenty Parade | Coburg | North | Lockbox on meter box, 536963; Do not use bleach on the timber floor | 1 | 1
JP0243 | JC0152 | Main office | 200 Nepean Avenue | Moorabbin | South | Vacuum bags in cupboard 2 | 0 | 1
JP0244 | JC0152 | Clinic | 455 Nicholson Highway | Moorabbin | South | Level 3, lift to the left | 0 | 2
JP0245 | JC0153 | Main office | 400 Albert Street | Mentone | South | Reception closes 5:30 pm, use the side entry | 0 | 2
JP0246 | JC0154 | Main office | 257 Hopkins Parade | Point Cook | West | Kitchen: 2 fridges, empty on Fridays | 0 | 1
JP0247 | JC0155 | Main office | 139 Glenferrie Parade | Brighton | South | Alarm 435194 then press OFF | 1 | 1
JP0248 | JC0155 | Clinic | 250 Bridge Highway | Werribee | West | Vacuum bags in cupboard 2 | 0 | 1
JP0249 | JC0156 | Main office | 284A Park Road | Point Cook | West | Key safe at side gate, code 607781; Call 0400 000 000 if the door is locked | 1 | 2
JP0250 | JC0156 | Clinic | 163 Barkly Highway | Essendon | North |  | 0 | 1
JP0251 | JC0157 | Main office | 448 Nicholson Street | Kew | East | Park in bay 12 under the building | 0 | 1
JP0252 | JC0158 | Main office | 360 Burke Street | Maribyrnong | West | Key safe at side gate, code 480576 | 1 | 1

## Jobber Jobs
Jobber recurring jobs (export) with billing basis
Work sample: realistic data, built to show how I approach this work.
Job | Property | Client | Location | Service | Frequency | Visits/wk | Days | Start | Hours | Cleaner | Rate | Billing | Invoicing | Status | First visit | Monthly basis | Avg weekly hours | Wave
J1001 | JP0001 | Oakwood Vet Clinic | Main office - Bentleigh | Office clean | Weekly | 1 | TU | 05:30 | 2 | CL43 | 127 | Per visit, billed monthly | Auto | Active | 2026-07-21 | 550.33 | 2 | Wave 3 South
J1002 | JP0002 | Oakwood Vet Clinic | Clinic - Oakleigh | Kitchen and bathrooms | Weekly | 1 | TU | 05:30 | 1 | CL39 | 58 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 251.33 | 1 | Wave 3 South
J1003 | JP0002 | Oakwood Vet Clinic | Clinic - Oakleigh | Window clean | Every 4 weeks | 0 | MO | 09:00 | 3 | CL59 | 218 | Fixed 4-weekly | Auto | Active | 2026-07-13 | 218 | 0.75 | Wave 3 South
J1004 | JP0003 | Clearwater Dental Pty Ltd | Main office - Deer Park | Kitchen and bathrooms | Weekly | 1 | MO | 05:30 | 1 | CL48 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 307.67 | 1 | Wave 4 West
J1005 | JP0004 | Riverside Insurance Brokers Pty Ltd | Main office - Bundoora | Kitchen and bathrooms | Weekly | 2 | TU WE | 05:30 | 1 | CL37 | 70 | Per visit, billed monthly | Auto | Active | 2026-07-21 | 606.67 | 2 | Wave 1 North
J1006 | JP0004 | Riverside Insurance Brokers Pty Ltd | Main office - Bundoora | Window clean | Every 4 weeks | 0 | TH | 09:00 | 2 | CL60 | 156 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-16 | 156 | 0.5 | Wave 1 North
J1007 | JP0005 | Ironbark Pathology Pty Ltd | Main office - Footscray | Kitchen and bathrooms | Weekly | 2 | MO WE | 05:30 | 1 | CL12 | 69 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 598 | 2 | Wave 4 West
J1008 | JP0006 | Westend Fitness Pty Ltd | Main office - Brighton | Office clean | Weekly | 3 | WE TH FR | 05:30 | 2.5 | CL23 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 2093 | 7.5 | Wave 3 South
J1009 | JP0007 | Redgum Dental | Main office - Bundoora | Office clean | Weekly | 2 | TU WE | 05:30 | 2 | CL13 | 131 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 1135.33 | 4 | Wave 1 North
J1010 | JP0008 | Redgum Dental | Clinic - Werribee | Office clean | Weekly | 2 | TU WE | 05:30 | 3 | CL32 | 204 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-21 | 1768 | 6 | Wave 4 West
J1011 | JP0009 | Elm Street Physiotherapy | Main office - Oakleigh | Office clean | Weekly | 1 | WE | 05:30 | 1 | CL27 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 277.33 | 1 | Wave 3 South
J1012 | JP0010 | Elm Street Physiotherapy | Clinic - Point Cook | Office clean | Weekly | 2 | MO WE | 05:30 | 1 | CL36 | 73 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 632.67 | 2 | Wave 4 West
J1013 | JP0010 | Elm Street Physiotherapy | Clinic - Point Cook | Washroom service | Monthly | 0 | TH | 09:00 | 0.5 | CL55 | 99 | Fixed monthly | Auto | Active | 2026-07-23 | 99 | 0.125 | Wave 4 West
J1014 | JP0011 | Wattle Grove Property Group | Main office - Hawthorn | Office clean | Weekly | 2 | MO TU | 05:30 | 1 | CL10 | 68 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 589.33 | 2 | Wave 2 East
J1015 | JP0011 | Wattle Grove Property Group | Main office - Hawthorn | Washroom service | Monthly | 0 | WE | 09:00 | 0.5 | CL53 | 88 | Fixed monthly | Outside Jobber | Active | 2026-07-22 | 88 | 0.125 | Wave 2 East
J1016 | JP0012 | Hillcrest Physiotherapy Pty Ltd | Main office - Epping | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 05:30 | 1 | CL45 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1386.67 | 5 | Wave 1 North
J1017 | JP0013 | Hillcrest Physiotherapy Pty Ltd | Clinic - Thornbury | Office clean | Weekly | 2 | WE TH | 05:30 | 1.5 | CL29 | 96 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 832 | 3 | Wave 1 North
J1018 | JP0014 | Kingsley Real Estate | Main office - Mitcham | Office clean | Weekly | 1 | TH | 05:30 | 1.5 | CL34 | 90 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-02 | 390 | 1.5 | Wave 2 East
J1019 | JP0015 | Kingsley Real Estate | Clinic - Kew | Office clean | Weekly | 1 | FR | 05:30 | 1.5 | CL50 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 442 | 1.5 | Wave 2 East
J1020 | JP0016 | Wattle Grove Medical Centre Pty Ltd | Main office - Clayton | Office clean | Weekly | 1 | TH | 05:30 | 3 | CL11 | 186 | Per visit, billed monthly | Auto | Active | 2026-07-02 | 806 | 3 | Wave 3 South
J1021 | JP0017 | Bluestone Engineering | Main office - Coburg | Office clean | Weekly | 2 | MO TU | 05:30 | 2.5 | CL25 | 156 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1352 | 5 | Wave 1 North
J1022 | JP0018 | Clearwater Insurance Brokers Pty Ltd | Main office - Mentone | Office clean | Weekly | 3 | MO TU WE | 05:30 | 1 | CL51 | 63 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 819 | 3 | Wave 3 South
J1023 | JP0019 | Redgum Optometrists Pty Ltd | Main office - Camberwell | Office clean | Weekly | 2 | WE FR | 05:30 | 2.5 | CL46 | 151 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 1308.67 | 5 | Wave 2 East
J1024 | JP0019 | Redgum Optometrists Pty Ltd | Main office - Camberwell | Carpet steam clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL58 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-24 | 218 | 0.75 | Wave 2 East
J1025 | JP0020 | Northside Accountants Pty Ltd | Main office - Cheltenham | Kitchen and bathrooms | Weekly | 2 | WE FR | 05:30 | 0.5 | CL07 | 35 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 303.33 | 1 | Wave 3 South
J1026 | JP0020 | Northside Accountants Pty Ltd | Main office - Cheltenham | Window clean | Every 4 weeks | 0 | TU | 09:00 | 3 | CL54 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-30 | 218 | 0.75 | Wave 3 South
J1027 | JP0021 | Northside Accountants Pty Ltd | Clinic - Oakleigh | Office clean | Weekly | 3 | MO WE TH | 05:30 | 2 | CL31 | 122 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 1586 | 6 | Wave 3 South
J1028 | JP0022 | Northside Accountants Pty Ltd | Warehouse - Clayton | Kitchen and bathrooms | Weekly | 2 | MO TH | 05:30 | 1 | CL03 | 62 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 537.33 | 2 | Wave 3 South
J1029 | JP0023 | Oakwood Accountants Pty Ltd | Main office - Reservoir | Office clean | Weekly | 1 | MO | 05:30 | 1.5 | CL33 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 442 | 1.5 | Pilot
J1030 | JP0024 | Northside Engineering Pty Ltd | Main office - St Kilda | Office clean | Weekly | 2 | MO WE | 05:30 | 1.5 | CL47 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 884 | 3 | Wave 3 South
J1031 | JP0025 | Northside Engineering Pty Ltd | Clinic - Bentleigh | Office clean | Weekly | 2 | WE FR | 05:30 | 1.5 | CL15 | 93 | Per visit, billed monthly | Auto | Active | 2026-07-22 | 806 | 3 | Wave 3 South
J1032 | JP0025 | Northside Engineering Pty Ltd | Clinic - Bentleigh | Carpet steam clean | Every 4 weeks | 0 | TH | 09:00 | 3 | CL56 | 234 | Fixed 4-weekly | Auto | Active | 2026-07-16 | 234 | 0.75 | Wave 3 South
J1033 | JP0026 | Northside Engineering Pty Ltd | Warehouse - Deer Park | Office clean | Weekly | 5 | MO TU WE TH FR | 05:30 | 3 | CL52 | 187 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 4051.67 | 15 | Wave 4 West
J1034 | JP0027 | Northside Engineering Pty Ltd | Showroom - St Kilda | Kitchen and bathrooms | Weekly | 2 | MO WE | 05:30 | 1 | CL19 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 606.67 | 2 | Wave 3 South
J1035 | JP0028 | Ashwood Early Learning | Main office - Camberwell | Office clean | Weekly | 3 | MO TH FR | 05:30 | 1 | CL14 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 910 | 3 | Wave 2 East
J1036 | JP0028 | Ashwood Early Learning | Main office - Camberwell | Window clean | Every 4 weeks | 0 | TU | 09:00 | 3 | CL56 | 203 | Fixed 4-weekly | Auto | Active | 2026-07-21 | 203 | 0.75 | Wave 2 East
J1037 | JP0029 | Silverton Pharmacy | Main office - Point Cook | Office clean | Weekly | 1 | MO | 05:30 | 1 | CL40 | 66 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 286 | 1 | Wave 4 West
J1038 | JP0030 | Silverton Pharmacy | Clinic - Kew | Office clean | Weekly | 1 | TH | 05:30 | 1 | CL22 | 69 | Per visit, billed monthly | Auto | Active | 2026-07-09 | 299 | 1 | Wave 2 East
J1039 | JP0031 | Silverton Pharmacy | Warehouse - Bundoora | Office clean | Weekly | 1 | WE | 05:30 | 3 | CL21 | 187 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 810.33 | 3 | Wave 1 North
J1040 | JP0032 | Silverton Pharmacy | Showroom - Footscray | Office clean | Weekly | 2 | TU WE | 05:30 | 1.5 | CL20 | 97 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 840.67 | 3 | Wave 4 West
J1041 | JP0032 | Silverton Pharmacy | Showroom - Footscray | Carpet steam clean | Every 4 weeks | 0 | MO | 09:00 | 2 | CL58 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-13 | 135 | 0.5 | Wave 4 West
J1042 | JP0033 | Brightside Podiatry | Main office - Camberwell | Kitchen and bathrooms | Weekly | 1 | TU | 05:30 | 0.5 | CL06 | 32 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 138.67 | 0.5 | Wave 2 East
J1043 | JP0034 | Ashwood Optometrists | Main office - Ringwood | Office clean | Weekly | 2 | TU WE | 05:30 | 2 | CL30 | 125 | Per visit, billed monthly | Auto | Active | 2026-07-21 | 1083.33 | 4 | Wave 2 East
J1044 | JP0034 | Ashwood Optometrists | Main office - Ringwood | Window clean | Every 4 weeks | 0 | TU | 09:00 | 1.5 | CL57 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-21 | 109 | 0.375 | Wave 2 East
J1045 | JP0035 | Ashwood Optometrists | Clinic - Ringwood | Kitchen and bathrooms | Weekly | 1 | TH | 05:30 | 0.5 | CL42 | 40 | Per visit, billed monthly | Auto | Active | 2026-07-23 | 173.33 | 0.5 | Wave 2 East
J1046 | JP0035 | Ashwood Optometrists | Clinic - Ringwood | Washroom service | Monthly | 0 | MO | 09:00 | 0.5 | CL59 | 125 | Fixed monthly | Outside Jobber | Active | 2026-07-20 | 125 | 0.125 | Wave 2 East
J1047 | JP0036 | Parkside Accountants | Main office - Bundoora | Kitchen and bathrooms | Weekly | 2 | TU WE | 05:30 | 0.5 | CL41 | 30 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 260 | 1 | Wave 1 North
J1048 | JP0037 | Parkside Accountants | Clinic - Northcote | Office clean | Weekly | 1 | FR | 05:30 | 3 | CL09 | 193 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 836.33 | 3 | Pilot
J1049 | JP0037 | Parkside Accountants | Clinic - Northcote | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL57 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-07 | 135 | 0.5 | Wave 1 North
J1050 | JP0038 | Brightside Motors Pty Ltd | Main office - Heidelberg | Office clean | Weekly | 1 | WE | 05:30 | 1.5 | CL05 | 101 | Per visit, billed monthly | Auto | Active | 2026-07-08 | 437.67 | 1.5 | Wave 1 North
J1051 | JP0039 | Westend Motors Pty Ltd | Main office - Sunshine | Office clean | Weekly | 3 | MO TH FR | 05:30 | 1 | CL24 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 923 | 3 | Wave 4 West
J1052 | JP0040 | Westend Motors Pty Ltd | Clinic - Williamstown | Office clean | Weekly | 2 | TU WE | 05:30 | 3 | CL08 | 185 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 1603.33 | 6 | Wave 4 West
J1053 | JP0041 | Westend Motors Pty Ltd | Warehouse - Epping | Office clean | Weekly | 1 | WE | 05:30 | 2.5 | CL17 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 697.67 | 2.5 | Wave 1 North
J1054 | JP0042 | Oakwood Lawyers Pty Ltd | Main office - Moorabbin | Office clean | Weekly | 1 | TU | 05:30 | 2 | CL35 | 116 | Per visit, billed monthly | Auto | Active | 2026-06-30 | 502.67 | 2 | Wave 3 South
J1055 | JP0043 | Oakwood Lawyers Pty Ltd | Clinic - Essendon | Office clean | Weekly | 2 | MO WE | 05:30 | 3 | CL01 | 204 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1768 | 6 | Wave 1 North
J1056 | JP0044 | Riverside Medical Centre | Main office - Camberwell | Office clean | Weekly | 1 | MO | 05:30 | 1.5 | CL26 | 90 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 390 | 1.5 | Wave 2 East
J1057 | JP0045 | Riverside Motors Pty Ltd | Main office - Altona | Office clean | Weekly | 1 | WE | 06:00 | 2 | CL44 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 524.33 | 2 | Wave 4 West
J1058 | JP0046 | Parkside Pathology Pty Ltd | Main office - Yarraville | Office clean | Weekly | 3 | MO TU WE | 05:30 | 1 | CL04 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 975 | 3 | Wave 4 West
J1059 | JP0047 | Sunbury Accountants Pty Ltd | Main office - Camberwell | Office clean | Weekly | 2 | WE FR | 05:30 | 2 | CL18 | 135 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 1170 | 4 | Wave 2 East
J1060 | JP0048 | Sunbury Early Learning | Main office - Glen Waverley | Office clean | Weekly | 2 | MO TH | 05:30 | 3 | CL38 | 185 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1603.33 | 6 | Wave 2 East
J1061 | JP0049 | Silverton Lawyers Pty Ltd | Main office - Thornbury | Office clean | Weekly | 2 | TU TH | 08:00 | 2 | CL29 | 127 | Per visit, billed monthly | Auto | Active | 2026-07-07 | 1100.67 | 4 | Wave 1 North
J1062 | JP0050 | Waverley Accountants Pty Ltd | Main office - Brunswick | Office clean | Weekly | 5 | MO TU WE TH FR | 06:30 | 2 | CL41 | 116 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 2513.33 | 10 | Wave 1 North
J1063 | JP0050 | Waverley Accountants Pty Ltd | Main office - Brunswick | Window clean | Every 4 weeks | 0 | TH | 09:00 | 3 | CL60 | 218 | Fixed 4-weekly | Auto | Active | 2026-07-09 | 218 | 0.75 | Wave 1 North
J1064 | JP0051 | Westend Podiatry | Main office - Brunswick | Office clean | Weekly | 2 | MO TH | 05:30 | 2.5 | CL05 | 156 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1352 | 5 | Wave 1 North
J1065 | JP0051 | Westend Podiatry | Main office - Brunswick | Carpet steam clean | Every 4 weeks | 0 | WE | 09:00 | 2 | CL58 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-08 | 135 | 0.5 | Wave 1 North
J1066 | JP0052 | Westend Podiatry | Clinic - Thornbury | Office clean | Weekly | 3 | MO WE FR | 17:30 | 2.5 | CL33 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 2093 | 7.5 | Pilot
J1067 | JP0052 | Westend Podiatry | Clinic - Thornbury | Window clean | Every 4 weeks | 0 | MO | 09:00 | 1.5 | CL56 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-06 | 116 | 0.375 | Wave 1 North
J1068 | JP0053 | Westend Podiatry | Warehouse - Essendon | Office clean | Weekly | 1 | TH | 05:30 | 2.5 | CL37 | 151 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-23 | 654.33 | 2.5 | Wave 1 North
J1069 | JP0054 | Lakeside Engineering Pty Ltd | Main office - Deer Park | Office clean | Weekly | 3 | MO TH FR | 06:00 | 1 | CL24 | 69 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 897 | 3 | Wave 4 West
J1070 | JP0055 | Lakeside Engineering Pty Ltd | Clinic - Maribyrnong | Kitchen and bathrooms | Weekly | 2 | TU FR | 05:30 | 1 | CL44 | 69 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 598 | 2 | Wave 4 West
J1071 | JP0056 | Kingsley Financial Planning | Main office - Oakleigh | Office clean | Weekly | 1 | TH | 05:30 | 3 | CL27 | 181 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-23 | 784.33 | 3 | Wave 3 South
J1072 | JP0057 | Wattle Grove Physiotherapy | Main office - Cheltenham | Office clean | Weekly | 1 | TU | 17:30 | 2 | CL39 | 134 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 580.67 | 2 | Wave 3 South
J1073 | JP0058 | Elm Street Fitness Pty Ltd | Main office - Hawthorn | Kitchen and bathrooms | Weekly | 1 | MO | 05:30 | 1 | CL02 | 63 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 273 | 1 | Wave 2 East
J1074 | JP0058 | Elm Street Fitness Pty Ltd | Main office - Hawthorn | Window clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL60 | 218 | Fixed 4-weekly | Auto | Active | 2026-07-24 | 218 | 0.75 | Wave 2 East
J1075 | JP0059 | Elm Street Fitness Pty Ltd | Clinic - Doncaster | Kitchen and bathrooms | Weekly | 2 | MO TH | 05:30 | 0.5 | CL06 | 37 | Per visit, billed monthly | Auto | Active | 2026-07-20 | 320.67 | 1 | Wave 2 East
J1076 | JP0059 | Elm Street Fitness Pty Ltd | Clinic - Doncaster | Window clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL57 | 102 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-02 | 102 | 0.375 | Wave 2 East
J1077 | JP0060 | Wattle Grove Dental | Main office - Hawthorn | Office clean | Weekly | 3 | WE TH FR | 06:30 | 2 | CL42 | 125 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 1625 | 6 | Wave 2 East
J1078 | JP0061 | Lakeside Vet Clinic | Main office - Point Cook | Office clean | Weekly | 1 | FR | 05:30 | 1 | CL48 | 63 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-17 | 273 | 1 | Wave 4 West
J1079 | JP0062 | Lakeside Vet Clinic | Clinic - Laverton | Office clean | Weekly | 1 | TU | 05:30 | 1 | CL40 | 66 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 286 | 1 | Wave 4 West
J1080 | JP0062 | Lakeside Vet Clinic | Clinic - Laverton | Window clean | Every 4 weeks | 0 | MO | 09:00 | 1.5 | CL60 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-06 | 109 | 0.375 | Wave 4 West
J1081 | JP0063 | Clearwater Property Group Pty Ltd | Main office - Frankston | Office clean | Weekly | 3 | MO WE FR | 06:30 | 2 | CL07 | 130 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1690 | 6 | Wave 3 South
J1082 | JP0063 | Clearwater Property Group Pty Ltd | Main office - Frankston | Washroom service | Monthly | 0 | MO | 09:00 | 0.5 | CL56 | 151 | Fixed monthly | Outside Jobber | Active | 2026-07-06 | 151 | 0.125 | Wave 3 South
J1083 | JP0064 | Clearwater Property Group Pty Ltd | Clinic - Laverton | Office clean | Weekly | 5 | MO TU WE TH FR | 07:00 | 1 | CL48 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1625 | 5 | Wave 4 West
J1084 | JP0064 | Clearwater Property Group Pty Ltd | Clinic - Laverton | Window clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL53 | 234 | Fixed 4-weekly | Auto | Active | 2026-07-24 | 234 | 0.75 | Wave 4 West
J1085 | JP0065 | Eastwood Real Estate Pty Ltd | Main office - Hawthorn | Office clean | Weekly | 2 | TU WE | 05:30 | 3 | CL02 | 193 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 1672.67 | 6 | Wave 2 East
J1086 | JP0065 | Eastwood Real Estate Pty Ltd | Main office - Hawthorn | Window clean | Every 4 weeks | 0 | TH | 12:30 | 1.5 | CL60 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-09 | 109 | 0.375 | Wave 2 East
J1087 | JP0065 | Eastwood Real Estate Pty Ltd | Main office - Hawthorn | Washroom service | Monthly | 0 | TH | 09:00 | 0.5 | CL58 | 151 | Fixed monthly | Outside Jobber | Active | 2026-07-16 | 151 | 0.125 | Wave 2 East
J1088 | JP0066 | Clearwater Physiotherapy | Main office - Bentleigh | Kitchen and bathrooms | Weekly | 1 | WE | 07:00 | 1 | CL19 | 69 | Per visit, billed monthly | Auto | Active | 2026-07-22 | 299 | 1 | Wave 3 South
J1089 | JP0066 | Clearwater Physiotherapy | Main office - Bentleigh | Carpet steam clean | Every 4 weeks | 0 | WE | 09:00 | 1.5 | CL60 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-15 | 109 | 0.375 | Wave 3 South
J1090 | JP0066 | Clearwater Physiotherapy | Main office - Bentleigh | Washroom service | Monthly | 0 | MO | 09:00 | 0.5 | CL60 | 151 | Fixed monthly | Outside Jobber | Active | 2026-06-29 | 151 | 0.125 | Wave 3 South
J1091 | JP0067 | Clearwater Physiotherapy | Clinic - Burwood | Kitchen and bathrooms | Weekly | 2 | MO TU | 05:30 | 1 | CL22 | 60 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 520 | 2 | Wave 2 East
J1092 | JP0068 | Greenway Physiotherapy | Main office - Burwood | Office clean | Weekly | 1 | WE | 05:30 | 3 | CL06 | 204 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 884 | 3 | Wave 2 East
J1093 | JP0069 | Fairfield Engineering Pty Ltd | Main office - Bentleigh | Office clean | Weekly | 1 | TH | 17:30 | 2 | CL03 | 129 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-02 | 559 | 2 | Wave 3 South
J1094 | JP0070 | Fairfield Engineering Pty Ltd | Clinic - Cheltenham | Office clean | Weekly | 2 | TU TH | 17:30 | 1.5 | CL35 | 93 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 806 | 3 | Wave 3 South
J1095 | JP0070 | Fairfield Engineering Pty Ltd | Clinic - Cheltenham | Window clean | Every 4 weeks | 0 | TU | 09:00 | 1.5 | CL60 | 102 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-07 | 102 | 0.375 | Wave 3 South
J1096 | JP0071 | Westend Optometrists Pty Ltd | Main office - Mentone | Office clean | Weekly | 3 | WE TH FR | 05:30 | 2 | CL43 | 135 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 1755 | 6 | Wave 3 South
J1097 | JP0072 | Kingsley Insurance Brokers | Main office - Reservoir | Office clean | Weekly | 2 | WE FR | 17:30 | 3 | CL17 | 198 | Per visit, billed monthly | Auto | Active | 2026-07-08 | 1716 | 6 | Wave 1 North
J1098 | JP0072 | Kingsley Insurance Brokers | Main office - Reservoir | Carpet steam clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL60 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-02 | 116 | 0.375 | Wave 1 North
J1099 | JP0072 | Kingsley Insurance Brokers | Main office - Reservoir | Washroom service | Monthly | 0 | FR | 09:00 | 0.5 | CL53 | 125 | Fixed monthly | Outside Jobber | Active | 2026-07-17 | 125 | 0.125 | Wave 1 North
J1100 | JP0073 | Kingsley Insurance Brokers | Clinic - Point Cook | Office clean | Weekly | 2 | MO FR | 05:30 | 2 | CL16 | 116 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1005.33 | 4 | Wave 4 West
J1101 | JP0073 | Kingsley Insurance Brokers | Clinic - Point Cook | Window clean | Every 4 weeks | 0 | MO | 09:00 | 3 | CL59 | 218 | Fixed 4-weekly | Auto | Active | 2026-07-06 | 218 | 0.75 | Wave 4 West
J1102 | JP0074 | Bluestone Learning Centre Pty Ltd | Main office - Glen Waverley | Office clean | Weekly | 2 | MO WE | 05:30 | 1.5 | CL50 | 101 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 875.33 | 3 | Wave 2 East
J1103 | JP0074 | Bluestone Learning Centre Pty Ltd | Main office - Glen Waverley | Washroom service | Monthly | 0 | TH | 10:00 | 0.5 | CL55 | 88 | Fixed monthly | Outside Jobber | Active | 2026-07-16 | 88 | 0.125 | Wave 2 East
J1104 | JP0075 | Oakwood Logistics | Main office - Hawthorn | Office clean | Weekly | 2 | MO FR | 05:30 | 1 | CL34 | 58 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 502.67 | 2 | Wave 2 East
J1105 | JP0075 | Oakwood Logistics | Main office - Hawthorn | Carpet steam clean | Every 4 weeks | 0 | WE | 11:30 | 3 | CL58 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-08 | 218 | 0.75 | Wave 2 East
J1106 | JP0076 | Oakwood Logistics | Clinic - Blackburn | Kitchen and bathrooms | Weekly | 3 | MO TH FR | 07:30 | 0.5 | CL26 | 42 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 546 | 1.5 | Wave 2 East
J1107 | JP0077 | Oakwood Logistics | Warehouse - Cheltenham | Office clean | Weekly | 5 | MO TU WE TH FR | 17:30 | 2 | CL15 | 122 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 2643.33 | 10 | Wave 3 South
J1108 | JP0077 | Oakwood Logistics | Warehouse - Cheltenham | Window clean | Every 4 weeks | 0 | MO | 09:00 | 1.5 | CL56 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-20 | 116 | 0.375 | Wave 3 South
J1109 | JP0078 | Oakwood Logistics | Showroom - Box Hill | Office clean | Weekly | 2 | TU FR | 07:00 | 1 | CL10 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 606.67 | 2 | Wave 2 East
J1110 | JP0079 | Banksia Insurance Brokers | Main office - Burwood | Office clean | Weekly | 5 | MO TU WE TH FR | 07:00 | 1.5 | CL22 | 98 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 2123.33 | 7.5 | Wave 2 East
J1111 | JP0079 | Banksia Insurance Brokers | Main office - Burwood | Window clean | Every 4 weeks | 0 | TH | 10:00 | 1.5 | CL58 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-02 | 109 | 0.375 | Wave 2 East
J1112 | JP0080 | Sunbury Lawyers Pty Ltd | Main office - Reservoir | Kitchen and bathrooms | Weekly | 1 | TU | 05:30 | 0.5 | CL09 | 30 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 130 | 0.5 | Pilot
J1113 | JP0081 | Sunbury Lawyers Pty Ltd | Clinic - Essendon | Office clean | Weekly | 2 | MO WE | 17:30 | 1.5 | CL29 | 94 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 814.67 | 3 | Wave 1 North
J1114 | JP0081 | Sunbury Lawyers Pty Ltd | Clinic - Essendon | Washroom service | Monthly | 0 | TH | 09:00 | 0.5 | CL56 | 125 | Fixed monthly | Outside Jobber | Active | 2026-07-09 | 125 | 0.125 | Wave 1 North
J1115 | JP0082 | Sunbury Lawyers Pty Ltd | Warehouse - Mentone | Kitchen and bathrooms | Weekly | 1 | WE | 20:30 | 1 | CL15 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 325 | 1 | Wave 3 South
J1116 | JP0083 | Cobblestone Real Estate Pty Ltd | Main office - Frankston | Office clean | Weekly | 1 | WE | 05:30 | 3 | CL11 | 185 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 801.67 | 3 | Wave 3 South
J1117 | JP0084 | Bayview Engineering Pty Ltd | Main office - Sunshine | Office clean | Weekly | 2 | TH FR | 05:30 | 2 | CL40 | 127 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-02 | 1100.67 | 4 | Wave 4 West
J1118 | JP0085 | Oakwood Financial Planning Pty Ltd | Main office - Brighton | Office clean | Weekly | 1 | FR | 05:30 | 3 | CL19 | 187 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 810.33 | 3 | Wave 3 South
J1119 | JP0085 | Oakwood Financial Planning Pty Ltd | Main office - Brighton | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 1.5 | CL59 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-07 | 116 | 0.375 | Wave 3 South
J1120 | JP0086 | Brightside Dental Pty Ltd | Main office - Dandenong | Office clean | Weekly | 1 | MO | 17:30 | 2 | CL47 | 116 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 502.67 | 2 | Wave 3 South
J1121 | JP0087 | Brightside Dental Pty Ltd | Clinic - Moorabbin | Kitchen and bathrooms | Weekly | 1 | WE | 07:00 | 0.5 | CL51 | 32 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 138.67 | 0.5 | Wave 3 South
J1122 | JP0088 | Ashwood Physiotherapy | Main office - Point Cook | Kitchen and bathrooms | Weekly | 3 | MO WE FR | 07:00 | 0.5 | CL12 | 43 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 559 | 1.5 | Wave 4 West
J1123 | JP0088 | Ashwood Physiotherapy | Main office - Point Cook | Window clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL59 | 135 | Fixed 4-weekly | Auto | Active | 2026-06-30 | 135 | 0.5 | Wave 4 West
J1124 | JP0089 | Ashwood Physiotherapy | Clinic - Camberwell | Office clean | Weekly | 1 | TH | 17:30 | 2 | CL26 | 134 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-23 | 580.67 | 2 | Wave 2 East
J1125 | JP0090 | Ashwood Physiotherapy | Warehouse - Coburg | Office clean | Weekly | 2 | TU FR | 05:30 | 2.5 | CL21 | 156 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 1352 | 5 | Wave 1 North
J1126 | JP0090 | Ashwood Physiotherapy | Warehouse - Coburg | Window clean | Every 4 weeks | 0 | MO | 09:00 | 1.5 | CL55 | 116 | Fixed 4-weekly | Auto | Active | 2026-07-06 | 116 | 0.375 | Wave 1 North
J1127 | JP0091 | Ashwood Physiotherapy | Showroom - Footscray | Office clean | Weekly | 2 | MO FR | 17:30 | 2.5 | CL36 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1395.33 | 5 | Wave 4 West
J1128 | JP0092 | Bluestone Dental | Main office - Camberwell | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 07:00 | 0.5 | CL14 | 30 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 650 | 2.5 | Wave 2 East
J1129 | JP0093 | Bluestone Dental | Clinic - Burwood | Office clean | Weekly | 1 | TU | 05:30 | 2 | CL34 | 127 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 550.33 | 2 | Wave 2 East
J1130 | JP0093 | Bluestone Dental | Clinic - Burwood | Carpet steam clean | Every 4 weeks | 0 | MO | 11:00 | 3 | CL56 | 203 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-06 | 203 | 0.75 | Wave 2 East
J1131 | JP0094 | Bluestone Dental | Warehouse - Burwood | Office clean | Weekly | 2 | TU WE | 17:30 | 1 | CL10 | 68 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 589.33 | 2 | Wave 2 East
J1132 | JP0095 | Bluestone Dental | Showroom - Ringwood | Office clean | Weekly | 2 | MO FR | 17:30 | 2 | CL18 | 131 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 1135.33 | 4 | Wave 2 East
J1133 | JP0095 | Bluestone Dental | Showroom - Ringwood | Carpet steam clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL55 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-03 | 218 | 0.75 | Wave 2 East
J1134 | JP0096 | Kingsley Accountants | Main office - Altona | Office clean | Weekly | 1 | TH | 05:30 | 1 | CL44 | 58 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-23 | 251.33 | 1 | Wave 4 West
J1135 | JP0097 | Clearwater Early Learning Pty Ltd | Main office - Northcote | Office clean | Weekly | 2 | MO TU | 17:30 | 2.5 | CL09 | 166 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1438.67 | 5 | Pilot
J1136 | JP0097 | Clearwater Early Learning Pty Ltd | Main office - Northcote | Window clean | Every 4 weeks | 0 | MO | 11:00 | 2 | CL56 | 156 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-20 | 156 | 0.5 | Wave 1 North
J1137 | JP0098 | Banksia Pathology Pty Ltd | Main office - Deer Park | Office clean | Weekly | 1 | TU | 17:30 | 2 | CL20 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 524.33 | 2 | Wave 4 West
J1138 | JP0099 | Southgate Financial Planning Pty Ltd | Main office - Blackburn | Office clean | Weekly | 1 | MO | 05:30 | 2.5 | CL30 | 146 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 632.67 | 2.5 | Wave 2 East
J1139 | JP0100 | Southgate Financial Planning Pty Ltd | Clinic - Bentleigh | Office clean | Weekly | 2 | TU TH | 17:30 | 2 | CL51 | 135 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 1170 | 4 | Wave 3 South
J1140 | JP0101 | Bluestone Lawyers Pty Ltd | Main office - Burwood | Office clean | Weekly | 2 | TU WE | 17:30 | 1 | CL06 | 75 | Per visit, billed monthly | Auto | Active | 2026-07-21 | 650 | 2 | Wave 2 East
J1141 | JP0102 | Riverside Lawyers Pty Ltd | Main office - Glen Waverley | Office clean | Weekly | 1 | TH | 05:30 | 1 | CL50 | 68 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-09 | 294.67 | 1 | Wave 2 East
J1142 | JP0102 | Riverside Lawyers Pty Ltd | Main office - Glen Waverley | Washroom service | Monthly | 0 | FR | 10:00 | 0.5 | CL53 | 99 | Fixed monthly | Outside Jobber | Active | 2026-07-10 | 99 | 0.125 | Wave 2 East
J1143 | JP0103 | Banksia Accountants | Main office - Altona | Office clean | Weekly | 2 | TU WE | 17:30 | 2 | CL04 | 126 | Per visit, billed monthly | Auto | Active | 2026-07-07 | 1092 | 4 | Wave 4 West
J1144 | JP0104 | Banksia Accountants | Clinic - Doncaster | Office clean | Weekly | 1 | WE | 05:30 | 2.5 | CL26 | 156 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 676 | 2.5 | Wave 2 East
J1145 | JP0104 | Banksia Accountants | Clinic - Doncaster | Window clean | Every 4 weeks | 0 | MO | 10:00 | 1.5 | CL56 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-29 | 109 | 0.375 | Wave 2 East
J1146 | JP0105 | Banksia Accountants | Warehouse - Glen Waverley | Kitchen and bathrooms | Weekly | 2 | MO WE | 17:30 | 0.5 | CL46 | 30 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 260 | 1 | Wave 2 East
J1147 | JP0106 | Ironbark Physiotherapy Pty Ltd | Main office - Point Cook | Office clean | Weekly | 3 | TU TH FR | 07:00 | 1 | CL28 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 923 | 3 | Wave 4 West
J1148 | JP0107 | Ironbark Physiotherapy Pty Ltd | Clinic - Point Cook | Office clean | Weekly | 1 | FR | 07:00 | 1 | CL24 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-17 | 277.33 | 1 | Wave 4 West
J1149 | JP0107 | Ironbark Physiotherapy Pty Ltd | Clinic - Point Cook | Window clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL53 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-30 | 135 | 0.5 | Wave 4 West
J1150 | JP0108 | Wattle Grove Lawyers Pty Ltd | Main office - Point Cook | Kitchen and bathrooms | Weekly | 3 | MO TU TH | 07:00 | 1 | CL44 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 975 | 3 | Wave 4 West
J1151 | JP0108 | Wattle Grove Lawyers Pty Ltd | Main office - Point Cook | Window clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL57 | 203 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-10 | 203 | 0.75 | Wave 4 West
J1152 | JP0109 | Kingsley Medical Centre Pty Ltd | Main office - Point Cook | Office clean | Weekly | 2 | WE TH | 17:30 | 3 | CL12 | 181 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 1568.67 | 6 | Wave 4 West
J1153 | JP0109 | Kingsley Medical Centre Pty Ltd | Main office - Point Cook | Washroom service | Monthly | 0 | MO | 09:00 | 0.5 | CL57 | 99 | Fixed monthly | Outside Jobber | Active | 2026-06-29 | 99 | 0.125 | Wave 4 West
J1154 | JP0110 | Kingsley Medical Centre Pty Ltd | Clinic - Hawthorn | Office clean | Weekly | 1 | TU | 05:30 | 1.5 | CL50 | 101 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 437.67 | 1.5 | Wave 2 East
J1155 | JP0111 | Ashwood Engineering | Main office - Glen Waverley | Office clean | Weekly | 1 | FR | 17:30 | 2 | CL14 | 122 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 528.67 | 2 | Wave 2 East
J1156 | JP0112 | Sunbury Physiotherapy Pty Ltd | Main office - Point Cook | Office clean | Weekly | 2 | MO TH | 17:30 | 3 | CL24 | 191 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1655.33 | 6 | Wave 4 West
J1157 | JP0113 | Sunbury Physiotherapy Pty Ltd | Clinic - Frankston | Office clean | Weekly | 3 | MO TU TH | 20:00 | 2.5 | CL03 | 146 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1898 | 7.5 | Wave 3 South
J1158 | JP0114 | Sunbury Physiotherapy Pty Ltd | Warehouse - Hawthorn | Office clean | Weekly | 5 | MO TU WE TH FR | 07:00 | 1 | CL14 | 58 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1256.67 | 5 | Wave 2 East
J1159 | JP0115 | Eastwood Pathology | Main office - Werribee | Kitchen and bathrooms | Weekly | 2 | WE TH | 07:30 | 0.5 | CL20 | 32 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 277.33 | 1 | Wave 4 West
J1160 | JP0115 | Eastwood Pathology | Main office - Werribee | Washroom service | Monthly | 0 | WE | 09:00 | 0.5 | CL58 | 88 | Fixed monthly | Outside Jobber | Active | 2026-07-22 | 88 | 0.125 | Wave 4 West
J1161 | JP0116 | Waverley Fitness Pty Ltd | Main office - Footscray | Office clean | Weekly | 1 | TU | 17:30 | 1 | CL32 | 62 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 268.67 | 1 | Wave 4 West
J1162 | JP0117 | Waverley Fitness Pty Ltd | Clinic - Footscray | Office clean | Weekly | 1 | WE | 05:30 | 2 | CL44 | 135 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 585 | 2 | Wave 4 West
J1163 | JP0118 | Clearwater Logistics | Main office - Reservoir | Office clean | Weekly | 1 | MO | 05:30 | 1 | CL13 | 62 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 268.67 | 1 | Wave 1 North
J1164 | JP0118 | Clearwater Logistics | Main office - Reservoir | Carpet steam clean | Every 4 weeks | 0 | WE | 09:00 | 2 | CL60 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-22 | 146 | 0.5 | Wave 1 North
J1165 | JP0119 | Wattle Grove Fitness | Main office - Essendon | Kitchen and bathrooms | Weekly | 2 | MO WE | 05:30 | 1 | CL49 | 63 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 546 | 2 | Wave 1 North
J1166 | JP0120 | Wattle Grove Fitness | Clinic - St Kilda | Office clean | Weekly | 2 | MO FR | 05:30 | 2.5 | CL27 | 166 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1438.67 | 5 | Wave 3 South
J1167 | JP0121 | Ashwood Medical Centre | Main office - Bundoora | Kitchen and bathrooms | Weekly | 1 | MO | 05:30 | 1 | CL37 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 307.67 | 1 | Wave 1 North
J1168 | JP0121 | Ashwood Medical Centre | Main office - Bundoora | Window clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL60 | 135 | Fixed 4-weekly | Auto | Active | 2026-07-14 | 135 | 0.5 | Wave 1 North
J1169 | JP0122 | Parkside Vet Clinic | Main office - Deer Park | Office clean | Weekly | 2 | TU WE | 17:30 | 3 | CL40 | 180 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 1560 | 6 | Wave 4 West
J1170 | JP0123 | Wattle Grove Architects | Main office - Bentleigh | Kitchen and bathrooms | Weekly | 1 | FR | 05:30 | 1 | CL39 | 58 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-17 | 251.33 | 1 | Wave 3 South
J1171 | JP0124 | Bayview Pharmacy Pty Ltd | Main office - Footscray | Office clean | Weekly | 5 | MO TU WE TH FR | 21:30 | 2 | CL12 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 2621.67 | 10 | Wave 4 West
J1172 | JP0125 | Hillcrest Accountants | Main office - Mitcham | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 20:30 | 1 | CL14 | 62 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 1343.33 | 5 | Wave 2 East
J1173 | JP0125 | Hillcrest Accountants | Main office - Mitcham | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 1.5 | CL57 | 116 | Fixed 4-weekly | Auto | Active | 2026-06-30 | 116 | 0.375 | Wave 2 East
J1174 | JP0126 | Lakeside Architects | Main office - Reservoir | Office clean | Weekly | 2 | MO TH | 07:00 | 1.5 | CL45 | 93 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 806 | 3 | Wave 1 North
J1175 | JP0127 | Lakeside Architects | Clinic - Mitcham | Office clean | Weekly | 1 | FR | 17:30 | 1.5 | CL46 | 97 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 420.33 | 1.5 | Wave 2 East
J1176 | JP0128 | Ashwood Accountants | Main office - Yarraville | Office clean | Weekly | 1 | FR | 17:30 | 1 | CL16 | 73 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 316.33 | 1 | Wave 4 West
J1177 | JP0129 | Westend Property Group | Main office - Heidelberg | Kitchen and bathrooms | Weekly | 2 | TU FR | 08:00 | 0.5 | CL13 | 37 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 320.67 | 1 | Wave 1 North
J1178 | JP0129 | Westend Property Group | Main office - Heidelberg | Carpet steam clean | Every 4 weeks | 0 | FR | 12:30 | 2 | CL60 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-24 | 135 | 0.5 | Wave 1 North
J1179 | JP0130 | Eastwood Optometrists | Main office - Burwood | Office clean | Weekly | 1 | WE | 05:30 | 2 | CL38 | 122 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 528.67 | 2 | Wave 2 East
J1180 | JP0131 | Eastwood Optometrists | Clinic - Mitcham | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 19:00 | 1 | CL06 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1516.67 | 5 | Wave 2 East
J1181 | JP0132 | Westend Medical Centre | Main office - Sunshine | Office clean | Weekly | 2 | WE FR | 17:30 | 1.5 | CL28 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 884 | 3 | Wave 4 West
J1182 | JP0133 | Riverside Learning Centre | Main office - Mentone | Office clean | Weekly | 1 | TU | 20:00 | 2.5 | CL39 | 151 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-21 | 654.33 | 2.5 | Wave 3 South
J1183 | JP0134 | Riverside Learning Centre | Clinic - Cheltenham | Office clean | Weekly | 2 | WE TH | 05:30 | 2 | CL35 | 125 | Per visit, billed monthly | Auto | Active | 2026-07-01 | 1083.33 | 4 | Wave 3 South
J1184 | JP0135 | Riverside Learning Centre | Warehouse - Moorabbin | Office clean | Weekly | 2 | MO FR | 20:00 | 2.5 | CL47 | 156 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1352 | 5 | Wave 3 South
J1185 | JP0135 | Riverside Learning Centre | Warehouse - Moorabbin | Window clean | Every 4 weeks | 0 | FR | 09:00 | 2 | CL60 | 146 | Fixed 4-weekly | Auto | Active | 2026-07-17 | 146 | 0.5 | Wave 3 South
J1186 | JP0136 | Silverton Insurance Brokers Pty Ltd | Main office - Cheltenham | Office clean | Weekly | 1 | TH | 18:00 | 2 | CL03 | 130 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-16 | 563.33 | 2 | Wave 3 South
J1187 | JP0137 | Silverton Insurance Brokers Pty Ltd | Clinic - Frankston | Office clean | Weekly | 2 | WE TH | 17:30 | 1 | CL11 | 63 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 546 | 2 | Wave 3 South
J1188 | JP0138 | Silverton Insurance Brokers Pty Ltd | Warehouse - Glen Waverley | Office clean | Weekly | 2 | MO WE | 17:30 | 2 | CL30 | 127 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1100.67 | 4 | Wave 2 East
J1189 | JP0138 | Silverton Insurance Brokers Pty Ltd | Warehouse - Glen Waverley | Washroom service | Monthly | 0 | MO | 10:00 | 0.5 | CL60 | 88 | Fixed monthly | Outside Jobber | Active | 2026-06-29 | 88 | 0.125 | Wave 2 East
J1190 | JP0139 | Greenway Podiatry Pty Ltd | Main office - Burwood | Kitchen and bathrooms | Weekly | 1 | WE | 05:30 | 0.5 | CL42 | 40 | Per visit, billed monthly | Auto | Active | 2026-07-01 | 173.33 | 0.5 | Wave 2 East
J1191 | JP0140 | Banksia Logistics | Main office - Northcote | Office clean | Weekly | 1 | TU | 17:30 | 1.5 | CL25 | 94 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 407.33 | 1.5 | Wave 1 North
J1192 | JP0141 | Banksia Logistics | Clinic - Northcote | Office clean | Weekly | 1 | WE | 17:30 | 3 | CL37 | 199 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 862.33 | 3 | Wave 1 North
J1193 | JP0142 | Banksia Logistics | Warehouse - Thornbury | Office clean | Weekly | 1 | TH | 05:30 | 1.5 | CL13 | 107 | Per visit, billed monthly | Auto | Active | 2026-07-09 | 463.67 | 1.5 | Wave 1 North
J1194 | JP0143 | Sunbury Architects Pty Ltd | Main office - Epping | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 17:30 | 1 | CL49 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 1386.67 | 5 | Wave 1 North
J1195 | JP0144 | Cobblestone Physiotherapy Pty Ltd | Main office - Bundoora | Kitchen and bathrooms | Weekly | 1 | FR | 05:30 | 0.5 | CL01 | 36 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-03 | 156 | 0.5 | Wave 1 North
J1196 | JP0145 | Banksia Real Estate | Main office - Maribyrnong | Office clean | Weekly | 2 | MO TU | 20:00 | 2 | CL20 | 139 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1204.67 | 4 | Wave 4 West
J1197 | JP0145 | Banksia Real Estate | Main office - Maribyrnong | Window clean | Every 4 weeks | 0 | WE | 11:30 | 3 | CL60 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-22 | 218 | 0.75 | Wave 4 West
J1198 | JP0146 | Northside Pathology Pty Ltd | Main office - Ringwood | Office clean | Weekly | 1 | MO | 05:30 | 2 | CL42 | 139 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 602.33 | 2 | Wave 2 East
J1199 | JP0147 | Harbourside Lawyers | Main office - Glen Waverley | Kitchen and bathrooms | Weekly | 2 | TH FR | 05:30 | 0.5 | CL02 | 37 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-16 | 320.67 | 1 | Wave 2 East
J1200 | JP0148 | Kingsley Fitness Pty Ltd | Main office - Werribee | Kitchen and bathrooms | Weekly | 1 | FR | 07:30 | 1 | CL20 | 60 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 260 | 1 | Wave 4 West
J1201 | JP0149 | Lakeside Optometrists | Main office - Footscray | Office clean | Weekly | 1 | TH | 05:30 | 2 | CL32 | 130 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-23 | 563.33 | 2 | Wave 4 West
J1202 | JP0149 | Lakeside Optometrists | Main office - Footscray | Carpet steam clean | Every 4 weeks | 0 | TH | 09:00 | 3 | CL59 | 234 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-02 | 234 | 0.75 | Wave 4 West
J1203 | JP0150 | Southgate Dental | Main office - Hawthorn | Office clean | Weekly | 3 | MO WE TH | 17:30 | 1.5 | CL50 | 104 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1352 | 4.5 | Wave 2 East
J1204 | JP0151 | Sunbury Optometrists | Main office - Altona | Office clean | Weekly | 5 | MO TU WE TH FR | 17:30 | 1 | CL48 | 69 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 1495 | 5 | Wave 4 West
J1205 | JP0152 | Bayview Vet Clinic | Main office - Coburg | Office clean | Weekly | 3 | WE TH FR | 19:30 | 1.5 | CL29 | 97 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-08 | 1261 | 4.5 | Wave 1 North
J1206 | JP0152 | Bayview Vet Clinic | Main office - Coburg | Window clean | Every 4 weeks | 0 | MO | 12:00 | 2 | CL56 | 135 | Fixed 4-weekly | Auto | Active | 2026-06-29 | 135 | 0.5 | Wave 1 North
J1207 | JP0153 | Bayview Vet Clinic | Clinic - Reservoir | Office clean | Weekly | 2 | TU FR | 19:30 | 1.5 | CL25 | 93 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 806 | 3 | Wave 1 North
J1208 | JP0153 | Bayview Vet Clinic | Clinic - Reservoir | Window clean | Every 4 weeks | 0 | MO | 09:00 | 3 | CL58 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-29 | 218 | 0.75 | Wave 1 North
J1209 | JP0154 | Redgum Pathology Pty Ltd | Main office - Camberwell | Office clean | Weekly | 1 | WE | 18:30 | 3 | CL46 | 198 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 858 | 3 | Wave 2 East
J1210 | JP0155 | Greenway Medical Centre Pty Ltd | Main office - Glen Waverley | Office clean | Weekly | 1 | MO | 17:30 | 1.5 | CL26 | 98 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 424.67 | 1.5 | Wave 2 East
J1211 | JP0155 | Greenway Medical Centre Pty Ltd | Main office - Glen Waverley | Carpet steam clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL60 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-03 | 218 | 0.75 | Wave 2 East
J1212 | JP0156 | Westend Physiotherapy | Main office - Glen Waverley | Office clean | Weekly | 5 | MO TU WE TH FR | 20:00 | 2.5 | CL14 | 166 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 3596.67 | 12.5 | Wave 2 East
J1213 | JP0157 | Riverside Podiatry | Main office - Point Cook | Office clean | Weekly | 3 | MO TU FR | 20:00 | 2 | CL04 | 135 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 1755 | 6 | Wave 4 West
J1214 | JP0158 | Riverside Podiatry | Clinic - Brighton | Office clean | Weekly | 1 | WE | 17:30 | 1.5 | CL19 | 107 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 463.67 | 1.5 | Wave 3 South
J1215 | JP0159 | Northside Learning Centre | Main office - Camberwell | Office clean | Weekly | 5 | MO TU WE TH FR | 17:30 | 1 | CL02 | 69 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 1495 | 5 | Wave 2 East
J1216 | JP0160 | Harbourside Logistics Pty Ltd | Main office - Hawthorn | Office clean | Weekly | 3 | MO TU WE | 17:30 | 1.5 | CL38 | 97 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1261 | 4.5 | Wave 2 East
J1217 | JP0161 | Harbourside Logistics Pty Ltd | Clinic - Kew | Office clean | Weekly | 2 | TU WE | 17:30 | 1 | CL18 | 66 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 572 | 2 | Wave 2 East
J1218 | JP0162 | Redgum Podiatry | Main office - Williamstown | Office clean | Weekly | 2 | MO TH | 07:00 | 1.5 | CL36 | 94 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 814.67 | 3 | Wave 4 West
J1219 | JP0163 | Redgum Podiatry | Clinic - Cheltenham | Office clean | Weekly | 2 | MO TH | 17:30 | 1.5 | CL07 | 104 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 901.33 | 3 | Wave 3 South
J1220 | JP0163 | Redgum Podiatry | Clinic - Cheltenham | Window clean | Every 4 weeks | 0 | MO | 09:00 | 1.5 | CL54 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-20 | 116 | 0.375 | Wave 3 South
J1221 | JP0164 | Harbourside Chiropractic | Main office - Oakleigh | Office clean | Weekly | 2 | MO TU | 20:00 | 1.5 | CL35 | 90 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 780 | 3 | Wave 3 South
J1222 | JP0165 | Harbourside Chiropractic | Clinic - Moorabbin | Office clean | Weekly | 2 | TU WE | 19:30 | 2 | CL19 | 116 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 1005.33 | 4 | Wave 3 South
J1223 | JP0165 | Harbourside Chiropractic | Clinic - Moorabbin | Carpet steam clean | Every 4 weeks | 0 | FR | 09:00 | 2 | CL54 | 135 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-24 | 135 | 0.5 | Wave 3 South
J1224 | JP0166 | Harbourside Chiropractic | Warehouse - St Kilda | Office clean | Weekly | 5 | MO TU WE TH FR | 20:00 | 2 | CL51 | 134 | Per visit, billed monthly | Auto | Active | 2026-07-20 | 2903.33 | 10 | Wave 3 South
J1225 | JP0167 | Hillcrest Lawyers | Main office - Mentone | Office clean | Weekly | 2 | WE FR | 07:00 | 1 | CL39 | 62 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 537.33 | 2 | Wave 3 South
J1226 | JP0168 | Hillcrest Lawyers | Clinic - Northcote | Office clean | Weekly | 5 | MO TU WE TH FR | 17:30 | 1.5 | CL01 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 2210 | 7.5 | Wave 1 North
J1227 | JP0169 | Silverton Logistics Pty Ltd | Main office - Brunswick | Kitchen and bathrooms | Weekly | 2 | MO TU | 17:30 | 1 | CL05 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 554.67 | 2 | Wave 1 North
J1228 | JP0169 | Silverton Logistics Pty Ltd | Main office - Brunswick | Window clean | Every 4 weeks | 0 | WE | 09:00 | 2 | CL54 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-15 | 146 | 0.5 | Wave 1 North
J1229 | JP0170 | Silverton Logistics Pty Ltd | Clinic - Frankston | Kitchen and bathrooms | Weekly | 1 | WE | 08:00 | 0.5 | CL31 | 29 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 125.67 | 0.5 | Wave 3 South
J1230 | JP0171 | Hillcrest Motors Pty Ltd | Main office - Bentleigh | Office clean | Weekly | 1 | FR | 05:30 | 2 | CL11 | 134 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-17 | 580.67 | 2 | Wave 3 South
J1231 | JP0171 | Hillcrest Motors Pty Ltd | Main office - Bentleigh | Carpet steam clean | Every 4 weeks | 0 | WE | 11:30 | 3 | CL54 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-15 | 218 | 0.75 | Wave 3 South
J1232 | JP0172 | Southgate Pathology | Main office - Brunswick | Office clean | Weekly | 2 | TU WE | 17:30 | 3 | CL13 | 193 | Per visit, billed monthly | Auto | Active | 2026-07-14 | 1672.67 | 6 | Wave 1 North
J1233 | JP0173 | Southgate Pathology | Clinic - Hawthorn | Office clean | Weekly | 2 | MO TH | 17:30 | 2.5 | CL42 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1395.33 | 5 | Wave 2 East
J1234 | JP0174 | Southgate Pathology | Warehouse - Altona | Kitchen and bathrooms | Weekly | 3 | WE TH FR | 20:30 | 1 | CL16 | 62 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 806 | 3 | Wave 4 West
J1235 | JP0175 | Westend Engineering | Main office - Deer Park | Office clean | Weekly | 2 | MO TH | 17:30 | 2 | CL44 | 126 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1092 | 4 | Wave 4 West
J1236 | JP0176 | Westend Engineering | Clinic - Reservoir | Kitchen and bathrooms | Weekly | 3 | TU WE TH | 17:30 | 1 | CL45 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 832 | 3 | Wave 1 North
J1237 | JP0176 | Westend Engineering | Clinic - Reservoir | Carpet steam clean | Every 4 weeks | 0 | WE | 09:00 | 2 | CL53 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-15 | 146 | 0.5 | Wave 1 North
J1238 | JP0177 | Lakeside Real Estate Pty Ltd | Main office - Brunswick | Office clean | Weekly | 3 | MO TH FR | 17:30 | 1 | CL21 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 910 | 3 | Wave 1 North
J1239 | JP0178 | Lakeside Real Estate Pty Ltd | Clinic - Preston | Office clean | Weekly | 3 | TU WE TH | 19:00 | 1.5 | CL05 | 96 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 1248 | 4.5 | Wave 1 North
J1240 | JP0179 | Lakeside Real Estate Pty Ltd | Warehouse - Mitcham | Office clean | Weekly | 2 | WE TH | 20:00 | 1 | CL26 | 63 | Per visit, billed monthly | Auto | Active | 2026-07-08 | 546 | 2 | Wave 2 East
J1241 | JP0179 | Lakeside Real Estate Pty Ltd | Warehouse - Mitcham | Window clean | Every 4 weeks | 0 | MO | 11:00 | 2 | CL54 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-20 | 146 | 0.5 | Wave 2 East
J1242 | JP0179 | Lakeside Real Estate Pty Ltd | Warehouse - Mitcham | Washroom service | Monthly | 0 | TU | 12:30 | 0.5 | CL54 | 99 | Fixed monthly | Outside Jobber | Active | 2026-06-30 | 99 | 0.125 | Wave 2 East
J1243 | JP0180 | Harbourside Pharmacy Pty Ltd | Main office - Yarraville | Office clean | Weekly | 2 | MO TU | 19:00 | 2 | CL32 | 134 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1161.33 | 4 | Wave 4 West
J1244 | JP0181 | Harbourside Pharmacy Pty Ltd | Clinic - Williamstown | Office clean | Weekly | 2 | TU FR | 19:30 | 1.5 | CL28 | 104 | Per visit, billed monthly | Auto | Active | 2026-07-07 | 901.33 | 3 | Wave 4 West
J1245 | JP0182 | Brightside Early Learning Pty Ltd | Main office - Footscray | Office clean | Weekly | 5 | MO TU WE TH FR | 21:00 | 1.5 | CL12 | 90 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1950 | 7.5 | Wave 4 West
J1246 | JP0183 | Southgate Engineering | Main office - Frankston | Office clean | Weekly | 2 | MO WE | 17:30 | 2 | CL43 | 126 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 1092 | 4 | Wave 3 South
J1247 | JP0184 | Riverside Dental Pty Ltd | Main office - Northcote | Kitchen and bathrooms | Weekly | 1 | FR | 05:30 | 1 | CL17 | 62 | Per visit, billed monthly | Auto | Active | 2026-07-17 | 268.67 | 1 | Wave 1 North
J1248 | JP0185 | Bayview Early Learning | Main office - Laverton | Office clean | Weekly | 1 | TH | 07:00 | 1.5 | CL24 | 90 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-09 | 390 | 1.5 | Wave 4 West
J1249 | JP0185 | Bayview Early Learning | Main office - Laverton | Window clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL54 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-23 | 116 | 0.375 | Wave 4 West
J1250 | JP0186 | Bayview Early Learning | Clinic - Brighton | Office clean | Weekly | 1 | MO | 17:30 | 1 | CL31 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 325 | 1 | Wave 3 South
J1251 | JP0187 | Elm Street Financial Planning Pty Ltd | Main office - Yarraville | Kitchen and bathrooms | Weekly | 2 | TH FR | 05:30 | 1 | CL20 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-02 | 615.33 | 2 | Wave 4 West
J1252 | JP0188 | Ashwood Property Group | Main office - Cheltenham | Kitchen and bathrooms | Weekly | 1 | MO | 17:30 | 0.5 | CL27 | 35 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 151.67 | 0.5 | Wave 3 South
J1253 | JP0188 | Ashwood Property Group | Main office - Cheltenham | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 1.5 | CL53 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-14 | 116 | 0.375 | Wave 3 South
J1254 | JP0189 | Northside Early Learning Pty Ltd | Main office - Bentleigh | Kitchen and bathrooms | Weekly | 2 | MO TU | 19:30 | 1 | CL35 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 554.67 | 2 | Wave 3 South
J1255 | JP0190 | Brightside Logistics Pty Ltd | Main office - Bentleigh | Office clean | Weekly | 2 | TU WE | 17:30 | 1.5 | CL31 | 101 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-30 | 875.33 | 3 | Wave 3 South
J1256 | JP0191 | Elm Street Early Learning | Main office - Hawthorn | Office clean | Weekly | 5 | MO TU WE TH FR | 20:00 | 1 | CL18 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1516.67 | 5 | Wave 2 East
J1257 | JP0192 | Elm Street Early Learning | Clinic - Camberwell | Office clean | Weekly | 1 | MO | 17:30 | 1 | CL22 | 73 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 316.33 | 1 | Wave 2 East
J1258 | JP0193 | Elm Street Early Learning | Warehouse - Glen Waverley | Office clean | Weekly | 2 | MO WE | 07:00 | 1.5 | CL34 | 98 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 849.33 | 3 | Wave 2 East
J1259 | JP0193 | Elm Street Early Learning | Warehouse - Glen Waverley | Window clean | Every 4 weeks | 0 | MO | 09:00 | 3 | CL53 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-29 | 218 | 0.75 | Wave 2 East
J1260 | JP0193 | Elm Street Early Learning | Warehouse - Glen Waverley | Washroom service | Monthly | 0 | FR | 09:00 | 0.5 | CL54 | 99 | Fixed monthly | Auto | Active | 2026-07-03 | 99 | 0.125 | Wave 2 East
J1261 | JP0194 | Redgum Financial Planning | Main office - Williamstown | Office clean | Weekly | 2 | TU FR | 05:30 | 1.5 | CL36 | 96 | Per visit, billed monthly | Auto | Active | 2026-07-07 | 832 | 3 | Wave 4 West
J1262 | JP0195 | Redgum Financial Planning | Clinic - Epping | Office clean | Weekly | 2 | TU WE | 06:30 | 1.5 | CL09 | 98 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 849.33 | 3 | Pilot
J1263 | JP0196 | Lakeside Fitness Pty Ltd | Main office - Mitcham | Office clean | Weekly | 2 | TU TH | 06:00 | 1.5 | CL46 | 104 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-21 | 901.33 | 3 | Wave 2 East
J1264 | JP0197 | Elm Street Logistics Pty Ltd | Main office - Kew | Office clean | Weekly | 5 | MO TU WE TH FR | 20:30 | 1.5 | CL10 | 97 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 2101.67 | 7.5 | Wave 2 East
J1265 | JP0198 | Elm Street Logistics Pty Ltd | Clinic - Ringwood | Office clean | Weekly | 2 | MO WE | 22:00 | 1 | CL46 | 62 | Per visit, billed monthly | Auto | Active | 2026-07-20 | 537.33 | 2 | Wave 2 East
J1266 | JP0199 | Elm Street Logistics Pty Ltd | Warehouse - Blackburn | Office clean | Weekly | 5 | MO TU WE TH FR | 21:30 | 1 | CL26 | 64 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 1386.67 | 5 | Wave 2 East
J1267 | JP0199 | Elm Street Logistics Pty Ltd | Warehouse - Blackburn | Window clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL57 | 203 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-24 | 203 | 0.75 | Wave 2 East
J1268 | JP0200 | Lakeside Insurance Brokers | Main office - Sunshine | Kitchen and bathrooms | Weekly | 3 | MO WE FR | 22:00 | 1 | CL16 | 68 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 884 | 3 | Wave 4 West
J1269 | JP0200 | Lakeside Insurance Brokers | Main office - Sunshine | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL57 | 156 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-14 | 156 | 0.5 | Wave 4 West
J1270 | JP0201 | Elm Street Pathology Pty Ltd | Main office - Maribyrnong | Kitchen and bathrooms | Weekly | 5 | MO TU WE TH FR | 21:00 | 1 | CL24 | 69 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1495 | 5 | Wave 4 West
J1271 | JP0202 | Fairfield Accountants Pty Ltd | Main office - Dandenong | Office clean | Weekly | 5 | MO TU WE TH FR | 18:30 | 2.5 | CL27 | 151 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 3271.67 | 12.5 | Wave 3 South
J1272 | JP0203 | Fairfield Accountants Pty Ltd | Clinic - Moorabbin | Office clean | Weekly | 2 | WE FR | 17:30 | 1.5 | CL39 | 87 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-15 | 754 | 3 | Wave 3 South
J1273 | JP0203 | Fairfield Accountants Pty Ltd | Clinic - Moorabbin | Window clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL57 | 109 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-09 | 109 | 0.375 | Wave 3 South
J1274 | JP0204 | Fairfield Dental | Main office - Box Hill | Office clean | Weekly | 2 | MO WE | 19:00 | 2.5 | CL22 | 146 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1265.33 | 5 | Wave 2 East
J1275 | JP0205 | Oakwood Medical Centre Pty Ltd | Main office - Coburg | Office clean | Weekly | 3 | MO TU TH | 17:30 | 1.5 | CL37 | 93 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 1209 | 4.5 | Wave 1 North
J1276 | JP0206 | Banksia Architects Pty Ltd | Main office - Frankston | Office clean | Weekly | 3 | MO TU TH | 19:30 | 3 | CL07 | 186 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 2418 | 9 | Wave 3 South
J1277 | JP0207 | Ironbark Engineering Pty Ltd | Main office - Preston | Office clean | Weekly | 3 | MO TU WE | 20:30 | 1.5 | CL33 | 99 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 1287 | 4.5 | Pilot
J1278 | JP0208 | Ironbark Engineering Pty Ltd | Clinic - Thornbury | Office clean | Weekly | 5 | MO TU WE TH FR | 21:00 | 2 | CL17 | 135 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 2925 | 10 | Wave 1 North
J1279 | JP0209 | Wattle Grove Financial Planning | Main office - Northcote | Office clean | Weekly | 2 | TH FR | 05:30 | 2 | CL25 | 130 | Per visit, billed monthly | Auto | Active | 2026-07-09 | 1126.67 | 4 | Wave 1 North
J1280 | JP0210 | Parkside Fitness Pty Ltd | Main office - Burwood | Office clean | Weekly | 2 | MO TU | 19:30 | 1.5 | CL50 | 90 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 780 | 3 | Wave 2 East
J1281 | JP0211 | Parkside Fitness Pty Ltd | Clinic - Maribyrnong | Office clean | Weekly | 1 | FR | 07:00 | 1 | CL20 | 75 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-24 | 325 | 1 | Wave 4 West
J1282 | JP0211 | Parkside Fitness Pty Ltd | Clinic - Maribyrnong | Window clean | Every 4 weeks | 0 | TU | 11:00 | 2 | CL57 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-06-30 | 146 | 0.5 | Wave 4 West
J1283 | JP0212 | Greenway Chiropractic Pty Ltd | Main office - Ringwood | Office clean | Weekly | 5 | MO TU WE TH FR | 20:30 | 1.5 | CL06 | 93 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 2015 | 7.5 | Wave 2 East
J1284 | JP0212 | Greenway Chiropractic Pty Ltd | Main office - Ringwood | Window clean | Every 4 weeks | 0 | FR | 09:00 | 3 | CL54 | 218 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-10 | 218 | 0.75 | Wave 2 East
J1285 | JP0213 | Greenway Chiropractic Pty Ltd | Clinic - Kew | Office clean | Weekly | 5 | MO TU WE TH FR | 19:30 | 3 | CL38 | 175 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 3791.67 | 15 | Wave 2 East
J1286 | JP0214 | Greenway Chiropractic Pty Ltd | Warehouse - Burwood | Office clean | Weekly | 5 | MO TU WE TH FR | 19:00 | 2 | CL02 | 116 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 2513.33 | 10 | Wave 2 East
J1287 | JP0215 | Bayview Real Estate Pty Ltd | Main office - Brighton | Office clean | Weekly | 3 | MO TU WE | 19:00 | 1.5 | CL11 | 102 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 1326 | 4.5 | Wave 3 South
J1288 | JP0216 | Riverside Pharmacy | Main office - Box Hill | Kitchen and bathrooms | Weekly | 2 | WE TH | 19:00 | 1 | CL34 | 66 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 572 | 2 | Wave 2 East
J1289 | JP0217 | Riverside Pharmacy | Clinic - Glen Waverley | Office clean | Weekly | 5 | MO TU WE TH FR | 20:00 | 2 | CL30 | 121 | Per visit, billed monthly | Auto | Active | 2026-07-20 | 2621.67 | 10 | Wave 2 East
J1290 | JP0217 | Riverside Pharmacy | Clinic - Glen Waverley | Window clean | Every 4 weeks | 0 | MO | 09:00 | 3 | CL54 | 234 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-13 | 234 | 0.75 | Wave 2 East
J1291 | JP0217 | Riverside Pharmacy | Clinic - Glen Waverley | Washroom service | Monthly | 0 | FR | 10:00 | 0.5 | CL54 | 99 | Fixed monthly | Outside Jobber | Active | 2026-07-17 | 99 | 0.125 | Wave 2 East
J1292 | JP0218 | Elm Street Chiropractic Pty Ltd | Main office - Mentone | Office clean | Weekly | 2 | MO TH | 17:30 | 2 | CL23 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-20 | 1048.67 | 4 | Wave 3 South
J1293 | JP0218 | Elm Street Chiropractic Pty Ltd | Main office - Mentone | Window clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL55 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-23 | 116 | 0.375 | Wave 3 South
J1294 | JP0219 | Elm Street Chiropractic Pty Ltd | Clinic - Cheltenham | Office clean | Weekly | 1 | FR | 05:30 | 2.5 | CL47 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-03 | 697.67 | 2.5 | Wave 3 South
J1295 | JP0219 | Elm Street Chiropractic Pty Ltd | Clinic - Cheltenham | Washroom service | Monthly | 0 | TU | 09:00 | 0.5 | CL55 | 151 | Fixed monthly | Outside Jobber | Active | 2026-07-14 | 151 | 0.125 | Wave 3 South
J1296 | JP0220 | Ironbark Real Estate Pty Ltd | Main office - Oakleigh | Office clean | Weekly | 1 | TH | 19:30 | 1 | CL35 | 70 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-09 | 303.33 | 1 | Wave 3 South
J1297 | JP0221 | Ironbark Real Estate Pty Ltd | Clinic - Oakleigh | Office clean | Weekly | 2 | TU WE | 05:30 | 2 | CL03 | 121 | Per visit, billed monthly | Auto | Active | 2026-07-21 | 1048.67 | 4 | Wave 3 South
J1298 | JP0222 | Elm Street Motors | Main office - Brighton | Office clean | Weekly | 1 | TU | 05:30 | 3 | CL19 | 187 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 810.33 | 3 | Wave 3 South
J1299 | JP0223 | Elm Street Motors | Clinic - Oakleigh | Kitchen and bathrooms | Weekly | 1 | TU | 08:00 | 0.5 | CL43 | 35 | Per visit, billed monthly | Auto | Active | 2026-07-07 | 151.67 | 0.5 | Wave 3 South
J1300 | JP0224 | Sunbury Engineering | Main office - Point Cook | Office clean | Weekly | 3 | MO WE FR | 21:00 | 1 | CL40 | 71 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 923 | 3 | Wave 4 West
J1301 | JP0225 | Ashwood Dental Pty Ltd | Main office - Northcote | Office clean | Weekly | 2 | TU TH | 07:30 | 1 | CL29 | 75 | Per visit, billed monthly | Auto | Active | 2026-07-14 | 650 | 2 | Wave 1 North
J1302 | JP0226 | Ashwood Dental Pty Ltd | Clinic - Mentone | Kitchen and bathrooms | Weekly | 1 | FR | 05:30 | 0.5 | CL35 | 35 | Per visit, billed monthly | Auto | Active | 2026-07-10 | 151.67 | 0.5 | Wave 3 South
J1303 | JP0227 | Bluestone Early Learning Pty Ltd | Main office - Altona | Office clean | Weekly | 5 | MO TU WE TH FR | 19:00 | 1.5 | CL48 | 102 | Per visit, billed monthly | Auto | Active | 2026-06-29 | 2210 | 7.5 | Wave 4 West
J1304 | JP0227 | Bluestone Early Learning Pty Ltd | Main office - Altona | Window clean | Every 4 weeks | 0 | TU | 09:00 | 2 | CL55 | 135 | Fixed 4-weekly | Auto | Active | 2026-07-14 | 135 | 0.5 | Wave 4 West
J1305 | JP0228 | Bluestone Early Learning Pty Ltd | Clinic - Hawthorn | Office clean | Weekly | 5 | MO TU WE TH FR | 20:30 | 1.5 | CL42 | 93 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 2015 | 7.5 | Wave 2 East
J1306 | JP0228 | Bluestone Early Learning Pty Ltd | Clinic - Hawthorn | Window clean | Every 4 weeks | 0 | TH | 09:00 | 2 | CL55 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-09 | 146 | 0.5 | Wave 2 East
J1307 | JP0228 | Bluestone Early Learning Pty Ltd | Clinic - Hawthorn | Washroom service | Monthly | 0 | TH | 10:00 | 0.5 | CL56 | 88 | Fixed monthly | Outside Jobber | Active | 2026-07-23 | 88 | 0.125 | Wave 2 East
J1308 | JP0229 | Harbourside Property Group | Main office - Maribyrnong | Office clean | Weekly | 1 | MO | 07:00 | 1.5 | CL28 | 96 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 416 | 1.5 | Wave 4 West
J1309 | JP0229 | Harbourside Property Group | Main office - Maribyrnong | Carpet steam clean | Every 4 weeks | 0 | MO | 09:00 | 2 | CL54 | 146 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-06 | 146 | 0.5 | Wave 4 West
J1310 | JP0229 | Harbourside Property Group | Main office - Maribyrnong | Washroom service | Monthly | 0 | TH | 09:00 | 0.5 | CL54 | 99 | Fixed monthly | Outside Jobber | Active | 2026-07-16 | 99 | 0.125 | Wave 4 West
J1311 | JP0230 | Riverside Engineering Pty Ltd | Main office - Bundoora | Office clean | Weekly | 1 | MO | 05:30 | 1 | CL21 | 68 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 294.67 | 1 | Wave 1 North
J1312 | JP0231 | Ashwood Lawyers | Main office - Werribee | Kitchen and bathrooms | Weekly | 2 | WE FR | 17:30 | 1 | CL44 | 68 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-22 | 589.33 | 2 | Wave 4 West
J1313 | JP0232 | Bayview Fitness Pty Ltd | Main office - Thornbury | Office clean | Weekly | 1 | WE | 17:30 | 1.5 | CL41 | 94 | Per visit, billed monthly | Auto | Active | 2026-07-08 | 407.33 | 1.5 | Wave 1 North
J1314 | JP0233 | Ironbark Property Group Pty Ltd | Main office - Mitcham | Kitchen and bathrooms | Weekly | 2 | TH FR | 19:30 | 0.5 | CL46 | 42 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-09 | 364 | 1 | Wave 2 East
J1315 | JP0234 | Ironbark Property Group Pty Ltd | Clinic - Reservoir | Office clean | Weekly | 5 | MO TU WE TH FR | 19:00 | 2 | CL49 | 125 | Per visit, billed monthly | Auto | Active | 2026-07-13 | 2708.33 | 10 | Wave 1 North
J1316 | JP0234 | Ironbark Property Group Pty Ltd | Clinic - Reservoir | Washroom service | Monthly | 0 | TH | 11:00 | 0.5 | CL55 | 151 | Fixed monthly | Outside Jobber | Active | 2026-07-23 | 151 | 0.125 | Wave 1 North
J1317 | JP0235 | Oakwood Engineering | Main office - Burwood | Office clean | Weekly | 2 | TU TH | 05:30 | 2 | CL46 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-21 | 1048.67 | 4 | Wave 2 East
J1318 | JP0235 | Oakwood Engineering | Main office - Burwood | Window clean | Every 4 weeks | 0 | TU | 09:00 | 3 | CL54 | 218 | Fixed 4-weekly | Auto | Active | 2026-07-21 | 218 | 0.75 | Wave 2 East
J1319 | JP0236 | Waverley Physiotherapy Pty Ltd | Main office - Bentleigh | Office clean | Weekly | 2 | MO FR | 20:00 | 2 | CL43 | 122 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 1057.33 | 4 | Wave 3 South
J1320 | JP0237 | Waverley Physiotherapy Pty Ltd | Clinic - Bentleigh | Office clean | Weekly | 1 | TH | 05:30 | 2.5 | CL39 | 166 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-16 | 719.33 | 2.5 | Wave 3 South
J1321 | JP0237 | Waverley Physiotherapy Pty Ltd | Clinic - Bentleigh | Carpet steam clean | Every 4 weeks | 0 | TU | 09:00 | 3 | CL55 | 203 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-21 | 203 | 0.75 | Wave 3 South
J1322 | JP0238 | Waverley Physiotherapy Pty Ltd | Warehouse - St Kilda | Office clean | Weekly | 1 | MO | 05:30 | 2.5 | CL35 | 161 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 697.67 | 2.5 | Wave 3 South
J1323 | JP0239 | Harbourside Insurance Brokers Pty Ltd | Main office - Northcote | Office clean | Weekly | 1 | TU | 19:00 | 3 | CL45 | 181 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-14 | 784.33 | 3 | Wave 1 North
J1324 | JP0240 | Harbourside Real Estate | Main office - Glen Waverley | Office clean | Weekly | 1 | WE | 19:30 | 1.5 | CL50 | 101 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 437.67 | 1.5 | Wave 2 East
J1325 | JP0241 | Harbourside Real Estate | Clinic - Clayton | Office clean | Weekly | 2 | TU FR | 05:30 | 3 | CL31 | 193 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 1672.67 | 6 | Wave 3 South
J1326 | JP0242 | Eastwood Podiatry | Main office - Coburg | Office clean | Weekly | 5 | MO TU WE TH FR | 20:30 | 2 | CL09 | 121 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 2621.67 | 10 | Pilot
J1327 | JP0243 | Cityside Real Estate | Main office - Moorabbin | Office clean | Weekly | 1 | FR | 17:30 | 2 | CL47 | 134 | Per visit, billed monthly | Auto | Active | 2026-07-17 | 580.67 | 2 | Wave 3 South
J1328 | JP0244 | Cityside Real Estate | Clinic - Moorabbin | Office clean | Weekly | 1 | WE | 20:00 | 1.5 | CL15 | 104 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 450.67 | 1.5 | Wave 3 South
J1329 | JP0244 | Cityside Real Estate | Clinic - Moorabbin | Window clean | Every 4 weeks | 0 | TH | 09:00 | 1.5 | CL54 | 116 | Fixed 4-weekly | Outside Jobber | Active | 2026-07-09 | 116 | 0.375 | Wave 3 South
J1330 | JP0245 | Parkside Dental | Main office - Mentone | Office clean | Weekly | 3 | MO TH FR | 20:00 | 1.5 | CL15 | 101 | Per visit, billed monthly | Outside Jobber | Active | 2026-06-29 | 1313 | 4.5 | Wave 3 South
J1331 | JP0245 | Parkside Dental | Main office - Mentone | Washroom service | Monthly | 0 | TU | 09:00 | 0.5 | CL56 | 151 | Fixed monthly | Outside Jobber | Active | 2026-07-21 | 151 | 0.125 | Wave 3 South
J1332 | JP0246 | Parkside Dental Group | Main office - Point Cook | Office clean | Weekly | 3 | TU WE TH | 07:00 | 1.5 | CL04 | 107 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 1391 | 4.5 | Wave 4 West
J1333 | JP0247 | Northside Physiotherapy | Main office - Brighton | Kitchen and bathrooms | Weekly | 2 | MO TH | 07:00 | 1 | CL19 | 69 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-13 | 598 | 2 | Wave 3 South
J1334 | JP0248 | Northside Physiotherapy | Clinic - Werribee | Office clean | Weekly | 2 | WE TH | 17:30 | 3 | CL20 | 192 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-01 | 1664 | 6 | Wave 4 West
J1335 | JP0249 | North Side Physiotherapy | Main office - Point Cook | Office clean | Weekly | 1 | FR | 05:30 | 2 | CL32 | 131 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-17 | 567.67 | 2 | Wave 4 West
J1336 | JP0249 | North Side Physiotherapy | Main office - Point Cook | Window clean | Every 4 weeks | 0 | TH | 11:30 | 3 | CL55 | 203 | Fixed 4-weekly | Auto | Active | 2026-07-09 | 203 | 0.75 | Wave 4 West
J1337 | JP0250 | North Side Physiotherapy | Clinic - Essendon | Office clean | Weekly | 1 | MO | 19:00 | 3 | CL21 | 185 | Per visit, billed monthly | Auto | Active | 2026-07-06 | 801.67 | 3 | Wave 1 North
J1338 | JP0251 | Bayview Accountants | Main office - Kew | Office clean | Weekly | 1 | MO | 05:30 | 1.5 | CL18 | 99 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-06 | 429 | 1.5 | Wave 2 East
J1339 | JP0252 | Bay View Accountants | Main office - Maribyrnong | Office clean | Weekly | 1 | TU | 17:30 | 2 | CL36 | 126 | Per visit, billed monthly | Outside Jobber | Active | 2026-07-07 | 546 | 2 | Wave 4 West
J1340 | JP0205 | Oakwood Medical Centre Pty Ltd | Main office - Coburg | Office clean | Weekly | 1 | WE | 18:00 | 1.5 | CL13 | 87 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-22 | 377 | 0 | Wave 1 North
J1341 | JP0148 | Kingsley Fitness Pty Ltd | Main office - Werribee | Office clean | Weekly | 1 | MO | 06:00 | 1 | CL08 | 61 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-20 | 264.33 | 0 | Wave 4 West
J1342 | JP0120 | Wattle Grove Fitness | Clinic - St Kilda | Office clean | Weekly | 1 | FR | 06:00 | 3 | CL03 | 178 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-24 | 771.33 | 0 | Wave 3 South
J1343 | JP0174 | Southgate Pathology | Warehouse - Altona | Office clean | Weekly | 2 | MO TU | 18:00 | 2 | CL08 | 120 | Per visit, billed monthly | Outside Jobber | Archived | 2026-06-29 | 1040 | 0 | Wave 4 West
J1344 | JP0001 | Oakwood Vet Clinic | Main office - Bentleigh | Office clean | Weekly | 1 | MO | 18:00 | 2 | CL51 | 126 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-06 | 546 | 0 | Wave 3 South
J1345 | JP0168 | Hillcrest Lawyers | Clinic - Northcote | Office clean | Weekly | 2 | TU TH | 18:00 | 1.5 | CL37 | 95 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-14 | 823.33 | 0 | Wave 1 North
J1346 | JP0143 | Sunbury Architects Pty Ltd | Main office - Epping | Office clean | Weekly | 3 | MO TU TH | 18:00 | 1.5 | CL13 | 98 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-06 | 1274 | 0 | Wave 1 North
J1347 | JP0033 | Brightside Podiatry | Main office - Camberwell | Office clean | Weekly | 1 | TH | 19:00 | 1 | CL10 | 63 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-16 | 273 | 0 | Wave 2 East
J1348 | JP0191 | Elm Street Early Learning | Main office - Hawthorn | Office clean | Weekly | 1 | MO | 18:00 | 2 | CL14 | 124 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-06 | 537.33 | 0 | Wave 2 East
J1349 | JP0177 | Lakeside Real Estate Pty Ltd | Main office - Brunswick | Office clean | Weekly | 2 | TU WE | 06:00 | 1.5 | CL49 | 90 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-21 | 780 | 0 | Wave 1 North
J1350 | JP0127 | Lakeside Architects | Clinic - Mitcham | Office clean | Weekly | 1 | WE | 06:00 | 3 | CL42 | 186 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-08 | 806 | 0 | Wave 2 East
J1351 | JP0219 | Elm Street Chiropractic Pty Ltd | Clinic - Cheltenham | Office clean | Weekly | 1 | FR | 19:00 | 2.5 | CL51 | 145 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-24 | 628.33 | 0 | Wave 3 South
J1352 | JP0023 | Oakwood Accountants Pty Ltd | Main office - Reservoir | Office clean | Weekly | 3 | TU TH FR | 18:00 | 2.5 | CL33 | 155 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-21 | 2015 | 0 | Pilot
J1353 | JP0201 | Elm Street Pathology Pty Ltd | Main office - Maribyrnong | Office clean | Weekly | 2 | TU FR | 06:00 | 1 | CL12 | 58 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-14 | 502.67 | 0 | Wave 4 West
J1354 | JP0042 | Oakwood Lawyers Pty Ltd | Main office - Moorabbin | Office clean | Weekly | 3 | WE TH FR | 19:00 | 1.5 | CL51 | 94 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-08 | 1222 | 0 | Wave 3 South
J1355 | JP0089 | Ashwood Physiotherapy | Clinic - Camberwell | Office clean | Weekly | 1 | TH | 06:00 | 1.5 | CL30 | 100 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-02 | 433.33 | 0 | Wave 2 East
J1356 | JP0184 | Riverside Dental Pty Ltd | Main office - Northcote | Office clean | Weekly | 3 | TU WE FR | 19:00 | 1.5 | CL09 | 100 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-14 | 1300 | 0 | Pilot
J1357 | JP0088 | Ashwood Physiotherapy | Main office - Point Cook | Office clean | Weekly | 1 | WE | 18:00 | 2 | CL08 | 126 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-22 | 546 | 0 | Wave 4 West
J1358 | JP0236 | Waverley Physiotherapy Pty Ltd | Main office - Bentleigh | Office clean | Weekly | 2 | MO TU | 06:00 | 2 | CL35 | 124 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-06 | 1074.67 | 0 | Wave 3 South
J1359 | JP0134 | Riverside Learning Centre | Clinic - Cheltenham | Office clean | Weekly | 3 | MO TU TH | 18:00 | 2 | CL43 | 125 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-13 | 1625 | 0 | Wave 3 South
J1360 | JP0063 | Clearwater Property Group Pty Ltd | Main office - Frankston | Office clean | Weekly | 2 | MO FR | 18:00 | 2 | CL47 | 120 | Per visit, billed monthly | Outside Jobber | Archived | 2026-06-29 | 1040 | 0 | Wave 3 South
J1361 | JP0162 | Redgum Podiatry | Main office - Williamstown | Office clean | Weekly | 3 | TU TH FR | 06:00 | 1 | CL12 | 67 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-07 | 871 | 0 | Wave 4 West
J1362 | JP0024 | Northside Engineering Pty Ltd | Main office - St Kilda | Office clean | Weekly | 3 | MO TH FR | 19:00 | 1.5 | CL51 | 103 | Per visit, billed monthly | Outside Jobber | Archived | 2026-07-06 | 1339 | 0 | Wave 3 South
J1363 | JP0072 | Kingsley Insurance Brokers | Main office - Reservoir | Office clean | Weekly | 1 | TU | 18:00 | 2 | CL33 | 117 | Per visit, billed monthly | Outside Jobber | Archived | 2026-06-30 | 507 | 0 | Pilot

## Jobber Invoices
Jobber invoices Aug-Oct 2026 (issued on the 1st for the previous month)
Work sample: realistic data, built to show how I approach this work.
Invoice | Job | Client | Date | Visits | Amount | Service month
JB-5001 | J1001 | Oakwood Vet Clinic | 2026-09-01 | 3 | 550.33 | 2026-08
JB-5002 | J1001 | Oakwood Vet Clinic | 2026-10-01 | 5 | 550.33 | 2026-09
JB-5003 | J1001 | Oakwood Vet Clinic | 2026-11-01 | 4 | 550.33 | 2026-10
JB-5004 | J1003 | Oakwood Vet Clinic | 2026-09-01 | 1 | 218 | 2026-08
JB-5005 | J1003 | Oakwood Vet Clinic | 2026-10-01 | 1 | 218 | 2026-09
JB-5006 | J1003 | Oakwood Vet Clinic | 2026-11-01 | 1 | 218 | 2026-10
JB-5007 | J1005 | Riverside Insurance Brokers Pty Ltd | 2026-09-01 | 8 | 606.67 | 2026-08
JB-5008 | J1005 | Riverside Insurance Brokers Pty Ltd | 2026-10-01 | 10 | 606.67 | 2026-09
JB-5009 | J1005 | Riverside Insurance Brokers Pty Ltd | 2026-11-01 | 8 | 606.67 | 2026-10
JB-5010 | J1012 | Elm Street Physiotherapy | 2026-09-01 | 9 | 632.67 | 2026-08
JB-5011 | J1012 | Elm Street Physiotherapy | 2026-10-01 | 7 | 632.67 | 2026-09
JB-5012 | J1012 | Elm Street Physiotherapy | 2026-11-01 | 8 | 632.67 | 2026-10
JB-5013 | J1013 | Elm Street Physiotherapy | 2026-09-01 | 1 | 99 | 2026-08
JB-5014 | J1013 | Elm Street Physiotherapy | 2026-10-01 | 1 | 99 | 2026-09
JB-5015 | J1013 | Elm Street Physiotherapy | 2026-11-01 | 1 | 99 | 2026-10
JB-5016 | J1014 | Wattle Grove Property Group | 2026-09-01 | 9 | 589.33 | 2026-08
JB-5017 | J1014 | Wattle Grove Property Group | 2026-10-01 | 9 | 589.33 | 2026-09
JB-5018 | J1014 | Wattle Grove Property Group | 2026-11-01 | 8 | 589.33 | 2026-10
JB-5019 | J1020 | Wattle Grove Medical Centre Pty Ltd | 2026-09-01 | 4 | 806 | 2026-08
JB-5020 | J1020 | Wattle Grove Medical Centre Pty Ltd | 2026-10-01 | 4 | 806 | 2026-09
JB-5021 | J1020 | Wattle Grove Medical Centre Pty Ltd | 2026-11-01 | 5 | 806 | 2026-10
JB-5022 | J1031 | Northside Engineering Pty Ltd | 2026-09-01 | 8 | 806 | 2026-08
JB-5023 | J1031 | Northside Engineering Pty Ltd | 2026-10-01 | 9 | 806 | 2026-09
JB-5024 | J1031 | Northside Engineering Pty Ltd | 2026-11-01 | 8 | 806 | 2026-10
JB-5025 | J1032 | Northside Engineering Pty Ltd | 2026-09-01 | 1 | 234 | 2026-08
JB-5026 | J1032 | Northside Engineering Pty Ltd | 2026-10-01 | 1 | 234 | 2026-09
JB-5027 | J1032 | Northside Engineering Pty Ltd | 2026-11-01 | 1 | 234 | 2026-10
JB-5028 | J1036 | Ashwood Early Learning | 2026-09-01 | 1 | 203 | 2026-08
JB-5029 | J1036 | Ashwood Early Learning | 2026-10-01 | 1 | 203 | 2026-09
JB-5030 | J1036 | Ashwood Early Learning | 2026-11-01 | 1 | 203 | 2026-10
JB-5031 | J1038 | Silverton Pharmacy | 2026-09-01 | 3 | 299 | 2026-08
JB-5032 | J1038 | Silverton Pharmacy | 2026-10-01 | 4 | 299 | 2026-09
JB-5033 | J1038 | Silverton Pharmacy | 2026-11-01 | 5 | 299 | 2026-10
JB-5034 | J1043 | Ashwood Optometrists | 2026-09-01 | 8 | 1083.33 | 2026-08
JB-5035 | J1043 | Ashwood Optometrists | 2026-10-01 | 9 | 1083.33 | 2026-09
JB-5036 | J1043 | Ashwood Optometrists | 2026-11-01 | 8 | 1083.33 | 2026-10
JB-5037 | J1045 | Ashwood Optometrists | 2026-09-01 | 4 | 173.33 | 2026-08
JB-5038 | J1045 | Ashwood Optometrists | 2026-10-01 | 4 | 173.33 | 2026-09
JB-5039 | J1045 | Ashwood Optometrists | 2026-11-01 | 5 | 173.33 | 2026-10
JB-5040 | J1050 | Brightside Motors Pty Ltd | 2026-09-01 | 4 | 437.67 | 2026-08
JB-5041 | J1050 | Brightside Motors Pty Ltd | 2026-10-01 | 3 | 437.67 | 2026-09
JB-5042 | J1050 | Brightside Motors Pty Ltd | 2026-11-01 | 4 | 437.67 | 2026-10
JB-5043 | J1054 | Oakwood Lawyers Pty Ltd | 2026-09-01 | 4 | 502.67 | 2026-08
JB-5044 | J1054 | Oakwood Lawyers Pty Ltd | 2026-10-01 | 5 | 502.67 | 2026-09
JB-5045 | J1054 | Oakwood Lawyers Pty Ltd | 2026-11-01 | 3 | 502.67 | 2026-10
JB-5046 | J1056 | Riverside Medical Centre | 2026-09-01 | 5 | 390 | 2026-08
JB-5047 | J1056 | Riverside Medical Centre | 2026-10-01 | 4 | 390 | 2026-09
JB-5048 | J1056 | Riverside Medical Centre | 2026-11-01 | 4 | 390 | 2026-10
JB-5049 | J1061 | Silverton Lawyers Pty Ltd | 2026-09-01 | 8 | 1100.67 | 2026-08
JB-5050 | J1061 | Silverton Lawyers Pty Ltd | 2026-10-01 | 8 | 1100.67 | 2026-09
JB-5051 | J1061 | Silverton Lawyers Pty Ltd | 2026-11-01 | 9 | 1100.67 | 2026-10
JB-5052 | J1062 | Waverley Accountants Pty Ltd | 2026-09-01 | 21 | 2513.33 | 2026-08
JB-5053 | J1062 | Waverley Accountants Pty Ltd | 2026-10-01 | 22 | 2513.33 | 2026-09
JB-5054 | J1062 | Waverley Accountants Pty Ltd | 2026-11-01 | 22 | 2513.33 | 2026-10
JB-5055 | J1063 | Waverley Accountants Pty Ltd | 2026-09-01 | 1 | 218 | 2026-08
JB-5056 | J1063 | Waverley Accountants Pty Ltd | 2026-10-01 | 1 | 218 | 2026-09
JB-5057 | J1063 | Waverley Accountants Pty Ltd | 2026-11-01 | 2 | 436 | 2026-10
JB-5058 | J1074 | Elm Street Fitness Pty Ltd | 2026-09-01 | 1 | 218 | 2026-08
JB-5059 | J1074 | Elm Street Fitness Pty Ltd | 2026-10-01 | 1 | 218 | 2026-09
JB-5060 | J1074 | Elm Street Fitness Pty Ltd | 2026-11-01 | 1 | 218 | 2026-10
JB-5061 | J1075 | Elm Street Fitness Pty Ltd | 2026-09-01 | 9 | 320.67 | 2026-08
JB-5062 | J1075 | Elm Street Fitness Pty Ltd | 2026-10-01 | 8 | 320.67 | 2026-09
JB-5063 | J1075 | Elm Street Fitness Pty Ltd | 2026-11-01 | 9 | 320.67 | 2026-10
JB-5064 | J1084 | Clearwater Property Group Pty Ltd | 2026-09-01 | 0 | 234 | 2026-08
JB-5065 | J1084 | Clearwater Property Group Pty Ltd | 2026-10-01 | 1 | 234 | 2026-09
JB-5066 | J1084 | Clearwater Property Group Pty Ltd | 2026-11-01 | 1 | 234 | 2026-10
JB-5067 | J1088 | Clearwater Physiotherapy | 2026-09-01 | 3 | 299 | 2026-08
JB-5068 | J1088 | Clearwater Physiotherapy | 2026-10-01 | 4 | 299 | 2026-09
JB-5069 | J1088 | Clearwater Physiotherapy | 2026-11-01 | 3 | 299 | 2026-10
JB-5070 | J1097 | Kingsley Insurance Brokers | 2026-09-01 | 8 | 1716 | 2026-08
JB-5071 | J1097 | Kingsley Insurance Brokers | 2026-10-01 | 9 | 1716 | 2026-09
JB-5072 | J1097 | Kingsley Insurance Brokers | 2026-11-01 | 9 | 1716 | 2026-10
JB-5073 | J1101 | Kingsley Insurance Brokers | 2026-09-01 | 2 | 436 | 2026-08
JB-5074 | J1101 | Kingsley Insurance Brokers | 2026-10-01 | 1 | 218 | 2026-09
JB-5075 | J1101 | Kingsley Insurance Brokers | 2026-11-01 | 1 | 218 | 2026-10
JB-5076 | J1102 | Bluestone Learning Centre Pty Ltd | 2026-09-01 | 9 | 875.33 | 2026-08
JB-5077 | J1102 | Bluestone Learning Centre Pty Ltd | 2026-10-01 | 9 | 875.33 | 2026-09
JB-5078 | J1102 | Bluestone Learning Centre Pty Ltd | 2026-11-01 | 8 | 875.33 | 2026-10
JB-5079 | J1106 | Oakwood Logistics | 2026-09-01 | 13 | 546 | 2026-08
JB-5080 | J1106 | Oakwood Logistics | 2026-10-01 | 12 | 546 | 2026-09
JB-5081 | J1106 | Oakwood Logistics | 2026-11-01 | 14 | 546 | 2026-10
JB-5082 | J1113 | Sunbury Lawyers Pty Ltd | 2026-09-01 | 9 | 814.67 | 2026-08
JB-5083 | J1113 | Sunbury Lawyers Pty Ltd | 2026-10-01 | 8 | 814.67 | 2026-09
JB-5084 | J1113 | Sunbury Lawyers Pty Ltd | 2026-11-01 | 8 | 814.67 | 2026-10
JB-5085 | J1123 | Ashwood Physiotherapy | 2026-09-01 | 1 | 135 | 2026-08
JB-5086 | J1123 | Ashwood Physiotherapy | 2026-10-01 | 0 | 135 | 2026-09
JB-5087 | J1123 | Ashwood Physiotherapy | 2026-11-01 | 1 | 135 | 2026-10
JB-5088 | J1126 | Ashwood Physiotherapy | 2026-09-01 | 2 | 232 | 2026-08
JB-5089 | J1126 | Ashwood Physiotherapy | 2026-10-01 | 1 | 116 | 2026-09
JB-5090 | J1126 | Ashwood Physiotherapy | 2026-11-01 | 1 | 116 | 2026-10
JB-5091 | J1132 | Bluestone Dental | 2026-09-01 | 9 | 1135.33 | 2026-08
JB-5092 | J1132 | Bluestone Dental | 2026-10-01 | 7 | 1135.33 | 2026-09
JB-5093 | J1132 | Bluestone Dental | 2026-11-01 | 9 | 1135.33 | 2026-10
JB-5094 | J1140 | Bluestone Lawyers Pty Ltd | 2026-09-01 | 8 | 650 | 2026-08
JB-5095 | J1140 | Bluestone Lawyers Pty Ltd | 2026-10-01 | 10 | 650 | 2026-09
JB-5096 | J1140 | Bluestone Lawyers Pty Ltd | 2026-11-01 | 8 | 650 | 2026-10
JB-5097 | J1143 | Banksia Accountants | 2026-09-01 | 8 | 1092 | 2026-08
JB-5098 | J1143 | Banksia Accountants | 2026-10-01 | 9 | 1092 | 2026-09
JB-5099 | J1143 | Banksia Accountants | 2026-11-01 | 8 | 1092 | 2026-10
JB-5100 | J1168 | Ashwood Medical Centre | 2026-09-01 | 1 | 135 | 2026-08
JB-5101 | J1168 | Ashwood Medical Centre | 2026-10-01 | 1 | 135 | 2026-09
JB-5102 | J1168 | Ashwood Medical Centre | 2026-11-01 | 1 | 135 | 2026-10
JB-5103 | J1172 | Hillcrest Accountants | 2026-09-01 | 21 | 1343.33 | 2026-08
JB-5104 | J1172 | Hillcrest Accountants | 2026-10-01 | 22 | 1343.33 | 2026-09
JB-5105 | J1172 | Hillcrest Accountants | 2026-11-01 | 22 | 1343.33 | 2026-10
JB-5106 | J1173 | Hillcrest Accountants | 2026-09-01 | 1 | 116 | 2026-08
JB-5107 | J1173 | Hillcrest Accountants | 2026-10-01 | 1 | 116 | 2026-09
JB-5108 | J1173 | Hillcrest Accountants | 2026-11-01 | 1 | 116 | 2026-10
JB-5109 | J1183 | Riverside Learning Centre | 2026-09-01 | 7 | 1083.33 | 2026-08
JB-5110 | J1183 | Riverside Learning Centre | 2026-10-01 | 8 | 1083.33 | 2026-09
JB-5111 | J1183 | Riverside Learning Centre | 2026-11-01 | 9 | 1083.33 | 2026-10
JB-5112 | J1185 | Riverside Learning Centre | 2026-09-01 | 1 | 146 | 2026-08
JB-5113 | J1185 | Riverside Learning Centre | 2026-10-01 | 1 | 146 | 2026-09
JB-5114 | J1185 | Riverside Learning Centre | 2026-11-01 | 1 | 146 | 2026-10
JB-5115 | J1190 | Greenway Podiatry Pty Ltd | 2026-09-01 | 4 | 173.33 | 2026-08
JB-5116 | J1190 | Greenway Podiatry Pty Ltd | 2026-10-01 | 5 | 173.33 | 2026-09
JB-5117 | J1190 | Greenway Podiatry Pty Ltd | 2026-11-01 | 3 | 173.33 | 2026-10
JB-5118 | J1193 | Banksia Logistics | 2026-09-01 | 4 | 463.67 | 2026-08
JB-5119 | J1193 | Banksia Logistics | 2026-10-01 | 4 | 463.67 | 2026-09
JB-5120 | J1193 | Banksia Logistics | 2026-11-01 | 5 | 463.67 | 2026-10
JB-5121 | J1204 | Sunbury Optometrists | 2026-09-01 | 21 | 1495 | 2026-08
JB-5122 | J1204 | Sunbury Optometrists | 2026-10-01 | 22 | 1495 | 2026-09
JB-5123 | J1204 | Sunbury Optometrists | 2026-11-01 | 22 | 1495 | 2026-10
JB-5124 | J1206 | Bayview Vet Clinic | 2026-09-01 | 1 | 135 | 2026-08
JB-5125 | J1206 | Bayview Vet Clinic | 2026-10-01 | 1 | 135 | 2026-09
JB-5126 | J1206 | Bayview Vet Clinic | 2026-11-01 | 1 | 135 | 2026-10
JB-5127 | J1213 | Riverside Podiatry | 2026-09-01 | 13 | 1755 | 2026-08
JB-5128 | J1213 | Riverside Podiatry | 2026-10-01 | 13 | 1755 | 2026-09
JB-5129 | J1213 | Riverside Podiatry | 2026-11-01 | 13 | 1755 | 2026-10
JB-5130 | J1215 | Northside Learning Centre | 2026-09-01 | 20 | 1495 | 2026-08
JB-5131 | J1215 | Northside Learning Centre | 2026-10-01 | 22 | 1495 | 2026-09
JB-5132 | J1215 | Northside Learning Centre | 2026-11-01 | 22 | 1495 | 2026-10
JB-5133 | J1224 | Harbourside Chiropractic | 2026-09-01 | 20 | 2903.33 | 2026-08
JB-5134 | J1224 | Harbourside Chiropractic | 2026-10-01 | 22 | 2903.33 | 2026-09
JB-5135 | J1224 | Harbourside Chiropractic | 2026-11-01 | 22 | 2903.33 | 2026-10
JB-5136 | J1232 | Southgate Pathology | 2026-09-01 | 7 | 1672.67 | 2026-08
JB-5137 | J1232 | Southgate Pathology | 2026-10-01 | 10 | 1672.67 | 2026-09
JB-5138 | J1232 | Southgate Pathology | 2026-11-01 | 8 | 1672.67 | 2026-10
JB-5139 | J1240 | Lakeside Real Estate Pty Ltd | 2026-09-01 | 8 | 546 | 2026-08
JB-5140 | J1240 | Lakeside Real Estate Pty Ltd | 2026-10-01 | 9 | 546 | 2026-09
JB-5141 | J1240 | Lakeside Real Estate Pty Ltd | 2026-11-01 | 9 | 546 | 2026-10
JB-5142 | J1244 | Harbourside Pharmacy Pty Ltd | 2026-09-01 | 8 | 901.33 | 2026-08
JB-5143 | J1244 | Harbourside Pharmacy Pty Ltd | 2026-10-01 | 9 | 901.33 | 2026-09
JB-5144 | J1244 | Harbourside Pharmacy Pty Ltd | 2026-11-01 | 9 | 901.33 | 2026-10
JB-5145 | J1246 | Southgate Engineering | 2026-09-01 | 9 | 1092 | 2026-08
JB-5146 | J1246 | Southgate Engineering | 2026-10-01 | 9 | 1092 | 2026-09
JB-5147 | J1246 | Southgate Engineering | 2026-11-01 | 8 | 1092 | 2026-10
JB-5148 | J1247 | Riverside Dental Pty Ltd | 2026-09-01 | 4 | 268.67 | 2026-08
JB-5149 | J1247 | Riverside Dental Pty Ltd | 2026-10-01 | 4 | 268.67 | 2026-09
JB-5150 | J1247 | Riverside Dental Pty Ltd | 2026-11-01 | 5 | 268.67 | 2026-10
JB-5151 | J1252 | Ashwood Property Group | 2026-09-01 | 5 | 151.67 | 2026-08
JB-5152 | J1252 | Ashwood Property Group | 2026-10-01 | 4 | 151.67 | 2026-09
JB-5153 | J1252 | Ashwood Property Group | 2026-11-01 | 4 | 151.67 | 2026-10
JB-5154 | J1257 | Elm Street Early Learning | 2026-09-01 | 5 | 316.33 | 2026-08
JB-5155 | J1257 | Elm Street Early Learning | 2026-10-01 | 4 | 316.33 | 2026-09
JB-5156 | J1257 | Elm Street Early Learning | 2026-11-01 | 4 | 316.33 | 2026-10
JB-5157 | J1260 | Elm Street Early Learning | 2026-09-01 | 1 | 99 | 2026-08
JB-5158 | J1260 | Elm Street Early Learning | 2026-10-01 | 1 | 99 | 2026-09
JB-5159 | J1260 | Elm Street Early Learning | 2026-11-01 | 1 | 99 | 2026-10
JB-5160 | J1261 | Redgum Financial Planning | 2026-09-01 | 8 | 832 | 2026-08
JB-5161 | J1261 | Redgum Financial Planning | 2026-10-01 | 9 | 832 | 2026-09
JB-5162 | J1261 | Redgum Financial Planning | 2026-11-01 | 9 | 832 | 2026-10
JB-5163 | J1264 | Elm Street Logistics Pty Ltd | 2026-09-01 | 20 | 2101.67 | 2026-08
JB-5164 | J1264 | Elm Street Logistics Pty Ltd | 2026-10-01 | 22 | 2101.67 | 2026-09
JB-5165 | J1264 | Elm Street Logistics Pty Ltd | 2026-11-01 | 22 | 2101.67 | 2026-10
JB-5166 | J1265 | Elm Street Logistics Pty Ltd | 2026-09-01 | 9 | 537.33 | 2026-08
JB-5167 | J1265 | Elm Street Logistics Pty Ltd | 2026-10-01 | 9 | 537.33 | 2026-09
JB-5168 | J1265 | Elm Street Logistics Pty Ltd | 2026-11-01 | 8 | 537.33 | 2026-10
JB-5169 | J1268 | Lakeside Insurance Brokers | 2026-09-01 | 12 | 884 | 2026-08
JB-5170 | J1268 | Lakeside Insurance Brokers | 2026-10-01 | 13 | 884 | 2026-09
JB-5171 | J1268 | Lakeside Insurance Brokers | 2026-11-01 | 12 | 884 | 2026-10
JB-5172 | J1271 | Fairfield Accountants Pty Ltd | 2026-09-01 | 21 | 3271.67 | 2026-08
JB-5173 | J1271 | Fairfield Accountants Pty Ltd | 2026-10-01 | 22 | 3271.67 | 2026-09
JB-5174 | J1271 | Fairfield Accountants Pty Ltd | 2026-11-01 | 22 | 3271.67 | 2026-10
JB-5175 | J1275 | Oakwood Medical Centre Pty Ltd | 2026-09-01 | 13 | 1209 | 2026-08
JB-5176 | J1275 | Oakwood Medical Centre Pty Ltd | 2026-10-01 | 13 | 1209 | 2026-09
JB-5177 | J1275 | Oakwood Medical Centre Pty Ltd | 2026-11-01 | 13 | 1209 | 2026-10
JB-5178 | J1278 | Ironbark Engineering Pty Ltd | 2026-09-01 | 20 | 2925 | 2026-08
JB-5179 | J1278 | Ironbark Engineering Pty Ltd | 2026-10-01 | 21 | 2925 | 2026-09
JB-5180 | J1278 | Ironbark Engineering Pty Ltd | 2026-11-01 | 21 | 2925 | 2026-10
JB-5181 | J1279 | Wattle Grove Financial Planning | 2026-09-01 | 8 | 1126.67 | 2026-08
JB-5182 | J1279 | Wattle Grove Financial Planning | 2026-10-01 | 8 | 1126.67 | 2026-09
JB-5183 | J1279 | Wattle Grove Financial Planning | 2026-11-01 | 10 | 1126.67 | 2026-10
JB-5184 | J1285 | Greenway Chiropractic Pty Ltd | 2026-09-01 | 21 | 3791.67 | 2026-08
JB-5185 | J1285 | Greenway Chiropractic Pty Ltd | 2026-10-01 | 22 | 3791.67 | 2026-09
JB-5186 | J1285 | Greenway Chiropractic Pty Ltd | 2026-11-01 | 21 | 3791.67 | 2026-10
JB-5187 | J1289 | Riverside Pharmacy | 2026-09-01 | 21 | 2621.67 | 2026-08
JB-5188 | J1289 | Riverside Pharmacy | 2026-10-01 | 22 | 2621.67 | 2026-09
JB-5189 | J1289 | Riverside Pharmacy | 2026-11-01 | 22 | 2621.67 | 2026-10
JB-5190 | J1297 | Ironbark Real Estate Pty Ltd | 2026-09-01 | 8 | 1048.67 | 2026-08
JB-5191 | J1297 | Ironbark Real Estate Pty Ltd | 2026-10-01 | 9 | 1048.67 | 2026-09
JB-5192 | J1297 | Ironbark Real Estate Pty Ltd | 2026-11-01 | 8 | 1048.67 | 2026-10
JB-5193 | J1299 | Elm Street Motors | 2026-09-01 | 4 | 151.67 | 2026-08
JB-5194 | J1299 | Elm Street Motors | 2026-10-01 | 5 | 151.67 | 2026-09
JB-5195 | J1299 | Elm Street Motors | 2026-11-01 | 4 | 151.67 | 2026-10
JB-5196 | J1301 | Ashwood Dental Pty Ltd | 2026-09-01 | 7 | 650 | 2026-08
JB-5197 | J1301 | Ashwood Dental Pty Ltd | 2026-10-01 | 9 | 650 | 2026-09
JB-5198 | J1301 | Ashwood Dental Pty Ltd | 2026-11-01 | 9 | 650 | 2026-10
JB-5199 | J1302 | Ashwood Dental Pty Ltd | 2026-09-01 | 4 | 151.67 | 2026-08
JB-5200 | J1302 | Ashwood Dental Pty Ltd | 2026-10-01 | 4 | 151.67 | 2026-09
JB-5201 | J1302 | Ashwood Dental Pty Ltd | 2026-11-01 | 5 | 151.67 | 2026-10
JB-5202 | J1303 | Bluestone Early Learning Pty Ltd | 2026-09-01 | 21 | 2210 | 2026-08
JB-5203 | J1303 | Bluestone Early Learning Pty Ltd | 2026-10-01 | 21 | 2210 | 2026-09
JB-5204 | J1303 | Bluestone Early Learning Pty Ltd | 2026-11-01 | 22 | 2210 | 2026-10
JB-5205 | J1304 | Bluestone Early Learning Pty Ltd | 2026-09-01 | 0 | 135 | 2026-08
JB-5206 | J1304 | Bluestone Early Learning Pty Ltd | 2026-10-01 | 1 | 135 | 2026-09
JB-5207 | J1304 | Bluestone Early Learning Pty Ltd | 2026-11-01 | 1 | 135 | 2026-10
JB-5208 | J1308 | Harbourside Property Group | 2026-09-01 | 5 | 416 | 2026-08
JB-5209 | J1308 | Harbourside Property Group | 2026-10-01 | 4 | 416 | 2026-09
JB-5210 | J1308 | Harbourside Property Group | 2026-11-01 | 4 | 416 | 2026-10
JB-5211 | J1313 | Bayview Fitness Pty Ltd | 2026-09-01 | 4 | 407.33 | 2026-08
JB-5212 | J1313 | Bayview Fitness Pty Ltd | 2026-10-01 | 5 | 407.33 | 2026-09
JB-5213 | J1313 | Bayview Fitness Pty Ltd | 2026-11-01 | 4 | 407.33 | 2026-10
JB-5214 | J1315 | Ironbark Property Group Pty Ltd | 2026-09-01 | 20 | 2708.33 | 2026-08
JB-5215 | J1315 | Ironbark Property Group Pty Ltd | 2026-10-01 | 22 | 2708.33 | 2026-09
JB-5216 | J1315 | Ironbark Property Group Pty Ltd | 2026-11-01 | 22 | 2708.33 | 2026-10
JB-5217 | J1318 | Oakwood Engineering | 2026-09-01 | 1 | 218 | 2026-08
JB-5218 | J1318 | Oakwood Engineering | 2026-10-01 | 1 | 218 | 2026-09
JB-5219 | J1318 | Oakwood Engineering | 2026-11-01 | 1 | 218 | 2026-10
JB-5220 | J1319 | Waverley Physiotherapy Pty Ltd | 2026-09-01 | 9 | 1057.33 | 2026-08
JB-5221 | J1319 | Waverley Physiotherapy Pty Ltd | 2026-10-01 | 7 | 1057.33 | 2026-09
JB-5222 | J1319 | Waverley Physiotherapy Pty Ltd | 2026-11-01 | 9 | 1057.33 | 2026-10
JB-5223 | J1327 | Cityside Real Estate | 2026-09-01 | 4 | 580.67 | 2026-08
JB-5224 | J1327 | Cityside Real Estate | 2026-10-01 | 4 | 580.67 | 2026-09
JB-5225 | J1327 | Cityside Real Estate | 2026-11-01 | 5 | 580.67 | 2026-10
JB-5226 | J1336 | North Side Physiotherapy | 2026-09-01 | 1 | 203 | 2026-08
JB-5227 | J1336 | North Side Physiotherapy | 2026-10-01 | 1 | 203 | 2026-09
JB-5228 | J1336 | North Side Physiotherapy | 2026-11-01 | 2 | 406 | 2026-10
JB-5229 | J1337 | North Side Physiotherapy | 2026-09-01 | 5 | 801.67 | 2026-08
JB-5230 | J1337 | North Side Physiotherapy | 2026-10-01 | 4 | 801.67 | 2026-09
JB-5231 | J1337 | North Side Physiotherapy | 2026-11-01 | 4 | 801.67 | 2026-10
Formulas:
Service month = YEAR(EOMONTH([Date],-1))&"-"&TEXT(MONTH(EOMONTH([Date],-1)),"00")

## Jobber Visits
Jobber visit history Aug-Oct 2026
Work sample: realistic data, built to show how I approach this work.
Job | Date | Cleaner | Status
J1001 | 2026-08-04 | CL43 | Completed
J1001 | 2026-08-11 | CL43 | Completed
J1001 | 2026-08-18 | CL43 | Completed
J1001 | 2026-08-25 | CL43 | Skipped
J1001 | 2026-09-01 | CL43 | Completed
J1001 | 2026-09-08 | CL43 | Completed
J1001 | 2026-09-15 | CL43 | Completed
J1001 | 2026-09-22 | CL43 | Completed
J1001 | 2026-09-29 | CL43 | Completed
J1001 | 2026-10-06 | CL43 | Completed
J1001 | 2026-10-13 | CL43 | Completed
J1001 | 2026-10-20 | CL43 | Completed
J1001 | 2026-10-27 | CL43 | Completed
J1002 | 2026-08-04 | CL39 | Completed
J1002 | 2026-08-11 | CL39 | Completed
J1002 | 2026-08-18 | CL39 | Completed
J1002 | 2026-08-25 | CL39 | Completed
J1002 | 2026-09-01 | CL39 | Completed
J1002 | 2026-09-08 | CL39 | Completed
J1002 | 2026-09-15 | CL39 | Completed
J1002 | 2026-09-22 | CL39 | Completed
J1002 | 2026-09-29 | CL39 | Completed
J1002 | 2026-10-06 | CL39 | Completed
J1002 | 2026-10-13 | CL39 | Completed
J1002 | 2026-10-20 | CL39 | Completed
J1002 | 2026-10-27 | CL39 | Completed
J1003 | 2026-08-10 | CL59 | Completed
J1003 | 2026-09-07 | CL59 | Completed
J1003 | 2026-10-05 | CL59 | Completed
J1004 | 2026-08-03 | CL48 | Completed
J1004 | 2026-08-10 | CL48 | Completed
J1004 | 2026-08-17 | CL48 | Completed
J1004 | 2026-08-24 | CL48 | Completed
J1004 | 2026-08-31 | CL48 | Completed
J1004 | 2026-09-07 | CL48 | Completed
J1004 | 2026-09-14 | CL48 | Completed
J1004 | 2026-09-21 | CL48 | Completed
J1004 | 2026-09-28 | CL48 | Completed
J1004 | 2026-10-05 | CL48 | Completed
J1004 | 2026-10-12 | CL48 | Completed
J1004 | 2026-10-19 | CL48 | Completed
J1004 | 2026-10-26 | CL48 | Completed
J1005 | 2026-08-04 | CL37 | Completed
J1005 | 2026-08-05 | CL37 | Completed
J1005 | 2026-08-11 | CL37 | Completed
J1005 | 2026-08-12 | CL37 | Completed
J1005 | 2026-08-18 | CL37 | Completed
J1005 | 2026-08-19 | CL37 | Completed
J1005 | 2026-08-25 | CL37 | Completed
J1005 | 2026-08-26 | CL37 | Completed
J1005 | 2026-09-01 | CL37 | Completed
J1005 | 2026-09-02 | CL37 | Completed
J1005 | 2026-09-08 | CL37 | Completed
J1005 | 2026-09-09 | CL37 | Completed
J1005 | 2026-09-15 | CL37 | Completed
J1005 | 2026-09-16 | CL37 | Completed
J1005 | 2026-09-22 | CL37 | Completed
J1005 | 2026-09-23 | CL37 | Completed
J1005 | 2026-09-29 | CL37 | Completed
J1005 | 2026-09-30 | CL37 | Completed
J1005 | 2026-10-06 | CL37 | Completed
J1005 | 2026-10-07 | CL37 | Completed
J1005 | 2026-10-13 | CL37 | Completed
J1005 | 2026-10-14 | CL37 | Completed
J1005 | 2026-10-20 | CL37 | Completed
J1005 | 2026-10-21 | CL37 | Completed
J1005 | 2026-10-27 | CL37 | Completed
J1005 | 2026-10-28 | CL37 | Completed
J1006 | 2026-08-13 | CL60 | Completed
J1006 | 2026-09-10 | CL60 | Completed
J1006 | 2026-10-08 | CL60 | Completed
J1007 | 2026-08-03 | CL12 | Completed
J1007 | 2026-08-05 | CL12 | Completed
J1007 | 2026-08-10 | CL12 | Completed
J1007 | 2026-08-12 | CL12 | Completed
J1007 | 2026-08-17 | CL12 | Completed
J1007 | 2026-08-19 | CL12 | Completed
J1007 | 2026-08-24 | CL12 | Completed
J1007 | 2026-08-26 | CL12 | Completed
J1007 | 2026-08-31 | CL12 | Completed
J1007 | 2026-09-02 | CL12 | Completed
J1007 | 2026-09-07 | CL12 | Completed
J1007 | 2026-09-09 | CL12 | Completed
J1007 | 2026-09-14 | CL12 | Skipped
J1007 | 2026-09-16 | CL12 | Completed
J1007 | 2026-09-21 | CL12 | Completed
J1007 | 2026-09-23 | CL12 | Completed
J1007 | 2026-09-28 | CL12 | Completed
J1007 | 2026-09-30 | CL12 | Completed
J1007 | 2026-10-05 | CL12 | Completed
J1007 | 2026-10-07 | CL12 | Completed
J1007 | 2026-10-12 | CL12 | Completed
J1007 | 2026-10-14 | CL12 | Completed
J1007 | 2026-10-19 | CL12 | Completed
J1007 | 2026-10-21 | CL12 | Completed
J1007 | 2026-10-26 | CL12 | Completed
J1007 | 2026-10-28 | CL12 | Completed
J1008 | 2026-08-05 | CL23 | Completed
J1008 | 2026-08-06 | CL23 | Completed
J1008 | 2026-08-07 | CL23 | Completed
J1008 | 2026-08-12 | CL23 | Completed
J1008 | 2026-08-13 | CL23 | Completed
J1008 | 2026-08-14 | CL23 | Completed
J1008 | 2026-08-19 | CL23 | Completed
J1008 | 2026-08-20 | CL23 | Completed
J1008 | 2026-08-21 | CL23 | Completed
J1008 | 2026-08-26 | CL23 | Completed
J1008 | 2026-08-27 | CL23 | Completed
J1008 | 2026-08-28 | CL23 | Completed
J1008 | 2026-09-02 | CL23 | Completed
J1008 | 2026-09-03 | CL23 | Completed
J1008 | 2026-09-04 | CL23 | Completed
J1008 | 2026-09-09 | CL23 | Completed
J1008 | 2026-09-10 | CL23 | Completed
J1008 | 2026-09-11 | CL23 | Completed
J1008 | 2026-09-16 | CL23 | Completed
J1008 | 2026-09-17 | CL23 | Completed
J1008 | 2026-09-18 | CL23 | Completed
J1008 | 2026-09-23 | CL23 | Completed
J1008 | 2026-09-24 | CL23 | Completed
J1008 | 2026-09-25 | CL23 | Completed
J1008 | 2026-09-30 | CL23 | Completed
J1008 | 2026-10-01 | CL23 | Completed
J1008 | 2026-10-02 | CL23 | Completed
J1008 | 2026-10-07 | CL23 | Completed
J1008 | 2026-10-08 | CL23 | Completed
J1008 | 2026-10-09 | CL23 | Completed
J1008 | 2026-10-14 | CL23 | Completed
J1008 | 2026-10-15 | CL23 | Completed
J1008 | 2026-10-16 | CL23 | Completed
J1008 | 2026-10-21 | CL23 | Completed
J1008 | 2026-10-22 | CL23 | Completed
J1008 | 2026-10-23 | CL23 | Completed
J1008 | 2026-10-28 | CL23 | Completed
J1008 | 2026-10-29 | CL23 | Completed
J1008 | 2026-10-30 | CL23 | Completed
J1009 | 2026-08-04 | CL13 | Completed
J1009 | 2026-08-05 | CL13 | Completed
J1009 | 2026-08-11 | CL13 | Completed
J1009 | 2026-08-12 | CL13 | Completed
J1009 | 2026-08-18 | CL13 | Completed
J1009 | 2026-08-19 | CL13 | Completed
J1009 | 2026-08-25 | CL13 | Completed
J1009 | 2026-08-26 | CL13 | Completed
J1009 | 2026-09-01 | CL13 | Completed
J1009 | 2026-09-02 | CL13 | Completed
J1009 | 2026-09-08 | CL13 | Completed
J1009 | 2026-09-09 | CL13 | Completed
J1009 | 2026-09-15 | CL13 | Completed
J1009 | 2026-09-16 | CL13 | Completed
J1009 | 2026-09-22 | CL13 | Completed
J1009 | 2026-09-23 | CL13 | Completed
J1009 | 2026-09-29 | CL13 | Completed
J1009 | 2026-09-30 | CL13 | Completed
J1009 | 2026-10-06 | CL13 | Completed
J1009 | 2026-10-07 | CL13 | Completed
J1009 | 2026-10-13 | CL13 | Completed
J1009 | 2026-10-14 | CL13 | Completed
J1009 | 2026-10-20 | CL13 | Completed
J1009 | 2026-10-21 | CL13 | Completed
J1009 | 2026-10-27 | CL13 | Completed
J1009 | 2026-10-28 | CL13 | Completed
J1010 | 2026-08-04 | CL32 | Completed
J1010 | 2026-08-05 | CL32 | Completed
J1010 | 2026-08-11 | CL32 | Completed
J1010 | 2026-08-12 | CL32 | Completed
J1010 | 2026-08-18 | CL32 | Completed
J1010 | 2026-08-19 | CL32 | Completed
J1010 | 2026-08-25 | CL32 | Completed
J1010 | 2026-08-26 | CL32 | Completed
J1010 | 2026-09-01 | CL32 | Completed
J1010 | 2026-09-02 | CL32 | Completed
J1010 | 2026-09-08 | CL32 | Completed
J1010 | 2026-09-09 | CL32 | Completed
J1010 | 2026-09-15 | CL32 | Completed
J1010 | 2026-09-16 | CL32 | Completed
J1010 | 2026-09-22 | CL32 | Completed
J1010 | 2026-09-23 | CL32 | Completed
J1010 | 2026-09-29 | CL32 | Completed
J1010 | 2026-09-30 | CL32 | Completed
J1010 | 2026-10-06 | CL32 | Completed
J1010 | 2026-10-07 | CL32 | Completed
J1010 | 2026-10-13 | CL32 | Completed
J1010 | 2026-10-14 | CL32 | Completed
J1010 | 2026-10-20 | CL32 | Completed
J1010 | 2026-10-21 | CL32 | Completed
J1010 | 2026-10-27 | CL32 | Completed
J1010 | 2026-10-28 | CL32 | Completed
J1011 | 2026-08-05 | CL27 | Completed
J1011 | 2026-08-12 | CL27 | Completed
J1011 | 2026-08-19 | CL27 | Completed
J1011 | 2026-08-26 | CL27 | Completed
J1011 | 2026-09-02 | CL27 | Completed
J1011 | 2026-09-09 | CL27 | Completed
J1011 | 2026-09-16 | CL27 | Completed
J1011 | 2026-09-23 | CL27 | Completed
J1011 | 2026-09-30 | CL27 | Completed
J1011 | 2026-10-07 | CL27 | Completed
J1011 | 2026-10-14 | CL27 | Completed
J1011 | 2026-10-21 | CL27 | Completed
J1011 | 2026-10-28 | CL27 | Completed
J1012 | 2026-08-03 | CL36 | Completed
J1012 | 2026-08-05 | CL36 | Completed
J1012 | 2026-08-10 | CL36 | Completed
J1012 | 2026-08-12 | CL36 | Completed
J1012 | 2026-08-17 | CL36 | Completed
J1012 | 2026-08-19 | CL36 | Completed
J1012 | 2026-08-24 | CL36 | Completed
J1012 | 2026-08-26 | CL36 | Completed
J1012 | 2026-08-31 | CL36 | Completed
J1012 | 2026-09-02 | CL36 | Completed
J1012 | 2026-09-07 | CL36 | Completed
J1012 | 2026-09-09 | CL36 | Completed
J1012 | 2026-09-14 | CL36 | Completed
J1012 | 2026-09-16 | CL36 | Completed
J1012 | 2026-09-21 | CL36 | Completed
J1012 | 2026-09-23 | CL36 | Skipped
J1012 | 2026-09-28 | CL36 | Skipped
J1012 | 2026-09-30 | CL36 | Completed
J1012 | 2026-10-05 | CL36 | Completed
J1012 | 2026-10-07 | CL36 | Completed
J1012 | 2026-10-12 | CL36 | Completed
J1012 | 2026-10-14 | CL36 | Completed
J1012 | 2026-10-19 | CL36 | Completed
J1012 | 2026-10-21 | CL36 | Completed
J1012 | 2026-10-26 | CL36 | Completed
J1012 | 2026-10-28 | CL36 | Completed
J1013 | 2026-08-06 | CL55 | Completed
J1013 | 2026-09-03 | CL55 | Completed
J1013 | 2026-10-01 | CL55 | Completed
J1014 | 2026-08-03 | CL10 | Completed
J1014 | 2026-08-04 | CL10 | Completed
J1014 | 2026-08-10 | CL10 | Completed
J1014 | 2026-08-11 | CL10 | Completed
J1014 | 2026-08-17 | CL10 | Completed
J1014 | 2026-08-18 | CL10 | Completed
J1014 | 2026-08-24 | CL10 | Completed
J1014 | 2026-08-25 | CL10 | Completed
J1014 | 2026-08-31 | CL10 | Completed
J1014 | 2026-09-01 | CL10 | Completed
J1014 | 2026-09-07 | CL10 | Completed
J1014 | 2026-09-08 | CL10 | Completed
J1014 | 2026-09-14 | CL10 | Completed
J1014 | 2026-09-15 | CL10 | Completed
J1014 | 2026-09-21 | CL10 | Completed
J1014 | 2026-09-22 | CL10 | Completed
J1014 | 2026-09-28 | CL10 | Completed
J1014 | 2026-09-29 | CL10 | Completed
J1014 | 2026-10-05 | CL10 | Completed
J1014 | 2026-10-06 | CL10 | Completed
J1014 | 2026-10-12 | CL10 | Completed
J1014 | 2026-10-13 | CL10 | Completed
J1014 | 2026-10-19 | CL10 | Completed
J1014 | 2026-10-20 | CL10 | Completed
J1014 | 2026-10-26 | CL10 | Completed
J1014 | 2026-10-27 | CL10 | Completed
J1015 | 2026-08-05 | CL53 | Completed
J1015 | 2026-09-02 | CL53 | Completed
J1015 | 2026-10-07 | CL53 | Completed
J1016 | 2026-08-03 | CL45 | Completed
J1016 | 2026-08-04 | CL45 | Completed
J1016 | 2026-08-05 | CL45 | Completed
J1016 | 2026-08-06 | CL45 | Completed
J1016 | 2026-08-07 | CL45 | Completed
J1016 | 2026-08-10 | CL45 | Completed
J1016 | 2026-08-11 | CL45 | Completed
J1016 | 2026-08-12 | CL45 | Completed
J1016 | 2026-08-13 | CL45 | Completed
J1016 | 2026-08-14 | CL45 | Completed
J1016 | 2026-08-17 | CL45 | Completed
J1016 | 2026-08-18 | CL45 | Completed
J1016 | 2026-08-19 | CL45 | Completed
J1016 | 2026-08-20 | CL45 | Completed
J1016 | 2026-08-21 | CL45 | Completed
J1016 | 2026-08-24 | CL45 | Completed
J1016 | 2026-08-25 | CL45 | Completed
J1016 | 2026-08-26 | CL45 | Completed
J1016 | 2026-08-27 | CL45 | Completed
J1016 | 2026-08-28 | CL45 | Completed
J1016 | 2026-08-31 | CL45 | Completed
J1016 | 2026-09-01 | CL45 | Completed
J1016 | 2026-09-02 | CL45 | Completed
J1016 | 2026-09-03 | CL45 | Completed
J1016 | 2026-09-04 | CL45 | Completed
J1016 | 2026-09-07 | CL45 | Completed
J1016 | 2026-09-08 | CL45 | Completed
J1016 | 2026-09-09 | CL45 | Completed
J1016 | 2026-09-10 | CL45 | Completed
J1016 | 2026-09-11 | CL45 | Completed
J1016 | 2026-09-14 | CL45 | Completed
J1016 | 2026-09-15 | CL45 | Completed
J1016 | 2026-09-16 | CL45 | Completed
J1016 | 2026-09-17 | CL45 | Completed
J1016 | 2026-09-18 | CL45 | Completed
J1016 | 2026-09-21 | CL45 | Completed
J1016 | 2026-09-22 | CL45 | Completed
J1016 | 2026-09-23 | CL45 | Completed
J1016 | 2026-09-24 | CL45 | Completed
J1016 | 2026-09-25 | CL45 | Completed
J1016 | 2026-09-28 | CL45 | Completed
J1016 | 2026-09-29 | CL45 | Completed
J1016 | 2026-09-30 | CL45 | Completed
J1016 | 2026-10-01 | CL45 | Completed
J1016 | 2026-10-02 | CL45 | Completed
J1016 | 2026-10-05 | CL45 | Completed
J1016 | 2026-10-06 | CL45 | Completed
J1016 | 2026-10-07 | CL45 | Completed
J1016 | 2026-10-08 | CL45 | Completed
J1016 | 2026-10-09 | CL45 | Completed
J1016 | 2026-10-12 | CL45 | Completed
J1016 | 2026-10-13 | CL45 | Completed
J1016 | 2026-10-14 | CL45 | Completed
J1016 | 2026-10-15 | CL45 | Completed
J1016 | 2026-10-16 | CL45 | Completed
J1016 | 2026-10-19 | CL45 | Completed
J1016 | 2026-10-20 | CL45 | Completed
J1016 | 2026-10-21 | CL45 | Completed
J1016 | 2026-10-22 | CL45 | Completed
J1016 | 2026-10-23 | CL45 | Completed
J1016 | 2026-10-26 | CL45 | Completed
J1016 | 2026-10-27 | CL45 | Completed
J1016 | 2026-10-28 | CL45 | Completed
J1016 | 2026-10-29 | CL45 | Completed
J1016 | 2026-10-30 | CL45 | Completed
J1017 | 2026-08-05 | CL29 | Completed
J1017 | 2026-08-06 | CL29 | Completed
J1017 | 2026-08-12 | CL29 | Completed
J1017 | 2026-08-13 | CL29 | Completed
J1017 | 2026-08-19 | CL29 | Completed
J1017 | 2026-08-20 | CL29 | Completed
J1017 | 2026-08-26 | CL29 | Completed
J1017 | 2026-08-27 | CL29 | Completed
J1017 | 2026-09-02 | CL29 | Completed
J1017 | 2026-09-03 | CL29 | Completed
J1017 | 2026-09-09 | CL29 | Completed
J1017 | 2026-09-10 | CL29 | Completed
J1017 | 2026-09-16 | CL29 | Completed
J1017 | 2026-09-17 | CL29 | Completed
J1017 | 2026-09-23 | CL29 | Completed
J1017 | 2026-09-24 | CL29 | Completed
J1017 | 2026-09-30 | CL29 | Completed
J1017 | 2026-10-01 | CL29 | Completed
J1017 | 2026-10-07 | CL29 | Completed
J1017 | 2026-10-08 | CL29 | Completed
J1017 | 2026-10-14 | CL29 | Completed
J1017 | 2026-10-15 | CL29 | Completed
J1017 | 2026-10-21 | CL29 | Completed
J1017 | 2026-10-22 | CL29 | Completed
J1017 | 2026-10-28 | CL29 | Completed
J1017 | 2026-10-29 | CL29 | Completed
J1018 | 2026-08-06 | CL34 | Completed
J1018 | 2026-08-13 | CL34 | Completed
J1018 | 2026-08-20 | CL34 | Completed
J1018 | 2026-08-27 | CL34 | Completed
J1018 | 2026-09-03 | CL34 | Completed
J1018 | 2026-09-10 | CL34 | Completed
J1018 | 2026-09-17 | CL34 | Completed
J1018 | 2026-09-24 | CL34 | Completed
J1018 | 2026-10-01 | CL34 | Completed
J1018 | 2026-10-08 | CL34 | Completed
J1018 | 2026-10-15 | CL34 | Completed
J1018 | 2026-10-22 | CL34 | Completed
J1018 | 2026-10-29 | CL34 | Completed
J1019 | 2026-08-07 | CL50 | Completed
J1019 | 2026-08-14 | CL50 | Completed
J1019 | 2026-08-21 | CL50 | Completed
J1019 | 2026-08-28 | CL50 | Completed
J1019 | 2026-09-04 | CL50 | Completed
J1019 | 2026-09-11 | CL50 | Completed
J1019 | 2026-09-18 | CL50 | Completed
J1019 | 2026-09-25 | CL50 | Completed
J1019 | 2026-10-02 | CL50 | Completed
J1019 | 2026-10-09 | CL50 | Completed
J1019 | 2026-10-16 | CL50 | Completed
J1019 | 2026-10-23 | CL50 | Completed
J1019 | 2026-10-30 | CL50 | Completed
J1020 | 2026-08-06 | CL11 | Completed
J1020 | 2026-08-13 | CL11 | Completed
J1020 | 2026-08-20 | CL11 | Completed
J1020 | 2026-08-27 | CL11 | Completed
J1020 | 2026-09-03 | CL11 | Completed
J1020 | 2026-09-10 | CL11 | Completed
J1020 | 2026-09-17 | CL11 | Completed
J1020 | 2026-09-24 | CL11 | Completed
J1020 | 2026-10-01 | CL11 | Completed
J1020 | 2026-10-08 | CL11 | Completed
J1020 | 2026-10-15 | CL11 | Completed
J1020 | 2026-10-22 | CL11 | Completed
J1020 | 2026-10-29 | CL11 | Completed
J1021 | 2026-08-03 | CL25 | Completed
J1021 | 2026-08-04 | CL25 | Completed
J1021 | 2026-08-10 | CL25 | Completed
J1021 | 2026-08-11 | CL25 | Completed
J1021 | 2026-08-17 | CL25 | Completed
J1021 | 2026-08-18 | CL25 | Completed
J1021 | 2026-08-24 | CL25 | Completed
J1021 | 2026-08-25 | CL25 | Completed
J1021 | 2026-08-31 | CL25 | Completed
J1021 | 2026-09-01 | CL25 | Completed
J1021 | 2026-09-07 | CL25 | Completed
J1021 | 2026-09-08 | CL25 | Completed
J1021 | 2026-09-14 | CL25 | Completed
J1021 | 2026-09-15 | CL25 | Completed
J1021 | 2026-09-21 | CL25 | Completed
J1021 | 2026-09-22 | CL25 | Completed
J1021 | 2026-09-28 | CL25 | Completed
J1021 | 2026-09-29 | CL25 | Completed
J1021 | 2026-10-05 | CL25 | Completed
J1021 | 2026-10-06 | CL25 | Completed
J1021 | 2026-10-12 | CL25 | Completed
J1021 | 2026-10-13 | CL25 | Completed
J1021 | 2026-10-19 | CL25 | Completed
J1021 | 2026-10-20 | CL25 | Completed
J1021 | 2026-10-26 | CL25 | Completed
J1021 | 2026-10-27 | CL25 | Completed
J1022 | 2026-08-03 | CL51 | Completed
J1022 | 2026-08-04 | CL51 | Completed
J1022 | 2026-08-05 | CL51 | Completed
J1022 | 2026-08-10 | CL51 | Completed
J1022 | 2026-08-11 | CL51 | Completed
J1022 | 2026-08-12 | CL51 | Completed
J1022 | 2026-08-17 | CL51 | Completed
J1022 | 2026-08-18 | CL51 | Completed
J1022 | 2026-08-19 | CL51 | Completed
J1022 | 2026-08-24 | CL51 | Completed
J1022 | 2026-08-25 | CL51 | Completed
J1022 | 2026-08-26 | CL51 | Completed
J1022 | 2026-08-31 | CL51 | Completed
J1022 | 2026-09-01 | CL51 | Completed
J1022 | 2026-09-02 | CL51 | Completed
J1022 | 2026-09-07 | CL51 | Completed
J1022 | 2026-09-08 | CL51 | Completed
J1022 | 2026-09-09 | CL51 | Completed
J1022 | 2026-09-14 | CL51 | Completed
J1022 | 2026-09-15 | CL51 | Completed
J1022 | 2026-09-16 | CL51 | Completed
J1022 | 2026-09-21 | CL51 | Completed
J1022 | 2026-09-22 | CL51 | Completed
J1022 | 2026-09-23 | CL51 | Completed
J1022 | 2026-09-28 | CL51 | Completed
J1022 | 2026-09-29 | CL51 | Completed
J1022 | 2026-09-30 | CL51 | Completed
J1022 | 2026-10-05 | CL51 | Completed
J1022 | 2026-10-06 | CL51 | Completed
J1022 | 2026-10-07 | CL51 | Completed
J1022 | 2026-10-12 | CL51 | Completed
J1022 | 2026-10-13 | CL51 | Completed
J1022 | 2026-10-14 | CL51 | Completed
J1022 | 2026-10-19 | CL51 | Completed
J1022 | 2026-10-20 | CL51 | Completed
J1022 | 2026-10-21 | CL51 | Completed
J1022 | 2026-10-26 | CL51 | Completed
J1022 | 2026-10-27 | CL51 | Completed
J1022 | 2026-10-28 | CL51 | Completed
J1023 | 2026-08-05 | CL46 | Completed
J1023 | 2026-08-07 | CL46 | Completed
J1023 | 2026-08-12 | CL46 | Completed
J1023 | 2026-08-14 | CL46 | Completed
J1023 | 2026-08-19 | CL46 | Completed
J1023 | 2026-08-21 | CL46 | Completed
J1023 | 2026-08-26 | CL46 | Completed
J1023 | 2026-08-28 | CL46 | Completed
J1023 | 2026-09-02 | CL46 | Completed
J1023 | 2026-09-04 | CL46 | Completed
J1023 | 2026-09-09 | CL46 | Completed
J1023 | 2026-09-11 | CL46 | Completed
J1023 | 2026-09-16 | CL46 | Completed
J1023 | 2026-09-18 | CL46 | Completed
J1023 | 2026-09-23 | CL46 | Completed
J1023 | 2026-09-25 | CL46 | Completed
J1023 | 2026-09-30 | CL46 | Completed
J1023 | 2026-10-02 | CL46 | Completed
J1023 | 2026-10-07 | CL46 | Completed
J1023 | 2026-10-09 | CL46 | Completed
J1023 | 2026-10-14 | CL46 | Completed
J1023 | 2026-10-16 | CL46 | Completed
J1023 | 2026-10-21 | CL46 | Completed
J1023 | 2026-10-23 | CL46 | Completed
J1023 | 2026-10-28 | CL46 | Completed
J1023 | 2026-10-30 | CL46 | Completed
J1024 | 2026-08-21 | CL58 | Completed
J1024 | 2026-09-18 | CL58 | Completed
J1024 | 2026-10-16 | CL58 | Completed
J1025 | 2026-08-05 | CL07 | Completed
J1025 | 2026-08-07 | CL07 | Completed
J1025 | 2026-08-12 | CL07 | Completed
J1025 | 2026-08-14 | CL07 | Completed
J1025 | 2026-08-19 | CL07 | Completed
J1025 | 2026-08-21 | CL07 | Completed
J1025 | 2026-08-26 | CL07 | Completed
J1025 | 2026-08-28 | CL07 | Completed
J1025 | 2026-09-02 | CL07 | Completed
J1025 | 2026-09-04 | CL07 | Completed
J1025 | 2026-09-09 | CL07 | Completed
J1025 | 2026-09-11 | CL07 | Completed
J1025 | 2026-09-16 | CL07 | Completed
J1025 | 2026-09-18 | CL07 | Completed
J1025 | 2026-09-23 | CL07 | Completed
J1025 | 2026-09-25 | CL07 | Completed
J1025 | 2026-09-30 | CL07 | Completed
J1025 | 2026-10-02 | CL07 | Completed
J1025 | 2026-10-07 | CL07 | Completed
J1025 | 2026-10-09 | CL07 | Completed
J1025 | 2026-10-14 | CL07 | Completed
J1025 | 2026-10-16 | CL07 | Completed
J1025 | 2026-10-21 | CL07 | Completed
J1025 | 2026-10-23 | CL07 | Completed
J1025 | 2026-10-28 | CL07 | Completed
J1025 | 2026-10-30 | CL07 | Completed
J1026 | 2026-08-25 | CL54 | Completed
J1026 | 2026-09-22 | CL54 | Completed
J1026 | 2026-10-20 | CL54 | Completed
J1027 | 2026-08-03 | CL31 | Completed
J1027 | 2026-08-05 | CL31 | Completed
J1027 | 2026-08-06 | CL31 | Completed
J1027 | 2026-08-10 | CL31 | Completed
J1027 | 2026-08-12 | CL31 | Completed
J1027 | 2026-08-13 | CL31 | Completed
J1027 | 2026-08-17 | CL31 | Completed
J1027 | 2026-08-19 | CL31 | Completed
J1027 | 2026-08-20 | CL31 | Completed
J1027 | 2026-08-24 | CL31 | Completed
J1027 | 2026-08-26 | CL31 | Completed
J1027 | 2026-08-27 | CL31 | Completed
J1027 | 2026-08-31 | CL31 | Completed
J1027 | 2026-09-02 | CL31 | Completed
J1027 | 2026-09-03 | CL31 | Completed
J1027 | 2026-09-07 | CL31 | Completed
J1027 | 2026-09-09 | CL31 | Completed
J1027 | 2026-09-10 | CL31 | Completed
J1027 | 2026-09-14 | CL31 | Completed
J1027 | 2026-09-16 | CL31 | Completed
J1027 | 2026-09-17 | CL31 | Completed
J1027 | 2026-09-21 | CL31 | Skipped
J1027 | 2026-09-23 | CL31 | Completed
J1027 | 2026-09-24 | CL31 | Completed
J1027 | 2026-09-28 | CL31 | Completed
J1027 | 2026-09-30 | CL31 | Completed
J1027 | 2026-10-01 | CL31 | Skipped
J1027 | 2026-10-05 | CL31 | Completed
J1027 | 2026-10-07 | CL31 | Completed
J1027 | 2026-10-08 | CL31 | Completed
J1027 | 2026-10-12 | CL31 | Completed
J1027 | 2026-10-14 | CL31 | Completed
J1027 | 2026-10-15 | CL31 | Completed
J1027 | 2026-10-19 | CL31 | Completed
J1027 | 2026-10-21 | CL31 | Completed
J1027 | 2026-10-22 | CL31 | Completed
J1027 | 2026-10-26 | CL31 | Completed
J1027 | 2026-10-28 | CL31 | Completed
J1027 | 2026-10-29 | CL31 | Completed
J1028 | 2026-08-03 | CL03 | Completed
J1028 | 2026-08-06 | CL03 | Completed
J1028 | 2026-08-10 | CL03 | Completed
J1028 | 2026-08-13 | CL03 | Completed
J1028 | 2026-08-17 | CL03 | Completed
J1028 | 2026-08-20 | CL03 | Completed
J1028 | 2026-08-24 | CL03 | Completed
J1028 | 2026-08-27 | CL03 | Completed
J1028 | 2026-08-31 | CL03 | Completed
J1028 | 2026-09-03 | CL03 | Completed
J1028 | 2026-09-07 | CL03 | Completed
J1028 | 2026-09-10 | CL03 | Completed
J1028 | 2026-09-14 | CL03 | Completed
J1028 | 2026-09-17 | CL03 | Completed
J1028 | 2026-09-21 | CL03 | Completed
J1028 | 2026-09-24 | CL03 | Completed
J1028 | 2026-09-28 | CL03 | Completed
J1028 | 2026-10-01 | CL03 | Completed
J1028 | 2026-10-05 | CL03 | Completed
J1028 | 2026-10-08 | CL03 | Completed
J1028 | 2026-10-12 | CL03 | Completed
J1028 | 2026-10-15 | CL03 | Completed
J1028 | 2026-10-19 | CL03 | Completed
J1028 | 2026-10-22 | CL03 | Completed
J1028 | 2026-10-26 | CL03 | Completed
J1028 | 2026-10-29 | CL03 | Completed
J1029 | 2026-08-03 | CL33 | Completed
J1029 | 2026-08-10 | CL33 | Completed
J1029 | 2026-08-17 | CL33 | Completed
J1029 | 2026-08-24 | CL33 | Completed
J1029 | 2026-08-31 | CL33 | Completed
J1029 | 2026-09-07 | CL33 | Completed
J1029 | 2026-09-14 | CL33 | Completed
J1029 | 2026-09-21 | CL33 | Completed
J1029 | 2026-09-28 | CL33 | Completed
J1029 | 2026-10-05 | CL33 | Completed
J1029 | 2026-10-12 | CL33 | Completed
J1029 | 2026-10-19 | CL33 | Completed
J1029 | 2026-10-26 | CL33 | Completed
J1030 | 2026-08-03 | CL47 | Completed
J1030 | 2026-08-05 | CL47 | Completed
J1030 | 2026-08-10 | CL47 | Completed
J1030 | 2026-08-12 | CL47 | Completed
J1030 | 2026-08-17 | CL47 | Completed
J1030 | 2026-08-19 | CL47 | Completed
J1030 | 2026-08-24 | CL47 | Completed
J1030 | 2026-08-26 | CL47 | Completed
J1030 | 2026-08-31 | CL47 | Completed
J1030 | 2026-09-02 | CL47 | Completed
J1030 | 2026-09-07 | CL47 | Completed
J1030 | 2026-09-09 | CL47 | Completed
J1030 | 2026-09-14 | CL47 | Completed
J1030 | 2026-09-16 | CL47 | Completed
J1030 | 2026-09-21 | CL47 | Completed
J1030 | 2026-09-23 | CL47 | Completed
J1030 | 2026-09-28 | CL47 | Completed
J1030 | 2026-09-30 | CL47 | Completed
J1030 | 2026-10-05 | CL47 | Completed
J1030 | 2026-10-07 | CL47 | Skipped
J1030 | 2026-10-12 | CL47 | Completed
J1030 | 2026-10-14 | CL47 | Completed
J1030 | 2026-10-19 | CL47 | Completed
J1030 | 2026-10-21 | CL47 | Completed
J1030 | 2026-10-26 | CL47 | Completed
J1030 | 2026-10-28 | CL47 | Completed
J1031 | 2026-08-05 | CL15 | Completed
J1031 | 2026-08-07 | CL15 | Completed
J1031 | 2026-08-12 | CL15 | Completed
J1031 | 2026-08-14 | CL15 | Completed
J1031 | 2026-08-19 | CL15 | Completed
J1031 | 2026-08-21 | CL15 | Completed
J1031 | 2026-08-26 | CL15 | Completed
J1031 | 2026-08-28 | CL15 | Completed
J1031 | 2026-09-02 | CL15 | Completed
J1031 | 2026-09-04 | CL15 | Completed
J1031 | 2026-09-09 | CL15 | Completed
J1031 | 2026-09-11 | CL15 | Completed
J1031 | 2026-09-16 | CL15 | Completed
J1031 | 2026-09-18 | CL15 | Completed
J1031 | 2026-09-23 | CL15 | Completed
J1031 | 2026-09-25 | CL15 | Completed
J1031 | 2026-09-30 | CL15 | Completed
J1031 | 2026-10-02 | CL15 | Completed
J1031 | 2026-10-07 | CL15 | Completed
J1031 | 2026-10-09 | CL15 | Completed
J1031 | 2026-10-14 | CL15 | Completed
J1031 | 2026-10-16 | CL15 | Completed
J1031 | 2026-10-21 | CL15 | Completed
J1031 | 2026-10-23 | CL15 | Completed
J1031 | 2026-10-28 | CL15 | Completed
J1031 | 2026-10-30 | CL15 | Skipped
J1032 | 2026-08-13 | CL56 | Completed
J1032 | 2026-09-10 | CL56 | Completed
J1032 | 2026-10-08 | CL56 | Completed
J1033 | 2026-08-03 | CL52 | Completed
J1033 | 2026-08-04 | CL52 | Completed
J1033 | 2026-08-05 | CL52 | Completed
J1033 | 2026-08-06 | CL52 | Completed
J1033 | 2026-08-07 | CL52 | Completed
J1033 | 2026-08-10 | CL52 | Completed
J1033 | 2026-08-11 | CL52 | Completed
J1033 | 2026-08-12 | CL52 | Completed
J1033 | 2026-08-13 | CL52 | Completed
J1033 | 2026-08-14 | CL52 | Completed
J1033 | 2026-08-17 | CL52 | Completed
J1033 | 2026-08-18 | CL52 | Completed
J1033 | 2026-08-19 | CL52 | Completed
J1033 | 2026-08-20 | CL52 | Completed
J1033 | 2026-08-21 | CL52 | Completed
J1033 | 2026-08-24 | CL52 | Completed
J1033 | 2026-08-25 | CL52 | Completed
J1033 | 2026-08-26 | CL52 | Completed
J1033 | 2026-08-27 | CL52 | Completed
J1033 | 2026-08-28 | CL52 | Completed
J1033 | 2026-08-31 | CL52 | Completed
J1033 | 2026-09-01 | CL52 | Completed
J1033 | 2026-09-02 | CL52 | Completed
J1033 | 2026-09-03 | CL52 | Completed
J1033 | 2026-09-04 | CL52 | Completed
J1033 | 2026-09-07 | CL52 | Completed
J1033 | 2026-09-08 | CL52 | Completed
J1033 | 2026-09-09 | CL52 | Completed
J1033 | 2026-09-10 | CL52 | Completed
J1033 | 2026-09-11 | CL52 | Completed
J1033 | 2026-09-14 | CL52 | Completed
J1033 | 2026-09-15 | CL52 | Skipped
J1033 | 2026-09-16 | CL52 | Completed
J1033 | 2026-09-17 | CL52 | Completed
J1033 | 2026-09-18 | CL52 | Completed
J1033 | 2026-09-21 | CL52 | Completed
J1033 | 2026-09-22 | CL52 | Completed
J1033 | 2026-09-23 | CL52 | Completed
J1033 | 2026-09-24 | CL52 | Completed
J1033 | 2026-09-25 | CL52 | Completed
J1033 | 2026-09-28 | CL52 | Completed
J1033 | 2026-09-29 | CL52 | Completed
J1033 | 2026-09-30 | CL52 | Completed
J1033 | 2026-10-01 | CL52 | Completed
J1033 | 2026-10-02 | CL52 | Completed
J1033 | 2026-10-05 | CL52 | Completed
J1033 | 2026-10-06 | CL52 | Completed
J1033 | 2026-10-07 | CL52 | Completed
J1033 | 2026-10-08 | CL52 | Completed
J1033 | 2026-10-09 | CL52 | Completed
J1033 | 2026-10-12 | CL52 | Completed
J1033 | 2026-10-13 | CL52 | Completed
J1033 | 2026-10-14 | CL52 | Completed
J1033 | 2026-10-15 | CL52 | Completed
J1033 | 2026-10-16 | CL52 | Completed
J1033 | 2026-10-19 | CL52 | Completed
J1033 | 2026-10-20 | CL52 | Completed
J1033 | 2026-10-21 | CL52 | Completed
J1033 | 2026-10-22 | CL52 | Completed
J1033 | 2026-10-23 | CL52 | Completed
J1033 | 2026-10-26 | CL52 | Completed
J1033 | 2026-10-27 | CL52 | Completed
J1033 | 2026-10-28 | CL52 | Completed
J1033 | 2026-10-29 | CL52 | Completed
J1033 | 2026-10-30 | CL52 | Completed
J1034 | 2026-08-03 | CL19 | Completed
J1034 | 2026-08-05 | CL19 | Completed
J1034 | 2026-08-10 | CL19 | Completed
J1034 | 2026-08-12 | CL19 | Completed
J1034 | 2026-08-17 | CL19 | Completed
J1034 | 2026-08-19 | CL19 | Completed
J1034 | 2026-08-24 | CL19 | Completed
J1034 | 2026-08-26 | CL19 | Completed
J1034 | 2026-08-31 | CL19 | Completed
J1034 | 2026-09-02 | CL19 | Completed
J1034 | 2026-09-07 | CL19 | Completed
J1034 | 2026-09-09 | CL19 | Completed
J1034 | 2026-09-14 | CL19 | Completed
J1034 | 2026-09-16 | CL19 | Completed
J1034 | 2026-09-21 | CL19 | Completed
J1034 | 2026-09-23 | CL19 | Completed
J1034 | 2026-09-28 | CL19 | Completed
J1034 | 2026-09-30 | CL19 | Completed
J1034 | 2026-10-05 | CL19 | Completed
J1034 | 2026-10-07 | CL19 | Completed
J1034 | 2026-10-12 | CL19 | Completed
J1034 | 2026-10-14 | CL19 | Completed
J1034 | 2026-10-19 | CL19 | Completed
J1034 | 2026-10-21 | CL19 | Completed
J1034 | 2026-10-26 | CL19 | Completed
J1034 | 2026-10-28 | CL19 | Completed
J1035 | 2026-08-03 | CL14 | Completed
J1035 | 2026-08-06 | CL14 | Completed
J1035 | 2026-08-07 | CL14 | Completed
J1035 | 2026-08-10 | CL14 | Completed
J1035 | 2026-08-13 | CL14 | Completed
J1035 | 2026-08-14 | CL14 | Completed
J1035 | 2026-08-17 | CL14 | Completed
J1035 | 2026-08-20 | CL14 | Completed
J1035 | 2026-08-21 | CL14 | Completed
J1035 | 2026-08-24 | CL14 | Completed
J1035 | 2026-08-27 | CL14 | Completed
J1035 | 2026-08-28 | CL14 | Completed
J1035 | 2026-08-31 | CL14 | Completed
J1035 | 2026-09-03 | CL14 | Completed
J1035 | 2026-09-04 | CL14 | Completed
J1035 | 2026-09-07 | CL14 | Completed
J1035 | 2026-09-10 | CL14 | Completed
J1035 | 2026-09-11 | CL14 | Completed
J1035 | 2026-09-14 | CL14 | Completed
J1035 | 2026-09-17 | CL14 | Completed
J1035 | 2026-09-18 | CL14 | Completed
J1035 | 2026-09-21 | CL14 | Completed
J1035 | 2026-09-24 | CL14 | Completed
J1035 | 2026-09-25 | CL14 | Completed
J1035 | 2026-09-28 | CL14 | Completed
J1035 | 2026-10-01 | CL14 | Completed
J1035 | 2026-10-02 | CL14 | Completed
J1035 | 2026-10-05 | CL14 | Completed
J1035 | 2026-10-08 | CL14 | Completed
J1035 | 2026-10-09 | CL14 | Completed
J1035 | 2026-10-12 | CL14 | Completed
J1035 | 2026-10-15 | CL14 | Completed
J1035 | 2026-10-16 | CL14 | Completed
J1035 | 2026-10-19 | CL14 | Completed
J1035 | 2026-10-22 | CL14 | Completed
J1035 | 2026-10-23 | CL14 | Completed
J1035 | 2026-10-26 | CL14 | Completed
J1035 | 2026-10-29 | CL14 | Completed
J1035 | 2026-10-30 | CL14 | Completed
J1036 | 2026-08-18 | CL56 | Completed
J1036 | 2026-09-15 | CL56 | Completed
J1036 | 2026-10-13 | CL56 | Completed
J1037 | 2026-08-03 | CL40 | Completed
J1037 | 2026-08-10 | CL40 | Completed
J1037 | 2026-08-17 | CL40 | Completed
J1037 | 2026-08-24 | CL40 | Completed
J1037 | 2026-08-31 | CL40 | Completed
J1037 | 2026-09-07 | CL40 | Completed
J1037 | 2026-09-14 | CL40 | Completed
J1037 | 2026-09-21 | CL40 | Completed
J1037 | 2026-09-28 | CL40 | Completed
J1037 | 2026-10-05 | CL40 | Completed
J1037 | 2026-10-12 | CL40 | Completed
J1037 | 2026-10-19 | CL40 | Completed
J1037 | 2026-10-26 | CL40 | Completed
J1038 | 2026-08-06 | CL22 | Completed
J1038 | 2026-08-13 | CL22 | Completed
J1038 | 2026-08-20 | CL22 | Completed
J1038 | 2026-08-27 | CL22 | Skipped
J1038 | 2026-09-03 | CL22 | Completed
J1038 | 2026-09-10 | CL22 | Completed
J1038 | 2026-09-17 | CL22 | Completed
J1038 | 2026-09-24 | CL22 | Completed
J1038 | 2026-10-01 | CL22 | Completed
J1038 | 2026-10-08 | CL22 | Completed
J1038 | 2026-10-15 | CL22 | Completed
J1038 | 2026-10-22 | CL22 | Completed
J1038 | 2026-10-29 | CL22 | Completed
J1039 | 2026-08-05 | CL21 | Completed
J1039 | 2026-08-12 | CL21 | Completed
J1039 | 2026-08-19 | CL21 | Completed
J1039 | 2026-08-26 | CL21 | Completed
J1039 | 2026-09-02 | CL21 | Completed
J1039 | 2026-09-09 | CL21 | Completed
J1039 | 2026-09-16 | CL21 | Completed
J1039 | 2026-09-23 | CL21 | Completed
J1039 | 2026-09-30 | CL21 | Completed
J1039 | 2026-10-07 | CL21 | Completed
J1039 | 2026-10-14 | CL21 | Completed
J1039 | 2026-10-21 | CL21 | Completed
J1039 | 2026-10-28 | CL21 | Skipped
J1040 | 2026-08-04 | CL20 | Completed
J1040 | 2026-08-05 | CL20 | Completed
J1040 | 2026-08-11 | CL20 | Completed
J1040 | 2026-08-12 | CL20 | Completed
J1040 | 2026-08-18 | CL20 | Completed
J1040 | 2026-08-19 | CL20 | Completed
J1040 | 2026-08-25 | CL20 | Completed
J1040 | 2026-08-26 | CL20 | Completed
J1040 | 2026-09-01 | CL20 | Completed
J1040 | 2026-09-02 | CL20 | Completed
J1040 | 2026-09-08 | CL20 | Completed
J1040 | 2026-09-09 | CL20 | Completed
J1040 | 2026-09-15 | CL20 | Completed
J1040 | 2026-09-16 | CL20 | Completed
J1040 | 2026-09-22 | CL20 | Completed
J1040 | 2026-09-23 | CL20 | Completed
J1040 | 2026-09-29 | CL20 | Completed
J1040 | 2026-09-30 | CL20 | Completed
J1040 | 2026-10-06 | CL20 | Completed
J1040 | 2026-10-07 | CL20 | Completed
J1040 | 2026-10-13 | CL20 | Completed
J1040 | 2026-10-14 | CL20 | Completed
J1040 | 2026-10-20 | CL20 | Completed
J1040 | 2026-10-21 | CL20 | Completed
J1040 | 2026-10-27 | CL20 | Completed
J1040 | 2026-10-28 | CL20 | Completed
J1041 | 2026-08-10 | CL58 | Completed
J1041 | 2026-09-07 | CL58 | Completed
J1041 | 2026-10-05 | CL58 | Completed
J1042 | 2026-08-04 | CL06 | Completed
J1042 | 2026-08-11 | CL06 | Completed
J1042 | 2026-08-18 | CL06 | Completed
J1042 | 2026-08-25 | CL06 | Completed
J1042 | 2026-09-01 | CL06 | Completed
J1042 | 2026-09-08 | CL06 | Completed
J1042 | 2026-09-15 | CL06 | Completed
J1042 | 2026-09-22 | CL06 | Completed
J1042 | 2026-09-29 | CL06 | Completed
J1042 | 2026-10-06 | CL06 | Completed
J1042 | 2026-10-13 | CL06 | Completed
J1042 | 2026-10-20 | CL06 | Completed
J1042 | 2026-10-27 | CL06 | Completed
J1043 | 2026-08-04 | CL30 | Completed
J1043 | 2026-08-05 | CL30 | Completed
J1043 | 2026-08-11 | CL30 | Completed
J1043 | 2026-08-12 | CL30 | Completed
J1043 | 2026-08-18 | CL30 | Completed
J1043 | 2026-08-19 | CL30 | Completed
J1043 | 2026-08-25 | CL30 | Completed
J1043 | 2026-08-26 | CL30 | Completed
J1043 | 2026-09-01 | CL30 | Completed
J1043 | 2026-09-02 | CL30 | Completed
J1043 | 2026-09-08 | CL30 | Completed
J1043 | 2026-09-09 | CL30 | Skipped
J1043 | 2026-09-15 | CL30 | Completed
J1043 | 2026-09-16 | CL30 | Completed
J1043 | 2026-09-22 | CL30 | Completed
J1043 | 2026-09-23 | CL30 | Completed
J1043 | 2026-09-29 | CL30 | Completed
J1043 | 2026-09-30 | CL30 | Completed
J1043 | 2026-10-06 | CL30 | Completed
J1043 | 2026-10-07 | CL30 | Completed
J1043 | 2026-10-13 | CL30 | Completed
J1043 | 2026-10-14 | CL30 | Completed
J1043 | 2026-10-20 | CL30 | Completed
J1043 | 2026-10-21 | CL30 | Completed
J1043 | 2026-10-27 | CL30 | Completed
J1043 | 2026-10-28 | CL30 | Completed
J1044 | 2026-08-18 | CL57 | Completed
J1044 | 2026-09-15 | CL57 | Completed
J1044 | 2026-10-13 | CL57 | Completed
J1045 | 2026-08-06 | CL42 | Completed
J1045 | 2026-08-13 | CL42 | Completed
J1045 | 2026-08-20 | CL42 | Completed
J1045 | 2026-08-27 | CL42 | Completed
J1045 | 2026-09-03 | CL42 | Completed
J1045 | 2026-09-10 | CL42 | Completed
J1045 | 2026-09-17 | CL42 | Completed
J1045 | 2026-09-24 | CL42 | Completed
J1045 | 2026-10-01 | CL42 | Completed
J1045 | 2026-10-08 | CL42 | Completed
J1045 | 2026-10-15 | CL42 | Completed
J1045 | 2026-10-22 | CL42 | Completed
J1045 | 2026-10-29 | CL42 | Completed
J1046 | 2026-08-03 | CL59 | Completed
J1046 | 2026-09-07 | CL59 | Completed
J1046 | 2026-10-05 | CL59 | Completed
J1047 | 2026-08-04 | CL41 | Completed
J1047 | 2026-08-05 | CL41 | Completed
J1047 | 2026-08-11 | CL41 | Completed
J1047 | 2026-08-12 | CL41 | Completed
J1047 | 2026-08-18 | CL41 | Completed
J1047 | 2026-08-19 | CL41 | Completed
J1047 | 2026-08-25 | CL41 | Completed
J1047 | 2026-08-26 | CL41 | Completed
J1047 | 2026-09-01 | CL41 | Completed
J1047 | 2026-09-02 | CL41 | Completed
J1047 | 2026-09-08 | CL41 | Completed
J1047 | 2026-09-09 | CL41 | Completed
J1047 | 2026-09-15 | CL41 | Completed
J1047 | 2026-09-16 | CL41 | Completed
J1047 | 2026-09-22 | CL41 | Completed
J1047 | 2026-09-23 | CL41 | Completed
J1047 | 2026-09-29 | CL41 | Completed
J1047 | 2026-09-30 | CL41 | Completed
J1047 | 2026-10-06 | CL41 | Skipped
J1047 | 2026-10-07 | CL41 | Completed
J1047 | 2026-10-13 | CL41 | Completed
J1047 | 2026-10-14 | CL41 | Completed
J1047 | 2026-10-20 | CL41 | Completed
J1047 | 2026-10-21 | CL41 | Completed
J1047 | 2026-10-27 | CL41 | Completed
J1047 | 2026-10-28 | CL41 | Completed
J1048 | 2026-08-07 | CL09 | Completed
J1048 | 2026-08-14 | CL09 | Completed
J1048 | 2026-08-21 | CL09 | Completed
J1048 | 2026-08-28 | CL09 | Completed
J1048 | 2026-09-04 | CL09 | Completed
J1048 | 2026-09-11 | CL09 | Completed
J1048 | 2026-09-18 | CL09 | Completed
J1048 | 2026-09-25 | CL09 | Completed
J1048 | 2026-10-02 | CL09 | Completed
J1048 | 2026-10-09 | CL09 | Completed
J1048 | 2026-10-16 | CL09 | Completed
J1048 | 2026-10-23 | CL09 | Completed
J1048 | 2026-10-30 | CL09 | Completed
J1049 | 2026-08-04 | CL57 | Completed
J1049 | 2026-09-01 | CL57 | Completed
J1049 | 2026-09-29 | CL57 | Completed
J1049 | 2026-10-27 | CL57 | Completed
J1050 | 2026-08-05 | CL05 | Completed
J1050 | 2026-08-12 | CL05 | Completed
J1050 | 2026-08-19 | CL05 | Completed
J1050 | 2026-08-26 | CL05 | Completed
J1050 | 2026-09-02 | CL05 | Completed
J1050 | 2026-09-09 | CL05 | Completed
J1050 | 2026-09-16 | CL05 | Skipped
J1050 | 2026-09-23 | CL05 | Completed
J1050 | 2026-09-30 | CL05 | Skipped
J1050 | 2026-10-07 | CL05 | Completed
J1050 | 2026-10-14 | CL05 | Completed
J1050 | 2026-10-21 | CL05 | Completed
J1050 | 2026-10-28 | CL05 | Completed
J1051 | 2026-08-03 | CL24 | Completed
J1051 | 2026-08-06 | CL24 | Completed
J1051 | 2026-08-07 | CL24 | Completed
J1051 | 2026-08-10 | CL24 | Completed
J1051 | 2026-08-13 | CL24 | Completed
J1051 | 2026-08-14 | CL24 | Completed
J1051 | 2026-08-17 | CL24 | Completed
J1051 | 2026-08-20 | CL24 | Completed
J1051 | 2026-08-21 | CL24 | Completed
J1051 | 2026-08-24 | CL24 | Completed
J1051 | 2026-08-27 | CL24 | Completed
J1051 | 2026-08-28 | CL24 | Completed
J1051 | 2026-08-31 | CL24 | Completed
J1051 | 2026-09-03 | CL24 | Completed
J1051 | 2026-09-04 | CL24 | Completed
J1051 | 2026-09-07 | CL24 | Completed
J1051 | 2026-09-10 | CL24 | Completed
J1051 | 2026-09-11 | CL24 | Completed
J1051 | 2026-09-14 | CL24 | Completed
J1051 | 2026-09-17 | CL24 | Completed
J1051 | 2026-09-18 | CL24 | Completed
J1051 | 2026-09-21 | CL24 | Completed
J1051 | 2026-09-24 | CL24 | Completed
J1051 | 2026-09-25 | CL24 | Completed
J1051 | 2026-09-28 | CL24 | Completed
J1051 | 2026-10-01 | CL24 | Completed
J1051 | 2026-10-02 | CL24 | Completed
J1051 | 2026-10-05 | CL24 | Completed
J1051 | 2026-10-08 | CL24 | Completed
J1051 | 2026-10-09 | CL24 | Completed
J1051 | 2026-10-12 | CL24 | Completed
J1051 | 2026-10-15 | CL24 | Completed
J1051 | 2026-10-16 | CL24 | Completed
J1051 | 2026-10-19 | CL24 | Completed
J1051 | 2026-10-22 | CL24 | Completed
J1051 | 2026-10-23 | CL24 | Completed
J1051 | 2026-10-26 | CL24 | Completed
J1051 | 2026-10-29 | CL24 | Completed
J1051 | 2026-10-30 | CL24 | Completed
J1052 | 2026-08-04 | CL08 | Completed
J1052 | 2026-08-05 | CL08 | Completed
J1052 | 2026-08-11 | CL08 | Completed
J1052 | 2026-08-12 | CL08 | Completed
J1052 | 2026-08-18 | CL08 | Completed
J1052 | 2026-08-19 | CL08 | Completed
J1052 | 2026-08-25 | CL08 | Completed
J1052 | 2026-08-26 | CL08 | Completed
J1052 | 2026-09-01 | CL08 | Completed
J1052 | 2026-09-02 | CL08 | Completed
J1052 | 2026-09-08 | CL08 | Completed
J1052 | 2026-09-09 | CL08 | Completed
J1052 | 2026-09-15 | CL08 | Completed
J1052 | 2026-09-16 | CL08 | Completed
J1052 | 2026-09-22 | CL08 | Skipped
J1052 | 2026-09-23 | CL08 | Completed
J1052 | 2026-09-29 | CL08 | Completed
J1052 | 2026-09-30 | CL08 | Completed
J1052 | 2026-10-06 | CL08 | Completed
J1052 | 2026-10-07 | CL08 | Completed
J1052 | 2026-10-13 | CL08 | Completed
J1052 | 2026-10-14 | CL08 | Completed
J1052 | 2026-10-20 | CL08 | Completed
J1052 | 2026-10-21 | CL08 | Completed
J1052 | 2026-10-27 | CL08 | Completed
J1052 | 2026-10-28 | CL08 | Completed
J1053 | 2026-08-05 | CL17 | Completed
J1053 | 2026-08-12 | CL17 | Completed
J1053 | 2026-08-19 | CL17 | Completed
J1053 | 2026-08-26 | CL17 | Completed
J1053 | 2026-09-02 | CL17 | Completed
J1053 | 2026-09-09 | CL17 | Completed
J1053 | 2026-09-16 | CL17 | Completed
J1053 | 2026-09-23 | CL17 | Completed
J1053 | 2026-09-30 | CL17 | Completed
J1053 | 2026-10-07 | CL17 | Completed
J1053 | 2026-10-14 | CL17 | Completed
J1053 | 2026-10-21 | CL17 | Completed
J1053 | 2026-10-28 | CL17 | Completed
J1054 | 2026-08-04 | CL35 | Completed
J1054 | 2026-08-11 | CL35 | Completed
J1054 | 2026-08-18 | CL35 | Completed
J1054 | 2026-08-25 | CL35 | Completed
J1054 | 2026-09-01 | CL35 | Completed
J1054 | 2026-09-08 | CL35 | Completed
J1054 | 2026-09-15 | CL35 | Completed
J1054 | 2026-09-22 | CL35 | Completed
J1054 | 2026-09-29 | CL35 | Completed
J1054 | 2026-10-06 | CL35 | Completed
J1054 | 2026-10-13 | CL35 | Skipped
J1054 | 2026-10-20 | CL35 | Completed
J1054 | 2026-10-27 | CL35 | Completed
J1055 | 2026-08-03 | CL01 | Completed
J1055 | 2026-08-05 | CL01 | Completed
J1055 | 2026-08-10 | CL01 | Completed
J1055 | 2026-08-12 | CL01 | Completed
J1055 | 2026-08-17 | CL01 | Completed
J1055 | 2026-08-19 | CL01 | Completed
J1055 | 2026-08-24 | CL01 | Completed
J1055 | 2026-08-26 | CL01 | Completed
J1055 | 2026-08-31 | CL01 | Completed
J1055 | 2026-09-02 | CL01 | Completed
J1055 | 2026-09-07 | CL01 | Completed
J1055 | 2026-09-09 | CL01 | Completed
J1055 | 2026-09-14 | CL01 | Completed
J1055 | 2026-09-16 | CL01 | Completed
J1055 | 2026-09-21 | CL01 | Completed
J1055 | 2026-09-23 | CL01 | Completed
J1055 | 2026-09-28 | CL01 | Completed
J1055 | 2026-09-30 | CL01 | Completed
J1055 | 2026-10-05 | CL01 | Completed
J1055 | 2026-10-07 | CL01 | Completed
J1055 | 2026-10-12 | CL01 | Completed
J1055 | 2026-10-14 | CL01 | Completed
J1055 | 2026-10-19 | CL01 | Completed
J1055 | 2026-10-21 | CL01 | Completed
J1055 | 2026-10-26 | CL01 | Completed
J1055 | 2026-10-28 | CL01 | Completed
J1056 | 2026-08-03 | CL26 | Completed
J1056 | 2026-08-10 | CL26 | Completed
J1056 | 2026-08-17 | CL26 | Completed
J1056 | 2026-08-24 | CL26 | Completed
J1056 | 2026-08-31 | CL26 | Completed
J1056 | 2026-09-07 | CL26 | Completed
J1056 | 2026-09-14 | CL26 | Completed
J1056 | 2026-09-21 | CL26 | Completed
J1056 | 2026-09-28 | CL26 | Completed
J1056 | 2026-10-05 | CL26 | Completed
J1056 | 2026-10-12 | CL26 | Completed
J1056 | 2026-10-19 | CL26 | Completed
J1056 | 2026-10-26 | CL26 | Completed
J1057 | 2026-08-05 | CL44 | Completed
J1057 | 2026-08-12 | CL44 | Completed
J1057 | 2026-08-19 | CL44 | Completed
J1057 | 2026-08-26 | CL44 | Completed
J1057 | 2026-09-02 | CL44 | Completed
J1057 | 2026-09-09 | CL44 | Completed
J1057 | 2026-09-16 | CL44 | Completed
J1057 | 2026-09-23 | CL44 | Completed
J1057 | 2026-09-30 | CL44 | Completed
J1057 | 2026-10-07 | CL44 | Completed
J1057 | 2026-10-14 | CL44 | Completed
J1057 | 2026-10-21 | CL44 | Completed
J1057 | 2026-10-28 | CL44 | Completed
J1058 | 2026-08-03 | CL04 | Completed
J1058 | 2026-08-04 | CL04 | Completed
J1058 | 2026-08-05 | CL04 | Completed
J1058 | 2026-08-10 | CL04 | Completed
J1058 | 2026-08-11 | CL04 | Completed
J1058 | 2026-08-12 | CL04 | Completed
J1058 | 2026-08-17 | CL04 | Completed
J1058 | 2026-08-18 | CL04 | Completed
J1058 | 2026-08-19 | CL04 | Completed
J1058 | 2026-08-24 | CL04 | Completed
J1058 | 2026-08-25 | CL04 | Completed
J1058 | 2026-08-26 | CL04 | Completed
J1058 | 2026-08-31 | CL04 | Completed
J1058 | 2026-09-01 | CL04 | Completed
J1058 | 2026-09-02 | CL04 | Completed
J1058 | 2026-09-07 | CL04 | Completed
J1058 | 2026-09-08 | CL04 | Completed
J1058 | 2026-09-09 | CL04 | Completed
J1058 | 2026-09-14 | CL04 | Completed
J1058 | 2026-09-15 | CL04 | Completed
J1058 | 2026-09-16 | CL04 | Completed
J1058 | 2026-09-21 | CL04 | Completed
J1058 | 2026-09-22 | CL04 | Completed
J1058 | 2026-09-23 | CL04 | Completed
J1058 | 2026-09-28 | CL04 | Completed
J1058 | 2026-09-29 | CL04 | Completed
J1058 | 2026-09-30 | CL04 | Completed
J1058 | 2026-10-05 | CL04 | Skipped
J1058 | 2026-10-06 | CL04 | Completed
J1058 | 2026-10-07 | CL04 | Completed
J1058 | 2026-10-12 | CL04 | Completed
J1058 | 2026-10-13 | CL04 | Skipped
J1058 | 2026-10-14 | CL04 | Completed
J1058 | 2026-10-19 | CL04 | Completed
J1058 | 2026-10-20 | CL04 | Completed
J1058 | 2026-10-21 | CL04 | Completed
J1058 | 2026-10-26 | CL04 | Skipped
J1058 | 2026-10-27 | CL04 | Completed
J1058 | 2026-10-28 | CL04 | Completed
J1059 | 2026-08-05 | CL18 | Completed
J1059 | 2026-08-07 | CL18 | Completed
J1059 | 2026-08-12 | CL18 | Completed
J1059 | 2026-08-14 | CL18 | Completed
J1059 | 2026-08-19 | CL18 | Completed
J1059 | 2026-08-21 | CL18 | Completed
J1059 | 2026-08-26 | CL18 | Completed
J1059 | 2026-08-28 | CL18 | Completed
J1059 | 2026-09-02 | CL18 | Completed
J1059 | 2026-09-04 | CL18 | Completed
J1059 | 2026-09-09 | CL18 | Completed
J1059 | 2026-09-11 | CL18 | Completed
J1059 | 2026-09-16 | CL18 | Completed
J1059 | 2026-09-18 | CL18 | Completed
J1059 | 2026-09-23 | CL18 | Completed
J1059 | 2026-09-25 | CL18 | Completed
J1059 | 2026-09-30 | CL18 | Completed
J1059 | 2026-10-02 | CL18 | Completed
J1059 | 2026-10-07 | CL18 | Completed
J1059 | 2026-10-09 | CL18 | Completed
J1059 | 2026-10-14 | CL18 | Completed
J1059 | 2026-10-16 | CL18 | Completed
J1059 | 2026-10-21 | CL18 | Completed
J1059 | 2026-10-23 | CL18 | Completed
J1059 | 2026-10-28 | CL18 | Completed
J1059 | 2026-10-30 | CL18 | Completed
J1060 | 2026-08-03 | CL38 | Completed
J1060 | 2026-08-06 | CL38 | Completed
J1060 | 2026-08-10 | CL38 | Completed
J1060 | 2026-08-13 | CL38 | Completed
J1060 | 2026-08-17 | CL38 | Completed
J1060 | 2026-08-20 | CL38 | Completed
J1060 | 2026-08-24 | CL38 | Completed
J1060 | 2026-08-27 | CL38 | Completed
J1060 | 2026-08-31 | CL38 | Skipped
J1060 | 2026-09-03 | CL38 | Completed
J1060 | 2026-09-07 | CL38 | Completed
J1060 | 2026-09-10 | CL38 | Completed
J1060 | 2026-09-14 | CL38 | Completed
J1060 | 2026-09-17 | CL38 | Completed
J1060 | 2026-09-21 | CL38 | Completed
J1060 | 2026-09-24 | CL38 | Completed
J1060 | 2026-09-28 | CL38 | Completed
J1060 | 2026-10-01 | CL38 | Completed
J1060 | 2026-10-05 | CL38 | Completed
J1060 | 2026-10-08 | CL38 | Skipped
J1060 | 2026-10-12 | CL38 | Completed
J1060 | 2026-10-15 | CL38 | Completed
J1060 | 2026-10-19 | CL38 | Completed
J1060 | 2026-10-22 | CL38 | Completed
J1060 | 2026-10-26 | CL38 | Completed
J1060 | 2026-10-29 | CL38 | Completed
J1061 | 2026-08-04 | CL29 | Completed
J1061 | 2026-08-06 | CL29 | Completed
J1061 | 2026-08-11 | CL29 | Completed
J1061 | 2026-08-13 | CL29 | Completed
J1061 | 2026-08-18 | CL29 | Completed
J1061 | 2026-08-20 | CL29 | Completed
J1061 | 2026-08-25 | CL29 | Completed
J1061 | 2026-08-27 | CL29 | Completed
J1061 | 2026-09-01 | CL29 | Completed
J1061 | 2026-09-03 | CL29 | Completed
J1061 | 2026-09-08 | CL29 | Skipped
J1061 | 2026-09-10 | CL29 | Completed
J1061 | 2026-09-15 | CL29 | Completed
J1061 | 2026-09-17 | CL29 | Completed
J1061 | 2026-09-22 | CL29 | Completed
J1061 | 2026-09-24 | CL29 | Completed
J1061 | 2026-09-29 | CL29 | Completed
J1061 | 2026-10-01 | CL29 | Completed
J1061 | 2026-10-06 | CL29 | Completed
J1061 | 2026-10-08 | CL29 | Completed
J1061 | 2026-10-13 | CL29 | Completed
J1061 | 2026-10-15 | CL29 | Completed
J1061 | 2026-10-20 | CL29 | Completed
J1061 | 2026-10-22 | CL29 | Completed
J1061 | 2026-10-27 | CL29 | Completed
J1061 | 2026-10-29 | CL29 | Completed
J1062 | 2026-08-03 | CL41 | Completed
J1062 | 2026-08-04 | CL41 | Completed
J1062 | 2026-08-05 | CL41 | Completed
J1062 | 2026-08-06 | CL41 | Completed
J1062 | 2026-08-07 | CL41 | Completed
J1062 | 2026-08-10 | CL41 | Completed
J1062 | 2026-08-11 | CL41 | Completed
J1062 | 2026-08-12 | CL41 | Completed
J1062 | 2026-08-13 | CL41 | Completed
J1062 | 2026-08-14 | CL41 | Completed
J1062 | 2026-08-17 | CL41 | Completed
J1062 | 2026-08-18 | CL41 | Completed
J1062 | 2026-08-19 | CL41 | Completed
J1062 | 2026-08-20 | CL41 | Completed
J1062 | 2026-08-21 | CL41 | Completed
J1062 | 2026-08-24 | CL41 | Completed
J1062 | 2026-08-25 | CL41 | Completed
J1062 | 2026-08-26 | CL41 | Completed
J1062 | 2026-08-27 | CL41 | Completed
J1062 | 2026-08-28 | CL41 | Completed
J1062 | 2026-08-31 | CL41 | Completed
J1062 | 2026-09-01 | CL41 | Completed
J1062 | 2026-09-02 | CL41 | Completed
J1062 | 2026-09-03 | CL41 | Completed
J1062 | 2026-09-04 | CL41 | Completed
J1062 | 2026-09-07 | CL41 | Completed
J1062 | 2026-09-08 | CL41 | Completed
J1062 | 2026-09-09 | CL41 | Completed
J1062 | 2026-09-10 | CL41 | Completed
J1062 | 2026-09-11 | CL41 | Completed
J1062 | 2026-09-14 | CL41 | Completed
J1062 | 2026-09-15 | CL41 | Completed
J1062 | 2026-09-16 | CL41 | Completed
J1062 | 2026-09-17 | CL41 | Completed
J1062 | 2026-09-18 | CL41 | Completed
J1062 | 2026-09-21 | CL41 | Completed
J1062 | 2026-09-22 | CL41 | Completed
J1062 | 2026-09-23 | CL41 | Completed
J1062 | 2026-09-24 | CL41 | Completed
J1062 | 2026-09-25 | CL41 | Completed
J1062 | 2026-09-28 | CL41 | Completed
J1062 | 2026-09-29 | CL41 | Completed
J1062 | 2026-09-30 | CL41 | Completed
J1062 | 2026-10-01 | CL41 | Completed
J1062 | 2026-10-02 | CL41 | Completed
J1062 | 2026-10-05 | CL41 | Completed
J1062 | 2026-10-06 | CL41 | Completed
J1062 | 2026-10-07 | CL41 | Completed
J1062 | 2026-10-08 | CL41 | Completed
J1062 | 2026-10-09 | CL41 | Completed
J1062 | 2026-10-12 | CL41 | Completed
J1062 | 2026-10-13 | CL41 | Completed
J1062 | 2026-10-14 | CL41 | Completed
J1062 | 2026-10-15 | CL41 | Completed
J1062 | 2026-10-16 | CL41 | Completed
J1062 | 2026-10-19 | CL41 | Completed
J1062 | 2026-10-20 | CL41 | Completed
J1062 | 2026-10-21 | CL41 | Completed
J1062 | 2026-10-22 | CL41 | Completed
J1062 | 2026-10-23 | CL41 | Completed
J1062 | 2026-10-26 | CL41 | Completed
J1062 | 2026-10-27 | CL41 | Completed
J1062 | 2026-10-28 | CL41 | Completed
J1062 | 2026-10-29 | CL41 | Completed
J1062 | 2026-10-30 | CL41 | Completed
J1063 | 2026-08-06 | CL60 | Completed
J1063 | 2026-09-03 | CL60 | Completed
J1063 | 2026-10-01 | CL60 | Completed
J1063 | 2026-10-29 | CL60 | Completed
J1064 | 2026-08-03 | CL05 | Completed
J1064 | 2026-08-06 | CL05 | Completed
J1064 | 2026-08-10 | CL05 | Skipped
J1064 | 2026-08-13 | CL05 | Completed
J1064 | 2026-08-17 | CL05 | Completed
J1064 | 2026-08-20 | CL05 | Completed
J1064 | 2026-08-24 | CL05 | Completed
J1064 | 2026-08-27 | CL05 | Completed
J1064 | 2026-08-31 | CL05 | Completed
J1064 | 2026-09-03 | CL05 | Completed
J1064 | 2026-09-07 | CL05 | Completed
J1064 | 2026-09-10 | CL05 | Completed
J1064 | 2026-09-14 | CL05 | Completed
J1064 | 2026-09-17 | CL05 | Completed
J1064 | 2026-09-21 | CL05 | Completed
J1064 | 2026-09-24 | CL05 | Completed
J1064 | 2026-09-28 | CL05 | Completed
J1064 | 2026-10-01 | CL05 | Completed
J1064 | 2026-10-05 | CL05 | Completed
J1064 | 2026-10-08 | CL05 | Completed
J1064 | 2026-10-12 | CL05 | Completed
J1064 | 2026-10-15 | CL05 | Completed
J1064 | 2026-10-19 | CL05 | Completed
J1064 | 2026-10-22 | CL05 | Completed
J1064 | 2026-10-26 | CL05 | Completed
J1064 | 2026-10-29 | CL05 | Completed
J1065 | 2026-08-05 | CL58 | Completed
J1065 | 2026-09-02 | CL58 | Completed
J1065 | 2026-09-30 | CL58 | Completed
J1065 | 2026-10-28 | CL58 | Completed
J1066 | 2026-08-03 | CL33 | Completed
J1066 | 2026-08-05 | CL33 | Completed
J1066 | 2026-08-07 | CL33 | Completed
J1066 | 2026-08-10 | CL33 | Completed
J1066 | 2026-08-12 | CL33 | Completed
J1066 | 2026-08-14 | CL33 | Completed
J1066 | 2026-08-17 | CL33 | Completed
J1066 | 2026-08-19 | CL33 | Completed
J1066 | 2026-08-21 | CL33 | Completed
J1066 | 2026-08-24 | CL33 | Completed
J1066 | 2026-08-26 | CL33 | Completed
J1066 | 2026-08-28 | CL33 | Completed
J1066 | 2026-08-31 | CL33 | Completed
J1066 | 2026-09-02 | CL33 | Completed
J1066 | 2026-09-04 | CL33 | Completed
J1066 | 2026-09-07 | CL33 | Completed
J1066 | 2026-09-09 | CL33 | Completed
J1066 | 2026-09-11 | CL33 | Completed
J1066 | 2026-09-14 | CL33 | Completed
J1066 | 2026-09-16 | CL33 | Completed
J1066 | 2026-09-18 | CL33 | Completed
J1066 | 2026-09-21 | CL33 | Completed
J1066 | 2026-09-23 | CL33 | Completed
J1066 | 2026-09-25 | CL33 | Completed
J1066 | 2026-09-28 | CL33 | Completed
J1066 | 2026-09-30 | CL33 | Completed
J1066 | 2026-10-02 | CL33 | Completed
J1066 | 2026-10-05 | CL33 | Completed
J1066 | 2026-10-07 | CL33 | Completed
J1066 | 2026-10-09 | CL33 | Completed
J1066 | 2026-10-12 | CL33 | Completed
J1066 | 2026-10-14 | CL33 | Completed
J1066 | 2026-10-16 | CL33 | Completed
J1066 | 2026-10-19 | CL33 | Completed
J1066 | 2026-10-21 | CL33 | Completed
J1066 | 2026-10-23 | CL33 | Completed
J1066 | 2026-10-26 | CL33 | Completed
J1066 | 2026-10-28 | CL33 | Completed
J1066 | 2026-10-30 | CL33 | Completed
J1067 | 2026-08-03 | CL56 | Completed
J1067 | 2026-08-31 | CL56 | Completed
J1067 | 2026-09-28 | CL56 | Completed
J1067 | 2026-10-26 | CL56 | Completed
J1068 | 2026-08-06 | CL37 | Completed
J1068 | 2026-08-13 | CL37 | Completed
J1068 | 2026-08-20 | CL37 | Completed
J1068 | 2026-08-27 | CL37 | Completed
J1068 | 2026-09-03 | CL37 | Completed
J1068 | 2026-09-10 | CL37 | Completed
J1068 | 2026-09-17 | CL37 | Completed
J1068 | 2026-09-24 | CL37 | Completed
J1068 | 2026-10-01 | CL37 | Completed
J1068 | 2026-10-08 | CL37 | Completed
J1068 | 2026-10-15 | CL37 | Completed
J1068 | 2026-10-22 | CL37 | Completed
J1068 | 2026-10-29 | CL37 | Completed
J1069 | 2026-08-03 | CL24 | Completed
J1069 | 2026-08-06 | CL24 | Completed
J1069 | 2026-08-07 | CL24 | Completed
J1069 | 2026-08-10 | CL24 | Completed
J1069 | 2026-08-13 | CL24 | Completed
J1069 | 2026-08-14 | CL24 | Completed
J1069 | 2026-08-17 | CL24 | Completed
J1069 | 2026-08-20 | CL24 | Completed
J1069 | 2026-08-21 | CL24 | Completed
J1069 | 2026-08-24 | CL24 | Completed
J1069 | 2026-08-27 | CL24 | Completed
J1069 | 2026-08-28 | CL24 | Completed
J1069 | 2026-08-31 | CL24 | Completed
J1069 | 2026-09-03 | CL24 | Completed
J1069 | 2026-09-04 | CL24 | Completed
J1069 | 2026-09-07 | CL24 | Completed
J1069 | 2026-09-10 | CL24 | Completed
J1069 | 2026-09-11 | CL24 | Completed
J1069 | 2026-09-14 | CL24 | Completed
J1069 | 2026-09-17 | CL24 | Completed
J1069 | 2026-09-18 | CL24 | Completed
J1069 | 2026-09-21 | CL24 | Completed
J1069 | 2026-09-24 | CL24 | Completed
J1069 | 2026-09-25 | CL24 | Completed
J1069 | 2026-09-28 | CL24 | Completed
J1069 | 2026-10-01 | CL24 | Completed
J1069 | 2026-10-02 | CL24 | Completed
J1069 | 2026-10-05 | CL24 | Completed
J1069 | 2026-10-08 | CL24 | Completed
J1069 | 2026-10-09 | CL24 | Completed
J1069 | 2026-10-12 | CL24 | Completed
J1069 | 2026-10-15 | CL24 | Completed
J1069 | 2026-10-16 | CL24 | Completed
J1069 | 2026-10-19 | CL24 | Completed
J1069 | 2026-10-22 | CL24 | Completed
J1069 | 2026-10-23 | CL24 | Completed
J1069 | 2026-10-26 | CL24 | Completed
J1069 | 2026-10-29 | CL24 | Completed
J1069 | 2026-10-30 | CL24 | Completed
J1070 | 2026-08-04 | CL44 | Completed
J1070 | 2026-08-07 | CL44 | Completed
J1070 | 2026-08-11 | CL44 | Completed
J1070 | 2026-08-14 | CL44 | Completed
J1070 | 2026-08-18 | CL44 | Completed
J1070 | 2026-08-21 | CL44 | Completed
J1070 | 2026-08-25 | CL44 | Completed
J1070 | 2026-08-28 | CL44 | Completed
J1070 | 2026-09-01 | CL44 | Completed
J1070 | 2026-09-04 | CL44 | Completed
J1070 | 2026-09-08 | CL44 | Completed
J1070 | 2026-09-11 | CL44 | Completed
J1070 | 2026-09-15 | CL44 | Completed
J1070 | 2026-09-18 | CL44 | Completed
J1070 | 2026-09-22 | CL44 | Completed
J1070 | 2026-09-25 | CL44 | Completed
J1070 | 2026-09-29 | CL44 | Completed
J1070 | 2026-10-02 | CL44 | Skipped
J1070 | 2026-10-06 | CL44 | Completed
J1070 | 2026-10-09 | CL44 | Completed
J1070 | 2026-10-13 | CL44 | Completed
J1070 | 2026-10-16 | CL44 | Completed
J1070 | 2026-10-20 | CL44 | Completed
J1070 | 2026-10-23 | CL44 | Completed
J1070 | 2026-10-27 | CL44 | Completed
J1070 | 2026-10-30 | CL44 | Completed
J1071 | 2026-08-06 | CL27 | Skipped
J1071 | 2026-08-13 | CL27 | Completed
J1071 | 2026-08-20 | CL27 | Completed
J1071 | 2026-08-27 | CL27 | Completed
J1071 | 2026-09-03 | CL27 | Completed
J1071 | 2026-09-10 | CL27 | Completed
J1071 | 2026-09-17 | CL27 | Completed
J1071 | 2026-09-24 | CL27 | Completed
J1071 | 2026-10-01 | CL27 | Completed
J1071 | 2026-10-08 | CL27 | Completed
J1071 | 2026-10-15 | CL27 | Completed
J1071 | 2026-10-22 | CL27 | Completed
J1071 | 2026-10-29 | CL27 | Completed
J1072 | 2026-08-04 | CL39 | Completed
J1072 | 2026-08-11 | CL39 | Completed
J1072 | 2026-08-18 | CL39 | Completed
J1072 | 2026-08-25 | CL39 | Completed
J1072 | 2026-09-01 | CL39 | Completed
J1072 | 2026-09-08 | CL39 | Completed
J1072 | 2026-09-15 | CL39 | Completed
J1072 | 2026-09-22 | CL39 | Completed
J1072 | 2026-09-29 | CL39 | Completed
J1072 | 2026-10-06 | CL39 | Completed
J1072 | 2026-10-13 | CL39 | Completed
J1072 | 2026-10-20 | CL39 | Completed
J1072 | 2026-10-27 | CL39 | Completed
J1073 | 2026-08-03 | CL02 | Completed
J1073 | 2026-08-10 | CL02 | Completed
J1073 | 2026-08-17 | CL02 | Completed
J1073 | 2026-08-24 | CL02 | Completed
J1073 | 2026-08-31 | CL02 | Completed
J1073 | 2026-09-07 | CL02 | Completed
J1073 | 2026-09-14 | CL02 | Completed
J1073 | 2026-09-21 | CL02 | Completed
J1073 | 2026-09-28 | CL02 | Completed
J1073 | 2026-10-05 | CL02 | Completed
J1073 | 2026-10-12 | CL02 | Completed
J1073 | 2026-10-19 | CL02 | Completed
J1073 | 2026-10-26 | CL02 | Completed
J1074 | 2026-08-21 | CL60 | Completed
J1074 | 2026-09-18 | CL60 | Completed
J1074 | 2026-10-16 | CL60 | Completed
J1075 | 2026-08-03 | CL06 | Completed
J1075 | 2026-08-06 | CL06 | Completed
J1075 | 2026-08-10 | CL06 | Completed
J1075 | 2026-08-13 | CL06 | Completed
J1075 | 2026-08-17 | CL06 | Completed
J1075 | 2026-08-20 | CL06 | Completed
J1075 | 2026-08-24 | CL06 | Completed
J1075 | 2026-08-27 | CL06 | Completed
J1075 | 2026-08-31 | CL06 | Completed
J1075 | 2026-09-03 | CL06 | Completed
J1075 | 2026-09-07 | CL06 | Completed
J1075 | 2026-09-10 | CL06 | Completed
J1075 | 2026-09-14 | CL06 | Completed
J1075 | 2026-09-17 | CL06 | Completed
J1075 | 2026-09-21 | CL06 | Completed
J1075 | 2026-09-24 | CL06 | Completed
J1075 | 2026-09-28 | CL06 | Completed
J1075 | 2026-10-01 | CL06 | Completed
J1075 | 2026-10-05 | CL06 | Completed
J1075 | 2026-10-08 | CL06 | Completed
J1075 | 2026-10-12 | CL06 | Completed
J1075 | 2026-10-15 | CL06 | Completed
J1075 | 2026-10-19 | CL06 | Completed
J1075 | 2026-10-22 | CL06 | Completed
J1075 | 2026-10-26 | CL06 | Completed
J1075 | 2026-10-29 | CL06 | Completed
J1076 | 2026-08-27 | CL57 | Completed
J1076 | 2026-09-24 | CL57 | Completed
J1076 | 2026-10-22 | CL57 | Completed
J1077 | 2026-08-05 | CL42 | Completed
J1077 | 2026-08-06 | CL42 | Completed
J1077 | 2026-08-07 | CL42 | Completed
J1077 | 2026-08-12 | CL42 | Completed
J1077 | 2026-08-13 | CL42 | Completed
J1077 | 2026-08-14 | CL42 | Completed
J1077 | 2026-08-19 | CL42 | Completed
J1077 | 2026-08-20 | CL42 | Completed
J1077 | 2026-08-21 | CL42 | Completed
J1077 | 2026-08-26 | CL42 | Completed
J1077 | 2026-08-27 | CL42 | Completed
J1077 | 2026-08-28 | CL42 | Completed
J1077 | 2026-09-02 | CL42 | Skipped
J1077 | 2026-09-03 | CL42 | Completed
J1077 | 2026-09-04 | CL42 | Completed
J1077 | 2026-09-09 | CL42 | Completed
J1077 | 2026-09-10 | CL42 | Completed
J1077 | 2026-09-11 | CL42 | Completed
J1077 | 2026-09-16 | CL42 | Completed
J1077 | 2026-09-17 | CL42 | Completed
J1077 | 2026-09-18 | CL42 | Completed
J1077 | 2026-09-23 | CL42 | Completed
J1077 | 2026-09-24 | CL42 | Completed
J1077 | 2026-09-25 | CL42 | Completed
J1077 | 2026-09-30 | CL42 | Completed
J1077 | 2026-10-01 | CL42 | Completed
J1077 | 2026-10-02 | CL42 | Completed
J1077 | 2026-10-07 | CL42 | Completed
J1077 | 2026-10-08 | CL42 | Completed
J1077 | 2026-10-09 | CL42 | Completed
J1077 | 2026-10-14 | CL42 | Completed
J1077 | 2026-10-15 | CL42 | Completed
J1077 | 2026-10-16 | CL42 | Completed
J1077 | 2026-10-21 | CL42 | Completed
J1077 | 2026-10-22 | CL42 | Completed
J1077 | 2026-10-23 | CL42 | Completed
J1077 | 2026-10-28 | CL42 | Completed
J1077 | 2026-10-29 | CL42 | Completed
J1077 | 2026-10-30 | CL42 | Completed
J1078 | 2026-08-07 | CL48 | Completed
J1078 | 2026-08-14 | CL48 | Completed
J1078 | 2026-08-21 | CL48 | Completed
J1078 | 2026-08-28 | CL48 | Completed
J1078 | 2026-09-04 | CL48 | Completed
J1078 | 2026-09-11 | CL48 | Completed
J1078 | 2026-09-18 | CL48 | Completed
J1078 | 2026-09-25 | CL48 | Completed
J1078 | 2026-10-02 | CL48 | Completed
J1078 | 2026-10-09 | CL48 | Completed
J1078 | 2026-10-16 | CL48 | Completed
J1078 | 2026-10-23 | CL48 | Completed
J1078 | 2026-10-30 | CL48 | Completed
J1079 | 2026-08-04 | CL40 | Completed
J1079 | 2026-08-11 | CL40 | Completed
J1079 | 2026-08-18 | CL40 | Completed
J1079 | 2026-08-25 | CL40 | Completed
J1079 | 2026-09-01 | CL40 | Completed
J1079 | 2026-09-08 | CL40 | Completed
J1079 | 2026-09-15 | CL40 | Completed
J1079 | 2026-09-22 | CL40 | Completed
J1079 | 2026-09-29 | CL40 | Completed
J1079 | 2026-10-06 | CL40 | Completed
J1079 | 2026-10-13 | CL40 | Completed
J1079 | 2026-10-20 | CL40 | Completed
J1079 | 2026-10-27 | CL40 | Completed
J1080 | 2026-08-03 | CL60 | Completed
J1080 | 2026-08-31 | CL60 | Completed
J1080 | 2026-09-28 | CL60 | Completed
J1080 | 2026-10-26 | CL60 | Skipped
J1081 | 2026-08-03 | CL07 | Completed
J1081 | 2026-08-05 | CL07 | Completed
J1081 | 2026-08-07 | CL07 | Completed
J1081 | 2026-08-10 | CL07 | Completed
J1081 | 2026-08-12 | CL07 | Completed
J1081 | 2026-08-14 | CL07 | Completed
J1081 | 2026-08-17 | CL07 | Completed
J1081 | 2026-08-19 | CL07 | Completed
J1081 | 2026-08-21 | CL07 | Completed
J1081 | 2026-08-24 | CL07 | Completed
J1081 | 2026-08-26 | CL07 | Completed
J1081 | 2026-08-28 | CL07 | Completed
J1081 | 2026-08-31 | CL07 | Completed
J1081 | 2026-09-02 | CL07 | Completed
J1081 | 2026-09-04 | CL07 | Completed
J1081 | 2026-09-07 | CL07 | Completed
J1081 | 2026-09-09 | CL07 | Completed
J1081 | 2026-09-11 | CL07 | Completed
J1081 | 2026-09-14 | CL07 | Completed
J1081 | 2026-09-16 | CL07 | Completed
J1081 | 2026-09-18 | CL07 | Completed
J1081 | 2026-09-21 | CL07 | Completed
J1081 | 2026-09-23 | CL07 | Completed
J1081 | 2026-09-25 | CL07 | Completed
J1081 | 2026-09-28 | CL07 | Completed
J1081 | 2026-09-30 | CL07 | Completed
J1081 | 2026-10-02 | CL07 | Completed
J1081 | 2026-10-05 | CL07 | Completed
J1081 | 2026-10-07 | CL07 | Completed
J1081 | 2026-10-09 | CL07 | Completed
J1081 | 2026-10-12 | CL07 | Completed
J1081 | 2026-10-14 | CL07 | Completed
J1081 | 2026-10-16 | CL07 | Completed
J1081 | 2026-10-19 | CL07 | Completed
J1081 | 2026-10-21 | CL07 | Completed
J1081 | 2026-10-23 | CL07 | Completed
J1081 | 2026-10-26 | CL07 | Completed
J1081 | 2026-10-28 | CL07 | Completed
J1081 | 2026-10-30 | CL07 | Completed
J1082 | 2026-08-03 | CL56 | Completed
J1082 | 2026-09-07 | CL56 | Completed
J1082 | 2026-10-05 | CL56 | Completed
J1083 | 2026-08-03 | CL48 | Completed
J1083 | 2026-08-04 | CL48 | Completed
J1083 | 2026-08-05 | CL48 | Completed
J1083 | 2026-08-06 | CL48 | Completed
J1083 | 2026-08-07 | CL48 | Completed
J1083 | 2026-08-10 | CL48 | Completed
J1083 | 2026-08-11 | CL48 | Completed
J1083 | 2026-08-12 | CL48 | Completed
J1083 | 2026-08-13 | CL48 | Completed
J1083 | 2026-08-14 | CL48 | Completed
J1083 | 2026-08-17 | CL48 | Completed
J1083 | 2026-08-18 | CL48 | Completed
J1083 | 2026-08-19 | CL48 | Completed
J1083 | 2026-08-20 | CL48 | Completed
J1083 | 2026-08-21 | CL48 | Completed
J1083 | 2026-08-24 | CL48 | Completed
J1083 | 2026-08-25 | CL48 | Completed
J1083 | 2026-08-26 | CL48 | Completed
J1083 | 2026-08-27 | CL48 | Completed
J1083 | 2026-08-28 | CL48 | Completed
J1083 | 2026-08-31 | CL48 | Completed
J1083 | 2026-09-01 | CL48 | Completed
J1083 | 2026-09-02 | CL48 | Completed
J1083 | 2026-09-03 | CL48 | Completed
J1083 | 2026-09-04 | CL48 | Completed
J1083 | 2026-09-07 | CL48 | Completed
J1083 | 2026-09-08 | CL48 | Completed
J1083 | 2026-09-09 | CL48 | Completed
J1083 | 2026-09-10 | CL48 | Completed
J1083 | 2026-09-11 | CL48 | Completed
J1083 | 2026-09-14 | CL48 | Completed
J1083 | 2026-09-15 | CL48 | Completed
J1083 | 2026-09-16 | CL48 | Completed
J1083 | 2026-09-17 | CL48 | Completed
J1083 | 2026-09-18 | CL48 | Completed
J1083 | 2026-09-21 | CL48 | Completed
J1083 | 2026-09-22 | CL48 | Completed
J1083 | 2026-09-23 | CL48 | Completed
J1083 | 2026-09-24 | CL48 | Completed
J1083 | 2026-09-25 | CL48 | Completed
J1083 | 2026-09-28 | CL48 | Completed
J1083 | 2026-09-29 | CL48 | Completed
J1083 | 2026-09-30 | CL48 | Completed
J1083 | 2026-10-01 | CL48 | Completed
J1083 | 2026-10-02 | CL48 | Completed
J1083 | 2026-10-05 | CL48 | Completed
J1083 | 2026-10-06 | CL48 | Completed
J1083 | 2026-10-07 | CL48 | Completed
J1083 | 2026-10-08 | CL48 | Completed
J1083 | 2026-10-09 | CL48 | Completed
J1083 | 2026-10-12 | CL48 | Completed
J1083 | 2026-10-13 | CL48 | Completed
J1083 | 2026-10-14 | CL48 | Completed
J1083 | 2026-10-15 | CL48 | Completed
J1083 | 2026-10-16 | CL48 | Completed
J1083 | 2026-10-19 | CL48 | Completed
J1083 | 2026-10-20 | CL48 | Completed
J1083 | 2026-10-21 | CL48 | Completed
J1083 | 2026-10-22 | CL48 | Completed
J1083 | 2026-10-23 | CL48 | Completed
J1083 | 2026-10-26 | CL48 | Completed
J1083 | 2026-10-27 | CL48 | Completed
J1083 | 2026-10-28 | CL48 | Completed
J1083 | 2026-10-29 | CL48 | Completed
J1083 | 2026-10-30 | CL48 | Completed
J1084 | 2026-08-21 | CL53 | Skipped
J1084 | 2026-09-18 | CL53 | Completed
J1084 | 2026-10-16 | CL53 | Completed
J1085 | 2026-08-04 | CL02 | Completed
J1085 | 2026-08-05 | CL02 | Completed
J1085 | 2026-08-11 | CL02 | Completed
J1085 | 2026-08-12 | CL02 | Completed
J1085 | 2026-08-18 | CL02 | Completed
J1085 | 2026-08-19 | CL02 | Completed
J1085 | 2026-08-25 | CL02 | Completed
J1085 | 2026-08-26 | CL02 | Completed
J1085 | 2026-09-01 | CL02 | Completed
J1085 | 2026-09-02 | CL02 | Completed
J1085 | 2026-09-08 | CL02 | Completed
J1085 | 2026-09-09 | CL02 | Completed
J1085 | 2026-09-15 | CL02 | Completed
J1085 | 2026-09-16 | CL02 | Completed
J1085 | 2026-09-22 | CL02 | Completed
J1085 | 2026-09-23 | CL02 | Completed
J1085 | 2026-09-29 | CL02 | Completed
J1085 | 2026-09-30 | CL02 | Completed
J1085 | 2026-10-06 | CL02 | Completed
J1085 | 2026-10-07 | CL02 | Completed
J1085 | 2026-10-13 | CL02 | Completed
J1085 | 2026-10-14 | CL02 | Completed
J1085 | 2026-10-20 | CL02 | Completed
J1085 | 2026-10-21 | CL02 | Completed
J1085 | 2026-10-27 | CL02 | Completed
J1085 | 2026-10-28 | CL02 | Completed
J1086 | 2026-08-06 | CL60 | Completed
J1086 | 2026-09-03 | CL60 | Completed
J1086 | 2026-10-01 | CL60 | Completed
J1086 | 2026-10-29 | CL60 | Completed
J1087 | 2026-08-06 | CL58 | Completed
J1087 | 2026-09-03 | CL58 | Completed
J1087 | 2026-10-01 | CL58 | Completed
J1088 | 2026-08-05 | CL19 | Completed
J1088 | 2026-08-12 | CL19 | Completed
J1088 | 2026-08-19 | CL19 | Completed
J1088 | 2026-08-26 | CL19 | Skipped
J1088 | 2026-09-02 | CL19 | Completed
J1088 | 2026-09-09 | CL19 | Completed
J1088 | 2026-09-16 | CL19 | Skipped
J1088 | 2026-09-23 | CL19 | Completed
J1088 | 2026-09-30 | CL19 | Completed
J1088 | 2026-10-07 | CL19 | Completed
J1088 | 2026-10-14 | CL19 | Completed
J1088 | 2026-10-21 | CL19 | Skipped
J1088 | 2026-10-28 | CL19 | Completed
J1089 | 2026-08-12 | CL60 | Completed
J1089 | 2026-09-09 | CL60 | Completed
J1089 | 2026-10-07 | CL60 | Completed
J1090 | 2026-08-03 | CL60 | Completed
J1090 | 2026-09-07 | CL60 | Completed
J1090 | 2026-10-05 | CL60 | Completed
J1091 | 2026-08-03 | CL22 | Completed
J1091 | 2026-08-04 | CL22 | Completed
J1091 | 2026-08-10 | CL22 | Completed
J1091 | 2026-08-11 | CL22 | Completed
J1091 | 2026-08-17 | CL22 | Completed
J1091 | 2026-08-18 | CL22 | Completed
J1091 | 2026-08-24 | CL22 | Completed
J1091 | 2026-08-25 | CL22 | Completed
J1091 | 2026-08-31 | CL22 | Completed
J1091 | 2026-09-01 | CL22 | Completed
J1091 | 2026-09-07 | CL22 | Completed
J1091 | 2026-09-08 | CL22 | Completed
J1091 | 2026-09-14 | CL22 | Completed
J1091 | 2026-09-15 | CL22 | Completed
J1091 | 2026-09-21 | CL22 | Completed
J1091 | 2026-09-22 | CL22 | Completed
J1091 | 2026-09-28 | CL22 | Completed
J1091 | 2026-09-29 | CL22 | Completed
J1091 | 2026-10-05 | CL22 | Completed
J1091 | 2026-10-06 | CL22 | Completed
J1091 | 2026-10-12 | CL22 | Completed
J1091 | 2026-10-13 | CL22 | Completed
J1091 | 2026-10-19 | CL22 | Completed
J1091 | 2026-10-20 | CL22 | Completed
J1091 | 2026-10-26 | CL22 | Completed
J1091 | 2026-10-27 | CL22 | Skipped
J1092 | 2026-08-05 | CL06 | Completed
J1092 | 2026-08-12 | CL06 | Completed
J1092 | 2026-08-19 | CL06 | Completed
J1092 | 2026-08-26 | CL06 | Completed
J1092 | 2026-09-02 | CL06 | Completed
J1092 | 2026-09-09 | CL06 | Completed
J1092 | 2026-09-16 | CL06 | Completed
J1092 | 2026-09-23 | CL06 | Completed
J1092 | 2026-09-30 | CL06 | Completed
J1092 | 2026-10-07 | CL06 | Completed
J1092 | 2026-10-14 | CL06 | Completed
J1092 | 2026-10-21 | CL06 | Completed
J1092 | 2026-10-28 | CL06 | Completed
J1093 | 2026-08-06 | CL03 | Completed
J1093 | 2026-08-13 | CL03 | Completed
J1093 | 2026-08-20 | CL03 | Completed
J1093 | 2026-08-27 | CL03 | Completed
J1093 | 2026-09-03 | CL03 | Completed
J1093 | 2026-09-10 | CL03 | Completed
J1093 | 2026-09-17 | CL03 | Completed
J1093 | 2026-09-24 | CL03 | Completed
J1093 | 2026-10-01 | CL03 | Completed
J1093 | 2026-10-08 | CL03 | Completed
J1093 | 2026-10-15 | CL03 | Completed
J1093 | 2026-10-22 | CL03 | Completed
J1093 | 2026-10-29 | CL03 | Completed
J1094 | 2026-08-04 | CL35 | Completed
J1094 | 2026-08-06 | CL35 | Completed
J1094 | 2026-08-11 | CL35 | Completed
J1094 | 2026-08-13 | CL35 | Completed
J1094 | 2026-08-18 | CL35 | Completed
J1094 | 2026-08-20 | CL35 | Completed
J1094 | 2026-08-25 | CL35 | Completed
J1094 | 2026-08-27 | CL35 | Completed
J1094 | 2026-09-01 | CL35 | Completed
J1094 | 2026-09-03 | CL35 | Completed
J1094 | 2026-09-08 | CL35 | Completed
J1094 | 2026-09-10 | CL35 | Completed
J1094 | 2026-09-15 | CL35 | Completed
J1094 | 2026-09-17 | CL35 | Completed
J1094 | 2026-09-22 | CL35 | Completed
J1094 | 2026-09-24 | CL35 | Completed
J1094 | 2026-09-29 | CL35 | Completed
J1094 | 2026-10-01 | CL35 | Completed
J1094 | 2026-10-06 | CL35 | Completed
J1094 | 2026-10-08 | CL35 | Completed
J1094 | 2026-10-13 | CL35 | Completed
J1094 | 2026-10-15 | CL35 | Completed
J1094 | 2026-10-20 | CL35 | Completed
J1094 | 2026-10-22 | CL35 | Completed
J1094 | 2026-10-27 | CL35 | Completed
J1094 | 2026-10-29 | CL35 | Completed
J1095 | 2026-08-04 | CL60 | Completed
J1095 | 2026-09-01 | CL60 | Completed
J1095 | 2026-09-29 | CL60 | Completed
J1095 | 2026-10-27 | CL60 | Completed
J1096 | 2026-08-05 | CL43 | Completed
J1096 | 2026-08-06 | CL43 | Completed
J1096 | 2026-08-07 | CL43 | Completed
J1096 | 2026-08-12 | CL43 | Completed
J1096 | 2026-08-13 | CL43 | Completed
J1096 | 2026-08-14 | CL43 | Completed
J1096 | 2026-08-19 | CL43 | Completed
J1096 | 2026-08-20 | CL43 | Completed
J1096 | 2026-08-21 | CL43 | Completed
J1096 | 2026-08-26 | CL43 | Completed
J1096 | 2026-08-27 | CL43 | Completed
J1096 | 2026-08-28 | CL43 | Completed
J1096 | 2026-09-02 | CL43 | Completed
J1096 | 2026-09-03 | CL43 | Completed
J1096 | 2026-09-04 | CL43 | Completed
J1096 | 2026-09-09 | CL43 | Completed
J1096 | 2026-09-10 | CL43 | Completed
J1096 | 2026-09-11 | CL43 | Completed
J1096 | 2026-09-16 | CL43 | Completed
J1096 | 2026-09-17 | CL43 | Completed
J1096 | 2026-09-18 | CL43 | Completed
J1096 | 2026-09-23 | CL43 | Completed
J1096 | 2026-09-24 | CL43 | Completed
J1096 | 2026-09-25 | CL43 | Completed
J1096 | 2026-09-30 | CL43 | Completed
J1096 | 2026-10-01 | CL43 | Completed
J1096 | 2026-10-02 | CL43 | Completed
J1096 | 2026-10-07 | CL43 | Completed
J1096 | 2026-10-08 | CL43 | Completed
J1096 | 2026-10-09 | CL43 | Completed
J1096 | 2026-10-14 | CL43 | Completed
J1096 | 2026-10-15 | CL43 | Completed
J1096 | 2026-10-16 | CL43 | Completed
J1096 | 2026-10-21 | CL43 | Completed
J1096 | 2026-10-22 | CL43 | Completed
J1096 | 2026-10-23 | CL43 | Completed
J1096 | 2026-10-28 | CL43 | Completed
J1096 | 2026-10-29 | CL43 | Completed
J1096 | 2026-10-30 | CL43 | Completed
J1097 | 2026-08-05 | CL17 | Completed
J1097 | 2026-08-07 | CL17 | Completed
J1097 | 2026-08-12 | CL17 | Completed
J1097 | 2026-08-14 | CL17 | Completed
J1097 | 2026-08-19 | CL17 | Completed
J1097 | 2026-08-21 | CL17 | Completed
J1097 | 2026-08-26 | CL17 | Completed
J1097 | 2026-08-28 | CL17 | Completed
J1097 | 2026-09-02 | CL17 | Completed
J1097 | 2026-09-04 | CL17 | Completed
J1097 | 2026-09-09 | CL17 | Completed
J1097 | 2026-09-11 | CL17 | Completed
J1097 | 2026-09-16 | CL17 | Completed
J1097 | 2026-09-18 | CL17 | Completed
J1097 | 2026-09-23 | CL17 | Completed
J1097 | 2026-09-25 | CL17 | Completed
J1097 | 2026-09-30 | CL17 | Completed
J1097 | 2026-10-02 | CL17 | Completed
J1097 | 2026-10-07 | CL17 | Completed
J1097 | 2026-10-09 | CL17 | Completed
J1097 | 2026-10-14 | CL17 | Completed
J1097 | 2026-10-16 | CL17 | Completed
J1097 | 2026-10-21 | CL17 | Completed
J1097 | 2026-10-23 | CL17 | Completed
J1097 | 2026-10-28 | CL17 | Completed
J1097 | 2026-10-30 | CL17 | Completed
J1098 | 2026-08-27 | CL60 | Completed
J1098 | 2026-09-24 | CL60 | Completed
J1098 | 2026-10-22 | CL60 | Completed
J1099 | 2026-08-07 | CL53 | Completed
J1099 | 2026-09-04 | CL53 | Skipped
J1099 | 2026-10-02 | CL53 | Completed
J1100 | 2026-08-03 | CL16 | Completed
J1100 | 2026-08-07 | CL16 | Completed
J1100 | 2026-08-10 | CL16 | Completed
J1100 | 2026-08-14 | CL16 | Completed
J1100 | 2026-08-17 | CL16 | Completed
J1100 | 2026-08-21 | CL16 | Completed
J1100 | 2026-08-24 | CL16 | Completed
J1100 | 2026-08-28 | CL16 | Completed
J1100 | 2026-08-31 | CL16 | Completed
J1100 | 2026-09-04 | CL16 | Completed
J1100 | 2026-09-07 | CL16 | Completed
J1100 | 2026-09-11 | CL16 | Completed
J1100 | 2026-09-14 | CL16 | Completed
J1100 | 2026-09-18 | CL16 | Completed
J1100 | 2026-09-21 | CL16 | Completed
J1100 | 2026-09-25 | CL16 | Completed
J1100 | 2026-09-28 | CL16 | Completed
J1100 | 2026-10-02 | CL16 | Completed
J1100 | 2026-10-05 | CL16 | Completed
J1100 | 2026-10-09 | CL16 | Completed
J1100 | 2026-10-12 | CL16 | Completed
J1100 | 2026-10-16 | CL16 | Completed
J1100 | 2026-10-19 | CL16 | Completed
J1100 | 2026-10-23 | CL16 | Completed
J1100 | 2026-10-26 | CL16 | Completed
J1100 | 2026-10-30 | CL16 | Completed
J1101 | 2026-08-03 | CL59 | Completed
J1101 | 2026-08-31 | CL59 | Completed
J1101 | 2026-09-28 | CL59 | Completed
J1101 | 2026-10-26 | CL59 | Completed
J1102 | 2026-08-03 | CL50 | Completed
J1102 | 2026-08-05 | CL50 | Completed
J1102 | 2026-08-10 | CL50 | Completed
J1102 | 2026-08-12 | CL50 | Completed
J1102 | 2026-08-17 | CL50 | Completed
J1102 | 2026-08-19 | CL50 | Completed
J1102 | 2026-08-24 | CL50 | Completed
J1102 | 2026-08-26 | CL50 | Completed
J1102 | 2026-08-31 | CL50 | Completed
J1102 | 2026-09-02 | CL50 | Completed
J1102 | 2026-09-07 | CL50 | Completed
J1102 | 2026-09-09 | CL50 | Completed
J1102 | 2026-09-14 | CL50 | Completed
J1102 | 2026-09-16 | CL50 | Completed
J1102 | 2026-09-21 | CL50 | Completed
J1102 | 2026-09-23 | CL50 | Completed
J1102 | 2026-09-28 | CL50 | Completed
J1102 | 2026-09-30 | CL50 | Completed
J1102 | 2026-10-05 | CL50 | Completed
J1102 | 2026-10-07 | CL50 | Completed
J1102 | 2026-10-12 | CL50 | Completed
J1102 | 2026-10-14 | CL50 | Completed
J1102 | 2026-10-19 | CL50 | Completed
J1102 | 2026-10-21 | CL50 | Completed
J1102 | 2026-10-26 | CL50 | Completed
J1102 | 2026-10-28 | CL50 | Completed
J1103 | 2026-08-06 | CL55 | Completed
J1103 | 2026-09-03 | CL55 | Skipped
J1103 | 2026-10-01 | CL55 | Completed
J1104 | 2026-08-03 | CL34 | Completed
J1104 | 2026-08-07 | CL34 | Completed
J1104 | 2026-08-10 | CL34 | Completed
J1104 | 2026-08-14 | CL34 | Completed
J1104 | 2026-08-17 | CL34 | Completed
J1104 | 2026-08-21 | CL34 | Completed
J1104 | 2026-08-24 | CL34 | Completed
J1104 | 2026-08-28 | CL34 | Completed
J1104 | 2026-08-31 | CL34 | Completed
J1104 | 2026-09-04 | CL34 | Completed
J1104 | 2026-09-07 | CL34 | Completed
J1104 | 2026-09-11 | CL34 | Completed
J1104 | 2026-09-14 | CL34 | Completed
J1104 | 2026-09-18 | CL34 | Completed
J1104 | 2026-09-21 | CL34 | Completed
J1104 | 2026-09-25 | CL34 | Completed
J1104 | 2026-09-28 | CL34 | Completed
J1104 | 2026-10-02 | CL34 | Completed
J1104 | 2026-10-05 | CL34 | Completed
J1104 | 2026-10-09 | CL34 | Completed
J1104 | 2026-10-12 | CL34 | Completed
J1104 | 2026-10-16 | CL34 | Completed
J1104 | 2026-10-19 | CL34 | Completed
J1104 | 2026-10-23 | CL34 | Completed
J1104 | 2026-10-26 | CL34 | Completed
J1104 | 2026-10-30 | CL34 | Completed
J1105 | 2026-08-05 | CL58 | Completed
J1105 | 2026-09-02 | CL58 | Completed
J1105 | 2026-09-30 | CL58 | Completed
J1105 | 2026-10-28 | CL58 | Completed
J1106 | 2026-08-03 | CL26 | Completed
J1106 | 2026-08-06 | CL26 | Completed
J1106 | 2026-08-07 | CL26 | Completed
J1106 | 2026-08-10 | CL26 | Completed
J1106 | 2026-08-13 | CL26 | Completed
J1106 | 2026-08-14 | CL26 | Completed
J1106 | 2026-08-17 | CL26 | Completed
J1106 | 2026-08-20 | CL26 | Completed
J1106 | 2026-08-21 | CL26 | Completed
J1106 | 2026-08-24 | CL26 | Completed
J1106 | 2026-08-27 | CL26 | Completed
J1106 | 2026-08-28 | CL26 | Completed
J1106 | 2026-08-31 | CL26 | Completed
J1106 | 2026-09-03 | CL26 | Completed
J1106 | 2026-09-04 | CL26 | Completed
J1106 | 2026-09-07 | CL26 | Completed
J1106 | 2026-09-10 | CL26 | Completed
J1106 | 2026-09-11 | CL26 | Completed
J1106 | 2026-09-14 | CL26 | Completed
J1106 | 2026-09-17 | CL26 | Completed
J1106 | 2026-09-18 | CL26 | Completed
J1106 | 2026-09-21 | CL26 | Completed
J1106 | 2026-09-24 | CL26 | Completed
J1106 | 2026-09-25 | CL26 | Completed
J1106 | 2026-09-28 | CL26 | Completed
J1106 | 2026-10-01 | CL26 | Completed
J1106 | 2026-10-02 | CL26 | Completed
J1106 | 2026-10-05 | CL26 | Completed
J1106 | 2026-10-08 | CL26 | Completed
J1106 | 2026-10-09 | CL26 | Completed
J1106 | 2026-10-12 | CL26 | Completed
J1106 | 2026-10-15 | CL26 | Completed
J1106 | 2026-10-16 | CL26 | Completed
J1106 | 2026-10-19 | CL26 | Completed
J1106 | 2026-10-22 | CL26 | Completed
J1106 | 2026-10-23 | CL26 | Completed
J1106 | 2026-10-26 | CL26 | Completed
J1106 | 2026-10-29 | CL26 | Completed
J1106 | 2026-10-30 | CL26 | Completed
J1107 | 2026-08-03 | CL15 | Completed
J1107 | 2026-08-04 | CL15 | Completed
J1107 | 2026-08-05 | CL15 | Completed
J1107 | 2026-08-06 | CL15 | Completed
J1107 | 2026-08-07 | CL15 | Completed
J1107 | 2026-08-10 | CL15 | Completed
J1107 | 2026-08-11 | CL15 | Completed
J1107 | 2026-08-12 | CL15 | Completed
J1107 | 2026-08-13 | CL15 | Completed
J1107 | 2026-08-14 | CL15 | Completed
J1107 | 2026-08-17 | CL15 | Completed
J1107 | 2026-08-18 | CL15 | Completed
J1107 | 2026-08-19 | CL15 | Completed
J1107 | 2026-08-20 | CL15 | Completed
J1107 | 2026-08-21 | CL15 | Completed
J1107 | 2026-08-24 | CL15 | Completed
J1107 | 2026-08-25 | CL15 | Completed
J1107 | 2026-08-26 | CL15 | Completed
J1107 | 2026-08-27 | CL15 | Completed
J1107 | 2026-08-28 | CL15 | Completed
J1107 | 2026-08-31 | CL15 | Completed
J1107 | 2026-09-01 | CL15 | Completed
J1107 | 2026-09-02 | CL15 | Completed
J1107 | 2026-09-03 | CL15 | Completed
J1107 | 2026-09-04 | CL15 | Completed
J1107 | 2026-09-07 | CL15 | Completed
J1107 | 2026-09-08 | CL15 | Completed
J1107 | 2026-09-09 | CL15 | Completed
J1107 | 2026-09-10 | CL15 | Completed
J1107 | 2026-09-11 | CL15 | Completed
J1107 | 2026-09-14 | CL15 | Completed
J1107 | 2026-09-15 | CL15 | Completed
J1107 | 2026-09-16 | CL15 | Completed
J1107 | 2026-09-17 | CL15 | Completed
J1107 | 2026-09-18 | CL15 | Completed
J1107 | 2026-09-21 | CL15 | Completed
J1107 | 2026-09-22 | CL15 | Completed
J1107 | 2026-09-23 | CL15 | Completed
J1107 | 2026-09-24 | CL15 | Completed
J1107 | 2026-09-25 | CL15 | Completed
J1107 | 2026-09-28 | CL15 | Completed
J1107 | 2026-09-29 | CL15 | Completed
J1107 | 2026-09-30 | CL15 | Completed
J1107 | 2026-10-01 | CL15 | Completed
J1107 | 2026-10-02 | CL15 | Completed
J1107 | 2026-10-05 | CL15 | Completed
J1107 | 2026-10-06 | CL15 | Completed
J1107 | 2026-10-07 | CL15 | Completed
J1107 | 2026-10-08 | CL15 | Skipped
J1107 | 2026-10-09 | CL15 | Completed
J1107 | 2026-10-12 | CL15 | Completed
J1107 | 2026-10-13 | CL15 | Completed
J1107 | 2026-10-14 | CL15 | Completed
J1107 | 2026-10-15 | CL15 | Completed
J1107 | 2026-10-16 | CL15 | Completed
J1107 | 2026-10-19 | CL15 | Completed
J1107 | 2026-10-20 | CL15 | Completed
J1107 | 2026-10-21 | CL15 | Completed
J1107 | 2026-10-22 | CL15 | Completed
J1107 | 2026-10-23 | CL15 | Completed
J1107 | 2026-10-26 | CL15 | Skipped
J1107 | 2026-10-27 | CL15 | Completed
J1107 | 2026-10-28 | CL15 | Completed
J1107 | 2026-10-29 | CL15 | Completed
J1107 | 2026-10-30 | CL15 | Completed
J1108 | 2026-08-17 | CL56 | Completed
J1108 | 2026-09-14 | CL56 | Completed
J1108 | 2026-10-12 | CL56 | Completed
J1109 | 2026-08-04 | CL10 | Completed
J1109 | 2026-08-07 | CL10 | Completed
J1109 | 2026-08-11 | CL10 | Completed
J1109 | 2026-08-14 | CL10 | Completed
J1109 | 2026-08-18 | CL10 | Completed
J1109 | 2026-08-21 | CL10 | Completed
J1109 | 2026-08-25 | CL10 | Completed
J1109 | 2026-08-28 | CL10 | Completed
J1109 | 2026-09-01 | CL10 | Completed
J1109 | 2026-09-04 | CL10 | Completed
J1109 | 2026-09-08 | CL10 | Completed
J1109 | 2026-09-11 | CL10 | Completed
J1109 | 2026-09-15 | CL10 | Completed
J1109 | 2026-09-18 | CL10 | Completed
J1109 | 2026-09-22 | CL10 | Completed
J1109 | 2026-09-25 | CL10 | Completed
J1109 | 2026-09-29 | CL10 | Completed
J1109 | 2026-10-02 | CL10 | Skipped
J1109 | 2026-10-06 | CL10 | Completed
J1109 | 2026-10-09 | CL10 | Completed
J1109 | 2026-10-13 | CL10 | Completed
J1109 | 2026-10-16 | CL10 | Completed
J1109 | 2026-10-20 | CL10 | Completed
J1109 | 2026-10-23 | CL10 | Completed
J1109 | 2026-10-27 | CL10 | Completed
J1109 | 2026-10-30 | CL10 | Completed
J1110 | 2026-08-03 | CL22 | Completed
J1110 | 2026-08-04 | CL22 | Completed
J1110 | 2026-08-05 | CL22 | Completed
J1110 | 2026-08-06 | CL22 | Completed
J1110 | 2026-08-07 | CL22 | Completed
J1110 | 2026-08-10 | CL22 | Completed
J1110 | 2026-08-11 | CL22 | Completed
J1110 | 2026-08-12 | CL22 | Completed
J1110 | 2026-08-13 | CL22 | Completed
J1110 | 2026-08-14 | CL22 | Completed
J1110 | 2026-08-17 | CL22 | Completed
J1110 | 2026-08-18 | CL22 | Completed
J1110 | 2026-08-19 | CL22 | Completed
J1110 | 2026-08-20 | CL22 | Completed
J1110 | 2026-08-21 | CL22 | Completed
J1110 | 2026-08-24 | CL22 | Completed
J1110 | 2026-08-25 | CL22 | Completed
J1110 | 2026-08-26 | CL22 | Completed
J1110 | 2026-08-27 | CL22 | Completed
J1110 | 2026-08-28 | CL22 | Completed
J1110 | 2026-08-31 | CL22 | Completed
J1110 | 2026-09-01 | CL22 | Completed
J1110 | 2026-09-02 | CL22 | Completed
J1110 | 2026-09-03 | CL22 | Completed
J1110 | 2026-09-04 | CL22 | Completed
J1110 | 2026-09-07 | CL22 | Completed
J1110 | 2026-09-08 | CL22 | Completed
J1110 | 2026-09-09 | CL22 | Completed
J1110 | 2026-09-10 | CL22 | Completed
J1110 | 2026-09-11 | CL22 | Completed
J1110 | 2026-09-14 | CL22 | Completed
J1110 | 2026-09-15 | CL22 | Completed
J1110 | 2026-09-16 | CL22 | Completed
J1110 | 2026-09-17 | CL22 | Completed
J1110 | 2026-09-18 | CL22 | Completed
J1110 | 2026-09-21 | CL22 | Completed
J1110 | 2026-09-22 | CL22 | Completed
J1110 | 2026-09-23 | CL22 | Completed
J1110 | 2026-09-24 | CL22 | Completed
J1110 | 2026-09-25 | CL22 | Completed
J1110 | 2026-09-28 | CL22 | Completed
J1110 | 2026-09-29 | CL22 | Completed
J1110 | 2026-09-30 | CL22 | Completed
J1110 | 2026-10-01 | CL22 | Completed
J1110 | 2026-10-02 | CL22 | Completed
J1110 | 2026-10-05 | CL22 | Completed
J1110 | 2026-10-06 | CL22 | Completed
J1110 | 2026-10-07 | CL22 | Completed
J1110 | 2026-10-08 | CL22 | Completed
J1110 | 2026-10-09 | CL22 | Completed
J1110 | 2026-10-12 | CL22 | Completed
J1110 | 2026-10-13 | CL22 | Completed
J1110 | 2026-10-14 | CL22 | Completed
J1110 | 2026-10-15 | CL22 | Completed
J1110 | 2026-10-16 | CL22 | Completed
J1110 | 2026-10-19 | CL22 | Completed
J1110 | 2026-10-20 | CL22 | Completed
J1110 | 2026-10-21 | CL22 | Completed
J1110 | 2026-10-22 | CL22 | Completed
J1110 | 2026-10-23 | CL22 | Completed
J1110 | 2026-10-26 | CL22 | Completed
J1110 | 2026-10-27 | CL22 | Completed
J1110 | 2026-10-28 | CL22 | Completed
J1110 | 2026-10-29 | CL22 | Completed
J1110 | 2026-10-30 | CL22 | Completed
J1111 | 2026-08-27 | CL58 | Completed
J1111 | 2026-09-24 | CL58 | Completed
J1111 | 2026-10-22 | CL58 | Completed
J1112 | 2026-08-04 | CL09 | Skipped
J1112 | 2026-08-11 | CL09 | Completed
J1112 | 2026-08-18 | CL09 | Completed
J1112 | 2026-08-25 | CL09 | Completed
J1112 | 2026-09-01 | CL09 | Completed
J1112 | 2026-09-08 | CL09 | Skipped
J1112 | 2026-09-15 | CL09 | Completed
J1112 | 2026-09-22 | CL09 | Completed
J1112 | 2026-09-29 | CL09 | Completed
J1112 | 2026-10-06 | CL09 | Completed
J1112 | 2026-10-13 | CL09 | Completed
J1112 | 2026-10-20 | CL09 | Completed
J1112 | 2026-10-27 | CL09 | Completed
J1113 | 2026-08-03 | CL29 | Completed
J1113 | 2026-08-05 | CL29 | Completed
J1113 | 2026-08-10 | CL29 | Completed
J1113 | 2026-08-12 | CL29 | Completed
J1113 | 2026-08-17 | CL29 | Completed
J1113 | 2026-08-19 | CL29 | Completed
J1113 | 2026-08-24 | CL29 | Completed
J1113 | 2026-08-26 | CL29 | Completed
J1113 | 2026-08-31 | CL29 | Completed
J1113 | 2026-09-02 | CL29 | Completed
J1113 | 2026-09-07 | CL29 | Completed
J1113 | 2026-09-09 | CL29 | Skipped
J1113 | 2026-09-14 | CL29 | Completed
J1113 | 2026-09-16 | CL29 | Completed
J1113 | 2026-09-21 | CL29 | Completed
J1113 | 2026-09-23 | CL29 | Completed
J1113 | 2026-09-28 | CL29 | Completed
J1113 | 2026-09-30 | CL29 | Completed
J1113 | 2026-10-05 | CL29 | Completed
J1113 | 2026-10-07 | CL29 | Completed
J1113 | 2026-10-12 | CL29 | Completed
J1113 | 2026-10-14 | CL29 | Completed
J1113 | 2026-10-19 | CL29 | Completed
J1113 | 2026-10-21 | CL29 | Completed
J1113 | 2026-10-26 | CL29 | Completed
J1113 | 2026-10-28 | CL29 | Completed
J1114 | 2026-08-06 | CL56 | Completed
J1114 | 2026-09-03 | CL56 | Completed
J1114 | 2026-10-01 | CL56 | Completed
J1115 | 2026-08-05 | CL15 | Completed
J1115 | 2026-08-12 | CL15 | Completed
J1115 | 2026-08-19 | CL15 | Completed
J1115 | 2026-08-26 | CL15 | Completed
J1115 | 2026-09-02 | CL15 | Completed
J1115 | 2026-09-09 | CL15 | Completed
J1115 | 2026-09-16 | CL15 | Completed
J1115 | 2026-09-23 | CL15 | Completed
J1115 | 2026-09-30 | CL15 | Completed
J1115 | 2026-10-07 | CL15 | Completed
J1115 | 2026-10-14 | CL15 | Completed
J1115 | 2026-10-21 | CL15 | Completed
J1115 | 2026-10-28 | CL15 | Completed
J1116 | 2026-08-05 | CL11 | Completed
J1116 | 2026-08-12 | CL11 | Skipped
J1116 | 2026-08-19 | CL11 | Completed
J1116 | 2026-08-26 | CL11 | Completed
J1116 | 2026-09-02 | CL11 | Completed
J1116 | 2026-09-09 | CL11 | Completed
J1116 | 2026-09-16 | CL11 | Completed
J1116 | 2026-09-23 | CL11 | Completed
J1116 | 2026-09-30 | CL11 | Completed
J1116 | 2026-10-07 | CL11 | Completed
J1116 | 2026-10-14 | CL11 | Completed
J1116 | 2026-10-21 | CL11 | Completed
J1116 | 2026-10-28 | CL11 | Completed
J1117 | 2026-08-06 | CL40 | Completed
J1117 | 2026-08-07 | CL40 | Completed
J1117 | 2026-08-13 | CL40 | Completed
J1117 | 2026-08-14 | CL40 | Completed
J1117 | 2026-08-20 | CL40 | Completed
J1117 | 2026-08-21 | CL40 | Completed
J1117 | 2026-08-27 | CL40 | Completed
J1117 | 2026-08-28 | CL40 | Completed
J1117 | 2026-09-03 | CL40 | Completed
J1117 | 2026-09-04 | CL40 | Completed
J1117 | 2026-09-10 | CL40 | Skipped
J1117 | 2026-09-11 | CL40 | Completed
J1117 | 2026-09-17 | CL40 | Completed
J1117 | 2026-09-18 | CL40 | Completed
J1117 | 2026-09-24 | CL40 | Completed
J1117 | 2026-09-25 | CL40 | Completed
J1117 | 2026-10-01 | CL40 | Completed
J1117 | 2026-10-02 | CL40 | Completed
J1117 | 2026-10-08 | CL40 | Completed
J1117 | 2026-10-09 | CL40 | Completed
J1117 | 2026-10-15 | CL40 | Completed
J1117 | 2026-10-16 | CL40 | Completed
J1117 | 2026-10-22 | CL40 | Completed
J1117 | 2026-10-23 | CL40 | Completed
J1117 | 2026-10-29 | CL40 | Completed
J1117 | 2026-10-30 | CL40 | Completed
J1118 | 2026-08-07 | CL19 | Completed
J1118 | 2026-08-14 | CL19 | Completed
J1118 | 2026-08-21 | CL19 | Completed
J1118 | 2026-08-28 | CL19 | Completed
J1118 | 2026-09-04 | CL19 | Completed
J1118 | 2026-09-11 | CL19 | Completed
J1118 | 2026-09-18 | CL19 | Completed
J1118 | 2026-09-25 | CL19 | Completed
J1118 | 2026-10-02 | CL19 | Completed
J1118 | 2026-10-09 | CL19 | Skipped
J1118 | 2026-10-16 | CL19 | Completed
J1118 | 2026-10-23 | CL19 | Completed
J1118 | 2026-10-30 | CL19 | Completed
J1119 | 2026-08-04 | CL59 | Completed
J1119 | 2026-09-01 | CL59 | Completed
J1119 | 2026-09-29 | CL59 | Completed
J1119 | 2026-10-27 | CL59 | Completed
J1120 | 2026-08-03 | CL47 | Completed
J1120 | 2026-08-10 | CL47 | Completed
J1120 | 2026-08-17 | CL47 | Completed
J1120 | 2026-08-24 | CL47 | Completed
J1120 | 2026-08-31 | CL47 | Completed
J1120 | 2026-09-07 | CL47 | Completed
J1120 | 2026-09-14 | CL47 | Completed
J1120 | 2026-09-21 | CL47 | Completed
J1120 | 2026-09-28 | CL47 | Completed
J1120 | 2026-10-05 | CL47 | Completed
J1120 | 2026-10-12 | CL47 | Completed
J1120 | 2026-10-19 | CL47 | Completed
J1120 | 2026-10-26 | CL47 | Completed
J1121 | 2026-08-05 | CL51 | Completed
J1121 | 2026-08-12 | CL51 | Completed
J1121 | 2026-08-19 | CL51 | Completed
J1121 | 2026-08-26 | CL51 | Completed
J1121 | 2026-09-02 | CL51 | Completed
J1121 | 2026-09-09 | CL51 | Completed
J1121 | 2026-09-16 | CL51 | Completed
J1121 | 2026-09-23 | CL51 | Completed
J1121 | 2026-09-30 | CL51 | Completed
J1121 | 2026-10-07 | CL51 | Completed
J1121 | 2026-10-14 | CL51 | Completed
J1121 | 2026-10-21 | CL51 | Completed
J1121 | 2026-10-28 | CL51 | Completed
J1122 | 2026-08-03 | CL12 | Completed
J1122 | 2026-08-05 | CL12 | Completed
J1122 | 2026-08-07 | CL12 | Completed
J1122 | 2026-08-10 | CL12 | Completed
J1122 | 2026-08-12 | CL12 | Completed
J1122 | 2026-08-14 | CL12 | Completed
J1122 | 2026-08-17 | CL12 | Completed
J1122 | 2026-08-19 | CL12 | Completed
J1122 | 2026-08-21 | CL12 | Completed
J1122 | 2026-08-24 | CL12 | Completed
J1122 | 2026-08-26 | CL12 | Completed
J1122 | 2026-08-28 | CL12 | Completed
J1122 | 2026-08-31 | CL12 | Completed
J1122 | 2026-09-02 | CL12 | Completed
J1122 | 2026-09-04 | CL12 | Completed
J1122 | 2026-09-07 | CL12 | Completed
J1122 | 2026-09-09 | CL12 | Completed
J1122 | 2026-09-11 | CL12 | Completed
J1122 | 2026-09-14 | CL12 | Completed
J1122 | 2026-09-16 | CL12 | Completed
J1122 | 2026-09-18 | CL12 | Completed
J1122 | 2026-09-21 | CL12 | Completed
J1122 | 2026-09-23 | CL12 | Completed
J1122 | 2026-09-25 | CL12 | Completed
J1122 | 2026-09-28 | CL12 | Completed
J1122 | 2026-09-30 | CL12 | Completed
J1122 | 2026-10-02 | CL12 | Completed
J1122 | 2026-10-05 | CL12 | Completed
J1122 | 2026-10-07 | CL12 | Completed
J1122 | 2026-10-09 | CL12 | Completed
J1122 | 2026-10-12 | CL12 | Completed
J1122 | 2026-10-14 | CL12 | Completed
J1122 | 2026-10-16 | CL12 | Completed
J1122 | 2026-10-19 | CL12 | Completed
J1122 | 2026-10-21 | CL12 | Completed
J1122 | 2026-10-23 | CL12 | Completed
J1122 | 2026-10-26 | CL12 | Completed
J1122 | 2026-10-28 | CL12 | Completed
J1122 | 2026-10-30 | CL12 | Completed
J1123 | 2026-08-25 | CL59 | Completed
J1123 | 2026-09-22 | CL59 | Skipped
J1123 | 2026-10-20 | CL59 | Completed
J1124 | 2026-08-06 | CL26 | Completed
J1124 | 2026-08-13 | CL26 | Completed
J1124 | 2026-08-20 | CL26 | Completed
J1124 | 2026-08-27 | CL26 | Completed
J1124 | 2026-09-03 | CL26 | Completed
J1124 | 2026-09-10 | CL26 | Completed
J1124 | 2026-09-17 | CL26 | Completed
J1124 | 2026-09-24 | CL26 | Completed
J1124 | 2026-10-01 | CL26 | Completed
J1124 | 2026-10-08 | CL26 | Completed
J1124 | 2026-10-15 | CL26 | Completed
J1124 | 2026-10-22 | CL26 | Completed
J1124 | 2026-10-29 | CL26 | Completed
J1125 | 2026-08-04 | CL21 | Completed
J1125 | 2026-08-07 | CL21 | Completed
J1125 | 2026-08-11 | CL21 | Completed
J1125 | 2026-08-14 | CL21 | Completed
J1125 | 2026-08-18 | CL21 | Completed
J1125 | 2026-08-21 | CL21 | Completed
J1125 | 2026-08-25 | CL21 | Completed
J1125 | 2026-08-28 | CL21 | Completed
J1125 | 2026-09-01 | CL21 | Completed
J1125 | 2026-09-04 | CL21 | Completed
J1125 | 2026-09-08 | CL21 | Completed
J1125 | 2026-09-11 | CL21 | Completed
J1125 | 2026-09-15 | CL21 | Completed
J1125 | 2026-09-18 | CL21 | Completed
J1125 | 2026-09-22 | CL21 | Completed
J1125 | 2026-09-25 | CL21 | Completed
J1125 | 2026-09-29 | CL21 | Completed
J1125 | 2026-10-02 | CL21 | Completed
J1125 | 2026-10-06 | CL21 | Completed
J1125 | 2026-10-09 | CL21 | Completed
J1125 | 2026-10-13 | CL21 | Completed
J1125 | 2026-10-16 | CL21 | Completed
J1125 | 2026-10-20 | CL21 | Completed
J1125 | 2026-10-23 | CL21 | Completed
J1125 | 2026-10-27 | CL21 | Completed
J1125 | 2026-10-30 | CL21 | Completed
J1126 | 2026-08-03 | CL55 | Completed
J1126 | 2026-08-31 | CL55 | Completed
J1126 | 2026-09-28 | CL55 | Completed
J1126 | 2026-10-26 | CL55 | Completed
J1127 | 2026-08-03 | CL36 | Completed
J1127 | 2026-08-07 | CL36 | Completed
J1127 | 2026-08-10 | CL36 | Completed
J1127 | 2026-08-14 | CL36 | Completed
J1127 | 2026-08-17 | CL36 | Completed
J1127 | 2026-08-21 | CL36 | Completed
J1127 | 2026-08-24 | CL36 | Completed
J1127 | 2026-08-28 | CL36 | Completed
J1127 | 2026-08-31 | CL36 | Completed
J1127 | 2026-09-04 | CL36 | Completed
J1127 | 2026-09-07 | CL36 | Completed
J1127 | 2026-09-11 | CL36 | Completed
J1127 | 2026-09-14 | CL36 | Completed
J1127 | 2026-09-18 | CL36 | Completed
J1127 | 2026-09-21 | CL36 | Completed
J1127 | 2026-09-25 | CL36 | Completed
J1127 | 2026-09-28 | CL36 | Completed
J1127 | 2026-10-02 | CL36 | Completed
J1127 | 2026-10-05 | CL36 | Completed
J1127 | 2026-10-09 | CL36 | Completed
J1127 | 2026-10-12 | CL36 | Completed
J1127 | 2026-10-16 | CL36 | Completed
J1127 | 2026-10-19 | CL36 | Completed
J1127 | 2026-10-23 | CL36 | Completed
J1127 | 2026-10-26 | CL36 | Completed
J1127 | 2026-10-30 | CL36 | Completed
J1128 | 2026-08-03 | CL14 | Completed
J1128 | 2026-08-04 | CL14 | Completed
J1128 | 2026-08-05 | CL14 | Completed
J1128 | 2026-08-06 | CL14 | Completed
J1128 | 2026-08-07 | CL14 | Completed
J1128 | 2026-08-10 | CL14 | Completed
J1128 | 2026-08-11 | CL14 | Completed
J1128 | 2026-08-12 | CL14 | Completed
J1128 | 2026-08-13 | CL14 | Completed
J1128 | 2026-08-14 | CL14 | Completed
J1128 | 2026-08-17 | CL14 | Completed
J1128 | 2026-08-18 | CL14 | Completed
J1128 | 2026-08-19 | CL14 | Completed
J1128 | 2026-08-20 | CL14 | Completed
J1128 | 2026-08-21 | CL14 | Completed
J1128 | 2026-08-24 | CL14 | Completed
J1128 | 2026-08-25 | CL14 | Completed
J1128 | 2026-08-26 | CL14 | Completed
J1128 | 2026-08-27 | CL14 | Completed
J1128 | 2026-08-28 | CL14 | Completed
J1128 | 2026-08-31 | CL14 | Completed
J1128 | 2026-09-01 | CL14 | Completed
J1128 | 2026-09-02 | CL14 | Completed
J1128 | 2026-09-03 | CL14 | Completed
J1128 | 2026-09-04 | CL14 | Completed
J1128 | 2026-09-07 | CL14 | Completed
J1128 | 2026-09-08 | CL14 | Completed
J1128 | 2026-09-09 | CL14 | Completed
J1128 | 2026-09-10 | CL14 | Completed
J1128 | 2026-09-11 | CL14 | Completed
J1128 | 2026-09-14 | CL14 | Completed
J1128 | 2026-09-15 | CL14 | Completed
J1128 | 2026-09-16 | CL14 | Completed
J1128 | 2026-09-17 | CL14 | Completed
J1128 | 2026-09-18 | CL14 | Completed
J1128 | 2026-09-21 | CL14 | Completed
J1128 | 2026-09-22 | CL14 | Completed
J1128 | 2026-09-23 | CL14 | Completed
J1128 | 2026-09-24 | CL14 | Completed
J1128 | 2026-09-25 | CL14 | Completed
J1128 | 2026-09-28 | CL14 | Completed
J1128 | 2026-09-29 | CL14 | Completed
J1128 | 2026-09-30 | CL14 | Completed
J1128 | 2026-10-01 | CL14 | Completed
J1128 | 2026-10-02 | CL14 | Completed
J1128 | 2026-10-05 | CL14 | Completed
J1128 | 2026-10-06 | CL14 | Completed
J1128 | 2026-10-07 | CL14 | Completed
J1128 | 2026-10-08 | CL14 | Completed
J1128 | 2026-10-09 | CL14 | Completed
J1128 | 2026-10-12 | CL14 | Completed
J1128 | 2026-10-13 | CL14 | Completed
J1128 | 2026-10-14 | CL14 | Completed
J1128 | 2026-10-15 | CL14 | Completed
J1128 | 2026-10-16 | CL14 | Completed
J1128 | 2026-10-19 | CL14 | Completed
J1128 | 2026-10-20 | CL14 | Completed
J1128 | 2026-10-21 | CL14 | Completed
J1128 | 2026-10-22 | CL14 | Completed
J1128 | 2026-10-23 | CL14 | Completed
J1128 | 2026-10-26 | CL14 | Completed
J1128 | 2026-10-27 | CL14 | Completed
J1128 | 2026-10-28 | CL14 | Completed
J1128 | 2026-10-29 | CL14 | Completed
J1128 | 2026-10-30 | CL14 | Completed
J1129 | 2026-08-04 | CL34 | Completed
J1129 | 2026-08-11 | CL34 | Completed
J1129 | 2026-08-18 | CL34 | Completed
J1129 | 2026-08-25 | CL34 | Completed
J1129 | 2026-09-01 | CL34 | Skipped
J1129 | 2026-09-08 | CL34 | Completed
J1129 | 2026-09-15 | CL34 | Completed
J1129 | 2026-09-22 | CL34 | Completed
J1129 | 2026-09-29 | CL34 | Completed
J1129 | 2026-10-06 | CL34 | Completed
J1129 | 2026-10-13 | CL34 | Completed
J1129 | 2026-10-20 | CL34 | Completed
J1129 | 2026-10-27 | CL34 | Completed
J1130 | 2026-08-03 | CL56 | Skipped
J1130 | 2026-08-31 | CL56 | Completed
J1130 | 2026-09-28 | CL56 | Completed
J1130 | 2026-10-26 | CL56 | Completed
J1131 | 2026-08-04 | CL10 | Completed
J1131 | 2026-08-05 | CL10 | Completed
J1131 | 2026-08-11 | CL10 | Completed
J1131 | 2026-08-12 | CL10 | Completed
J1131 | 2026-08-18 | CL10 | Completed
J1131 | 2026-08-19 | CL10 | Completed
J1131 | 2026-08-25 | CL10 | Completed
J1131 | 2026-08-26 | CL10 | Completed
J1131 | 2026-09-01 | CL10 | Completed
J1131 | 2026-09-02 | CL10 | Completed
J1131 | 2026-09-08 | CL10 | Completed
J1131 | 2026-09-09 | CL10 | Completed
J1131 | 2026-09-15 | CL10 | Completed
J1131 | 2026-09-16 | CL10 | Completed
J1131 | 2026-09-22 | CL10 | Completed
J1131 | 2026-09-23 | CL10 | Completed
J1131 | 2026-09-29 | CL10 | Completed
J1131 | 2026-09-30 | CL10 | Completed
J1131 | 2026-10-06 | CL10 | Completed
J1131 | 2026-10-07 | CL10 | Completed
J1131 | 2026-10-13 | CL10 | Completed
J1131 | 2026-10-14 | CL10 | Completed
J1131 | 2026-10-20 | CL10 | Completed
J1131 | 2026-10-21 | CL10 | Completed
J1131 | 2026-10-27 | CL10 | Completed
J1131 | 2026-10-28 | CL10 | Completed
J1132 | 2026-08-03 | CL18 | Completed
J1132 | 2026-08-07 | CL18 | Completed
J1132 | 2026-08-10 | CL18 | Completed
J1132 | 2026-08-14 | CL18 | Completed
J1132 | 2026-08-17 | CL18 | Completed
J1132 | 2026-08-21 | CL18 | Completed
J1132 | 2026-08-24 | CL18 | Completed
J1132 | 2026-08-28 | CL18 | Completed
J1132 | 2026-08-31 | CL18 | Completed
J1132 | 2026-09-04 | CL18 | Completed
J1132 | 2026-09-07 | CL18 | Skipped
J1132 | 2026-09-11 | CL18 | Completed
J1132 | 2026-09-14 | CL18 | Completed
J1132 | 2026-09-18 | CL18 | Completed
J1132 | 2026-09-21 | CL18 | Completed
J1132 | 2026-09-25 | CL18 | Completed
J1132 | 2026-09-28 | CL18 | Completed
J1132 | 2026-10-02 | CL18 | Completed
J1132 | 2026-10-05 | CL18 | Completed
J1132 | 2026-10-09 | CL18 | Completed
J1132 | 2026-10-12 | CL18 | Completed
J1132 | 2026-10-16 | CL18 | Completed
J1132 | 2026-10-19 | CL18 | Completed
J1132 | 2026-10-23 | CL18 | Completed
J1132 | 2026-10-26 | CL18 | Completed
J1132 | 2026-10-30 | CL18 | Completed
J1133 | 2026-08-28 | CL55 | Completed
J1133 | 2026-09-25 | CL55 | Completed
J1133 | 2026-10-23 | CL55 | Completed
J1134 | 2026-08-06 | CL44 | Completed
J1134 | 2026-08-13 | CL44 | Completed
J1134 | 2026-08-20 | CL44 | Completed
J1134 | 2026-08-27 | CL44 | Completed
J1134 | 2026-09-03 | CL44 | Completed
J1134 | 2026-09-10 | CL44 | Completed
J1134 | 2026-09-17 | CL44 | Completed
J1134 | 2026-09-24 | CL44 | Completed
J1134 | 2026-10-01 | CL44 | Completed
J1134 | 2026-10-08 | CL44 | Completed
J1134 | 2026-10-15 | CL44 | Completed
J1134 | 2026-10-22 | CL44 | Completed
J1134 | 2026-10-29 | CL44 | Completed
J1135 | 2026-08-03 | CL09 | Completed
J1135 | 2026-08-04 | CL09 | Completed
J1135 | 2026-08-10 | CL09 | Completed
J1135 | 2026-08-11 | CL09 | Completed
J1135 | 2026-08-17 | CL09 | Completed
J1135 | 2026-08-18 | CL09 | Completed
J1135 | 2026-08-24 | CL09 | Completed
J1135 | 2026-08-25 | CL09 | Completed
J1135 | 2026-08-31 | CL09 | Completed
J1135 | 2026-09-01 | CL09 | Completed
J1135 | 2026-09-07 | CL09 | Completed
J1135 | 2026-09-08 | CL09 | Completed
J1135 | 2026-09-14 | CL09 | Completed
J1135 | 2026-09-15 | CL09 | Completed
J1135 | 2026-09-21 | CL09 | Completed
J1135 | 2026-09-22 | CL09 | Completed
J1135 | 2026-09-28 | CL09 | Completed
J1135 | 2026-09-29 | CL09 | Completed
J1135 | 2026-10-05 | CL09 | Completed
J1135 | 2026-10-06 | CL09 | Completed
J1135 | 2026-10-12 | CL09 | Completed
J1135 | 2026-10-13 | CL09 | Completed
J1135 | 2026-10-19 | CL09 | Completed
J1135 | 2026-10-20 | CL09 | Completed
J1135 | 2026-10-26 | CL09 | Completed
J1135 | 2026-10-27 | CL09 | Completed
J1136 | 2026-08-17 | CL56 | Skipped
J1136 | 2026-09-14 | CL56 | Completed
J1136 | 2026-10-12 | CL56 | Completed
J1137 | 2026-08-04 | CL20 | Completed
J1137 | 2026-08-11 | CL20 | Completed
J1137 | 2026-08-18 | CL20 | Completed
J1137 | 2026-08-25 | CL20 | Completed
J1137 | 2026-09-01 | CL20 | Completed
J1137 | 2026-09-08 | CL20 | Completed
J1137 | 2026-09-15 | CL20 | Completed
J1137 | 2026-09-22 | CL20 | Completed
J1137 | 2026-09-29 | CL20 | Completed
J1137 | 2026-10-06 | CL20 | Completed
J1137 | 2026-10-13 | CL20 | Completed
J1137 | 2026-10-20 | CL20 | Completed
J1137 | 2026-10-27 | CL20 | Completed
J1138 | 2026-08-03 | CL30 | Completed
J1138 | 2026-08-10 | CL30 | Completed
J1138 | 2026-08-17 | CL30 | Completed
J1138 | 2026-08-24 | CL30 | Completed
J1138 | 2026-08-31 | CL30 | Completed
J1138 | 2026-09-07 | CL30 | Completed
J1138 | 2026-09-14 | CL30 | Completed
J1138 | 2026-09-21 | CL30 | Completed
J1138 | 2026-09-28 | CL30 | Completed
J1138 | 2026-10-05 | CL30 | Completed
J1138 | 2026-10-12 | CL30 | Completed
J1138 | 2026-10-19 | CL30 | Completed
J1138 | 2026-10-26 | CL30 | Completed
J1139 | 2026-08-04 | CL51 | Completed
J1139 | 2026-08-06 | CL51 | Completed
J1139 | 2026-08-11 | CL51 | Completed
J1139 | 2026-08-13 | CL51 | Completed
J1139 | 2026-08-18 | CL51 | Completed
J1139 | 2026-08-20 | CL51 | Completed
J1139 | 2026-08-25 | CL51 | Completed
J1139 | 2026-08-27 | CL51 | Completed
J1139 | 2026-09-01 | CL51 | Skipped
J1139 | 2026-09-03 | CL51 | Completed
J1139 | 2026-09-08 | CL51 | Completed
J1139 | 2026-09-10 | CL51 | Completed
J1139 | 2026-09-15 | CL51 | Completed
J1139 | 2026-09-17 | CL51 | Completed
J1139 | 2026-09-22 | CL51 | Completed
J1139 | 2026-09-24 | CL51 | Completed
J1139 | 2026-09-29 | CL51 | Completed
J1139 | 2026-10-01 | CL51 | Completed
J1139 | 2026-10-06 | CL51 | Completed
J1139 | 2026-10-08 | CL51 | Completed
J1139 | 2026-10-13 | CL51 | Completed
J1139 | 2026-10-15 | CL51 | Completed
J1139 | 2026-10-20 | CL51 | Completed
J1139 | 2026-10-22 | CL51 | Completed
J1139 | 2026-10-27 | CL51 | Completed
J1139 | 2026-10-29 | CL51 | Completed
J1140 | 2026-08-04 | CL06 | Completed
J1140 | 2026-08-05 | CL06 | Completed
J1140 | 2026-08-11 | CL06 | Completed
J1140 | 2026-08-12 | CL06 | Completed
J1140 | 2026-08-18 | CL06 | Completed
J1140 | 2026-08-19 | CL06 | Completed
J1140 | 2026-08-25 | CL06 | Completed
J1140 | 2026-08-26 | CL06 | Completed
J1140 | 2026-09-01 | CL06 | Completed
J1140 | 2026-09-02 | CL06 | Completed
J1140 | 2026-09-08 | CL06 | Completed
J1140 | 2026-09-09 | CL06 | Completed
J1140 | 2026-09-15 | CL06 | Completed
J1140 | 2026-09-16 | CL06 | Completed
J1140 | 2026-09-22 | CL06 | Completed
J1140 | 2026-09-23 | CL06 | Completed
J1140 | 2026-09-29 | CL06 | Completed
J1140 | 2026-09-30 | CL06 | Completed
J1140 | 2026-10-06 | CL06 | Completed
J1140 | 2026-10-07 | CL06 | Completed
J1140 | 2026-10-13 | CL06 | Completed
J1140 | 2026-10-14 | CL06 | Completed
J1140 | 2026-10-20 | CL06 | Completed
J1140 | 2026-10-21 | CL06 | Completed
J1140 | 2026-10-27 | CL06 | Completed
J1140 | 2026-10-28 | CL06 | Completed
J1141 | 2026-08-06 | CL50 | Completed
J1141 | 2026-08-13 | CL50 | Completed
J1141 | 2026-08-20 | CL50 | Completed
J1141 | 2026-08-27 | CL50 | Completed
J1141 | 2026-09-03 | CL50 | Completed
J1141 | 2026-09-10 | CL50 | Completed
J1141 | 2026-09-17 | CL50 | Completed
J1141 | 2026-09-24 | CL50 | Completed
J1141 | 2026-10-01 | CL50 | Completed
J1141 | 2026-10-08 | CL50 | Completed
J1141 | 2026-10-15 | CL50 | Completed
J1141 | 2026-10-22 | CL50 | Completed
J1141 | 2026-10-29 | CL50 | Completed
J1142 | 2026-08-07 | CL53 | Completed
J1142 | 2026-09-04 | CL53 | Skipped
J1142 | 2026-10-02 | CL53 | Completed
J1143 | 2026-08-04 | CL04 | Completed
J1143 | 2026-08-05 | CL04 | Completed
J1143 | 2026-08-11 | CL04 | Completed
J1143 | 2026-08-12 | CL04 | Completed
J1143 | 2026-08-18 | CL04 | Completed
J1143 | 2026-08-19 | CL04 | Completed
J1143 | 2026-08-25 | CL04 | Completed
J1143 | 2026-08-26 | CL04 | Completed
J1143 | 2026-09-01 | CL04 | Completed
J1143 | 2026-09-02 | CL04 | Completed
J1143 | 2026-09-08 | CL04 | Completed
J1143 | 2026-09-09 | CL04 | Completed
J1143 | 2026-09-15 | CL04 | Completed
J1143 | 2026-09-16 | CL04 | Completed
J1143 | 2026-09-22 | CL04 | Completed
J1143 | 2026-09-23 | CL04 | Skipped
J1143 | 2026-09-29 | CL04 | Completed
J1143 | 2026-09-30 | CL04 | Completed
J1143 | 2026-10-06 | CL04 | Completed
J1143 | 2026-10-07 | CL04 | Completed
J1143 | 2026-10-13 | CL04 | Completed
J1143 | 2026-10-14 | CL04 | Completed
J1143 | 2026-10-20 | CL04 | Completed
J1143 | 2026-10-21 | CL04 | Completed
J1143 | 2026-10-27 | CL04 | Completed
J1143 | 2026-10-28 | CL04 | Completed
J1144 | 2026-08-05 | CL26 | Completed
J1144 | 2026-08-12 | CL26 | Completed
J1144 | 2026-08-19 | CL26 | Completed
J1144 | 2026-08-26 | CL26 | Completed
J1144 | 2026-09-02 | CL26 | Completed
J1144 | 2026-09-09 | CL26 | Completed
J1144 | 2026-09-16 | CL26 | Completed
J1144 | 2026-09-23 | CL26 | Completed
J1144 | 2026-09-30 | CL26 | Completed
J1144 | 2026-10-07 | CL26 | Completed
J1144 | 2026-10-14 | CL26 | Skipped
J1144 | 2026-10-21 | CL26 | Completed
J1144 | 2026-10-28 | CL26 | Completed
J1145 | 2026-08-24 | CL56 | Skipped
J1145 | 2026-09-21 | CL56 | Completed
J1145 | 2026-10-19 | CL56 | Completed
J1146 | 2026-08-03 | CL46 | Completed
J1146 | 2026-08-05 | CL46 | Completed
J1146 | 2026-08-10 | CL46 | Completed
J1146 | 2026-08-12 | CL46 | Completed
J1146 | 2026-08-17 | CL46 | Completed
J1146 | 2026-08-19 | CL46 | Completed
J1146 | 2026-08-24 | CL46 | Completed
J1146 | 2026-08-26 | CL46 | Skipped
J1146 | 2026-08-31 | CL46 | Completed
J1146 | 2026-09-02 | CL46 | Completed
J1146 | 2026-09-07 | CL46 | Completed
J1146 | 2026-09-09 | CL46 | Completed
J1146 | 2026-09-14 | CL46 | Completed
J1146 | 2026-09-16 | CL46 | Completed
J1146 | 2026-09-21 | CL46 | Completed
J1146 | 2026-09-23 | CL46 | Completed
J1146 | 2026-09-28 | CL46 | Completed
J1146 | 2026-09-30 | CL46 | Completed
J1146 | 2026-10-05 | CL46 | Completed
J1146 | 2026-10-07 | CL46 | Completed
J1146 | 2026-10-12 | CL46 | Completed
J1146 | 2026-10-14 | CL46 | Completed
J1146 | 2026-10-19 | CL46 | Completed
J1146 | 2026-10-21 | CL46 | Completed
J1146 | 2026-10-26 | CL46 | Completed
J1146 | 2026-10-28 | CL46 | Completed
J1147 | 2026-08-04 | CL28 | Completed
J1147 | 2026-08-06 | CL28 | Completed
J1147 | 2026-08-07 | CL28 | Completed
J1147 | 2026-08-11 | CL28 | Completed
J1147 | 2026-08-13 | CL28 | Completed
J1147 | 2026-08-14 | CL28 | Completed
J1147 | 2026-08-18 | CL28 | Skipped
J1147 | 2026-08-20 | CL28 | Completed
J1147 | 2026-08-21 | CL28 | Completed
J1147 | 2026-08-25 | CL28 | Completed
J1147 | 2026-08-27 | CL28 | Completed
J1147 | 2026-08-28 | CL28 | Completed
J1147 | 2026-09-01 | CL28 | Completed
J1147 | 2026-09-03 | CL28 | Completed
J1147 | 2026-09-04 | CL28 | Completed
J1147 | 2026-09-08 | CL28 | Completed
J1147 | 2026-09-10 | CL28 | Completed
J1147 | 2026-09-11 | CL28 | Completed
J1147 | 2026-09-15 | CL28 | Completed
J1147 | 2026-09-17 | CL28 | Completed
J1147 | 2026-09-18 | CL28 | Completed
J1147 | 2026-09-22 | CL28 | Completed
J1147 | 2026-09-24 | CL28 | Completed
J1147 | 2026-09-25 | CL28 | Completed
J1147 | 2026-09-29 | CL28 | Skipped
J1147 | 2026-10-01 | CL28 | Completed
J1147 | 2026-10-02 | CL28 | Completed
J1147 | 2026-10-06 | CL28 | Completed
J1147 | 2026-10-08 | CL28 | Completed
J1147 | 2026-10-09 | CL28 | Completed
J1147 | 2026-10-13 | CL28 | Completed
J1147 | 2026-10-15 | CL28 | Completed
J1147 | 2026-10-16 | CL28 | Completed
J1147 | 2026-10-20 | CL28 | Completed
J1147 | 2026-10-22 | CL28 | Completed
J1147 | 2026-10-23 | CL28 | Completed
J1147 | 2026-10-27 | CL28 | Completed
J1147 | 2026-10-29 | CL28 | Skipped
J1147 | 2026-10-30 | CL28 | Completed
J1148 | 2026-08-07 | CL24 | Completed
J1148 | 2026-08-14 | CL24 | Completed
J1148 | 2026-08-21 | CL24 | Completed
J1148 | 2026-08-28 | CL24 | Completed
J1148 | 2026-09-04 | CL24 | Completed
J1148 | 2026-09-11 | CL24 | Completed
J1148 | 2026-09-18 | CL24 | Completed
J1148 | 2026-09-25 | CL24 | Completed
J1148 | 2026-10-02 | CL24 | Completed
J1148 | 2026-10-09 | CL24 | Completed
J1148 | 2026-10-16 | CL24 | Completed
J1148 | 2026-10-23 | CL24 | Completed
J1148 | 2026-10-30 | CL24 | Skipped
J1149 | 2026-08-25 | CL53 | Completed
J1149 | 2026-09-22 | CL53 | Completed
J1149 | 2026-10-20 | CL53 | Completed
J1150 | 2026-08-03 | CL44 | Skipped
J1150 | 2026-08-04 | CL44 | Completed
J1150 | 2026-08-06 | CL44 | Completed
J1150 | 2026-08-10 | CL44 | Completed
J1150 | 2026-08-11 | CL44 | Skipped
J1150 | 2026-08-13 | CL44 | Completed
J1150 | 2026-08-17 | CL44 | Completed
J1150 | 2026-08-18 | CL44 | Completed
J1150 | 2026-08-20 | CL44 | Completed
J1150 | 2026-08-24 | CL44 | Completed
J1150 | 2026-08-25 | CL44 | Completed
J1150 | 2026-08-27 | CL44 | Completed
J1150 | 2026-08-31 | CL44 | Completed
J1150 | 2026-09-01 | CL44 | Completed
J1150 | 2026-09-03 | CL44 | Completed
J1150 | 2026-09-07 | CL44 | Skipped
J1150 | 2026-09-08 | CL44 | Completed
J1150 | 2026-09-10 | CL44 | Completed
J1150 | 2026-09-14 | CL44 | Completed
J1150 | 2026-09-15 | CL44 | Completed
J1150 | 2026-09-17 | CL44 | Completed
J1150 | 2026-09-21 | CL44 | Completed
J1150 | 2026-09-22 | CL44 | Completed
J1150 | 2026-09-24 | CL44 | Completed
J1150 | 2026-09-28 | CL44 | Completed
J1150 | 2026-09-29 | CL44 | Completed
J1150 | 2026-10-01 | CL44 | Completed
J1150 | 2026-10-05 | CL44 | Completed
J1150 | 2026-10-06 | CL44 | Completed
J1150 | 2026-10-08 | CL44 | Completed
J1150 | 2026-10-12 | CL44 | Completed
J1150 | 2026-10-13 | CL44 | Completed
J1150 | 2026-10-15 | CL44 | Completed
J1150 | 2026-10-19 | CL44 | Completed
J1150 | 2026-10-20 | CL44 | Completed
J1150 | 2026-10-22 | CL44 | Skipped
J1150 | 2026-10-26 | CL44 | Completed
J1150 | 2026-10-27 | CL44 | Completed
J1150 | 2026-10-29 | CL44 | Completed
J1151 | 2026-08-07 | CL57 | Completed
J1151 | 2026-09-04 | CL57 | Completed
J1151 | 2026-10-02 | CL57 | Completed
J1151 | 2026-10-30 | CL57 | Completed
J1152 | 2026-08-05 | CL12 | Completed
J1152 | 2026-08-06 | CL12 | Completed
J1152 | 2026-08-12 | CL12 | Completed
J1152 | 2026-08-13 | CL12 | Completed
J1152 | 2026-08-19 | CL12 | Completed
J1152 | 2026-08-20 | CL12 | Completed
J1152 | 2026-08-26 | CL12 | Completed
J1152 | 2026-08-27 | CL12 | Completed
J1152 | 2026-09-02 | CL12 | Completed
J1152 | 2026-09-03 | CL12 | Completed
J1152 | 2026-09-09 | CL12 | Completed
J1152 | 2026-09-10 | CL12 | Completed
J1152 | 2026-09-16 | CL12 | Completed
J1152 | 2026-09-17 | CL12 | Completed
J1152 | 2026-09-23 | CL12 | Completed
J1152 | 2026-09-24 | CL12 | Completed
J1152 | 2026-09-30 | CL12 | Completed
J1152 | 2026-10-01 | CL12 | Completed
J1152 | 2026-10-07 | CL12 | Completed
J1152 | 2026-10-08 | CL12 | Completed
J1152 | 2026-10-14 | CL12 | Completed
J1152 | 2026-10-15 | CL12 | Completed
J1152 | 2026-10-21 | CL12 | Completed
J1152 | 2026-10-22 | CL12 | Completed
J1152 | 2026-10-28 | CL12 | Completed
J1152 | 2026-10-29 | CL12 | Completed
J1153 | 2026-08-03 | CL57 | Completed
J1153 | 2026-09-07 | CL57 | Completed
J1153 | 2026-10-05 | CL57 | Completed
J1154 | 2026-08-04 | CL50 | Completed
J1154 | 2026-08-11 | CL50 | Completed
J1154 | 2026-08-18 | CL50 | Completed
J1154 | 2026-08-25 | CL50 | Completed
J1154 | 2026-09-01 | CL50 | Completed
J1154 | 2026-09-08 | CL50 | Completed
J1154 | 2026-09-15 | CL50 | Completed
J1154 | 2026-09-22 | CL50 | Completed
J1154 | 2026-09-29 | CL50 | Completed
J1154 | 2026-10-06 | CL50 | Completed
J1154 | 2026-10-13 | CL50 | Completed
J1154 | 2026-10-20 | CL50 | Completed
J1154 | 2026-10-27 | CL50 | Completed
J1155 | 2026-08-07 | CL14 | Completed
J1155 | 2026-08-14 | CL14 | Completed
J1155 | 2026-08-21 | CL14 | Completed
J1155 | 2026-08-28 | CL14 | Completed
J1155 | 2026-09-04 | CL14 | Completed
J1155 | 2026-09-11 | CL14 | Completed
J1155 | 2026-09-18 | CL14 | Completed
J1155 | 2026-09-25 | CL14 | Completed
J1155 | 2026-10-02 | CL14 | Completed
J1155 | 2026-10-09 | CL14 | Completed
J1155 | 2026-10-16 | CL14 | Completed
J1155 | 2026-10-23 | CL14 | Completed
J1155 | 2026-10-30 | CL14 | Completed
J1156 | 2026-08-03 | CL24 | Completed
J1156 | 2026-08-06 | CL24 | Completed
J1156 | 2026-08-10 | CL24 | Completed
J1156 | 2026-08-13 | CL24 | Completed
J1156 | 2026-08-17 | CL24 | Completed
J1156 | 2026-08-20 | CL24 | Completed
J1156 | 2026-08-24 | CL24 | Completed
J1156 | 2026-08-27 | CL24 | Completed
J1156 | 2026-08-31 | CL24 | Completed
J1156 | 2026-09-03 | CL24 | Completed
J1156 | 2026-09-07 | CL24 | Completed
J1156 | 2026-09-10 | CL24 | Completed
J1156 | 2026-09-14 | CL24 | Completed
J1156 | 2026-09-17 | CL24 | Completed
J1156 | 2026-09-21 | CL24 | Completed
J1156 | 2026-09-24 | CL24 | Completed
J1156 | 2026-09-28 | CL24 | Completed
J1156 | 2026-10-01 | CL24 | Completed
J1156 | 2026-10-05 | CL24 | Completed
J1156 | 2026-10-08 | CL24 | Completed
J1156 | 2026-10-12 | CL24 | Completed
J1156 | 2026-10-15 | CL24 | Completed
J1156 | 2026-10-19 | CL24 | Completed
J1156 | 2026-10-22 | CL24 | Skipped
J1156 | 2026-10-26 | CL24 | Completed
J1156 | 2026-10-29 | CL24 | Completed
J1157 | 2026-08-03 | CL03 | Completed
J1157 | 2026-08-04 | CL03 | Completed
J1157 | 2026-08-06 | CL03 | Completed
J1157 | 2026-08-10 | CL03 | Completed
J1157 | 2026-08-11 | CL03 | Completed
J1157 | 2026-08-13 | CL03 | Completed
J1157 | 2026-08-17 | CL03 | Completed
J1157 | 2026-08-18 | CL03 | Completed
J1157 | 2026-08-20 | CL03 | Completed
J1157 | 2026-08-24 | CL03 | Completed
J1157 | 2026-08-25 | CL03 | Completed
J1157 | 2026-08-27 | CL03 | Completed
J1157 | 2026-08-31 | CL03 | Completed
J1157 | 2026-09-01 | CL03 | Completed
J1157 | 2026-09-03 | CL03 | Completed
J1157 | 2026-09-07 | CL03 | Completed
J1157 | 2026-09-08 | CL03 | Completed
J1157 | 2026-09-10 | CL03 | Completed
J1157 | 2026-09-14 | CL03 | Completed
J1157 | 2026-09-15 | CL03 | Completed
J1157 | 2026-09-17 | CL03 | Completed
J1157 | 2026-09-21 | CL03 | Completed
J1157 | 2026-09-22 | CL03 | Skipped
J1157 | 2026-09-24 | CL03 | Completed
J1157 | 2026-09-28 | CL03 | Completed
J1157 | 2026-09-29 | CL03 | Completed
J1157 | 2026-10-01 | CL03 | Completed
J1157 | 2026-10-05 | CL03 | Completed
J1157 | 2026-10-06 | CL03 | Completed
J1157 | 2026-10-08 | CL03 | Skipped
J1157 | 2026-10-12 | CL03 | Completed
J1157 | 2026-10-13 | CL03 | Completed
J1157 | 2026-10-15 | CL03 | Completed
J1157 | 2026-10-19 | CL03 | Completed
J1157 | 2026-10-20 | CL03 | Completed
J1157 | 2026-10-22 | CL03 | Completed
J1157 | 2026-10-26 | CL03 | Completed
J1157 | 2026-10-27 | CL03 | Completed
J1157 | 2026-10-29 | CL03 | Completed
J1158 | 2026-08-03 | CL14 | Completed
J1158 | 2026-08-04 | CL14 | Completed
J1158 | 2026-08-05 | CL14 | Completed
J1158 | 2026-08-06 | CL14 | Completed
J1158 | 2026-08-07 | CL14 | Completed
J1158 | 2026-08-10 | CL14 | Completed
J1158 | 2026-08-11 | CL14 | Completed
J1158 | 2026-08-12 | CL14 | Completed
J1158 | 2026-08-13 | CL14 | Completed
J1158 | 2026-08-14 | CL14 | Completed
J1158 | 2026-08-17 | CL14 | Completed
J1158 | 2026-08-18 | CL14 | Completed
J1158 | 2026-08-19 | CL14 | Completed
J1158 | 2026-08-20 | CL14 | Completed
J1158 | 2026-08-21 | CL14 | Skipped
J1158 | 2026-08-24 | CL14 | Completed
J1158 | 2026-08-25 | CL14 | Completed
J1158 | 2026-08-26 | CL14 | Completed
J1158 | 2026-08-27 | CL14 | Completed
J1158 | 2026-08-28 | CL14 | Completed
J1158 | 2026-08-31 | CL14 | Completed
J1158 | 2026-09-01 | CL14 | Completed
J1158 | 2026-09-02 | CL14 | Completed
J1158 | 2026-09-03 | CL14 | Completed
J1158 | 2026-09-04 | CL14 | Completed
J1158 | 2026-09-07 | CL14 | Completed
J1158 | 2026-09-08 | CL14 | Completed
J1158 | 2026-09-09 | CL14 | Completed
J1158 | 2026-09-10 | CL14 | Completed
J1158 | 2026-09-11 | CL14 | Completed
J1158 | 2026-09-14 | CL14 | Completed
J1158 | 2026-09-15 | CL14 | Completed
J1158 | 2026-09-16 | CL14 | Completed
J1158 | 2026-09-17 | CL14 | Completed
J1158 | 2026-09-18 | CL14 | Completed
J1158 | 2026-09-21 | CL14 | Completed
J1158 | 2026-09-22 | CL14 | Completed
J1158 | 2026-09-23 | CL14 | Completed
J1158 | 2026-09-24 | CL14 | Completed
J1158 | 2026-09-25 | CL14 | Completed
J1158 | 2026-09-28 | CL14 | Completed
J1158 | 2026-09-29 | CL14 | Completed
J1158 | 2026-09-30 | CL14 | Completed
J1158 | 2026-10-01 | CL14 | Completed
J1158 | 2026-10-02 | CL14 | Completed
J1158 | 2026-10-05 | CL14 | Completed
J1158 | 2026-10-06 | CL14 | Completed
J1158 | 2026-10-07 | CL14 | Completed
J1158 | 2026-10-08 | CL14 | Completed
J1158 | 2026-10-09 | CL14 | Completed
J1158 | 2026-10-12 | CL14 | Completed
J1158 | 2026-10-13 | CL14 | Completed
J1158 | 2026-10-14 | CL14 | Completed
J1158 | 2026-10-15 | CL14 | Completed
J1158 | 2026-10-16 | CL14 | Completed
J1158 | 2026-10-19 | CL14 | Completed
J1158 | 2026-10-20 | CL14 | Completed
J1158 | 2026-10-21 | CL14 | Completed
J1158 | 2026-10-22 | CL14 | Completed
J1158 | 2026-10-23 | CL14 | Completed
J1158 | 2026-10-26 | CL14 | Completed
J1158 | 2026-10-27 | CL14 | Completed
J1158 | 2026-10-28 | CL14 | Completed
J1158 | 2026-10-29 | CL14 | Completed
J1158 | 2026-10-30 | CL14 | Completed
J1159 | 2026-08-05 | CL20 | Completed
J1159 | 2026-08-06 | CL20 | Completed
J1159 | 2026-08-12 | CL20 | Completed
J1159 | 2026-08-13 | CL20 | Completed
J1159 | 2026-08-19 | CL20 | Completed
J1159 | 2026-08-20 | CL20 | Completed
J1159 | 2026-08-26 | CL20 | Completed
J1159 | 2026-08-27 | CL20 | Completed
J1159 | 2026-09-02 | CL20 | Completed
J1159 | 2026-09-03 | CL20 | Completed
J1159 | 2026-09-09 | CL20 | Completed
J1159 | 2026-09-10 | CL20 | Completed
J1159 | 2026-09-16 | CL20 | Completed
J1159 | 2026-09-17 | CL20 | Completed
J1159 | 2026-09-23 | CL20 | Completed
J1159 | 2026-09-24 | CL20 | Completed
J1159 | 2026-09-30 | CL20 | Completed
J1159 | 2026-10-01 | CL20 | Completed
J1159 | 2026-10-07 | CL20 | Completed
J1159 | 2026-10-08 | CL20 | Completed
J1159 | 2026-10-14 | CL20 | Skipped
J1159 | 2026-10-15 | CL20 | Completed
J1159 | 2026-10-21 | CL20 | Completed
J1159 | 2026-10-22 | CL20 | Completed
J1159 | 2026-10-28 | CL20 | Completed
J1159 | 2026-10-29 | CL20 | Completed
J1160 | 2026-08-05 | CL58 | Completed
J1160 | 2026-09-02 | CL58 | Completed
J1160 | 2026-10-07 | CL58 | Completed
J1161 | 2026-08-04 | CL32 | Completed
J1161 | 2026-08-11 | CL32 | Completed
J1161 | 2026-08-18 | CL32 | Completed
J1161 | 2026-08-25 | CL32 | Completed
J1161 | 2026-09-01 | CL32 | Completed
J1161 | 2026-09-08 | CL32 | Completed
J1161 | 2026-09-15 | CL32 | Completed
J1161 | 2026-09-22 | CL32 | Completed
J1161 | 2026-09-29 | CL32 | Completed
J1161 | 2026-10-06 | CL32 | Completed
J1161 | 2026-10-13 | CL32 | Completed
J1161 | 2026-10-20 | CL32 | Completed
J1161 | 2026-10-27 | CL32 | Completed
J1162 | 2026-08-05 | CL44 | Completed
J1162 | 2026-08-12 | CL44 | Completed
J1162 | 2026-08-19 | CL44 | Completed
J1162 | 2026-08-26 | CL44 | Completed
J1162 | 2026-09-02 | CL44 | Completed
J1162 | 2026-09-09 | CL44 | Completed
J1162 | 2026-09-16 | CL44 | Completed
J1162 | 2026-09-23 | CL44 | Completed
J1162 | 2026-09-30 | CL44 | Completed
J1162 | 2026-10-07 | CL44 | Completed
J1162 | 2026-10-14 | CL44 | Completed
J1162 | 2026-10-21 | CL44 | Completed
J1162 | 2026-10-28 | CL44 | Completed
J1163 | 2026-08-03 | CL13 | Completed
J1163 | 2026-08-10 | CL13 | Completed
J1163 | 2026-08-17 | CL13 | Completed
J1163 | 2026-08-24 | CL13 | Completed
J1163 | 2026-08-31 | CL13 | Completed
J1163 | 2026-09-07 | CL13 | Completed
J1163 | 2026-09-14 | CL13 | Completed
J1163 | 2026-09-21 | CL13 | Completed
J1163 | 2026-09-28 | CL13 | Completed
J1163 | 2026-10-05 | CL13 | Completed
J1163 | 2026-10-12 | CL13 | Completed
J1163 | 2026-10-19 | CL13 | Completed
J1163 | 2026-10-26 | CL13 | Completed
J1164 | 2026-08-19 | CL60 | Completed
J1164 | 2026-09-16 | CL60 | Completed
J1164 | 2026-10-14 | CL60 | Completed
J1165 | 2026-08-03 | CL49 | Completed
J1165 | 2026-08-05 | CL49 | Completed
J1165 | 2026-08-10 | CL49 | Completed
J1165 | 2026-08-12 | CL49 | Completed
J1165 | 2026-08-17 | CL49 | Completed
J1165 | 2026-08-19 | CL49 | Completed
J1165 | 2026-08-24 | CL49 | Completed
J1165 | 2026-08-26 | CL49 | Completed
J1165 | 2026-08-31 | CL49 | Completed
J1165 | 2026-09-02 | CL49 | Completed
J1165 | 2026-09-07 | CL49 | Completed
J1165 | 2026-09-09 | CL49 | Completed
J1165 | 2026-09-14 | CL49 | Completed
J1165 | 2026-09-16 | CL49 | Completed
J1165 | 2026-09-21 | CL49 | Completed
J1165 | 2026-09-23 | CL49 | Completed
J1165 | 2026-09-28 | CL49 | Completed
J1165 | 2026-09-30 | CL49 | Completed
J1165 | 2026-10-05 | CL49 | Completed
J1165 | 2026-10-07 | CL49 | Completed
J1165 | 2026-10-12 | CL49 | Completed
J1165 | 2026-10-14 | CL49 | Completed
J1165 | 2026-10-19 | CL49 | Completed
J1165 | 2026-10-21 | CL49 | Completed
J1165 | 2026-10-26 | CL49 | Completed
J1165 | 2026-10-28 | CL49 | Completed
J1166 | 2026-08-03 | CL27 | Completed
J1166 | 2026-08-07 | CL27 | Completed
J1166 | 2026-08-10 | CL27 | Completed
J1166 | 2026-08-14 | CL27 | Completed
J1166 | 2026-08-17 | CL27 | Completed
J1166 | 2026-08-21 | CL27 | Completed
J1166 | 2026-08-24 | CL27 | Completed
J1166 | 2026-08-28 | CL27 | Completed
J1166 | 2026-08-31 | CL27 | Completed
J1166 | 2026-09-04 | CL27 | Completed
J1166 | 2026-09-07 | CL27 | Completed
J1166 | 2026-09-11 | CL27 | Completed
J1166 | 2026-09-14 | CL27 | Completed
J1166 | 2026-09-18 | CL27 | Completed
J1166 | 2026-09-21 | CL27 | Completed
J1166 | 2026-09-25 | CL27 | Completed
J1166 | 2026-09-28 | CL27 | Completed
J1166 | 2026-10-02 | CL27 | Completed
J1166 | 2026-10-05 | CL27 | Completed
J1166 | 2026-10-09 | CL27 | Completed
J1166 | 2026-10-12 | CL27 | Completed
J1166 | 2026-10-16 | CL27 | Completed
J1166 | 2026-10-19 | CL27 | Completed
J1166 | 2026-10-23 | CL27 | Skipped
J1166 | 2026-10-26 | CL27 | Completed
J1166 | 2026-10-30 | CL27 | Completed
J1167 | 2026-08-03 | CL37 | Skipped
J1167 | 2026-08-10 | CL37 | Completed
J1167 | 2026-08-17 | CL37 | Completed
J1167 | 2026-08-24 | CL37 | Completed
J1167 | 2026-08-31 | CL37 | Completed
J1167 | 2026-09-07 | CL37 | Completed
J1167 | 2026-09-14 | CL37 | Completed
J1167 | 2026-09-21 | CL37 | Completed
J1167 | 2026-09-28 | CL37 | Completed
J1167 | 2026-10-05 | CL37 | Completed
J1167 | 2026-10-12 | CL37 | Completed
J1167 | 2026-10-19 | CL37 | Skipped
J1167 | 2026-10-26 | CL37 | Completed
J1168 | 2026-08-11 | CL60 | Completed
J1168 | 2026-09-08 | CL60 | Completed
J1168 | 2026-10-06 | CL60 | Completed
J1169 | 2026-08-04 | CL40 | Completed
J1169 | 2026-08-05 | CL40 | Completed
J1169 | 2026-08-11 | CL40 | Completed
J1169 | 2026-08-12 | CL40 | Completed
J1169 | 2026-08-18 | CL40 | Completed
J1169 | 2026-08-19 | CL40 | Completed
J1169 | 2026-08-25 | CL40 | Completed
J1169 | 2026-08-26 | CL40 | Completed
J1169 | 2026-09-01 | CL40 | Completed
J1169 | 2026-09-02 | CL40 | Completed
J1169 | 2026-09-08 | CL40 | Completed
J1169 | 2026-09-09 | CL40 | Completed
J1169 | 2026-09-15 | CL40 | Completed
J1169 | 2026-09-16 | CL40 | Completed
J1169 | 2026-09-22 | CL40 | Completed
J1169 | 2026-09-23 | CL40 | Completed
J1169 | 2026-09-29 | CL40 | Completed
J1169 | 2026-09-30 | CL40 | Completed
J1169 | 2026-10-06 | CL40 | Completed
J1169 | 2026-10-07 | CL40 | Completed
J1169 | 2026-10-13 | CL40 | Completed
J1169 | 2026-10-14 | CL40 | Completed
J1169 | 2026-10-20 | CL40 | Completed
J1169 | 2026-10-21 | CL40 | Completed
J1169 | 2026-10-27 | CL40 | Completed
J1169 | 2026-10-28 | CL40 | Completed
J1170 | 2026-08-07 | CL39 | Completed
J1170 | 2026-08-14 | CL39 | Completed
J1170 | 2026-08-21 | CL39 | Completed
J1170 | 2026-08-28 | CL39 | Completed
J1170 | 2026-09-04 | CL39 | Completed
J1170 | 2026-09-11 | CL39 | Completed
J1170 | 2026-09-18 | CL39 | Completed
J1170 | 2026-09-25 | CL39 | Completed
J1170 | 2026-10-02 | CL39 | Skipped
J1170 | 2026-10-09 | CL39 | Completed
J1170 | 2026-10-16 | CL39 | Completed
J1170 | 2026-10-23 | CL39 | Completed
J1170 | 2026-10-30 | CL39 | Completed
J1171 | 2026-08-03 | CL12 | Completed
J1171 | 2026-08-04 | CL12 | Completed
J1171 | 2026-08-05 | CL12 | Completed
J1171 | 2026-08-06 | CL12 | Completed
J1171 | 2026-08-07 | CL12 | Completed
J1171 | 2026-08-10 | CL12 | Completed
J1171 | 2026-08-11 | CL12 | Completed
J1171 | 2026-08-12 | CL12 | Completed
J1171 | 2026-08-13 | CL12 | Completed
J1171 | 2026-08-14 | CL12 | Completed
J1171 | 2026-08-17 | CL12 | Completed
J1171 | 2026-08-18 | CL12 | Completed
J1171 | 2026-08-19 | CL12 | Completed
J1171 | 2026-08-20 | CL12 | Completed
J1171 | 2026-08-21 | CL12 | Completed
J1171 | 2026-08-24 | CL12 | Completed
J1171 | 2026-08-25 | CL12 | Completed
J1171 | 2026-08-26 | CL12 | Completed
J1171 | 2026-08-27 | CL12 | Completed
J1171 | 2026-08-28 | CL12 | Completed
J1171 | 2026-08-31 | CL12 | Completed
J1171 | 2026-09-01 | CL12 | Completed
J1171 | 2026-09-02 | CL12 | Completed
J1171 | 2026-09-03 | CL12 | Completed
J1171 | 2026-09-04 | CL12 | Skipped
J1171 | 2026-09-07 | CL12 | Completed
J1171 | 2026-09-08 | CL12 | Completed
J1171 | 2026-09-09 | CL12 | Completed
J1171 | 2026-09-10 | CL12 | Completed
J1171 | 2026-09-11 | CL12 | Completed
J1171 | 2026-09-14 | CL12 | Completed
J1171 | 2026-09-15 | CL12 | Completed
J1171 | 2026-09-16 | CL12 | Completed
J1171 | 2026-09-17 | CL12 | Completed
J1171 | 2026-09-18 | CL12 | Completed
J1171 | 2026-09-21 | CL12 | Completed
J1171 | 2026-09-22 | CL12 | Completed
J1171 | 2026-09-23 | CL12 | Completed
J1171 | 2026-09-24 | CL12 | Completed
J1171 | 2026-09-25 | CL12 | Completed
J1171 | 2026-09-28 | CL12 | Completed
J1171 | 2026-09-29 | CL12 | Skipped
J1171 | 2026-09-30 | CL12 | Completed
J1171 | 2026-10-01 | CL12 | Completed
J1171 | 2026-10-02 | CL12 | Completed
J1171 | 2026-10-05 | CL12 | Completed
J1171 | 2026-10-06 | CL12 | Skipped
J1171 | 2026-10-07 | CL12 | Completed
J1171 | 2026-10-08 | CL12 | Completed
J1171 | 2026-10-09 | CL12 | Completed
J1171 | 2026-10-12 | CL12 | Skipped
J1171 | 2026-10-13 | CL12 | Completed
J1171 | 2026-10-14 | CL12 | Completed
J1171 | 2026-10-15 | CL12 | Completed
J1171 | 2026-10-16 | CL12 | Completed
J1171 | 2026-10-19 | CL12 | Skipped
J1171 | 2026-10-20 | CL12 | Completed
J1171 | 2026-10-21 | CL12 | Completed
J1171 | 2026-10-22 | CL12 | Completed
J1171 | 2026-10-23 | CL12 | Completed
J1171 | 2026-10-26 | CL12 | Completed
J1171 | 2026-10-27 | CL12 | Completed
J1171 | 2026-10-28 | CL12 | Completed
J1171 | 2026-10-29 | CL12 | Completed
J1171 | 2026-10-30 | CL12 | Completed
J1172 | 2026-08-03 | CL14 | Completed
J1172 | 2026-08-04 | CL14 | Completed
J1172 | 2026-08-05 | CL14 | Completed
J1172 | 2026-08-06 | CL14 | Completed
J1172 | 2026-08-07 | CL14 | Completed
J1172 | 2026-08-10 | CL14 | Completed
J1172 | 2026-08-11 | CL14 | Completed
J1172 | 2026-08-12 | CL14 | Completed
J1172 | 2026-08-13 | CL14 | Completed
J1172 | 2026-08-14 | CL14 | Completed
J1172 | 2026-08-17 | CL14 | Completed
J1172 | 2026-08-18 | CL14 | Completed
J1172 | 2026-08-19 | CL14 | Completed
J1172 | 2026-08-20 | CL14 | Completed
J1172 | 2026-08-21 | CL14 | Completed
J1172 | 2026-08-24 | CL14 | Completed
J1172 | 2026-08-25 | CL14 | Completed
J1172 | 2026-08-26 | CL14 | Completed
J1172 | 2026-08-27 | CL14 | Completed
J1172 | 2026-08-28 | CL14 | Completed
J1172 | 2026-08-31 | CL14 | Completed
J1172 | 2026-09-01 | CL14 | Completed
J1172 | 2026-09-02 | CL14 | Completed
J1172 | 2026-09-03 | CL14 | Completed
J1172 | 2026-09-04 | CL14 | Completed
J1172 | 2026-09-07 | CL14 | Completed
J1172 | 2026-09-08 | CL14 | Completed
J1172 | 2026-09-09 | CL14 | Completed
J1172 | 2026-09-10 | CL14 | Completed
J1172 | 2026-09-11 | CL14 | Completed
J1172 | 2026-09-14 | CL14 | Completed
J1172 | 2026-09-15 | CL14 | Completed
J1172 | 2026-09-16 | CL14 | Completed
J1172 | 2026-09-17 | CL14 | Completed
J1172 | 2026-09-18 | CL14 | Completed
J1172 | 2026-09-21 | CL14 | Completed
J1172 | 2026-09-22 | CL14 | Completed
J1172 | 2026-09-23 | CL14 | Completed
J1172 | 2026-09-24 | CL14 | Completed
J1172 | 2026-09-25 | CL14 | Completed
J1172 | 2026-09-28 | CL14 | Completed
J1172 | 2026-09-29 | CL14 | Completed
J1172 | 2026-09-30 | CL14 | Completed
J1172 | 2026-10-01 | CL14 | Completed
J1172 | 2026-10-02 | CL14 | Completed
J1172 | 2026-10-05 | CL14 | Completed
J1172 | 2026-10-06 | CL14 | Completed
J1172 | 2026-10-07 | CL14 | Completed
J1172 | 2026-10-08 | CL14 | Completed
J1172 | 2026-10-09 | CL14 | Completed
J1172 | 2026-10-12 | CL14 | Completed
J1172 | 2026-10-13 | CL14 | Completed
J1172 | 2026-10-14 | CL14 | Completed
J1172 | 2026-10-15 | CL14 | Completed
J1172 | 2026-10-16 | CL14 | Completed
J1172 | 2026-10-19 | CL14 | Completed
J1172 | 2026-10-20 | CL14 | Completed
J1172 | 2026-10-21 | CL14 | Completed
J1172 | 2026-10-22 | CL14 | Completed
J1172 | 2026-10-23 | CL14 | Completed
J1172 | 2026-10-26 | CL14 | Completed
J1172 | 2026-10-27 | CL14 | Completed
J1172 | 2026-10-28 | CL14 | Completed
J1172 | 2026-10-29 | CL14 | Completed
J1172 | 2026-10-30 | CL14 | Completed
J1173 | 2026-08-25 | CL57 | Completed
J1173 | 2026-09-22 | CL57 | Completed
J1173 | 2026-10-20 | CL57 | Completed
J1174 | 2026-08-03 | CL45 | Completed
J1174 | 2026-08-06 | CL45 | Completed
J1174 | 2026-08-10 | CL45 | Completed
J1174 | 2026-08-13 | CL45 | Completed
J1174 | 2026-08-17 | CL45 | Completed
J1174 | 2026-08-20 | CL45 | Completed
J1174 | 2026-08-24 | CL45 | Completed
J1174 | 2026-08-27 | CL45 | Completed
J1174 | 2026-08-31 | CL45 | Completed
J1174 | 2026-09-03 | CL45 | Completed
J1174 | 2026-09-07 | CL45 | Completed
J1174 | 2026-09-10 | CL45 | Completed
J1174 | 2026-09-14 | CL45 | Completed
J1174 | 2026-09-17 | CL45 | Completed
J1174 | 2026-09-21 | CL45 | Completed
J1174 | 2026-09-24 | CL45 | Completed
J1174 | 2026-09-28 | CL45 | Completed
J1174 | 2026-10-01 | CL45 | Completed
J1174 | 2026-10-05 | CL45 | Completed
J1174 | 2026-10-08 | CL45 | Skipped
J1174 | 2026-10-12 | CL45 | Skipped
J1174 | 2026-10-15 | CL45 | Completed
J1174 | 2026-10-19 | CL45 | Completed
J1174 | 2026-10-22 | CL45 | Completed
J1174 | 2026-10-26 | CL45 | Completed
J1174 | 2026-10-29 | CL45 | Completed
J1175 | 2026-08-07 | CL46 | Completed
J1175 | 2026-08-14 | CL46 | Completed
J1175 | 2026-08-21 | CL46 | Completed
J1175 | 2026-08-28 | CL46 | Completed
J1175 | 2026-09-04 | CL46 | Completed
J1175 | 2026-09-11 | CL46 | Completed
J1175 | 2026-09-18 | CL46 | Completed
J1175 | 2026-09-25 | CL46 | Completed
J1175 | 2026-10-02 | CL46 | Completed
J1175 | 2026-10-09 | CL46 | Completed
J1175 | 2026-10-16 | CL46 | Completed
J1175 | 2026-10-23 | CL46 | Completed
J1175 | 2026-10-30 | CL46 | Completed
J1176 | 2026-08-07 | CL16 | Completed
J1176 | 2026-08-14 | CL16 | Completed
J1176 | 2026-08-21 | CL16 | Completed
J1176 | 2026-08-28 | CL16 | Completed
J1176 | 2026-09-04 | CL16 | Completed
J1176 | 2026-09-11 | CL16 | Completed
J1176 | 2026-09-18 | CL16 | Completed
J1176 | 2026-09-25 | CL16 | Completed
J1176 | 2026-10-02 | CL16 | Completed
J1176 | 2026-10-09 | CL16 | Completed
J1176 | 2026-10-16 | CL16 | Completed
J1176 | 2026-10-23 | CL16 | Completed
J1176 | 2026-10-30 | CL16 | Completed
J1177 | 2026-08-04 | CL13 | Completed
J1177 | 2026-08-07 | CL13 | Completed
J1177 | 2026-08-11 | CL13 | Completed
J1177 | 2026-08-14 | CL13 | Completed
J1177 | 2026-08-18 | CL13 | Completed
J1177 | 2026-08-21 | CL13 | Completed
J1177 | 2026-08-25 | CL13 | Completed
J1177 | 2026-08-28 | CL13 | Completed
J1177 | 2026-09-01 | CL13 | Completed
J1177 | 2026-09-04 | CL13 | Completed
J1177 | 2026-09-08 | CL13 | Completed
J1177 | 2026-09-11 | CL13 | Completed
J1177 | 2026-09-15 | CL13 | Completed
J1177 | 2026-09-18 | CL13 | Completed
J1177 | 2026-09-22 | CL13 | Completed
J1177 | 2026-09-25 | CL13 | Completed
J1177 | 2026-09-29 | CL13 | Completed
J1177 | 2026-10-02 | CL13 | Completed
J1177 | 2026-10-06 | CL13 | Completed
J1177 | 2026-10-09 | CL13 | Completed
J1177 | 2026-10-13 | CL13 | Completed
J1177 | 2026-10-16 | CL13 | Completed
J1177 | 2026-10-20 | CL13 | Completed
J1177 | 2026-10-23 | CL13 | Completed
J1177 | 2026-10-27 | CL13 | Completed
J1177 | 2026-10-30 | CL13 | Completed
J1178 | 2026-08-21 | CL60 | Completed
J1178 | 2026-09-18 | CL60 | Completed
J1178 | 2026-10-16 | CL60 | Completed
J1179 | 2026-08-05 | CL38 | Completed
J1179 | 2026-08-12 | CL38 | Completed
J1179 | 2026-08-19 | CL38 | Completed
J1179 | 2026-08-26 | CL38 | Completed
J1179 | 2026-09-02 | CL38 | Completed
J1179 | 2026-09-09 | CL38 | Completed
J1179 | 2026-09-16 | CL38 | Completed
J1179 | 2026-09-23 | CL38 | Completed
J1179 | 2026-09-30 | CL38 | Completed
J1179 | 2026-10-07 | CL38 | Completed
J1179 | 2026-10-14 | CL38 | Completed
J1179 | 2026-10-21 | CL38 | Skipped
J1179 | 2026-10-28 | CL38 | Completed
J1180 | 2026-08-03 | CL06 | Completed
J1180 | 2026-08-04 | CL06 | Completed
J1180 | 2026-08-05 | CL06 | Completed
J1180 | 2026-08-06 | CL06 | Completed
J1180 | 2026-08-07 | CL06 | Completed
J1180 | 2026-08-10 | CL06 | Completed
J1180 | 2026-08-11 | CL06 | Completed
J1180 | 2026-08-12 | CL06 | Completed
J1180 | 2026-08-13 | CL06 | Completed
J1180 | 2026-08-14 | CL06 | Completed
J1180 | 2026-08-17 | CL06 | Completed
J1180 | 2026-08-18 | CL06 | Completed
J1180 | 2026-08-19 | CL06 | Completed
J1180 | 2026-08-20 | CL06 | Completed
J1180 | 2026-08-21 | CL06 | Completed
J1180 | 2026-08-24 | CL06 | Completed
J1180 | 2026-08-25 | CL06 | Completed
J1180 | 2026-08-26 | CL06 | Completed
J1180 | 2026-08-27 | CL06 | Completed
J1180 | 2026-08-28 | CL06 | Completed
J1180 | 2026-08-31 | CL06 | Completed
J1180 | 2026-09-01 | CL06 | Skipped
J1180 | 2026-09-02 | CL06 | Completed
J1180 | 2026-09-03 | CL06 | Completed
J1180 | 2026-09-04 | CL06 | Completed
J1180 | 2026-09-07 | CL06 | Completed
J1180 | 2026-09-08 | CL06 | Completed
J1180 | 2026-09-09 | CL06 | Completed
J1180 | 2026-09-10 | CL06 | Completed
J1180 | 2026-09-11 | CL06 | Completed
J1180 | 2026-09-14 | CL06 | Skipped
J1180 | 2026-09-15 | CL06 | Completed
J1180 | 2026-09-16 | CL06 | Completed
J1180 | 2026-09-17 | CL06 | Completed
J1180 | 2026-09-18 | CL06 | Completed
J1180 | 2026-09-21 | CL06 | Completed
J1180 | 2026-09-22 | CL06 | Completed
J1180 | 2026-09-23 | CL06 | Completed
J1180 | 2026-09-24 | CL06 | Completed
J1180 | 2026-09-25 | CL06 | Completed
J1180 | 2026-09-28 | CL06 | Completed
J1180 | 2026-09-29 | CL06 | Completed
J1180 | 2026-09-30 | CL06 | Skipped
J1180 | 2026-10-01 | CL06 | Completed
J1180 | 2026-10-02 | CL06 | Completed
J1180 | 2026-10-05 | CL06 | Completed
J1180 | 2026-10-06 | CL06 | Completed
J1180 | 2026-10-07 | CL06 | Completed
J1180 | 2026-10-08 | CL06 | Completed
J1180 | 2026-10-09 | CL06 | Completed
J1180 | 2026-10-12 | CL06 | Completed
J1180 | 2026-10-13 | CL06 | Completed
J1180 | 2026-10-14 | CL06 | Completed
J1180 | 2026-10-15 | CL06 | Completed
J1180 | 2026-10-16 | CL06 | Completed
J1180 | 2026-10-19 | CL06 | Completed
J1180 | 2026-10-20 | CL06 | Completed
J1180 | 2026-10-21 | CL06 | Completed
J1180 | 2026-10-22 | CL06 | Completed
J1180 | 2026-10-23 | CL06 | Completed
J1180 | 2026-10-26 | CL06 | Completed
J1180 | 2026-10-27 | CL06 | Completed
J1180 | 2026-10-28 | CL06 | Completed
J1180 | 2026-10-29 | CL06 | Completed
J1180 | 2026-10-30 | CL06 | Completed
J1181 | 2026-08-05 | CL28 | Completed
J1181 | 2026-08-07 | CL28 | Completed
J1181 | 2026-08-12 | CL28 | Completed
J1181 | 2026-08-14 | CL28 | Completed
J1181 | 2026-08-19 | CL28 | Completed
J1181 | 2026-08-21 | CL28 | Completed
J1181 | 2026-08-26 | CL28 | Completed
J1181 | 2026-08-28 | CL28 | Completed
J1181 | 2026-09-02 | CL28 | Completed
J1181 | 2026-09-04 | CL28 | Completed
J1181 | 2026-09-09 | CL28 | Completed
J1181 | 2026-09-11 | CL28 | Completed
J1181 | 2026-09-16 | CL28 | Completed
J1181 | 2026-09-18 | CL28 | Completed
J1181 | 2026-09-23 | CL28 | Completed
J1181 | 2026-09-25 | CL28 | Completed
J1181 | 2026-09-30 | CL28 | Completed
J1181 | 2026-10-02 | CL28 | Completed
J1181 | 2026-10-07 | CL28 | Completed
J1181 | 2026-10-09 | CL28 | Completed
J1181 | 2026-10-14 | CL28 | Completed
J1181 | 2026-10-16 | CL28 | Completed
J1181 | 2026-10-21 | CL28 | Completed
J1181 | 2026-10-23 | CL28 | Completed
J1181 | 2026-10-28 | CL28 | Completed
J1181 | 2026-10-30 | CL28 | Completed
J1182 | 2026-08-04 | CL39 | Completed
J1182 | 2026-08-11 | CL39 | Completed
J1182 | 2026-08-18 | CL39 | Completed
J1182 | 2026-08-25 | CL39 | Completed
J1182 | 2026-09-01 | CL39 | Completed
J1182 | 2026-09-08 | CL39 | Completed
J1182 | 2026-09-15 | CL39 | Completed
J1182 | 2026-09-22 | CL39 | Completed
J1182 | 2026-09-29 | CL39 | Completed
J1182 | 2026-10-06 | CL39 | Completed
J1182 | 2026-10-13 | CL39 | Completed
J1182 | 2026-10-20 | CL39 | Completed
J1182 | 2026-10-27 | CL39 | Completed
J1183 | 2026-08-05 | CL35 | Completed
J1183 | 2026-08-06 | CL35 | Completed
J1183 | 2026-08-12 | CL35 | Skipped
J1183 | 2026-08-13 | CL35 | Completed
J1183 | 2026-08-19 | CL35 | Completed
J1183 | 2026-08-20 | CL35 | Completed
J1183 | 2026-08-26 | CL35 | Completed
J1183 | 2026-08-27 | CL35 | Completed
J1183 | 2026-09-02 | CL35 | Completed
J1183 | 2026-09-03 | CL35 | Completed
J1183 | 2026-09-09 | CL35 | Completed
J1183 | 2026-09-10 | CL35 | Completed
J1183 | 2026-09-16 | CL35 | Skipped
J1183 | 2026-09-17 | CL35 | Completed
J1183 | 2026-09-23 | CL35 | Completed
J1183 | 2026-09-24 | CL35 | Completed
J1183 | 2026-09-30 | CL35 | Completed
J1183 | 2026-10-01 | CL35 | Completed
J1183 | 2026-10-07 | CL35 | Completed
J1183 | 2026-10-08 | CL35 | Completed
J1183 | 2026-10-14 | CL35 | Completed
J1183 | 2026-10-15 | CL35 | Completed
J1183 | 2026-10-21 | CL35 | Completed
J1183 | 2026-10-22 | CL35 | Completed
J1183 | 2026-10-28 | CL35 | Completed
J1183 | 2026-10-29 | CL35 | Completed
J1184 | 2026-08-03 | CL47 | Completed
J1184 | 2026-08-07 | CL47 | Completed
J1184 | 2026-08-10 | CL47 | Completed
J1184 | 2026-08-14 | CL47 | Skipped
J1184 | 2026-08-17 | CL47 | Completed
J1184 | 2026-08-21 | CL47 | Completed
J1184 | 2026-08-24 | CL47 | Completed
J1184 | 2026-08-28 | CL47 | Completed
J1184 | 2026-08-31 | CL47 | Completed
J1184 | 2026-09-04 | CL47 | Completed
J1184 | 2026-09-07 | CL47 | Completed
J1184 | 2026-09-11 | CL47 | Completed
J1184 | 2026-09-14 | CL47 | Completed
J1184 | 2026-09-18 | CL47 | Completed
J1184 | 2026-09-21 | CL47 | Completed
J1184 | 2026-09-25 | CL47 | Completed
J1184 | 2026-09-28 | CL47 | Completed
J1184 | 2026-10-02 | CL47 | Completed
J1184 | 2026-10-05 | CL47 | Completed
J1184 | 2026-10-09 | CL47 | Completed
J1184 | 2026-10-12 | CL47 | Completed
J1184 | 2026-10-16 | CL47 | Completed
J1184 | 2026-10-19 | CL47 | Completed
J1184 | 2026-10-23 | CL47 | Completed
J1184 | 2026-10-26 | CL47 | Completed
J1184 | 2026-10-30 | CL47 | Completed
J1185 | 2026-08-14 | CL60 | Completed
J1185 | 2026-09-11 | CL60 | Completed
J1185 | 2026-10-09 | CL60 | Completed
J1186 | 2026-08-06 | CL03 | Completed
J1186 | 2026-08-13 | CL03 | Completed
J1186 | 2026-08-20 | CL03 | Completed
J1186 | 2026-08-27 | CL03 | Completed
J1186 | 2026-09-03 | CL03 | Completed
J1186 | 2026-09-10 | CL03 | Completed
J1186 | 2026-09-17 | CL03 | Completed
J1186 | 2026-09-24 | CL03 | Completed
J1186 | 2026-10-01 | CL03 | Completed
J1186 | 2026-10-08 | CL03 | Completed
J1186 | 2026-10-15 | CL03 | Completed
J1186 | 2026-10-22 | CL03 | Completed
J1186 | 2026-10-29 | CL03 | Completed
J1187 | 2026-08-05 | CL11 | Completed
J1187 | 2026-08-06 | CL11 | Completed
J1187 | 2026-08-12 | CL11 | Completed
J1187 | 2026-08-13 | CL11 | Completed
J1187 | 2026-08-19 | CL11 | Completed
J1187 | 2026-08-20 | CL11 | Completed
J1187 | 2026-08-26 | CL11 | Skipped
J1187 | 2026-08-27 | CL11 | Completed
J1187 | 2026-09-02 | CL11 | Completed
J1187 | 2026-09-03 | CL11 | Completed
J1187 | 2026-09-09 | CL11 | Completed
J1187 | 2026-09-10 | CL11 | Completed
J1187 | 2026-09-16 | CL11 | Completed
J1187 | 2026-09-17 | CL11 | Completed
J1187 | 2026-09-23 | CL11 | Completed
J1187 | 2026-09-24 | CL11 | Completed
J1187 | 2026-09-30 | CL11 | Completed
J1187 | 2026-10-01 | CL11 | Completed
J1187 | 2026-10-07 | CL11 | Completed
J1187 | 2026-10-08 | CL11 | Completed
J1187 | 2026-10-14 | CL11 | Completed
J1187 | 2026-10-15 | CL11 | Completed
J1187 | 2026-10-21 | CL11 | Completed
J1187 | 2026-10-22 | CL11 | Completed
J1187 | 2026-10-28 | CL11 | Completed
J1187 | 2026-10-29 | CL11 | Completed
J1188 | 2026-08-03 | CL30 | Completed
J1188 | 2026-08-05 | CL30 | Completed
J1188 | 2026-08-10 | CL30 | Completed
J1188 | 2026-08-12 | CL30 | Completed
J1188 | 2026-08-17 | CL30 | Completed
J1188 | 2026-08-19 | CL30 | Completed
J1188 | 2026-08-24 | CL30 | Completed
J1188 | 2026-08-26 | CL30 | Completed
J1188 | 2026-08-31 | CL30 | Completed
J1188 | 2026-09-02 | CL30 | Completed
J1188 | 2026-09-07 | CL30 | Completed
J1188 | 2026-09-09 | CL30 | Completed
J1188 | 2026-09-14 | CL30 | Completed
J1188 | 2026-09-16 | CL30 | Completed
J1188 | 2026-09-21 | CL30 | Completed
J1188 | 2026-09-23 | CL30 | Completed
J1188 | 2026-09-28 | CL30 | Completed
J1188 | 2026-09-30 | CL30 | Completed
J1188 | 2026-10-05 | CL30 | Completed
J1188 | 2026-10-07 | CL30 | Completed
J1188 | 2026-10-12 | CL30 | Completed
J1188 | 2026-10-14 | CL30 | Completed
J1188 | 2026-10-19 | CL30 | Completed
J1188 | 2026-10-21 | CL30 | Skipped
J1188 | 2026-10-26 | CL30 | Completed
J1188 | 2026-10-28 | CL30 | Completed
J1189 | 2026-08-03 | CL60 | Completed
J1189 | 2026-09-07 | CL60 | Completed
J1189 | 2026-10-05 | CL60 | Completed
J1190 | 2026-08-05 | CL42 | Completed
J1190 | 2026-08-12 | CL42 | Completed
J1190 | 2026-08-19 | CL42 | Completed
J1190 | 2026-08-26 | CL42 | Completed
J1190 | 2026-09-02 | CL42 | Completed
J1190 | 2026-09-09 | CL42 | Completed
J1190 | 2026-09-16 | CL42 | Completed
J1190 | 2026-09-23 | CL42 | Completed
J1190 | 2026-09-30 | CL42 | Completed
J1190 | 2026-10-07 | CL42 | Completed
J1190 | 2026-10-14 | CL42 | Completed
J1190 | 2026-10-21 | CL42 | Skipped
J1190 | 2026-10-28 | CL42 | Completed
J1191 | 2026-08-04 | CL25 | Completed
J1191 | 2026-08-11 | CL25 | Completed
J1191 | 2026-08-18 | CL25 | Completed
J1191 | 2026-08-25 | CL25 | Completed
J1191 | 2026-09-01 | CL25 | Completed
J1191 | 2026-09-08 | CL25 | Completed
J1191 | 2026-09-15 | CL25 | Completed
J1191 | 2026-09-22 | CL25 | Completed
J1191 | 2026-09-29 | CL25 | Completed
J1191 | 2026-10-06 | CL25 | Completed
J1191 | 2026-10-13 | CL25 | Completed
J1191 | 2026-10-20 | CL25 | Completed
J1191 | 2026-10-27 | CL25 | Completed
J1192 | 2026-08-05 | CL37 | Completed
J1192 | 2026-08-12 | CL37 | Completed
J1192 | 2026-08-19 | CL37 | Completed
J1192 | 2026-08-26 | CL37 | Completed
J1192 | 2026-09-02 | CL37 | Completed
J1192 | 2026-09-09 | CL37 | Completed
J1192 | 2026-09-16 | CL37 | Completed
J1192 | 2026-09-23 | CL37 | Completed
J1192 | 2026-09-30 | CL37 | Completed
J1192 | 2026-10-07 | CL37 | Completed
J1192 | 2026-10-14 | CL37 | Completed
J1192 | 2026-10-21 | CL37 | Completed
J1192 | 2026-10-28 | CL37 | Completed
J1193 | 2026-08-06 | CL13 | Completed
J1193 | 2026-08-13 | CL13 | Completed
J1193 | 2026-08-20 | CL13 | Completed
J1193 | 2026-08-27 | CL13 | Completed
J1193 | 2026-09-03 | CL13 | Completed
J1193 | 2026-09-10 | CL13 | Completed
J1193 | 2026-09-17 | CL13 | Completed
J1193 | 2026-09-24 | CL13 | Completed
J1193 | 2026-10-01 | CL13 | Completed
J1193 | 2026-10-08 | CL13 | Completed
J1193 | 2026-10-15 | CL13 | Completed
J1193 | 2026-10-22 | CL13 | Completed
J1193 | 2026-10-29 | CL13 | Completed
J1194 | 2026-08-03 | CL49 | Completed
J1194 | 2026-08-04 | CL49 | Completed
J1194 | 2026-08-05 | CL49 | Completed
J1194 | 2026-08-06 | CL49 | Completed
J1194 | 2026-08-07 | CL49 | Completed
J1194 | 2026-08-10 | CL49 | Completed
J1194 | 2026-08-11 | CL49 | Completed
J1194 | 2026-08-12 | CL49 | Completed
J1194 | 2026-08-13 | CL49 | Completed
J1194 | 2026-08-14 | CL49 | Completed
J1194 | 2026-08-17 | CL49 | Completed
J1194 | 2026-08-18 | CL49 | Completed
J1194 | 2026-08-19 | CL49 | Completed
J1194 | 2026-08-20 | CL49 | Completed
J1194 | 2026-08-21 | CL49 | Completed
J1194 | 2026-08-24 | CL49 | Completed
J1194 | 2026-08-25 | CL49 | Completed
J1194 | 2026-08-26 | CL49 | Completed
J1194 | 2026-08-27 | CL49 | Completed
J1194 | 2026-08-28 | CL49 | Completed
J1194 | 2026-08-31 | CL49 | Completed
J1194 | 2026-09-01 | CL49 | Completed
J1194 | 2026-09-02 | CL49 | Completed
J1194 | 2026-09-03 | CL49 | Completed
J1194 | 2026-09-04 | CL49 | Completed
J1194 | 2026-09-07 | CL49 | Completed
J1194 | 2026-09-08 | CL49 | Completed
J1194 | 2026-09-09 | CL49 | Completed
J1194 | 2026-09-10 | CL49 | Completed
J1194 | 2026-09-11 | CL49 | Completed
J1194 | 2026-09-14 | CL49 | Completed
J1194 | 2026-09-15 | CL49 | Completed
J1194 | 2026-09-16 | CL49 | Completed
J1194 | 2026-09-17 | CL49 | Completed
J1194 | 2026-09-18 | CL49 | Completed
J1194 | 2026-09-21 | CL49 | Completed
J1194 | 2026-09-22 | CL49 | Completed
J1194 | 2026-09-23 | CL49 | Completed
J1194 | 2026-09-24 | CL49 | Completed
J1194 | 2026-09-25 | CL49 | Completed
J1194 | 2026-09-28 | CL49 | Completed
J1194 | 2026-09-29 | CL49 | Completed
J1194 | 2026-09-30 | CL49 | Completed
J1194 | 2026-10-01 | CL49 | Completed
J1194 | 2026-10-02 | CL49 | Completed
J1194 | 2026-10-05 | CL49 | Completed
J1194 | 2026-10-06 | CL49 | Completed
J1194 | 2026-10-07 | CL49 | Completed
J1194 | 2026-10-08 | CL49 | Completed
J1194 | 2026-10-09 | CL49 | Completed
J1194 | 2026-10-12 | CL49 | Completed
J1194 | 2026-10-13 | CL49 | Completed
J1194 | 2026-10-14 | CL49 | Completed
J1194 | 2026-10-15 | CL49 | Completed
J1194 | 2026-10-16 | CL49 | Completed
J1194 | 2026-10-19 | CL49 | Completed
J1194 | 2026-10-20 | CL49 | Completed
J1194 | 2026-10-21 | CL49 | Completed
J1194 | 2026-10-22 | CL49 | Completed
J1194 | 2026-10-23 | CL49 | Completed
J1194 | 2026-10-26 | CL49 | Completed
J1194 | 2026-10-27 | CL49 | Completed
J1194 | 2026-10-28 | CL49 | Completed
J1194 | 2026-10-29 | CL49 | Completed
J1194 | 2026-10-30 | CL49 | Completed
J1195 | 2026-08-07 | CL01 | Completed
J1195 | 2026-08-14 | CL01 | Completed
J1195 | 2026-08-21 | CL01 | Completed
J1195 | 2026-08-28 | CL01 | Completed
J1195 | 2026-09-04 | CL01 | Completed
J1195 | 2026-09-11 | CL01 | Completed
J1195 | 2026-09-18 | CL01 | Completed
J1195 | 2026-09-25 | CL01 | Completed
J1195 | 2026-10-02 | CL01 | Completed
J1195 | 2026-10-09 | CL01 | Completed
J1195 | 2026-10-16 | CL01 | Completed
J1195 | 2026-10-23 | CL01 | Completed
J1195 | 2026-10-30 | CL01 | Completed
J1196 | 2026-08-03 | CL20 | Completed
J1196 | 2026-08-04 | CL20 | Completed
J1196 | 2026-08-10 | CL20 | Completed
J1196 | 2026-08-11 | CL20 | Completed
J1196 | 2026-08-17 | CL20 | Completed
J1196 | 2026-08-18 | CL20 | Completed
J1196 | 2026-08-24 | CL20 | Completed
J1196 | 2026-08-25 | CL20 | Completed
J1196 | 2026-08-31 | CL20 | Completed
J1196 | 2026-09-01 | CL20 | Completed
J1196 | 2026-09-07 | CL20 | Completed
J1196 | 2026-09-08 | CL20 | Completed
J1196 | 2026-09-14 | CL20 | Completed
J1196 | 2026-09-15 | CL20 | Skipped
J1196 | 2026-09-21 | CL20 | Completed
J1196 | 2026-09-22 | CL20 | Completed
J1196 | 2026-09-28 | CL20 | Completed
J1196 | 2026-09-29 | CL20 | Completed
J1196 | 2026-10-05 | CL20 | Completed
J1196 | 2026-10-06 | CL20 | Completed
J1196 | 2026-10-12 | CL20 | Completed
J1196 | 2026-10-13 | CL20 | Completed
J1196 | 2026-10-19 | CL20 | Completed
J1196 | 2026-10-20 | CL20 | Completed
J1196 | 2026-10-26 | CL20 | Completed
J1196 | 2026-10-27 | CL20 | Completed
J1197 | 2026-08-19 | CL60 | Completed
J1197 | 2026-09-16 | CL60 | Completed
J1197 | 2026-10-14 | CL60 | Completed
J1198 | 2026-08-03 | CL42 | Completed
J1198 | 2026-08-10 | CL42 | Completed
J1198 | 2026-08-17 | CL42 | Completed
J1198 | 2026-08-24 | CL42 | Completed
J1198 | 2026-08-31 | CL42 | Completed
J1198 | 2026-09-07 | CL42 | Completed
J1198 | 2026-09-14 | CL42 | Skipped
J1198 | 2026-09-21 | CL42 | Completed
J1198 | 2026-09-28 | CL42 | Completed
J1198 | 2026-10-05 | CL42 | Completed
J1198 | 2026-10-12 | CL42 | Completed
J1198 | 2026-10-19 | CL42 | Completed
J1198 | 2026-10-26 | CL42 | Completed
J1199 | 2026-08-06 | CL02 | Completed
J1199 | 2026-08-07 | CL02 | Completed
J1199 | 2026-08-13 | CL02 | Completed
J1199 | 2026-08-14 | CL02 | Completed
J1199 | 2026-08-20 | CL02 | Completed
J1199 | 2026-08-21 | CL02 | Completed
J1199 | 2026-08-27 | CL02 | Completed
J1199 | 2026-08-28 | CL02 | Completed
J1199 | 2026-09-03 | CL02 | Completed
J1199 | 2026-09-04 | CL02 | Completed
J1199 | 2026-09-10 | CL02 | Completed
J1199 | 2026-09-11 | CL02 | Completed
J1199 | 2026-09-17 | CL02 | Completed
J1199 | 2026-09-18 | CL02 | Completed
J1199 | 2026-09-24 | CL02 | Completed
J1199 | 2026-09-25 | CL02 | Completed
J1199 | 2026-10-01 | CL02 | Completed
J1199 | 2026-10-02 | CL02 | Completed
J1199 | 2026-10-08 | CL02 | Completed
J1199 | 2026-10-09 | CL02 | Completed
J1199 | 2026-10-15 | CL02 | Completed
J1199 | 2026-10-16 | CL02 | Completed
J1199 | 2026-10-22 | CL02 | Completed
J1199 | 2026-10-23 | CL02 | Completed
J1199 | 2026-10-29 | CL02 | Completed
J1199 | 2026-10-30 | CL02 | Completed
J1200 | 2026-08-07 | CL20 | Completed
J1200 | 2026-08-14 | CL20 | Completed
J1200 | 2026-08-21 | CL20 | Completed
J1200 | 2026-08-28 | CL20 | Completed
J1200 | 2026-09-04 | CL20 | Completed
J1200 | 2026-09-11 | CL20 | Completed
J1200 | 2026-09-18 | CL20 | Completed
J1200 | 2026-09-25 | CL20 | Completed
J1200 | 2026-10-02 | CL20 | Completed
J1200 | 2026-10-09 | CL20 | Completed
J1200 | 2026-10-16 | CL20 | Completed
J1200 | 2026-10-23 | CL20 | Completed
J1200 | 2026-10-30 | CL20 | Completed
J1201 | 2026-08-06 | CL32 | Completed
J1201 | 2026-08-13 | CL32 | Completed
J1201 | 2026-08-20 | CL32 | Completed
J1201 | 2026-08-27 | CL32 | Completed
J1201 | 2026-09-03 | CL32 | Completed
J1201 | 2026-09-10 | CL32 | Completed
J1201 | 2026-09-17 | CL32 | Completed
J1201 | 2026-09-24 | CL32 | Completed
J1201 | 2026-10-01 | CL32 | Completed
J1201 | 2026-10-08 | CL32 | Completed
J1201 | 2026-10-15 | CL32 | Completed
J1201 | 2026-10-22 | CL32 | Completed
J1201 | 2026-10-29 | CL32 | Completed
J1202 | 2026-08-27 | CL59 | Completed
J1202 | 2026-09-24 | CL59 | Completed
J1202 | 2026-10-22 | CL59 | Completed
J1203 | 2026-08-03 | CL50 | Completed
J1203 | 2026-08-05 | CL50 | Completed
J1203 | 2026-08-06 | CL50 | Completed
J1203 | 2026-08-10 | CL50 | Completed
J1203 | 2026-08-12 | CL50 | Completed
J1203 | 2026-08-13 | CL50 | Completed
J1203 | 2026-08-17 | CL50 | Skipped
J1203 | 2026-08-19 | CL50 | Completed
J1203 | 2026-08-20 | CL50 | Completed
J1203 | 2026-08-24 | CL50 | Completed
J1203 | 2026-08-26 | CL50 | Completed
J1203 | 2026-08-27 | CL50 | Completed
J1203 | 2026-08-31 | CL50 | Completed
J1203 | 2026-09-02 | CL50 | Completed
J1203 | 2026-09-03 | CL50 | Completed
J1203 | 2026-09-07 | CL50 | Completed
J1203 | 2026-09-09 | CL50 | Completed
J1203 | 2026-09-10 | CL50 | Completed
J1203 | 2026-09-14 | CL50 | Completed
J1203 | 2026-09-16 | CL50 | Completed
J1203 | 2026-09-17 | CL50 | Completed
J1203 | 2026-09-21 | CL50 | Completed
J1203 | 2026-09-23 | CL50 | Completed
J1203 | 2026-09-24 | CL50 | Completed
J1203 | 2026-09-28 | CL50 | Completed
J1203 | 2026-09-30 | CL50 | Completed
J1203 | 2026-10-01 | CL50 | Completed
J1203 | 2026-10-05 | CL50 | Completed
J1203 | 2026-10-07 | CL50 | Completed
J1203 | 2026-10-08 | CL50 | Completed
J1203 | 2026-10-12 | CL50 | Completed
J1203 | 2026-10-14 | CL50 | Completed
J1203 | 2026-10-15 | CL50 | Completed
J1203 | 2026-10-19 | CL50 | Completed
J1203 | 2026-10-21 | CL50 | Completed
J1203 | 2026-10-22 | CL50 | Completed
J1203 | 2026-10-26 | CL50 | Completed
J1203 | 2026-10-28 | CL50 | Completed
J1203 | 2026-10-29 | CL50 | Completed
J1204 | 2026-08-03 | CL48 | Completed
J1204 | 2026-08-04 | CL48 | Completed
J1204 | 2026-08-05 | CL48 | Completed
J1204 | 2026-08-06 | CL48 | Completed
J1204 | 2026-08-07 | CL48 | Completed
J1204 | 2026-08-10 | CL48 | Completed
J1204 | 2026-08-11 | CL48 | Completed
J1204 | 2026-08-12 | CL48 | Completed
J1204 | 2026-08-13 | CL48 | Completed
J1204 | 2026-08-14 | CL48 | Completed
J1204 | 2026-08-17 | CL48 | Completed
J1204 | 2026-08-18 | CL48 | Completed
J1204 | 2026-08-19 | CL48 | Completed
J1204 | 2026-08-20 | CL48 | Completed
J1204 | 2026-08-21 | CL48 | Completed
J1204 | 2026-08-24 | CL48 | Completed
J1204 | 2026-08-25 | CL48 | Completed
J1204 | 2026-08-26 | CL48 | Completed
J1204 | 2026-08-27 | CL48 | Completed
J1204 | 2026-08-28 | CL48 | Completed
J1204 | 2026-08-31 | CL48 | Completed
J1204 | 2026-09-01 | CL48 | Completed
J1204 | 2026-09-02 | CL48 | Completed
J1204 | 2026-09-03 | CL48 | Completed
J1204 | 2026-09-04 | CL48 | Completed
J1204 | 2026-09-07 | CL48 | Completed
J1204 | 2026-09-08 | CL48 | Completed
J1204 | 2026-09-09 | CL48 | Completed
J1204 | 2026-09-10 | CL48 | Completed
J1204 | 2026-09-11 | CL48 | Completed
J1204 | 2026-09-14 | CL48 | Completed
J1204 | 2026-09-15 | CL48 | Completed
J1204 | 2026-09-16 | CL48 | Completed
J1204 | 2026-09-17 | CL48 | Completed
J1204 | 2026-09-18 | CL48 | Completed
J1204 | 2026-09-21 | CL48 | Completed
J1204 | 2026-09-22 | CL48 | Completed
J1204 | 2026-09-23 | CL48 | Completed
J1204 | 2026-09-24 | CL48 | Completed
J1204 | 2026-09-25 | CL48 | Completed
J1204 | 2026-09-28 | CL48 | Completed
J1204 | 2026-09-29 | CL48 | Completed
J1204 | 2026-09-30 | CL48 | Completed
J1204 | 2026-10-01 | CL48 | Completed
J1204 | 2026-10-02 | CL48 | Completed
J1204 | 2026-10-05 | CL48 | Completed
J1204 | 2026-10-06 | CL48 | Completed
J1204 | 2026-10-07 | CL48 | Completed
J1204 | 2026-10-08 | CL48 | Completed
J1204 | 2026-10-09 | CL48 | Completed
J1204 | 2026-10-12 | CL48 | Completed
J1204 | 2026-10-13 | CL48 | Completed
J1204 | 2026-10-14 | CL48 | Completed
J1204 | 2026-10-15 | CL48 | Completed
J1204 | 2026-10-16 | CL48 | Completed
J1204 | 2026-10-19 | CL48 | Completed
J1204 | 2026-10-20 | CL48 | Completed
J1204 | 2026-10-21 | CL48 | Completed
J1204 | 2026-10-22 | CL48 | Completed
J1204 | 2026-10-23 | CL48 | Completed
J1204 | 2026-10-26 | CL48 | Completed
J1204 | 2026-10-27 | CL48 | Completed
J1204 | 2026-10-28 | CL48 | Completed
J1204 | 2026-10-29 | CL48 | Completed
J1204 | 2026-10-30 | CL48 | Completed
J1205 | 2026-08-05 | CL29 | Completed
J1205 | 2026-08-06 | CL29 | Completed
J1205 | 2026-08-07 | CL29 | Completed
J1205 | 2026-08-12 | CL29 | Completed
J1205 | 2026-08-13 | CL29 | Completed
J1205 | 2026-08-14 | CL29 | Completed
J1205 | 2026-08-19 | CL29 | Completed
J1205 | 2026-08-20 | CL29 | Completed
J1205 | 2026-08-21 | CL29 | Completed
J1205 | 2026-08-26 | CL29 | Completed
J1205 | 2026-08-27 | CL29 | Completed
J1205 | 2026-08-28 | CL29 | Completed
J1205 | 2026-09-02 | CL29 | Completed
J1205 | 2026-09-03 | CL29 | Completed
J1205 | 2026-09-04 | CL29 | Completed
J1205 | 2026-09-09 | CL29 | Completed
J1205 | 2026-09-10 | CL29 | Completed
J1205 | 2026-09-11 | CL29 | Completed
J1205 | 2026-09-16 | CL29 | Skipped
J1205 | 2026-09-17 | CL29 | Completed
J1205 | 2026-09-18 | CL29 | Completed
J1205 | 2026-09-23 | CL29 | Completed
J1205 | 2026-09-24 | CL29 | Completed
J1205 | 2026-09-25 | CL29 | Completed
J1205 | 2026-09-30 | CL29 | Completed
J1205 | 2026-10-01 | CL29 | Completed
J1205 | 2026-10-02 | CL29 | Completed
J1205 | 2026-10-07 | CL29 | Completed
J1205 | 2026-10-08 | CL29 | Completed
J1205 | 2026-10-09 | CL29 | Completed
J1205 | 2026-10-14 | CL29 | Completed
J1205 | 2026-10-15 | CL29 | Completed
J1205 | 2026-10-16 | CL29 | Completed
J1205 | 2026-10-21 | CL29 | Completed
J1205 | 2026-10-22 | CL29 | Completed
J1205 | 2026-10-23 | CL29 | Completed
J1205 | 2026-10-28 | CL29 | Completed
J1205 | 2026-10-29 | CL29 | Skipped
J1205 | 2026-10-30 | CL29 | Completed
J1206 | 2026-08-24 | CL56 | Completed
J1206 | 2026-09-21 | CL56 | Completed
J1206 | 2026-10-19 | CL56 | Completed
J1207 | 2026-08-04 | CL25 | Completed
J1207 | 2026-08-07 | CL25 | Completed
J1207 | 2026-08-11 | CL25 | Completed
J1207 | 2026-08-14 | CL25 | Completed
J1207 | 2026-08-18 | CL25 | Completed
J1207 | 2026-08-21 | CL25 | Completed
J1207 | 2026-08-25 | CL25 | Completed
J1207 | 2026-08-28 | CL25 | Completed
J1207 | 2026-09-01 | CL25 | Completed
J1207 | 2026-09-04 | CL25 | Completed
J1207 | 2026-09-08 | CL25 | Completed
J1207 | 2026-09-11 | CL25 | Completed
J1207 | 2026-09-15 | CL25 | Completed
J1207 | 2026-09-18 | CL25 | Completed
J1207 | 2026-09-22 | CL25 | Completed
J1207 | 2026-09-25 | CL25 | Completed
J1207 | 2026-09-29 | CL25 | Completed
J1207 | 2026-10-02 | CL25 | Completed
J1207 | 2026-10-06 | CL25 | Completed
J1207 | 2026-10-09 | CL25 | Completed
J1207 | 2026-10-13 | CL25 | Completed
J1207 | 2026-10-16 | CL25 | Completed
J1207 | 2026-10-20 | CL25 | Completed
J1207 | 2026-10-23 | CL25 | Completed
J1207 | 2026-10-27 | CL25 | Completed
J1207 | 2026-10-30 | CL25 | Completed
J1208 | 2026-08-24 | CL58 | Completed
J1208 | 2026-09-21 | CL58 | Completed
J1208 | 2026-10-19 | CL58 | Completed
J1209 | 2026-08-05 | CL46 | Completed
J1209 | 2026-08-12 | CL46 | Completed
J1209 | 2026-08-19 | CL46 | Completed
J1209 | 2026-08-26 | CL46 | Completed
J1209 | 2026-09-02 | CL46 | Completed
J1209 | 2026-09-09 | CL46 | Completed
J1209 | 2026-09-16 | CL46 | Completed
J1209 | 2026-09-23 | CL46 | Completed
J1209 | 2026-09-30 | CL46 | Completed
J1209 | 2026-10-07 | CL46 | Completed
J1209 | 2026-10-14 | CL46 | Completed
J1209 | 2026-10-21 | CL46 | Completed
J1209 | 2026-10-28 | CL46 | Completed
J1210 | 2026-08-03 | CL26 | Completed
J1210 | 2026-08-10 | CL26 | Completed
J1210 | 2026-08-17 | CL26 | Completed
J1210 | 2026-08-24 | CL26 | Completed
J1210 | 2026-08-31 | CL26 | Completed
J1210 | 2026-09-07 | CL26 | Completed
J1210 | 2026-09-14 | CL26 | Completed
J1210 | 2026-09-21 | CL26 | Completed
J1210 | 2026-09-28 | CL26 | Completed
J1210 | 2026-10-05 | CL26 | Completed
J1210 | 2026-10-12 | CL26 | Completed
J1210 | 2026-10-19 | CL26 | Completed
J1210 | 2026-10-26 | CL26 | Completed
J1211 | 2026-08-28 | CL60 | Completed
J1211 | 2026-09-25 | CL60 | Completed
J1211 | 2026-10-23 | CL60 | Completed
J1212 | 2026-08-03 | CL14 | Completed
J1212 | 2026-08-04 | CL14 | Completed
J1212 | 2026-08-05 | CL14 | Completed
J1212 | 2026-08-06 | CL14 | Completed
J1212 | 2026-08-07 | CL14 | Completed
J1212 | 2026-08-10 | CL14 | Completed
J1212 | 2026-08-11 | CL14 | Completed
J1212 | 2026-08-12 | CL14 | Completed
J1212 | 2026-08-13 | CL14 | Completed
J1212 | 2026-08-14 | CL14 | Completed
J1212 | 2026-08-17 | CL14 | Completed
J1212 | 2026-08-18 | CL14 | Completed
J1212 | 2026-08-19 | CL14 | Completed
J1212 | 2026-08-20 | CL14 | Completed
J1212 | 2026-08-21 | CL14 | Completed
J1212 | 2026-08-24 | CL14 | Completed
J1212 | 2026-08-25 | CL14 | Completed
J1212 | 2026-08-26 | CL14 | Completed
J1212 | 2026-08-27 | CL14 | Completed
J1212 | 2026-08-28 | CL14 | Completed
J1212 | 2026-08-31 | CL14 | Completed
J1212 | 2026-09-01 | CL14 | Completed
J1212 | 2026-09-02 | CL14 | Completed
J1212 | 2026-09-03 | CL14 | Completed
J1212 | 2026-09-04 | CL14 | Completed
J1212 | 2026-09-07 | CL14 | Completed
J1212 | 2026-09-08 | CL14 | Completed
J1212 | 2026-09-09 | CL14 | Completed
J1212 | 2026-09-10 | CL14 | Completed
J1212 | 2026-09-11 | CL14 | Completed
J1212 | 2026-09-14 | CL14 | Completed
J1212 | 2026-09-15 | CL14 | Completed
J1212 | 2026-09-16 | CL14 | Completed
J1212 | 2026-09-17 | CL14 | Completed
J1212 | 2026-09-18 | CL14 | Completed
J1212 | 2026-09-21 | CL14 | Completed
J1212 | 2026-09-22 | CL14 | Completed
J1212 | 2026-09-23 | CL14 | Completed
J1212 | 2026-09-24 | CL14 | Completed
J1212 | 2026-09-25 | CL14 | Completed
J1212 | 2026-09-28 | CL14 | Completed
J1212 | 2026-09-29 | CL14 | Completed
J1212 | 2026-09-30 | CL14 | Completed
J1212 | 2026-10-01 | CL14 | Completed
J1212 | 2026-10-02 | CL14 | Skipped
J1212 | 2026-10-05 | CL14 | Completed
J1212 | 2026-10-06 | CL14 | Completed
J1212 | 2026-10-07 | CL14 | Completed
J1212 | 2026-10-08 | CL14 | Completed
J1212 | 2026-10-09 | CL14 | Completed
J1212 | 2026-10-12 | CL14 | Completed
J1212 | 2026-10-13 | CL14 | Completed
J1212 | 2026-10-14 | CL14 | Completed
J1212 | 2026-10-15 | CL14 | Completed
J1212 | 2026-10-16 | CL14 | Completed
J1212 | 2026-10-19 | CL14 | Completed
J1212 | 2026-10-20 | CL14 | Completed
J1212 | 2026-10-21 | CL14 | Completed
J1212 | 2026-10-22 | CL14 | Completed
J1212 | 2026-10-23 | CL14 | Completed
J1212 | 2026-10-26 | CL14 | Completed
J1212 | 2026-10-27 | CL14 | Completed
J1212 | 2026-10-28 | CL14 | Completed
J1212 | 2026-10-29 | CL14 | Completed
J1212 | 2026-10-30 | CL14 | Completed
J1213 | 2026-08-03 | CL04 | Completed
J1213 | 2026-08-04 | CL04 | Completed
J1213 | 2026-08-07 | CL04 | Completed
J1213 | 2026-08-10 | CL04 | Completed
J1213 | 2026-08-11 | CL04 | Completed
J1213 | 2026-08-14 | CL04 | Completed
J1213 | 2026-08-17 | CL04 | Completed
J1213 | 2026-08-18 | CL04 | Completed
J1213 | 2026-08-21 | CL04 | Completed
J1213 | 2026-08-24 | CL04 | Completed
J1213 | 2026-08-25 | CL04 | Completed
J1213 | 2026-08-28 | CL04 | Completed
J1213 | 2026-08-31 | CL04 | Completed
J1213 | 2026-09-01 | CL04 | Completed
J1213 | 2026-09-04 | CL04 | Completed
J1213 | 2026-09-07 | CL04 | Completed
J1213 | 2026-09-08 | CL04 | Completed
J1213 | 2026-09-11 | CL04 | Completed
J1213 | 2026-09-14 | CL04 | Completed
J1213 | 2026-09-15 | CL04 | Completed
J1213 | 2026-09-18 | CL04 | Completed
J1213 | 2026-09-21 | CL04 | Completed
J1213 | 2026-09-22 | CL04 | Completed
J1213 | 2026-09-25 | CL04 | Completed
J1213 | 2026-09-28 | CL04 | Completed
J1213 | 2026-09-29 | CL04 | Completed
J1213 | 2026-10-02 | CL04 | Completed
J1213 | 2026-10-05 | CL04 | Completed
J1213 | 2026-10-06 | CL04 | Completed
J1213 | 2026-10-09 | CL04 | Completed
J1213 | 2026-10-12 | CL04 | Completed
J1213 | 2026-10-13 | CL04 | Completed
J1213 | 2026-10-16 | CL04 | Completed
J1213 | 2026-10-19 | CL04 | Completed
J1213 | 2026-10-20 | CL04 | Completed
J1213 | 2026-10-23 | CL04 | Completed
J1213 | 2026-10-26 | CL04 | Completed
J1213 | 2026-10-27 | CL04 | Completed
J1213 | 2026-10-30 | CL04 | Completed
J1214 | 2026-08-05 | CL19 | Completed
J1214 | 2026-08-12 | CL19 | Completed
J1214 | 2026-08-19 | CL19 | Completed
J1214 | 2026-08-26 | CL19 | Completed
J1214 | 2026-09-02 | CL19 | Skipped
J1214 | 2026-09-09 | CL19 | Completed
J1214 | 2026-09-16 | CL19 | Completed
J1214 | 2026-09-23 | CL19 | Completed
J1214 | 2026-09-30 | CL19 | Completed
J1214 | 2026-10-07 | CL19 | Completed
J1214 | 2026-10-14 | CL19 | Completed
J1214 | 2026-10-21 | CL19 | Completed
J1214 | 2026-10-28 | CL19 | Completed
J1215 | 2026-08-03 | CL02 | Completed
J1215 | 2026-08-04 | CL02 | Completed
J1215 | 2026-08-05 | CL02 | Completed
J1215 | 2026-08-06 | CL02 | Completed
J1215 | 2026-08-07 | CL02 | Completed
J1215 | 2026-08-10 | CL02 | Completed
J1215 | 2026-08-11 | CL02 | Completed
J1215 | 2026-08-12 | CL02 | Completed
J1215 | 2026-08-13 | CL02 | Completed
J1215 | 2026-08-14 | CL02 | Completed
J1215 | 2026-08-17 | CL02 | Completed
J1215 | 2026-08-18 | CL02 | Completed
J1215 | 2026-08-19 | CL02 | Completed
J1215 | 2026-08-20 | CL02 | Completed
J1215 | 2026-08-21 | CL02 | Skipped
J1215 | 2026-08-24 | CL02 | Completed
J1215 | 2026-08-25 | CL02 | Completed
J1215 | 2026-08-26 | CL02 | Completed
J1215 | 2026-08-27 | CL02 | Completed
J1215 | 2026-08-28 | CL02 | Completed
J1215 | 2026-08-31 | CL02 | Completed
J1215 | 2026-09-01 | CL02 | Completed
J1215 | 2026-09-02 | CL02 | Completed
J1215 | 2026-09-03 | CL02 | Completed
J1215 | 2026-09-04 | CL02 | Completed
J1215 | 2026-09-07 | CL02 | Completed
J1215 | 2026-09-08 | CL02 | Completed
J1215 | 2026-09-09 | CL02 | Completed
J1215 | 2026-09-10 | CL02 | Completed
J1215 | 2026-09-11 | CL02 | Completed
J1215 | 2026-09-14 | CL02 | Completed
J1215 | 2026-09-15 | CL02 | Completed
J1215 | 2026-09-16 | CL02 | Completed
J1215 | 2026-09-17 | CL02 | Completed
J1215 | 2026-09-18 | CL02 | Completed
J1215 | 2026-09-21 | CL02 | Completed
J1215 | 2026-09-22 | CL02 | Completed
J1215 | 2026-09-23 | CL02 | Completed
J1215 | 2026-09-24 | CL02 | Completed
J1215 | 2026-09-25 | CL02 | Completed
J1215 | 2026-09-28 | CL02 | Completed
J1215 | 2026-09-29 | CL02 | Completed
J1215 | 2026-09-30 | CL02 | Completed
J1215 | 2026-10-01 | CL02 | Completed
J1215 | 2026-10-02 | CL02 | Completed
J1215 | 2026-10-05 | CL02 | Completed
J1215 | 2026-10-06 | CL02 | Completed
J1215 | 2026-10-07 | CL02 | Completed
J1215 | 2026-10-08 | CL02 | Completed
J1215 | 2026-10-09 | CL02 | Completed
J1215 | 2026-10-12 | CL02 | Completed
J1215 | 2026-10-13 | CL02 | Completed
J1215 | 2026-10-14 | CL02 | Completed
J1215 | 2026-10-15 | CL02 | Completed
J1215 | 2026-10-16 | CL02 | Completed
J1215 | 2026-10-19 | CL02 | Completed
J1215 | 2026-10-20 | CL02 | Completed
J1215 | 2026-10-21 | CL02 | Completed
J1215 | 2026-10-22 | CL02 | Completed
J1215 | 2026-10-23 | CL02 | Completed
J1215 | 2026-10-26 | CL02 | Completed
J1215 | 2026-10-27 | CL02 | Completed
J1215 | 2026-10-28 | CL02 | Completed
J1215 | 2026-10-29 | CL02 | Completed
J1215 | 2026-10-30 | CL02 | Completed
J1216 | 2026-08-03 | CL38 | Completed
J1216 | 2026-08-04 | CL38 | Completed
J1216 | 2026-08-05 | CL38 | Completed
J1216 | 2026-08-10 | CL38 | Completed
J1216 | 2026-08-11 | CL38 | Completed
J1216 | 2026-08-12 | CL38 | Completed
J1216 | 2026-08-17 | CL38 | Completed
J1216 | 2026-08-18 | CL38 | Completed
J1216 | 2026-08-19 | CL38 | Completed
J1216 | 2026-08-24 | CL38 | Completed
J1216 | 2026-08-25 | CL38 | Completed
J1216 | 2026-08-26 | CL38 | Completed
J1216 | 2026-08-31 | CL38 | Completed
J1216 | 2026-09-01 | CL38 | Completed
J1216 | 2026-09-02 | CL38 | Completed
J1216 | 2026-09-07 | CL38 | Completed
J1216 | 2026-09-08 | CL38 | Completed
J1216 | 2026-09-09 | CL38 | Skipped
J1216 | 2026-09-14 | CL38 | Completed
J1216 | 2026-09-15 | CL38 | Completed
J1216 | 2026-09-16 | CL38 | Completed
J1216 | 2026-09-21 | CL38 | Completed
J1216 | 2026-09-22 | CL38 | Completed
J1216 | 2026-09-23 | CL38 | Completed
J1216 | 2026-09-28 | CL38 | Completed
J1216 | 2026-09-29 | CL38 | Completed
J1216 | 2026-09-30 | CL38 | Completed
J1216 | 2026-10-05 | CL38 | Completed
J1216 | 2026-10-06 | CL38 | Completed
J1216 | 2026-10-07 | CL38 | Completed
J1216 | 2026-10-12 | CL38 | Completed
J1216 | 2026-10-13 | CL38 | Completed
J1216 | 2026-10-14 | CL38 | Completed
J1216 | 2026-10-19 | CL38 | Completed
J1216 | 2026-10-20 | CL38 | Completed
J1216 | 2026-10-21 | CL38 | Completed
J1216 | 2026-10-26 | CL38 | Completed
J1216 | 2026-10-27 | CL38 | Completed
J1216 | 2026-10-28 | CL38 | Completed
J1217 | 2026-08-04 | CL18 | Completed
J1217 | 2026-08-05 | CL18 | Completed
J1217 | 2026-08-11 | CL18 | Completed
J1217 | 2026-08-12 | CL18 | Completed
J1217 | 2026-08-18 | CL18 | Completed
J1217 | 2026-08-19 | CL18 | Completed
J1217 | 2026-08-25 | CL18 | Completed
J1217 | 2026-08-26 | CL18 | Completed
J1217 | 2026-09-01 | CL18 | Completed
J1217 | 2026-09-02 | CL18 | Completed
J1217 | 2026-09-08 | CL18 | Completed
J1217 | 2026-09-09 | CL18 | Completed
J1217 | 2026-09-15 | CL18 | Completed
J1217 | 2026-09-16 | CL18 | Completed
J1217 | 2026-09-22 | CL18 | Completed
J1217 | 2026-09-23 | CL18 | Completed
J1217 | 2026-09-29 | CL18 | Completed
J1217 | 2026-09-30 | CL18 | Completed
J1217 | 2026-10-06 | CL18 | Completed
J1217 | 2026-10-07 | CL18 | Completed
J1217 | 2026-10-13 | CL18 | Completed
J1217 | 2026-10-14 | CL18 | Completed
J1217 | 2026-10-20 | CL18 | Completed
J1217 | 2026-10-21 | CL18 | Completed
J1217 | 2026-10-27 | CL18 | Skipped
J1217 | 2026-10-28 | CL18 | Completed
J1218 | 2026-08-03 | CL36 | Completed
J1218 | 2026-08-06 | CL36 | Completed
J1218 | 2026-08-10 | CL36 | Completed
J1218 | 2026-08-13 | CL36 | Completed
J1218 | 2026-08-17 | CL36 | Completed
J1218 | 2026-08-20 | CL36 | Completed
J1218 | 2026-08-24 | CL36 | Completed
J1218 | 2026-08-27 | CL36 | Completed
J1218 | 2026-08-31 | CL36 | Completed
J1218 | 2026-09-03 | CL36 | Completed
J1218 | 2026-09-07 | CL36 | Completed
J1218 | 2026-09-10 | CL36 | Completed
J1218 | 2026-09-14 | CL36 | Completed
J1218 | 2026-09-17 | CL36 | Completed
J1218 | 2026-09-21 | CL36 | Completed
J1218 | 2026-09-24 | CL36 | Completed
J1218 | 2026-09-28 | CL36 | Completed
J1218 | 2026-10-01 | CL36 | Completed
J1218 | 2026-10-05 | CL36 | Completed
J1218 | 2026-10-08 | CL36 | Completed
J1218 | 2026-10-12 | CL36 | Completed
J1218 | 2026-10-15 | CL36 | Completed
J1218 | 2026-10-19 | CL36 | Completed
J1218 | 2026-10-22 | CL36 | Completed
J1218 | 2026-10-26 | CL36 | Completed
J1218 | 2026-10-29 | CL36 | Completed
J1219 | 2026-08-03 | CL07 | Completed
J1219 | 2026-08-06 | CL07 | Completed
J1219 | 2026-08-10 | CL07 | Completed
J1219 | 2026-08-13 | CL07 | Completed
J1219 | 2026-08-17 | CL07 | Completed
J1219 | 2026-08-20 | CL07 | Completed
J1219 | 2026-08-24 | CL07 | Completed
J1219 | 2026-08-27 | CL07 | Completed
J1219 | 2026-08-31 | CL07 | Completed
J1219 | 2026-09-03 | CL07 | Completed
J1219 | 2026-09-07 | CL07 | Completed
J1219 | 2026-09-10 | CL07 | Completed
J1219 | 2026-09-14 | CL07 | Completed
J1219 | 2026-09-17 | CL07 | Completed
J1219 | 2026-09-21 | CL07 | Completed
J1219 | 2026-09-24 | CL07 | Completed
J1219 | 2026-09-28 | CL07 | Completed
J1219 | 2026-10-01 | CL07 | Completed
J1219 | 2026-10-05 | CL07 | Completed
J1219 | 2026-10-08 | CL07 | Completed
J1219 | 2026-10-12 | CL07 | Completed
J1219 | 2026-10-15 | CL07 | Completed
J1219 | 2026-10-19 | CL07 | Completed
J1219 | 2026-10-22 | CL07 | Completed
J1219 | 2026-10-26 | CL07 | Completed
J1219 | 2026-10-29 | CL07 | Completed
J1220 | 2026-08-17 | CL54 | Completed
J1220 | 2026-09-14 | CL54 | Completed
J1220 | 2026-10-12 | CL54 | Completed
J1221 | 2026-08-03 | CL35 | Completed
J1221 | 2026-08-04 | CL35 | Completed
J1221 | 2026-08-10 | CL35 | Completed
J1221 | 2026-08-11 | CL35 | Completed
J1221 | 2026-08-17 | CL35 | Completed
J1221 | 2026-08-18 | CL35 | Completed
J1221 | 2026-08-24 | CL35 | Completed
J1221 | 2026-08-25 | CL35 | Completed
J1221 | 2026-08-31 | CL35 | Completed
J1221 | 2026-09-01 | CL35 | Completed
J1221 | 2026-09-07 | CL35 | Completed
J1221 | 2026-09-08 | CL35 | Completed
J1221 | 2026-09-14 | CL35 | Completed
J1221 | 2026-09-15 | CL35 | Completed
J1221 | 2026-09-21 | CL35 | Completed
J1221 | 2026-09-22 | CL35 | Completed
J1221 | 2026-09-28 | CL35 | Completed
J1221 | 2026-09-29 | CL35 | Completed
J1221 | 2026-10-05 | CL35 | Completed
J1221 | 2026-10-06 | CL35 | Completed
J1221 | 2026-10-12 | CL35 | Completed
J1221 | 2026-10-13 | CL35 | Completed
J1221 | 2026-10-19 | CL35 | Completed
J1221 | 2026-10-20 | CL35 | Completed
J1221 | 2026-10-26 | CL35 | Completed
J1221 | 2026-10-27 | CL35 | Completed
J1222 | 2026-08-04 | CL19 | Completed
J1222 | 2026-08-05 | CL19 | Completed
J1222 | 2026-08-11 | CL19 | Completed
J1222 | 2026-08-12 | CL19 | Completed
J1222 | 2026-08-18 | CL19 | Completed
J1222 | 2026-08-19 | CL19 | Completed
J1222 | 2026-08-25 | CL19 | Completed
J1222 | 2026-08-26 | CL19 | Completed
J1222 | 2026-09-01 | CL19 | Completed
J1222 | 2026-09-02 | CL19 | Completed
J1222 | 2026-09-08 | CL19 | Completed
J1222 | 2026-09-09 | CL19 | Skipped
J1222 | 2026-09-15 | CL19 | Completed
J1222 | 2026-09-16 | CL19 | Completed
J1222 | 2026-09-22 | CL19 | Completed
J1222 | 2026-09-23 | CL19 | Completed
J1222 | 2026-09-29 | CL19 | Completed
J1222 | 2026-09-30 | CL19 | Completed
J1222 | 2026-10-06 | CL19 | Completed
J1222 | 2026-10-07 | CL19 | Completed
J1222 | 2026-10-13 | CL19 | Completed
J1222 | 2026-10-14 | CL19 | Completed
J1222 | 2026-10-20 | CL19 | Completed
J1222 | 2026-10-21 | CL19 | Completed
J1222 | 2026-10-27 | CL19 | Completed
J1222 | 2026-10-28 | CL19 | Completed
J1223 | 2026-08-21 | CL54 | Completed
J1223 | 2026-09-18 | CL54 | Completed
J1223 | 2026-10-16 | CL54 | Completed
J1224 | 2026-08-03 | CL51 | Completed
J1224 | 2026-08-04 | CL51 | Completed
J1224 | 2026-08-05 | CL51 | Completed
J1224 | 2026-08-06 | CL51 | Completed
J1224 | 2026-08-07 | CL51 | Completed
J1224 | 2026-08-10 | CL51 | Completed
J1224 | 2026-08-11 | CL51 | Completed
J1224 | 2026-08-12 | CL51 | Completed
J1224 | 2026-08-13 | CL51 | Completed
J1224 | 2026-08-14 | CL51 | Completed
J1224 | 2026-08-17 | CL51 | Completed
J1224 | 2026-08-18 | CL51 | Skipped
J1224 | 2026-08-19 | CL51 | Completed
J1224 | 2026-08-20 | CL51 | Completed
J1224 | 2026-08-21 | CL51 | Completed
J1224 | 2026-08-24 | CL51 | Completed
J1224 | 2026-08-25 | CL51 | Completed
J1224 | 2026-08-26 | CL51 | Completed
J1224 | 2026-08-27 | CL51 | Completed
J1224 | 2026-08-28 | CL51 | Completed
J1224 | 2026-08-31 | CL51 | Completed
J1224 | 2026-09-01 | CL51 | Completed
J1224 | 2026-09-02 | CL51 | Completed
J1224 | 2026-09-03 | CL51 | Completed
J1224 | 2026-09-04 | CL51 | Completed
J1224 | 2026-09-07 | CL51 | Completed
J1224 | 2026-09-08 | CL51 | Completed
J1224 | 2026-09-09 | CL51 | Completed
J1224 | 2026-09-10 | CL51 | Completed
J1224 | 2026-09-11 | CL51 | Completed
J1224 | 2026-09-14 | CL51 | Completed
J1224 | 2026-09-15 | CL51 | Completed
J1224 | 2026-09-16 | CL51 | Completed
J1224 | 2026-09-17 | CL51 | Completed
J1224 | 2026-09-18 | CL51 | Completed
J1224 | 2026-09-21 | CL51 | Completed
J1224 | 2026-09-22 | CL51 | Completed
J1224 | 2026-09-23 | CL51 | Completed
J1224 | 2026-09-24 | CL51 | Completed
J1224 | 2026-09-25 | CL51 | Completed
J1224 | 2026-09-28 | CL51 | Completed
J1224 | 2026-09-29 | CL51 | Completed
J1224 | 2026-09-30 | CL51 | Completed
J1224 | 2026-10-01 | CL51 | Completed
J1224 | 2026-10-02 | CL51 | Completed
J1224 | 2026-10-05 | CL51 | Completed
J1224 | 2026-10-06 | CL51 | Completed
J1224 | 2026-10-07 | CL51 | Completed
J1224 | 2026-10-08 | CL51 | Completed
J1224 | 2026-10-09 | CL51 | Completed
J1224 | 2026-10-12 | CL51 | Completed
J1224 | 2026-10-13 | CL51 | Completed
J1224 | 2026-10-14 | CL51 | Completed
J1224 | 2026-10-15 | CL51 | Completed
J1224 | 2026-10-16 | CL51 | Completed
J1224 | 2026-10-19 | CL51 | Completed
J1224 | 2026-10-20 | CL51 | Completed
J1224 | 2026-10-21 | CL51 | Completed
J1224 | 2026-10-22 | CL51 | Completed
J1224 | 2026-10-23 | CL51 | Completed
J1224 | 2026-10-26 | CL51 | Completed
J1224 | 2026-10-27 | CL51 | Completed
J1224 | 2026-10-28 | CL51 | Completed
J1224 | 2026-10-29 | CL51 | Completed
J1224 | 2026-10-30 | CL51 | Completed
J1225 | 2026-08-05 | CL39 | Completed
J1225 | 2026-08-07 | CL39 | Completed
J1225 | 2026-08-12 | CL39 | Completed
J1225 | 2026-08-14 | CL39 | Completed
J1225 | 2026-08-19 | CL39 | Completed
J1225 | 2026-08-21 | CL39 | Completed
J1225 | 2026-08-26 | CL39 | Completed
J1225 | 2026-08-28 | CL39 | Completed
J1225 | 2026-09-02 | CL39 | Completed
J1225 | 2026-09-04 | CL39 | Completed
J1225 | 2026-09-09 | CL39 | Completed
J1225 | 2026-09-11 | CL39 | Completed
J1225 | 2026-09-16 | CL39 | Completed
J1225 | 2026-09-18 | CL39 | Completed
J1225 | 2026-09-23 | CL39 | Completed
J1225 | 2026-09-25 | CL39 | Completed
J1225 | 2026-09-30 | CL39 | Completed
J1225 | 2026-10-02 | CL39 | Completed
J1225 | 2026-10-07 | CL39 | Completed
J1225 | 2026-10-09 | CL39 | Completed
J1225 | 2026-10-14 | CL39 | Completed
J1225 | 2026-10-16 | CL39 | Completed
J1225 | 2026-10-21 | CL39 | Completed
J1225 | 2026-10-23 | CL39 | Completed
J1225 | 2026-10-28 | CL39 | Completed
J1225 | 2026-10-30 | CL39 | Completed
J1226 | 2026-08-03 | CL01 | Completed
J1226 | 2026-08-04 | CL01 | Completed
J1226 | 2026-08-05 | CL01 | Skipped
J1226 | 2026-08-06 | CL01 | Completed
J1226 | 2026-08-07 | CL01 | Completed
J1226 | 2026-08-10 | CL01 | Completed
J1226 | 2026-08-11 | CL01 | Completed
J1226 | 2026-08-12 | CL01 | Completed
J1226 | 2026-08-13 | CL01 | Completed
J1226 | 2026-08-14 | CL01 | Completed
J1226 | 2026-08-17 | CL01 | Completed
J1226 | 2026-08-18 | CL01 | Completed
J1226 | 2026-08-19 | CL01 | Completed
J1226 | 2026-08-20 | CL01 | Completed
J1226 | 2026-08-21 | CL01 | Completed
J1226 | 2026-08-24 | CL01 | Completed
J1226 | 2026-08-25 | CL01 | Completed
J1226 | 2026-08-26 | CL01 | Completed
J1226 | 2026-08-27 | CL01 | Completed
J1226 | 2026-08-28 | CL01 | Completed
J1226 | 2026-08-31 | CL01 | Completed
J1226 | 2026-09-01 | CL01 | Completed
J1226 | 2026-09-02 | CL01 | Completed
J1226 | 2026-09-03 | CL01 | Completed
J1226 | 2026-09-04 | CL01 | Completed
J1226 | 2026-09-07 | CL01 | Completed
J1226 | 2026-09-08 | CL01 | Completed
J1226 | 2026-09-09 | CL01 | Completed
J1226 | 2026-09-10 | CL01 | Completed
J1226 | 2026-09-11 | CL01 | Completed
J1226 | 2026-09-14 | CL01 | Completed
J1226 | 2026-09-15 | CL01 | Completed
J1226 | 2026-09-16 | CL01 | Completed
J1226 | 2026-09-17 | CL01 | Completed
J1226 | 2026-09-18 | CL01 | Completed
J1226 | 2026-09-21 | CL01 | Completed
J1226 | 2026-09-22 | CL01 | Completed
J1226 | 2026-09-23 | CL01 | Completed
J1226 | 2026-09-24 | CL01 | Completed
J1226 | 2026-09-25 | CL01 | Completed
J1226 | 2026-09-28 | CL01 | Completed
J1226 | 2026-09-29 | CL01 | Completed
J1226 | 2026-09-30 | CL01 | Completed
J1226 | 2026-10-01 | CL01 | Completed
J1226 | 2026-10-02 | CL01 | Completed
J1226 | 2026-10-05 | CL01 | Completed
J1226 | 2026-10-06 | CL01 | Completed
J1226 | 2026-10-07 | CL01 | Completed
J1226 | 2026-10-08 | CL01 | Completed
J1226 | 2026-10-09 | CL01 | Completed
J1226 | 2026-10-12 | CL01 | Completed
J1226 | 2026-10-13 | CL01 | Completed
J1226 | 2026-10-14 | CL01 | Completed
J1226 | 2026-10-15 | CL01 | Completed
J1226 | 2026-10-16 | CL01 | Completed
J1226 | 2026-10-19 | CL01 | Completed
J1226 | 2026-10-20 | CL01 | Completed
J1226 | 2026-10-21 | CL01 | Completed
J1226 | 2026-10-22 | CL01 | Completed
J1226 | 2026-10-23 | CL01 | Completed
J1226 | 2026-10-26 | CL01 | Completed
J1226 | 2026-10-27 | CL01 | Completed
J1226 | 2026-10-28 | CL01 | Completed
J1226 | 2026-10-29 | CL01 | Completed
J1226 | 2026-10-30 | CL01 | Completed
J1227 | 2026-08-03 | CL05 | Completed
J1227 | 2026-08-04 | CL05 | Completed
J1227 | 2026-08-10 | CL05 | Completed
J1227 | 2026-08-11 | CL05 | Completed
J1227 | 2026-08-17 | CL05 | Completed
J1227 | 2026-08-18 | CL05 | Completed
J1227 | 2026-08-24 | CL05 | Completed
J1227 | 2026-08-25 | CL05 | Completed
J1227 | 2026-08-31 | CL05 | Completed
J1227 | 2026-09-01 | CL05 | Completed
J1227 | 2026-09-07 | CL05 | Completed
J1227 | 2026-09-08 | CL05 | Completed
J1227 | 2026-09-14 | CL05 | Completed
J1227 | 2026-09-15 | CL05 | Completed
J1227 | 2026-09-21 | CL05 | Completed
J1227 | 2026-09-22 | CL05 | Completed
J1227 | 2026-09-28 | CL05 | Completed
J1227 | 2026-09-29 | CL05 | Completed
J1227 | 2026-10-05 | CL05 | Completed
J1227 | 2026-10-06 | CL05 | Completed
J1227 | 2026-10-12 | CL05 | Completed
J1227 | 2026-10-13 | CL05 | Completed
J1227 | 2026-10-19 | CL05 | Completed
J1227 | 2026-10-20 | CL05 | Completed
J1227 | 2026-10-26 | CL05 | Completed
J1227 | 2026-10-27 | CL05 | Completed
J1228 | 2026-08-12 | CL54 | Completed
J1228 | 2026-09-09 | CL54 | Completed
J1228 | 2026-10-07 | CL54 | Completed
J1229 | 2026-08-05 | CL31 | Completed
J1229 | 2026-08-12 | CL31 | Completed
J1229 | 2026-08-19 | CL31 | Completed
J1229 | 2026-08-26 | CL31 | Completed
J1229 | 2026-09-02 | CL31 | Skipped
J1229 | 2026-09-09 | CL31 | Completed
J1229 | 2026-09-16 | CL31 | Completed
J1229 | 2026-09-23 | CL31 | Completed
J1229 | 2026-09-30 | CL31 | Completed
J1229 | 2026-10-07 | CL31 | Completed
J1229 | 2026-10-14 | CL31 | Completed
J1229 | 2026-10-21 | CL31 | Completed
J1229 | 2026-10-28 | CL31 | Completed
J1230 | 2026-08-07 | CL11 | Completed
J1230 | 2026-08-14 | CL11 | Completed
J1230 | 2026-08-21 | CL11 | Completed
J1230 | 2026-08-28 | CL11 | Completed
J1230 | 2026-09-04 | CL11 | Completed
J1230 | 2026-09-11 | CL11 | Completed
J1230 | 2026-09-18 | CL11 | Completed
J1230 | 2026-09-25 | CL11 | Completed
J1230 | 2026-10-02 | CL11 | Completed
J1230 | 2026-10-09 | CL11 | Completed
J1230 | 2026-10-16 | CL11 | Completed
J1230 | 2026-10-23 | CL11 | Completed
J1230 | 2026-10-30 | CL11 | Skipped
J1231 | 2026-08-12 | CL54 | Completed
J1231 | 2026-09-09 | CL54 | Completed
J1231 | 2026-10-07 | CL54 | Completed
J1232 | 2026-08-04 | CL13 | Completed
J1232 | 2026-08-05 | CL13 | Skipped
J1232 | 2026-08-11 | CL13 | Completed
J1232 | 2026-08-12 | CL13 | Completed
J1232 | 2026-08-18 | CL13 | Completed
J1232 | 2026-08-19 | CL13 | Completed
J1232 | 2026-08-25 | CL13 | Completed
J1232 | 2026-08-26 | CL13 | Completed
J1232 | 2026-09-01 | CL13 | Completed
J1232 | 2026-09-02 | CL13 | Completed
J1232 | 2026-09-08 | CL13 | Completed
J1232 | 2026-09-09 | CL13 | Completed
J1232 | 2026-09-15 | CL13 | Completed
J1232 | 2026-09-16 | CL13 | Completed
J1232 | 2026-09-22 | CL13 | Completed
J1232 | 2026-09-23 | CL13 | Completed
J1232 | 2026-09-29 | CL13 | Completed
J1232 | 2026-09-30 | CL13 | Completed
J1232 | 2026-10-06 | CL13 | Completed
J1232 | 2026-10-07 | CL13 | Completed
J1232 | 2026-10-13 | CL13 | Completed
J1232 | 2026-10-14 | CL13 | Completed
J1232 | 2026-10-20 | CL13 | Completed
J1232 | 2026-10-21 | CL13 | Completed
J1232 | 2026-10-27 | CL13 | Completed
J1232 | 2026-10-28 | CL13 | Completed
J1233 | 2026-08-03 | CL42 | Completed
J1233 | 2026-08-06 | CL42 | Completed
J1233 | 2026-08-10 | CL42 | Completed
J1233 | 2026-08-13 | CL42 | Completed
J1233 | 2026-08-17 | CL42 | Completed
J1233 | 2026-08-20 | CL42 | Completed
J1233 | 2026-08-24 | CL42 | Completed
J1233 | 2026-08-27 | CL42 | Completed
J1233 | 2026-08-31 | CL42 | Completed
J1233 | 2026-09-03 | CL42 | Completed
J1233 | 2026-09-07 | CL42 | Completed
J1233 | 2026-09-10 | CL42 | Completed
J1233 | 2026-09-14 | CL42 | Completed
J1233 | 2026-09-17 | CL42 | Completed
J1233 | 2026-09-21 | CL42 | Completed
J1233 | 2026-09-24 | CL42 | Completed
J1233 | 2026-09-28 | CL42 | Completed
J1233 | 2026-10-01 | CL42 | Completed
J1233 | 2026-10-05 | CL42 | Completed
J1233 | 2026-10-08 | CL42 | Completed
J1233 | 2026-10-12 | CL42 | Completed
J1233 | 2026-10-15 | CL42 | Completed
J1233 | 2026-10-19 | CL42 | Completed
J1233 | 2026-10-22 | CL42 | Completed
J1233 | 2026-10-26 | CL42 | Completed
J1233 | 2026-10-29 | CL42 | Completed
J1234 | 2026-08-05 | CL16 | Completed
J1234 | 2026-08-06 | CL16 | Completed
J1234 | 2026-08-07 | CL16 | Completed
J1234 | 2026-08-12 | CL16 | Completed
J1234 | 2026-08-13 | CL16 | Completed
J1234 | 2026-08-14 | CL16 | Completed
J1234 | 2026-08-19 | CL16 | Completed
J1234 | 2026-08-20 | CL16 | Completed
J1234 | 2026-08-21 | CL16 | Completed
J1234 | 2026-08-26 | CL16 | Completed
J1234 | 2026-08-27 | CL16 | Completed
J1234 | 2026-08-28 | CL16 | Completed
J1234 | 2026-09-02 | CL16 | Completed
J1234 | 2026-09-03 | CL16 | Completed
J1234 | 2026-09-04 | CL16 | Completed
J1234 | 2026-09-09 | CL16 | Completed
J1234 | 2026-09-10 | CL16 | Completed
J1234 | 2026-09-11 | CL16 | Completed
J1234 | 2026-09-16 | CL16 | Completed
J1234 | 2026-09-17 | CL16 | Completed
J1234 | 2026-09-18 | CL16 | Completed
J1234 | 2026-09-23 | CL16 | Completed
J1234 | 2026-09-24 | CL16 | Completed
J1234 | 2026-09-25 | CL16 | Completed
J1234 | 2026-09-30 | CL16 | Completed
J1234 | 2026-10-01 | CL16 | Completed
J1234 | 2026-10-02 | CL16 | Completed
J1234 | 2026-10-07 | CL16 | Completed
J1234 | 2026-10-08 | CL16 | Completed
J1234 | 2026-10-09 | CL16 | Completed
J1234 | 2026-10-14 | CL16 | Completed
J1234 | 2026-10-15 | CL16 | Completed
J1234 | 2026-10-16 | CL16 | Completed
J1234 | 2026-10-21 | CL16 | Completed
J1234 | 2026-10-22 | CL16 | Completed
J1234 | 2026-10-23 | CL16 | Completed
J1234 | 2026-10-28 | CL16 | Completed
J1234 | 2026-10-29 | CL16 | Completed
J1234 | 2026-10-30 | CL16 | Completed
J1235 | 2026-08-03 | CL44 | Completed
J1235 | 2026-08-06 | CL44 | Completed
J1235 | 2026-08-10 | CL44 | Completed
J1235 | 2026-08-13 | CL44 | Completed
J1235 | 2026-08-17 | CL44 | Completed
J1235 | 2026-08-20 | CL44 | Completed
J1235 | 2026-08-24 | CL44 | Completed
J1235 | 2026-08-27 | CL44 | Completed
J1235 | 2026-08-31 | CL44 | Completed
J1235 | 2026-09-03 | CL44 | Completed
J1235 | 2026-09-07 | CL44 | Completed
J1235 | 2026-09-10 | CL44 | Completed
J1235 | 2026-09-14 | CL44 | Completed
J1235 | 2026-09-17 | CL44 | Completed
J1235 | 2026-09-21 | CL44 | Completed
J1235 | 2026-09-24 | CL44 | Completed
J1235 | 2026-09-28 | CL44 | Completed
J1235 | 2026-10-01 | CL44 | Completed
J1235 | 2026-10-05 | CL44 | Skipped
J1235 | 2026-10-08 | CL44 | Completed
J1235 | 2026-10-12 | CL44 | Completed
J1235 | 2026-10-15 | CL44 | Completed
J1235 | 2026-10-19 | CL44 | Completed
J1235 | 2026-10-22 | CL44 | Completed
J1235 | 2026-10-26 | CL44 | Completed
J1235 | 2026-10-29 | CL44 | Completed
J1236 | 2026-08-04 | CL45 | Completed
J1236 | 2026-08-05 | CL45 | Completed
J1236 | 2026-08-06 | CL45 | Completed
J1236 | 2026-08-11 | CL45 | Completed
J1236 | 2026-08-12 | CL45 | Completed
J1236 | 2026-08-13 | CL45 | Completed
J1236 | 2026-08-18 | CL45 | Completed
J1236 | 2026-08-19 | CL45 | Completed
J1236 | 2026-08-20 | CL45 | Completed
J1236 | 2026-08-25 | CL45 | Completed
J1236 | 2026-08-26 | CL45 | Completed
J1236 | 2026-08-27 | CL45 | Completed
J1236 | 2026-09-01 | CL45 | Completed
J1236 | 2026-09-02 | CL45 | Completed
J1236 | 2026-09-03 | CL45 | Completed
J1236 | 2026-09-08 | CL45 | Completed
J1236 | 2026-09-09 | CL45 | Completed
J1236 | 2026-09-10 | CL45 | Completed
J1236 | 2026-09-15 | CL45 | Completed
J1236 | 2026-09-16 | CL45 | Completed
J1236 | 2026-09-17 | CL45 | Completed
J1236 | 2026-09-22 | CL45 | Completed
J1236 | 2026-09-23 | CL45 | Completed
J1236 | 2026-09-24 | CL45 | Completed
J1236 | 2026-09-29 | CL45 | Completed
J1236 | 2026-09-30 | CL45 | Completed
J1236 | 2026-10-01 | CL45 | Completed
J1236 | 2026-10-06 | CL45 | Completed
J1236 | 2026-10-07 | CL45 | Completed
J1236 | 2026-10-08 | CL45 | Completed
J1236 | 2026-10-13 | CL45 | Completed
J1236 | 2026-10-14 | CL45 | Completed
J1236 | 2026-10-15 | CL45 | Completed
J1236 | 2026-10-20 | CL45 | Completed
J1236 | 2026-10-21 | CL45 | Completed
J1236 | 2026-10-22 | CL45 | Completed
J1236 | 2026-10-27 | CL45 | Completed
J1236 | 2026-10-28 | CL45 | Completed
J1236 | 2026-10-29 | CL45 | Completed
J1237 | 2026-08-12 | CL53 | Completed
J1237 | 2026-09-09 | CL53 | Completed
J1237 | 2026-10-07 | CL53 | Completed
J1238 | 2026-08-03 | CL21 | Completed
J1238 | 2026-08-06 | CL21 | Completed
J1238 | 2026-08-07 | CL21 | Completed
J1238 | 2026-08-10 | CL21 | Completed
J1238 | 2026-08-13 | CL21 | Completed
J1238 | 2026-08-14 | CL21 | Completed
J1238 | 2026-08-17 | CL21 | Completed
J1238 | 2026-08-20 | CL21 | Completed
J1238 | 2026-08-21 | CL21 | Completed
J1238 | 2026-08-24 | CL21 | Skipped
J1238 | 2026-08-27 | CL21 | Completed
J1238 | 2026-08-28 | CL21 | Completed
J1238 | 2026-08-31 | CL21 | Completed
J1238 | 2026-09-03 | CL21 | Completed
J1238 | 2026-09-04 | CL21 | Completed
J1238 | 2026-09-07 | CL21 | Completed
J1238 | 2026-09-10 | CL21 | Completed
J1238 | 2026-09-11 | CL21 | Completed
J1238 | 2026-09-14 | CL21 | Completed
J1238 | 2026-09-17 | CL21 | Completed
J1238 | 2026-09-18 | CL21 | Completed
J1238 | 2026-09-21 | CL21 | Completed
J1238 | 2026-09-24 | CL21 | Completed
J1238 | 2026-09-25 | CL21 | Completed
J1238 | 2026-09-28 | CL21 | Completed
J1238 | 2026-10-01 | CL21 | Completed
J1238 | 2026-10-02 | CL21 | Completed
J1238 | 2026-10-05 | CL21 | Completed
J1238 | 2026-10-08 | CL21 | Completed
J1238 | 2026-10-09 | CL21 | Completed
J1238 | 2026-10-12 | CL21 | Completed
J1238 | 2026-10-15 | CL21 | Completed
J1238 | 2026-10-16 | CL21 | Completed
J1238 | 2026-10-19 | CL21 | Completed
J1238 | 2026-10-22 | CL21 | Completed
J1238 | 2026-10-23 | CL21 | Completed
J1238 | 2026-10-26 | CL21 | Completed
J1238 | 2026-10-29 | CL21 | Completed
J1238 | 2026-10-30 | CL21 | Completed
J1239 | 2026-08-04 | CL05 | Completed
J1239 | 2026-08-05 | CL05 | Completed
J1239 | 2026-08-06 | CL05 | Completed
J1239 | 2026-08-11 | CL05 | Completed
J1239 | 2026-08-12 | CL05 | Completed
J1239 | 2026-08-13 | CL05 | Completed
J1239 | 2026-08-18 | CL05 | Completed
J1239 | 2026-08-19 | CL05 | Completed
J1239 | 2026-08-20 | CL05 | Completed
J1239 | 2026-08-25 | CL05 | Completed
J1239 | 2026-08-26 | CL05 | Completed
J1239 | 2026-08-27 | CL05 | Completed
J1239 | 2026-09-01 | CL05 | Completed
J1239 | 2026-09-02 | CL05 | Completed
J1239 | 2026-09-03 | CL05 | Completed
J1239 | 2026-09-08 | CL05 | Completed
J1239 | 2026-09-09 | CL05 | Completed
J1239 | 2026-09-10 | CL05 | Completed
J1239 | 2026-09-15 | CL05 | Completed
J1239 | 2026-09-16 | CL05 | Completed
J1239 | 2026-09-17 | CL05 | Completed
J1239 | 2026-09-22 | CL05 | Completed
J1239 | 2026-09-23 | CL05 | Completed
J1239 | 2026-09-24 | CL05 | Completed
J1239 | 2026-09-29 | CL05 | Completed
J1239 | 2026-09-30 | CL05 | Completed
J1239 | 2026-10-01 | CL05 | Completed
J1239 | 2026-10-06 | CL05 | Completed
J1239 | 2026-10-07 | CL05 | Completed
J1239 | 2026-10-08 | CL05 | Completed
J1239 | 2026-10-13 | CL05 | Completed
J1239 | 2026-10-14 | CL05 | Completed
J1239 | 2026-10-15 | CL05 | Completed
J1239 | 2026-10-20 | CL05 | Completed
J1239 | 2026-10-21 | CL05 | Completed
J1239 | 2026-10-22 | CL05 | Completed
J1239 | 2026-10-27 | CL05 | Completed
J1239 | 2026-10-28 | CL05 | Completed
J1239 | 2026-10-29 | CL05 | Completed
J1240 | 2026-08-05 | CL26 | Completed
J1240 | 2026-08-06 | CL26 | Completed
J1240 | 2026-08-12 | CL26 | Completed
J1240 | 2026-08-13 | CL26 | Completed
J1240 | 2026-08-19 | CL26 | Completed
J1240 | 2026-08-20 | CL26 | Completed
J1240 | 2026-08-26 | CL26 | Completed
J1240 | 2026-08-27 | CL26 | Completed
J1240 | 2026-09-02 | CL26 | Completed
J1240 | 2026-09-03 | CL26 | Completed
J1240 | 2026-09-09 | CL26 | Completed
J1240 | 2026-09-10 | CL26 | Completed
J1240 | 2026-09-16 | CL26 | Completed
J1240 | 2026-09-17 | CL26 | Completed
J1240 | 2026-09-23 | CL26 | Completed
J1240 | 2026-09-24 | CL26 | Completed
J1240 | 2026-09-30 | CL26 | Completed
J1240 | 2026-10-01 | CL26 | Completed
J1240 | 2026-10-07 | CL26 | Completed
J1240 | 2026-10-08 | CL26 | Completed
J1240 | 2026-10-14 | CL26 | Completed
J1240 | 2026-10-15 | CL26 | Completed
J1240 | 2026-10-21 | CL26 | Completed
J1240 | 2026-10-22 | CL26 | Completed
J1240 | 2026-10-28 | CL26 | Completed
J1240 | 2026-10-29 | CL26 | Completed
J1241 | 2026-08-17 | CL54 | Completed
J1241 | 2026-09-14 | CL54 | Completed
J1241 | 2026-10-12 | CL54 | Completed
J1242 | 2026-08-04 | CL54 | Completed
J1242 | 2026-09-01 | CL54 | Completed
J1242 | 2026-10-06 | CL54 | Completed
J1243 | 2026-08-03 | CL32 | Completed
J1243 | 2026-08-04 | CL32 | Completed
J1243 | 2026-08-10 | CL32 | Completed
J1243 | 2026-08-11 | CL32 | Completed
J1243 | 2026-08-17 | CL32 | Completed
J1243 | 2026-08-18 | CL32 | Completed
J1243 | 2026-08-24 | CL32 | Completed
J1243 | 2026-08-25 | CL32 | Completed
J1243 | 2026-08-31 | CL32 | Completed
J1243 | 2026-09-01 | CL32 | Completed
J1243 | 2026-09-07 | CL32 | Completed
J1243 | 2026-09-08 | CL32 | Completed
J1243 | 2026-09-14 | CL32 | Completed
J1243 | 2026-09-15 | CL32 | Completed
J1243 | 2026-09-21 | CL32 | Completed
J1243 | 2026-09-22 | CL32 | Completed
J1243 | 2026-09-28 | CL32 | Completed
J1243 | 2026-09-29 | CL32 | Completed
J1243 | 2026-10-05 | CL32 | Completed
J1243 | 2026-10-06 | CL32 | Completed
J1243 | 2026-10-12 | CL32 | Completed
J1243 | 2026-10-13 | CL32 | Completed
J1243 | 2026-10-19 | CL32 | Completed
J1243 | 2026-10-20 | CL32 | Skipped
J1243 | 2026-10-26 | CL32 | Completed
J1243 | 2026-10-27 | CL32 | Completed
J1244 | 2026-08-04 | CL28 | Completed
J1244 | 2026-08-07 | CL28 | Completed
J1244 | 2026-08-11 | CL28 | Completed
J1244 | 2026-08-14 | CL28 | Completed
J1244 | 2026-08-18 | CL28 | Completed
J1244 | 2026-08-21 | CL28 | Completed
J1244 | 2026-08-25 | CL28 | Completed
J1244 | 2026-08-28 | CL28 | Completed
J1244 | 2026-09-01 | CL28 | Completed
J1244 | 2026-09-04 | CL28 | Completed
J1244 | 2026-09-08 | CL28 | Completed
J1244 | 2026-09-11 | CL28 | Completed
J1244 | 2026-09-15 | CL28 | Completed
J1244 | 2026-09-18 | CL28 | Completed
J1244 | 2026-09-22 | CL28 | Completed
J1244 | 2026-09-25 | CL28 | Completed
J1244 | 2026-09-29 | CL28 | Completed
J1244 | 2026-10-02 | CL28 | Completed
J1244 | 2026-10-06 | CL28 | Completed
J1244 | 2026-10-09 | CL28 | Completed
J1244 | 2026-10-13 | CL28 | Completed
J1244 | 2026-10-16 | CL28 | Completed
J1244 | 2026-10-20 | CL28 | Completed
J1244 | 2026-10-23 | CL28 | Completed
J1244 | 2026-10-27 | CL28 | Completed
J1244 | 2026-10-30 | CL28 | Completed
J1245 | 2026-08-03 | CL12 | Completed
J1245 | 2026-08-04 | CL12 | Completed
J1245 | 2026-08-05 | CL12 | Completed
J1245 | 2026-08-06 | CL12 | Completed
J1245 | 2026-08-07 | CL12 | Completed
J1245 | 2026-08-10 | CL12 | Completed
J1245 | 2026-08-11 | CL12 | Completed
J1245 | 2026-08-12 | CL12 | Completed
J1245 | 2026-08-13 | CL12 | Completed
J1245 | 2026-08-14 | CL12 | Completed
J1245 | 2026-08-17 | CL12 | Completed
J1245 | 2026-08-18 | CL12 | Completed
J1245 | 2026-08-19 | CL12 | Completed
J1245 | 2026-08-20 | CL12 | Completed
J1245 | 2026-08-21 | CL12 | Completed
J1245 | 2026-08-24 | CL12 | Completed
J1245 | 2026-08-25 | CL12 | Completed
J1245 | 2026-08-26 | CL12 | Completed
J1245 | 2026-08-27 | CL12 | Completed
J1245 | 2026-08-28 | CL12 | Completed
J1245 | 2026-08-31 | CL12 | Completed
J1245 | 2026-09-01 | CL12 | Completed
J1245 | 2026-09-02 | CL12 | Completed
J1245 | 2026-09-03 | CL12 | Completed
J1245 | 2026-09-04 | CL12 | Completed
J1245 | 2026-09-07 | CL12 | Completed
J1245 | 2026-09-08 | CL12 | Completed
J1245 | 2026-09-09 | CL12 | Completed
J1245 | 2026-09-10 | CL12 | Completed
J1245 | 2026-09-11 | CL12 | Completed
J1245 | 2026-09-14 | CL12 | Completed
J1245 | 2026-09-15 | CL12 | Completed
J1245 | 2026-09-16 | CL12 | Completed
J1245 | 2026-09-17 | CL12 | Completed
J1245 | 2026-09-18 | CL12 | Completed
J1245 | 2026-09-21 | CL12 | Completed
J1245 | 2026-09-22 | CL12 | Completed
J1245 | 2026-09-23 | CL12 | Completed
J1245 | 2026-09-24 | CL12 | Completed
J1245 | 2026-09-25 | CL12 | Completed
J1245 | 2026-09-28 | CL12 | Completed
J1245 | 2026-09-29 | CL12 | Completed
J1245 | 2026-09-30 | CL12 | Completed
J1245 | 2026-10-01 | CL12 | Completed
J1245 | 2026-10-02 | CL12 | Completed
J1245 | 2026-10-05 | CL12 | Completed
J1245 | 2026-10-06 | CL12 | Completed
J1245 | 2026-10-07 | CL12 | Completed
J1245 | 2026-10-08 | CL12 | Completed
J1245 | 2026-10-09 | CL12 | Completed
J1245 | 2026-10-12 | CL12 | Completed
J1245 | 2026-10-13 | CL12 | Completed
J1245 | 2026-10-14 | CL12 | Completed
J1245 | 2026-10-15 | CL12 | Completed
J1245 | 2026-10-16 | CL12 | Completed
J1245 | 2026-10-19 | CL12 | Completed
J1245 | 2026-10-20 | CL12 | Completed
J1245 | 2026-10-21 | CL12 | Completed
J1245 | 2026-10-22 | CL12 | Completed
J1245 | 2026-10-23 | CL12 | Completed
J1245 | 2026-10-26 | CL12 | Completed
J1245 | 2026-10-27 | CL12 | Skipped
J1245 | 2026-10-28 | CL12 | Completed
J1245 | 2026-10-29 | CL12 | Completed
J1245 | 2026-10-30 | CL12 | Completed
J1246 | 2026-08-03 | CL43 | Completed
J1246 | 2026-08-05 | CL43 | Completed
J1246 | 2026-08-10 | CL43 | Completed
J1246 | 2026-08-12 | CL43 | Completed
J1246 | 2026-08-17 | CL43 | Completed
J1246 | 2026-08-19 | CL43 | Completed
J1246 | 2026-08-24 | CL43 | Completed
J1246 | 2026-08-26 | CL43 | Completed
J1246 | 2026-08-31 | CL43 | Completed
J1246 | 2026-09-02 | CL43 | Completed
J1246 | 2026-09-07 | CL43 | Completed
J1246 | 2026-09-09 | CL43 | Completed
J1246 | 2026-09-14 | CL43 | Completed
J1246 | 2026-09-16 | CL43 | Completed
J1246 | 2026-09-21 | CL43 | Completed
J1246 | 2026-09-23 | CL43 | Completed
J1246 | 2026-09-28 | CL43 | Completed
J1246 | 2026-09-30 | CL43 | Completed
J1246 | 2026-10-05 | CL43 | Completed
J1246 | 2026-10-07 | CL43 | Completed
J1246 | 2026-10-12 | CL43 | Completed
J1246 | 2026-10-14 | CL43 | Completed
J1246 | 2026-10-19 | CL43 | Completed
J1246 | 2026-10-21 | CL43 | Completed
J1246 | 2026-10-26 | CL43 | Completed
J1246 | 2026-10-28 | CL43 | Completed
J1247 | 2026-08-07 | CL17 | Completed
J1247 | 2026-08-14 | CL17 | Completed
J1247 | 2026-08-21 | CL17 | Completed
J1247 | 2026-08-28 | CL17 | Completed
J1247 | 2026-09-04 | CL17 | Completed
J1247 | 2026-09-11 | CL17 | Completed
J1247 | 2026-09-18 | CL17 | Completed
J1247 | 2026-09-25 | CL17 | Completed
J1247 | 2026-10-02 | CL17 | Completed
J1247 | 2026-10-09 | CL17 | Completed
J1247 | 2026-10-16 | CL17 | Completed
J1247 | 2026-10-23 | CL17 | Completed
J1247 | 2026-10-30 | CL17 | Completed
J1248 | 2026-08-06 | CL24 | Completed
J1248 | 2026-08-13 | CL24 | Completed
J1248 | 2026-08-20 | CL24 | Completed
J1248 | 2026-08-27 | CL24 | Completed
J1248 | 2026-09-03 | CL24 | Completed
J1248 | 2026-09-10 | CL24 | Completed
J1248 | 2026-09-17 | CL24 | Completed
J1248 | 2026-09-24 | CL24 | Skipped
J1248 | 2026-10-01 | CL24 | Completed
J1248 | 2026-10-08 | CL24 | Completed
J1248 | 2026-10-15 | CL24 | Completed
J1248 | 2026-10-22 | CL24 | Completed
J1248 | 2026-10-29 | CL24 | Completed
J1249 | 2026-08-20 | CL54 | Completed
J1249 | 2026-09-17 | CL54 | Completed
J1249 | 2026-10-15 | CL54 | Completed
J1250 | 2026-08-03 | CL31 | Completed
J1250 | 2026-08-10 | CL31 | Completed
J1250 | 2026-08-17 | CL31 | Completed
J1250 | 2026-08-24 | CL31 | Completed
J1250 | 2026-08-31 | CL31 | Completed
J1250 | 2026-09-07 | CL31 | Completed
J1250 | 2026-09-14 | CL31 | Completed
J1250 | 2026-09-21 | CL31 | Completed
J1250 | 2026-09-28 | CL31 | Skipped
J1250 | 2026-10-05 | CL31 | Completed
J1250 | 2026-10-12 | CL31 | Completed
J1250 | 2026-10-19 | CL31 | Completed
J1250 | 2026-10-26 | CL31 | Completed
J1251 | 2026-08-06 | CL20 | Completed
J1251 | 2026-08-07 | CL20 | Completed
J1251 | 2026-08-13 | CL20 | Completed
J1251 | 2026-08-14 | CL20 | Completed
J1251 | 2026-08-20 | CL20 | Completed
J1251 | 2026-08-21 | CL20 | Completed
J1251 | 2026-08-27 | CL20 | Completed
J1251 | 2026-08-28 | CL20 | Completed
J1251 | 2026-09-03 | CL20 | Completed
J1251 | 2026-09-04 | CL20 | Completed
J1251 | 2026-09-10 | CL20 | Completed
J1251 | 2026-09-11 | CL20 | Completed
J1251 | 2026-09-17 | CL20 | Completed
J1251 | 2026-09-18 | CL20 | Completed
J1251 | 2026-09-24 | CL20 | Completed
J1251 | 2026-09-25 | CL20 | Completed
J1251 | 2026-10-01 | CL20 | Completed
J1251 | 2026-10-02 | CL20 | Completed
J1251 | 2026-10-08 | CL20 | Completed
J1251 | 2026-10-09 | CL20 | Completed
J1251 | 2026-10-15 | CL20 | Completed
J1251 | 2026-10-16 | CL20 | Completed
J1251 | 2026-10-22 | CL20 | Completed
J1251 | 2026-10-23 | CL20 | Completed
J1251 | 2026-10-29 | CL20 | Completed
J1251 | 2026-10-30 | CL20 | Completed
J1252 | 2026-08-03 | CL27 | Completed
J1252 | 2026-08-10 | CL27 | Completed
J1252 | 2026-08-17 | CL27 | Completed
J1252 | 2026-08-24 | CL27 | Completed
J1252 | 2026-08-31 | CL27 | Completed
J1252 | 2026-09-07 | CL27 | Completed
J1252 | 2026-09-14 | CL27 | Completed
J1252 | 2026-09-21 | CL27 | Completed
J1252 | 2026-09-28 | CL27 | Completed
J1252 | 2026-10-05 | CL27 | Completed
J1252 | 2026-10-12 | CL27 | Completed
J1252 | 2026-10-19 | CL27 | Completed
J1252 | 2026-10-26 | CL27 | Completed
J1253 | 2026-08-11 | CL53 | Completed
J1253 | 2026-09-08 | CL53 | Completed
J1253 | 2026-10-06 | CL53 | Completed
J1254 | 2026-08-03 | CL35 | Completed
J1254 | 2026-08-04 | CL35 | Completed
J1254 | 2026-08-10 | CL35 | Completed
J1254 | 2026-08-11 | CL35 | Completed
J1254 | 2026-08-17 | CL35 | Completed
J1254 | 2026-08-18 | CL35 | Completed
J1254 | 2026-08-24 | CL35 | Skipped
J1254 | 2026-08-25 | CL35 | Completed
J1254 | 2026-08-31 | CL35 | Completed
J1254 | 2026-09-01 | CL35 | Completed
J1254 | 2026-09-07 | CL35 | Completed
J1254 | 2026-09-08 | CL35 | Completed
J1254 | 2026-09-14 | CL35 | Completed
J1254 | 2026-09-15 | CL35 | Completed
J1254 | 2026-09-21 | CL35 | Completed
J1254 | 2026-09-22 | CL35 | Completed
J1254 | 2026-09-28 | CL35 | Completed
J1254 | 2026-09-29 | CL35 | Completed
J1254 | 2026-10-05 | CL35 | Completed
J1254 | 2026-10-06 | CL35 | Completed
J1254 | 2026-10-12 | CL35 | Completed
J1254 | 2026-10-13 | CL35 | Completed
J1254 | 2026-10-19 | CL35 | Completed
J1254 | 2026-10-20 | CL35 | Completed
J1254 | 2026-10-26 | CL35 | Completed
J1254 | 2026-10-27 | CL35 | Completed
J1255 | 2026-08-04 | CL31 | Completed
J1255 | 2026-08-05 | CL31 | Completed
J1255 | 2026-08-11 | CL31 | Completed
J1255 | 2026-08-12 | CL31 | Completed
J1255 | 2026-08-18 | CL31 | Completed
J1255 | 2026-08-19 | CL31 | Completed
J1255 | 2026-08-25 | CL31 | Completed
J1255 | 2026-08-26 | CL31 | Completed
J1255 | 2026-09-01 | CL31 | Completed
J1255 | 2026-09-02 | CL31 | Completed
J1255 | 2026-09-08 | CL31 | Completed
J1255 | 2026-09-09 | CL31 | Completed
J1255 | 2026-09-15 | CL31 | Completed
J1255 | 2026-09-16 | CL31 | Completed
J1255 | 2026-09-22 | CL31 | Completed
J1255 | 2026-09-23 | CL31 | Completed
J1255 | 2026-09-29 | CL31 | Completed
J1255 | 2026-09-30 | CL31 | Completed
J1255 | 2026-10-06 | CL31 | Completed
J1255 | 2026-10-07 | CL31 | Completed
J1255 | 2026-10-13 | CL31 | Completed
J1255 | 2026-10-14 | CL31 | Completed
J1255 | 2026-10-20 | CL31 | Completed
J1255 | 2026-10-21 | CL31 | Completed
J1255 | 2026-10-27 | CL31 | Completed
J1255 | 2026-10-28 | CL31 | Completed
J1256 | 2026-08-03 | CL18 | Completed
J1256 | 2026-08-04 | CL18 | Completed
J1256 | 2026-08-05 | CL18 | Completed
J1256 | 2026-08-06 | CL18 | Completed
J1256 | 2026-08-07 | CL18 | Completed
J1256 | 2026-08-10 | CL18 | Completed
J1256 | 2026-08-11 | CL18 | Completed
J1256 | 2026-08-12 | CL18 | Completed
J1256 | 2026-08-13 | CL18 | Completed
J1256 | 2026-08-14 | CL18 | Completed
J1256 | 2026-08-17 | CL18 | Completed
J1256 | 2026-08-18 | CL18 | Completed
J1256 | 2026-08-19 | CL18 | Skipped
J1256 | 2026-08-20 | CL18 | Completed
J1256 | 2026-08-21 | CL18 | Completed
J1256 | 2026-08-24 | CL18 | Completed
J1256 | 2026-08-25 | CL18 | Completed
J1256 | 2026-08-26 | CL18 | Skipped
J1256 | 2026-08-27 | CL18 | Completed
J1256 | 2026-08-28 | CL18 | Completed
J1256 | 2026-08-31 | CL18 | Completed
J1256 | 2026-09-01 | CL18 | Completed
J1256 | 2026-09-02 | CL18 | Completed
J1256 | 2026-09-03 | CL18 | Completed
J1256 | 2026-09-04 | CL18 | Completed
J1256 | 2026-09-07 | CL18 | Completed
J1256 | 2026-09-08 | CL18 | Completed
J1256 | 2026-09-09 | CL18 | Completed
J1256 | 2026-09-10 | CL18 | Completed
J1256 | 2026-09-11 | CL18 | Completed
J1256 | 2026-09-14 | CL18 | Completed
J1256 | 2026-09-15 | CL18 | Completed
J1256 | 2026-09-16 | CL18 | Completed
J1256 | 2026-09-17 | CL18 | Completed
J1256 | 2026-09-18 | CL18 | Completed
J1256 | 2026-09-21 | CL18 | Completed
J1256 | 2026-09-22 | CL18 | Completed
J1256 | 2026-09-23 | CL18 | Completed
J1256 | 2026-09-24 | CL18 | Completed
J1256 | 2026-09-25 | CL18 | Completed
J1256 | 2026-09-28 | CL18 | Completed
J1256 | 2026-09-29 | CL18 | Completed
J1256 | 2026-09-30 | CL18 | Completed
J1256 | 2026-10-01 | CL18 | Completed
J1256 | 2026-10-02 | CL18 | Completed
J1256 | 2026-10-05 | CL18 | Skipped
J1256 | 2026-10-06 | CL18 | Completed
J1256 | 2026-10-07 | CL18 | Completed
J1256 | 2026-10-08 | CL18 | Completed
J1256 | 2026-10-09 | CL18 | Completed
J1256 | 2026-10-12 | CL18 | Completed
J1256 | 2026-10-13 | CL18 | Completed
J1256 | 2026-10-14 | CL18 | Completed
J1256 | 2026-10-15 | CL18 | Completed
J1256 | 2026-10-16 | CL18 | Completed
J1256 | 2026-10-19 | CL18 | Completed
J1256 | 2026-10-20 | CL18 | Completed
J1256 | 2026-10-21 | CL18 | Completed
J1256 | 2026-10-22 | CL18 | Completed
J1256 | 2026-10-23 | CL18 | Completed
J1256 | 2026-10-26 | CL18 | Completed
J1256 | 2026-10-27 | CL18 | Completed
J1256 | 2026-10-28 | CL18 | Completed
J1256 | 2026-10-29 | CL18 | Completed
J1256 | 2026-10-30 | CL18 | Completed
J1257 | 2026-08-03 | CL22 | Completed
J1257 | 2026-08-10 | CL22 | Completed
J1257 | 2026-08-17 | CL22 | Completed
J1257 | 2026-08-24 | CL22 | Completed
J1257 | 2026-08-31 | CL22 | Completed
J1257 | 2026-09-07 | CL22 | Completed
J1257 | 2026-09-14 | CL22 | Completed
J1257 | 2026-09-21 | CL22 | Completed
J1257 | 2026-09-28 | CL22 | Completed
J1257 | 2026-10-05 | CL22 | Completed
J1257 | 2026-10-12 | CL22 | Completed
J1257 | 2026-10-19 | CL22 | Completed
J1257 | 2026-10-26 | CL22 | Completed
J1258 | 2026-08-03 | CL34 | Completed
J1258 | 2026-08-05 | CL34 | Completed
J1258 | 2026-08-10 | CL34 | Completed
J1258 | 2026-08-12 | CL34 | Completed
J1258 | 2026-08-17 | CL34 | Completed
J1258 | 2026-08-19 | CL34 | Completed
J1258 | 2026-08-24 | CL34 | Completed
J1258 | 2026-08-26 | CL34 | Completed
J1258 | 2026-08-31 | CL34 | Completed
J1258 | 2026-09-02 | CL34 | Completed
J1258 | 2026-09-07 | CL34 | Completed
J1258 | 2026-09-09 | CL34 | Completed
J1258 | 2026-09-14 | CL34 | Completed
J1258 | 2026-09-16 | CL34 | Completed
J1258 | 2026-09-21 | CL34 | Completed
J1258 | 2026-09-23 | CL34 | Completed
J1258 | 2026-09-28 | CL34 | Completed
J1258 | 2026-09-30 | CL34 | Completed
J1258 | 2026-10-05 | CL34 | Completed
J1258 | 2026-10-07 | CL34 | Completed
J1258 | 2026-10-12 | CL34 | Completed
J1258 | 2026-10-14 | CL34 | Completed
J1258 | 2026-10-19 | CL34 | Completed
J1258 | 2026-10-21 | CL34 | Completed
J1258 | 2026-10-26 | CL34 | Completed
J1258 | 2026-10-28 | CL34 | Completed
J1259 | 2026-08-24 | CL53 | Completed
J1259 | 2026-09-21 | CL53 | Completed
J1259 | 2026-10-19 | CL53 | Completed
J1260 | 2026-08-07 | CL54 | Completed
J1260 | 2026-09-04 | CL54 | Completed
J1260 | 2026-10-02 | CL54 | Completed
J1261 | 2026-08-04 | CL36 | Completed
J1261 | 2026-08-07 | CL36 | Completed
J1261 | 2026-08-11 | CL36 | Completed
J1261 | 2026-08-14 | CL36 | Completed
J1261 | 2026-08-18 | CL36 | Completed
J1261 | 2026-08-21 | CL36 | Completed
J1261 | 2026-08-25 | CL36 | Completed
J1261 | 2026-08-28 | CL36 | Completed
J1261 | 2026-09-01 | CL36 | Completed
J1261 | 2026-09-04 | CL36 | Completed
J1261 | 2026-09-08 | CL36 | Completed
J1261 | 2026-09-11 | CL36 | Completed
J1261 | 2026-09-15 | CL36 | Completed
J1261 | 2026-09-18 | CL36 | Completed
J1261 | 2026-09-22 | CL36 | Completed
J1261 | 2026-09-25 | CL36 | Completed
J1261 | 2026-09-29 | CL36 | Completed
J1261 | 2026-10-02 | CL36 | Completed
J1261 | 2026-10-06 | CL36 | Completed
J1261 | 2026-10-09 | CL36 | Completed
J1261 | 2026-10-13 | CL36 | Completed
J1261 | 2026-10-16 | CL36 | Completed
J1261 | 2026-10-20 | CL36 | Completed
J1261 | 2026-10-23 | CL36 | Completed
J1261 | 2026-10-27 | CL36 | Completed
J1261 | 2026-10-30 | CL36 | Completed
J1262 | 2026-08-04 | CL09 | Completed
J1262 | 2026-08-05 | CL09 | Completed
J1262 | 2026-08-11 | CL09 | Completed
J1262 | 2026-08-12 | CL09 | Completed
J1262 | 2026-08-18 | CL09 | Completed
J1262 | 2026-08-19 | CL09 | Completed
J1262 | 2026-08-25 | CL09 | Completed
J1262 | 2026-08-26 | CL09 | Completed
J1262 | 2026-09-01 | CL09 | Completed
J1262 | 2026-09-02 | CL09 | Completed
J1262 | 2026-09-08 | CL09 | Completed
J1262 | 2026-09-09 | CL09 | Completed
J1262 | 2026-09-15 | CL09 | Completed
J1262 | 2026-09-16 | CL09 | Completed
J1262 | 2026-09-22 | CL09 | Completed
J1262 | 2026-09-23 | CL09 | Completed
J1262 | 2026-09-29 | CL09 | Completed
J1262 | 2026-09-30 | CL09 | Completed
J1262 | 2026-10-06 | CL09 | Completed
J1262 | 2026-10-07 | CL09 | Completed
J1262 | 2026-10-13 | CL09 | Completed
J1262 | 2026-10-14 | CL09 | Completed
J1262 | 2026-10-20 | CL09 | Completed
J1262 | 2026-10-21 | CL09 | Completed
J1262 | 2026-10-27 | CL09 | Completed
J1262 | 2026-10-28 | CL09 | Completed
J1263 | 2026-08-04 | CL46 | Completed
J1263 | 2026-08-06 | CL46 | Completed
J1263 | 2026-08-11 | CL46 | Completed
J1263 | 2026-08-13 | CL46 | Completed
J1263 | 2026-08-18 | CL46 | Completed
J1263 | 2026-08-20 | CL46 | Completed
J1263 | 2026-08-25 | CL46 | Completed
J1263 | 2026-08-27 | CL46 | Completed
J1263 | 2026-09-01 | CL46 | Completed
J1263 | 2026-09-03 | CL46 | Completed
J1263 | 2026-09-08 | CL46 | Completed
J1263 | 2026-09-10 | CL46 | Completed
J1263 | 2026-09-15 | CL46 | Completed
J1263 | 2026-09-17 | CL46 | Completed
J1263 | 2026-09-22 | CL46 | Completed
J1263 | 2026-09-24 | CL46 | Completed
J1263 | 2026-09-29 | CL46 | Completed
J1263 | 2026-10-01 | CL46 | Completed
J1263 | 2026-10-06 | CL46 | Completed
J1263 | 2026-10-08 | CL46 | Completed
J1263 | 2026-10-13 | CL46 | Completed
J1263 | 2026-10-15 | CL46 | Completed
J1263 | 2026-10-20 | CL46 | Completed
J1263 | 2026-10-22 | CL46 | Completed
J1263 | 2026-10-27 | CL46 | Completed
J1263 | 2026-10-29 | CL46 | Completed
J1264 | 2026-08-03 | CL10 | Completed
J1264 | 2026-08-04 | CL10 | Completed
J1264 | 2026-08-05 | CL10 | Completed
J1264 | 2026-08-06 | CL10 | Completed
J1264 | 2026-08-07 | CL10 | Completed
J1264 | 2026-08-10 | CL10 | Completed
J1264 | 2026-08-11 | CL10 | Completed
J1264 | 2026-08-12 | CL10 | Completed
J1264 | 2026-08-13 | CL10 | Completed
J1264 | 2026-08-14 | CL10 | Completed
J1264 | 2026-08-17 | CL10 | Completed
J1264 | 2026-08-18 | CL10 | Completed
J1264 | 2026-08-19 | CL10 | Completed
J1264 | 2026-08-20 | CL10 | Completed
J1264 | 2026-08-21 | CL10 | Completed
J1264 | 2026-08-24 | CL10 | Completed
J1264 | 2026-08-25 | CL10 | Completed
J1264 | 2026-08-26 | CL10 | Completed
J1264 | 2026-08-27 | CL10 | Completed
J1264 | 2026-08-28 | CL10 | Completed
J1264 | 2026-08-31 | CL10 | Skipped
J1264 | 2026-09-01 | CL10 | Completed
J1264 | 2026-09-02 | CL10 | Completed
J1264 | 2026-09-03 | CL10 | Completed
J1264 | 2026-09-04 | CL10 | Completed
J1264 | 2026-09-07 | CL10 | Completed
J1264 | 2026-09-08 | CL10 | Completed
J1264 | 2026-09-09 | CL10 | Completed
J1264 | 2026-09-10 | CL10 | Completed
J1264 | 2026-09-11 | CL10 | Completed
J1264 | 2026-09-14 | CL10 | Completed
J1264 | 2026-09-15 | CL10 | Completed
J1264 | 2026-09-16 | CL10 | Completed
J1264 | 2026-09-17 | CL10 | Completed
J1264 | 2026-09-18 | CL10 | Completed
J1264 | 2026-09-21 | CL10 | Completed
J1264 | 2026-09-22 | CL10 | Completed
J1264 | 2026-09-23 | CL10 | Completed
J1264 | 2026-09-24 | CL10 | Completed
J1264 | 2026-09-25 | CL10 | Completed
J1264 | 2026-09-28 | CL10 | Completed
J1264 | 2026-09-29 | CL10 | Completed
J1264 | 2026-09-30 | CL10 | Completed
J1264 | 2026-10-01 | CL10 | Completed
J1264 | 2026-10-02 | CL10 | Completed
J1264 | 2026-10-05 | CL10 | Completed
J1264 | 2026-10-06 | CL10 | Completed
J1264 | 2026-10-07 | CL10 | Completed
J1264 | 2026-10-08 | CL10 | Completed
J1264 | 2026-10-09 | CL10 | Completed
J1264 | 2026-10-12 | CL10 | Completed
J1264 | 2026-10-13 | CL10 | Completed
J1264 | 2026-10-14 | CL10 | Completed
J1264 | 2026-10-15 | CL10 | Completed
J1264 | 2026-10-16 | CL10 | Completed
J1264 | 2026-10-19 | CL10 | Completed
J1264 | 2026-10-20 | CL10 | Completed
J1264 | 2026-10-21 | CL10 | Completed
J1264 | 2026-10-22 | CL10 | Completed
J1264 | 2026-10-23 | CL10 | Completed
J1264 | 2026-10-26 | CL10 | Completed
J1264 | 2026-10-27 | CL10 | Completed
J1264 | 2026-10-28 | CL10 | Completed
J1264 | 2026-10-29 | CL10 | Completed
J1264 | 2026-10-30 | CL10 | Completed
J1265 | 2026-08-03 | CL46 | Completed
J1265 | 2026-08-05 | CL46 | Completed
J1265 | 2026-08-10 | CL46 | Completed
J1265 | 2026-08-12 | CL46 | Completed
J1265 | 2026-08-17 | CL46 | Completed
J1265 | 2026-08-19 | CL46 | Completed
J1265 | 2026-08-24 | CL46 | Completed
J1265 | 2026-08-26 | CL46 | Completed
J1265 | 2026-08-31 | CL46 | Completed
J1265 | 2026-09-02 | CL46 | Completed
J1265 | 2026-09-07 | CL46 | Completed
J1265 | 2026-09-09 | CL46 | Completed
J1265 | 2026-09-14 | CL46 | Completed
J1265 | 2026-09-16 | CL46 | Completed
J1265 | 2026-09-21 | CL46 | Completed
J1265 | 2026-09-23 | CL46 | Completed
J1265 | 2026-09-28 | CL46 | Completed
J1265 | 2026-09-30 | CL46 | Completed
J1265 | 2026-10-05 | CL46 | Completed
J1265 | 2026-10-07 | CL46 | Completed
J1265 | 2026-10-12 | CL46 | Completed
J1265 | 2026-10-14 | CL46 | Completed
J1265 | 2026-10-19 | CL46 | Completed
J1265 | 2026-10-21 | CL46 | Completed
J1265 | 2026-10-26 | CL46 | Completed
J1265 | 2026-10-28 | CL46 | Completed
J1266 | 2026-08-03 | CL26 | Completed
J1266 | 2026-08-04 | CL26 | Completed
J1266 | 2026-08-05 | CL26 | Completed
J1266 | 2026-08-06 | CL26 | Completed
J1266 | 2026-08-07 | CL26 | Completed
J1266 | 2026-08-10 | CL26 | Completed
J1266 | 2026-08-11 | CL26 | Completed
J1266 | 2026-08-12 | CL26 | Completed
J1266 | 2026-08-13 | CL26 | Completed
J1266 | 2026-08-14 | CL26 | Completed
J1266 | 2026-08-17 | CL26 | Completed
J1266 | 2026-08-18 | CL26 | Completed
J1266 | 2026-08-19 | CL26 | Completed
J1266 | 2026-08-20 | CL26 | Completed
J1266 | 2026-08-21 | CL26 | Completed
J1266 | 2026-08-24 | CL26 | Completed
J1266 | 2026-08-25 | CL26 | Completed
J1266 | 2026-08-26 | CL26 | Completed
J1266 | 2026-08-27 | CL26 | Completed
J1266 | 2026-08-28 | CL26 | Completed
J1266 | 2026-08-31 | CL26 | Completed
J1266 | 2026-09-01 | CL26 | Completed
J1266 | 2026-09-02 | CL26 | Completed
J1266 | 2026-09-03 | CL26 | Completed
J1266 | 2026-09-04 | CL26 | Completed
J1266 | 2026-09-07 | CL26 | Completed
J1266 | 2026-09-08 | CL26 | Completed
J1266 | 2026-09-09 | CL26 | Completed
J1266 | 2026-09-10 | CL26 | Completed
J1266 | 2026-09-11 | CL26 | Completed
J1266 | 2026-09-14 | CL26 | Completed
J1266 | 2026-09-15 | CL26 | Completed
J1266 | 2026-09-16 | CL26 | Completed
J1266 | 2026-09-17 | CL26 | Completed
J1266 | 2026-09-18 | CL26 | Completed
J1266 | 2026-09-21 | CL26 | Completed
J1266 | 2026-09-22 | CL26 | Completed
J1266 | 2026-09-23 | CL26 | Completed
J1266 | 2026-09-24 | CL26 | Completed
J1266 | 2026-09-25 | CL26 | Completed
J1266 | 2026-09-28 | CL26 | Completed
J1266 | 2026-09-29 | CL26 | Completed
J1266 | 2026-09-30 | CL26 | Completed
J1266 | 2026-10-01 | CL26 | Completed
J1266 | 2026-10-02 | CL26 | Completed
J1266 | 2026-10-05 | CL26 | Completed
J1266 | 2026-10-06 | CL26 | Completed
J1266 | 2026-10-07 | CL26 | Completed
J1266 | 2026-10-08 | CL26 | Skipped
J1266 | 2026-10-09 | CL26 | Completed
J1266 | 2026-10-12 | CL26 | Completed
J1266 | 2026-10-13 | CL26 | Completed
J1266 | 2026-10-14 | CL26 | Completed
J1266 | 2026-10-15 | CL26 | Completed
J1266 | 2026-10-16 | CL26 | Completed
J1266 | 2026-10-19 | CL26 | Completed
J1266 | 2026-10-20 | CL26 | Completed
J1266 | 2026-10-21 | CL26 | Completed
J1266 | 2026-10-22 | CL26 | Completed
J1266 | 2026-10-23 | CL26 | Completed
J1266 | 2026-10-26 | CL26 | Completed
J1266 | 2026-10-27 | CL26 | Completed
J1266 | 2026-10-28 | CL26 | Completed
J1266 | 2026-10-29 | CL26 | Completed
J1266 | 2026-10-30 | CL26 | Completed
J1267 | 2026-08-21 | CL57 | Completed
J1267 | 2026-09-18 | CL57 | Completed
J1267 | 2026-10-16 | CL57 | Completed
J1268 | 2026-08-03 | CL16 | Completed
J1268 | 2026-08-05 | CL16 | Completed
J1268 | 2026-08-07 | CL16 | Skipped
J1268 | 2026-08-10 | CL16 | Completed
J1268 | 2026-08-12 | CL16 | Completed
J1268 | 2026-08-14 | CL16 | Completed
J1268 | 2026-08-17 | CL16 | Completed
J1268 | 2026-08-19 | CL16 | Completed
J1268 | 2026-08-21 | CL16 | Completed
J1268 | 2026-08-24 | CL16 | Completed
J1268 | 2026-08-26 | CL16 | Completed
J1268 | 2026-08-28 | CL16 | Completed
J1268 | 2026-08-31 | CL16 | Completed
J1268 | 2026-09-02 | CL16 | Completed
J1268 | 2026-09-04 | CL16 | Completed
J1268 | 2026-09-07 | CL16 | Completed
J1268 | 2026-09-09 | CL16 | Completed
J1268 | 2026-09-11 | CL16 | Completed
J1268 | 2026-09-14 | CL16 | Completed
J1268 | 2026-09-16 | CL16 | Completed
J1268 | 2026-09-18 | CL16 | Completed
J1268 | 2026-09-21 | CL16 | Completed
J1268 | 2026-09-23 | CL16 | Completed
J1268 | 2026-09-25 | CL16 | Completed
J1268 | 2026-09-28 | CL16 | Completed
J1268 | 2026-09-30 | CL16 | Completed
J1268 | 2026-10-02 | CL16 | Completed
J1268 | 2026-10-05 | CL16 | Completed
J1268 | 2026-10-07 | CL16 | Completed
J1268 | 2026-10-09 | CL16 | Completed
J1268 | 2026-10-12 | CL16 | Completed
J1268 | 2026-10-14 | CL16 | Skipped
J1268 | 2026-10-16 | CL16 | Completed
J1268 | 2026-10-19 | CL16 | Completed
J1268 | 2026-10-21 | CL16 | Completed
J1268 | 2026-10-23 | CL16 | Completed
J1268 | 2026-10-26 | CL16 | Completed
J1268 | 2026-10-28 | CL16 | Completed
J1268 | 2026-10-30 | CL16 | Completed
J1269 | 2026-08-11 | CL57 | Completed
J1269 | 2026-09-08 | CL57 | Completed
J1269 | 2026-10-06 | CL57 | Completed
J1270 | 2026-08-03 | CL24 | Completed
J1270 | 2026-08-04 | CL24 | Completed
J1270 | 2026-08-05 | CL24 | Completed
J1270 | 2026-08-06 | CL24 | Completed
J1270 | 2026-08-07 | CL24 | Completed
J1270 | 2026-08-10 | CL24 | Completed
J1270 | 2026-08-11 | CL24 | Completed
J1270 | 2026-08-12 | CL24 | Completed
J1270 | 2026-08-13 | CL24 | Completed
J1270 | 2026-08-14 | CL24 | Completed
J1270 | 2026-08-17 | CL24 | Completed
J1270 | 2026-08-18 | CL24 | Completed
J1270 | 2026-08-19 | CL24 | Completed
J1270 | 2026-08-20 | CL24 | Completed
J1270 | 2026-08-21 | CL24 | Completed
J1270 | 2026-08-24 | CL24 | Completed
J1270 | 2026-08-25 | CL24 | Completed
J1270 | 2026-08-26 | CL24 | Completed
J1270 | 2026-08-27 | CL24 | Completed
J1270 | 2026-08-28 | CL24 | Completed
J1270 | 2026-08-31 | CL24 | Completed
J1270 | 2026-09-01 | CL24 | Completed
J1270 | 2026-09-02 | CL24 | Completed
J1270 | 2026-09-03 | CL24 | Completed
J1270 | 2026-09-04 | CL24 | Completed
J1270 | 2026-09-07 | CL24 | Completed
J1270 | 2026-09-08 | CL24 | Completed
J1270 | 2026-09-09 | CL24 | Completed
J1270 | 2026-09-10 | CL24 | Completed
J1270 | 2026-09-11 | CL24 | Completed
J1270 | 2026-09-14 | CL24 | Completed
J1270 | 2026-09-15 | CL24 | Completed
J1270 | 2026-09-16 | CL24 | Completed
J1270 | 2026-09-17 | CL24 | Completed
J1270 | 2026-09-18 | CL24 | Completed
J1270 | 2026-09-21 | CL24 | Completed
J1270 | 2026-09-22 | CL24 | Completed
J1270 | 2026-09-23 | CL24 | Completed
J1270 | 2026-09-24 | CL24 | Completed
J1270 | 2026-09-25 | CL24 | Completed
J1270 | 2026-09-28 | CL24 | Completed
J1270 | 2026-09-29 | CL24 | Completed
J1270 | 2026-09-30 | CL24 | Completed
J1270 | 2026-10-01 | CL24 | Completed
J1270 | 2026-10-02 | CL24 | Completed
J1270 | 2026-10-05 | CL24 | Completed
J1270 | 2026-10-06 | CL24 | Completed
J1270 | 2026-10-07 | CL24 | Completed
J1270 | 2026-10-08 | CL24 | Completed
J1270 | 2026-10-09 | CL24 | Completed
J1270 | 2026-10-12 | CL24 | Completed
J1270 | 2026-10-13 | CL24 | Completed
J1270 | 2026-10-14 | CL24 | Completed
J1270 | 2026-10-15 | CL24 | Completed
J1270 | 2026-10-16 | CL24 | Completed
J1270 | 2026-10-19 | CL24 | Completed
J1270 | 2026-10-20 | CL24 | Completed
J1270 | 2026-10-21 | CL24 | Completed
J1270 | 2026-10-22 | CL24 | Completed
J1270 | 2026-10-23 | CL24 | Completed
J1270 | 2026-10-26 | CL24 | Completed
J1270 | 2026-10-27 | CL24 | Completed
J1270 | 2026-10-28 | CL24 | Completed
J1270 | 2026-10-29 | CL24 | Completed
J1270 | 2026-10-30 | CL24 | Completed
J1271 | 2026-08-03 | CL27 | Completed
J1271 | 2026-08-04 | CL27 | Completed
J1271 | 2026-08-05 | CL27 | Completed
J1271 | 2026-08-06 | CL27 | Completed
J1271 | 2026-08-07 | CL27 | Completed
J1271 | 2026-08-10 | CL27 | Completed
J1271 | 2026-08-11 | CL27 | Completed
J1271 | 2026-08-12 | CL27 | Completed
J1271 | 2026-08-13 | CL27 | Completed
J1271 | 2026-08-14 | CL27 | Completed
J1271 | 2026-08-17 | CL27 | Completed
J1271 | 2026-08-18 | CL27 | Completed
J1271 | 2026-08-19 | CL27 | Completed
J1271 | 2026-08-20 | CL27 | Completed
J1271 | 2026-08-21 | CL27 | Completed
J1271 | 2026-08-24 | CL27 | Completed
J1271 | 2026-08-25 | CL27 | Completed
J1271 | 2026-08-26 | CL27 | Completed
J1271 | 2026-08-27 | CL27 | Completed
J1271 | 2026-08-28 | CL27 | Completed
J1271 | 2026-08-31 | CL27 | Completed
J1271 | 2026-09-01 | CL27 | Completed
J1271 | 2026-09-02 | CL27 | Completed
J1271 | 2026-09-03 | CL27 | Completed
J1271 | 2026-09-04 | CL27 | Completed
J1271 | 2026-09-07 | CL27 | Completed
J1271 | 2026-09-08 | CL27 | Completed
J1271 | 2026-09-09 | CL27 | Completed
J1271 | 2026-09-10 | CL27 | Completed
J1271 | 2026-09-11 | CL27 | Completed
J1271 | 2026-09-14 | CL27 | Completed
J1271 | 2026-09-15 | CL27 | Completed
J1271 | 2026-09-16 | CL27 | Completed
J1271 | 2026-09-17 | CL27 | Completed
J1271 | 2026-09-18 | CL27 | Completed
J1271 | 2026-09-21 | CL27 | Completed
J1271 | 2026-09-22 | CL27 | Completed
J1271 | 2026-09-23 | CL27 | Completed
J1271 | 2026-09-24 | CL27 | Completed
J1271 | 2026-09-25 | CL27 | Completed
J1271 | 2026-09-28 | CL27 | Completed
J1271 | 2026-09-29 | CL27 | Completed
J1271 | 2026-09-30 | CL27 | Completed
J1271 | 2026-10-01 | CL27 | Completed
J1271 | 2026-10-02 | CL27 | Completed
J1271 | 2026-10-05 | CL27 | Completed
J1271 | 2026-10-06 | CL27 | Completed
J1271 | 2026-10-07 | CL27 | Completed
J1271 | 2026-10-08 | CL27 | Completed
J1271 | 2026-10-09 | CL27 | Completed
J1271 | 2026-10-12 | CL27 | Completed
J1271 | 2026-10-13 | CL27 | Completed
J1271 | 2026-10-14 | CL27 | Completed
J1271 | 2026-10-15 | CL27 | Completed
J1271 | 2026-10-16 | CL27 | Completed
J1271 | 2026-10-19 | CL27 | Completed
J1271 | 2026-10-20 | CL27 | Completed
J1271 | 2026-10-21 | CL27 | Completed
J1271 | 2026-10-22 | CL27 | Completed
J1271 | 2026-10-23 | CL27 | Completed
J1271 | 2026-10-26 | CL27 | Completed
J1271 | 2026-10-27 | CL27 | Completed
J1271 | 2026-10-28 | CL27 | Completed
J1271 | 2026-10-29 | CL27 | Completed
J1271 | 2026-10-30 | CL27 | Completed
J1272 | 2026-08-05 | CL39 | Completed
J1272 | 2026-08-07 | CL39 | Completed
J1272 | 2026-08-12 | CL39 | Completed
J1272 | 2026-08-14 | CL39 | Completed
J1272 | 2026-08-19 | CL39 | Completed
J1272 | 2026-08-21 | CL39 | Completed
J1272 | 2026-08-26 | CL39 | Completed
J1272 | 2026-08-28 | CL39 | Completed
J1272 | 2026-09-02 | CL39 | Completed
J1272 | 2026-09-04 | CL39 | Completed
J1272 | 2026-09-09 | CL39 | Completed
J1272 | 2026-09-11 | CL39 | Completed
J1272 | 2026-09-16 | CL39 | Completed
J1272 | 2026-09-18 | CL39 | Completed
J1272 | 2026-09-23 | CL39 | Completed
J1272 | 2026-09-25 | CL39 | Completed
J1272 | 2026-09-30 | CL39 | Completed
J1272 | 2026-10-02 | CL39 | Completed
J1272 | 2026-10-07 | CL39 | Completed
J1272 | 2026-10-09 | CL39 | Completed
J1272 | 2026-10-14 | CL39 | Completed
J1272 | 2026-10-16 | CL39 | Completed
J1272 | 2026-10-21 | CL39 | Completed
J1272 | 2026-10-23 | CL39 | Skipped
J1272 | 2026-10-28 | CL39 | Completed
J1272 | 2026-10-30 | CL39 | Completed
J1273 | 2026-08-06 | CL57 | Completed
J1273 | 2026-09-03 | CL57 | Completed
J1273 | 2026-10-01 | CL57 | Completed
J1273 | 2026-10-29 | CL57 | Completed
J1274 | 2026-08-03 | CL22 | Completed
J1274 | 2026-08-05 | CL22 | Completed
J1274 | 2026-08-10 | CL22 | Skipped
J1274 | 2026-08-12 | CL22 | Completed
J1274 | 2026-08-17 | CL22 | Completed
J1274 | 2026-08-19 | CL22 | Completed
J1274 | 2026-08-24 | CL22 | Completed
J1274 | 2026-08-26 | CL22 | Completed
J1274 | 2026-08-31 | CL22 | Completed
J1274 | 2026-09-02 | CL22 | Completed
J1274 | 2026-09-07 | CL22 | Completed
J1274 | 2026-09-09 | CL22 | Completed
J1274 | 2026-09-14 | CL22 | Completed
J1274 | 2026-09-16 | CL22 | Completed
J1274 | 2026-09-21 | CL22 | Completed
J1274 | 2026-09-23 | CL22 | Completed
J1274 | 2026-09-28 | CL22 | Completed
J1274 | 2026-09-30 | CL22 | Completed
J1274 | 2026-10-05 | CL22 | Completed
J1274 | 2026-10-07 | CL22 | Completed
J1274 | 2026-10-12 | CL22 | Completed
J1274 | 2026-10-14 | CL22 | Completed
J1274 | 2026-10-19 | CL22 | Completed
J1274 | 2026-10-21 | CL22 | Completed
J1274 | 2026-10-26 | CL22 | Completed
J1274 | 2026-10-28 | CL22 | Completed
J1275 | 2026-08-03 | CL37 | Completed
J1275 | 2026-08-04 | CL37 | Completed
J1275 | 2026-08-06 | CL37 | Completed
J1275 | 2026-08-10 | CL37 | Completed
J1275 | 2026-08-11 | CL37 | Completed
J1275 | 2026-08-13 | CL37 | Completed
J1275 | 2026-08-17 | CL37 | Completed
J1275 | 2026-08-18 | CL37 | Completed
J1275 | 2026-08-20 | CL37 | Completed
J1275 | 2026-08-24 | CL37 | Completed
J1275 | 2026-08-25 | CL37 | Completed
J1275 | 2026-08-27 | CL37 | Completed
J1275 | 2026-08-31 | CL37 | Completed
J1275 | 2026-09-01 | CL37 | Completed
J1275 | 2026-09-03 | CL37 | Completed
J1275 | 2026-09-07 | CL37 | Completed
J1275 | 2026-09-08 | CL37 | Completed
J1275 | 2026-09-10 | CL37 | Completed
J1275 | 2026-09-14 | CL37 | Completed
J1275 | 2026-09-15 | CL37 | Completed
J1275 | 2026-09-17 | CL37 | Completed
J1275 | 2026-09-21 | CL37 | Completed
J1275 | 2026-09-22 | CL37 | Completed
J1275 | 2026-09-24 | CL37 | Completed
J1275 | 2026-09-28 | CL37 | Completed
J1275 | 2026-09-29 | CL37 | Completed
J1275 | 2026-10-01 | CL37 | Completed
J1275 | 2026-10-05 | CL37 | Completed
J1275 | 2026-10-06 | CL37 | Completed
J1275 | 2026-10-08 | CL37 | Completed
J1275 | 2026-10-12 | CL37 | Completed
J1275 | 2026-10-13 | CL37 | Completed
J1275 | 2026-10-15 | CL37 | Completed
J1275 | 2026-10-19 | CL37 | Completed
J1275 | 2026-10-20 | CL37 | Completed
J1275 | 2026-10-22 | CL37 | Completed
J1275 | 2026-10-26 | CL37 | Completed
J1275 | 2026-10-27 | CL37 | Completed
J1275 | 2026-10-29 | CL37 | Completed
J1276 | 2026-08-03 | CL07 | Completed
J1276 | 2026-08-04 | CL07 | Completed
J1276 | 2026-08-06 | CL07 | Completed
J1276 | 2026-08-10 | CL07 | Completed
J1276 | 2026-08-11 | CL07 | Completed
J1276 | 2026-08-13 | CL07 | Completed
J1276 | 2026-08-17 | CL07 | Completed
J1276 | 2026-08-18 | CL07 | Completed
J1276 | 2026-08-20 | CL07 | Completed
J1276 | 2026-08-24 | CL07 | Completed
J1276 | 2026-08-25 | CL07 | Completed
J1276 | 2026-08-27 | CL07 | Completed
J1276 | 2026-08-31 | CL07 | Skipped
J1276 | 2026-09-01 | CL07 | Completed
J1276 | 2026-09-03 | CL07 | Completed
J1276 | 2026-09-07 | CL07 | Completed
J1276 | 2026-09-08 | CL07 | Completed
J1276 | 2026-09-10 | CL07 | Completed
J1276 | 2026-09-14 | CL07 | Completed
J1276 | 2026-09-15 | CL07 | Completed
J1276 | 2026-09-17 | CL07 | Completed
J1276 | 2026-09-21 | CL07 | Completed
J1276 | 2026-09-22 | CL07 | Completed
J1276 | 2026-09-24 | CL07 | Completed
J1276 | 2026-09-28 | CL07 | Completed
J1276 | 2026-09-29 | CL07 | Completed
J1276 | 2026-10-01 | CL07 | Completed
J1276 | 2026-10-05 | CL07 | Completed
J1276 | 2026-10-06 | CL07 | Completed
J1276 | 2026-10-08 | CL07 | Completed
J1276 | 2026-10-12 | CL07 | Completed
J1276 | 2026-10-13 | CL07 | Completed
J1276 | 2026-10-15 | CL07 | Completed
J1276 | 2026-10-19 | CL07 | Completed
J1276 | 2026-10-20 | CL07 | Completed
J1276 | 2026-10-22 | CL07 | Completed
J1276 | 2026-10-26 | CL07 | Completed
J1276 | 2026-10-27 | CL07 | Completed
J1276 | 2026-10-29 | CL07 | Completed
J1277 | 2026-08-03 | CL33 | Completed
J1277 | 2026-08-04 | CL33 | Completed
J1277 | 2026-08-05 | CL33 | Completed
J1277 | 2026-08-10 | CL33 | Completed
J1277 | 2026-08-11 | CL33 | Completed
J1277 | 2026-08-12 | CL33 | Completed
J1277 | 2026-08-17 | CL33 | Completed
J1277 | 2026-08-18 | CL33 | Completed
J1277 | 2026-08-19 | CL33 | Completed
J1277 | 2026-08-24 | CL33 | Completed
J1277 | 2026-08-25 | CL33 | Completed
J1277 | 2026-08-26 | CL33 | Completed
J1277 | 2026-08-31 | CL33 | Completed
J1277 | 2026-09-01 | CL33 | Completed
J1277 | 2026-09-02 | CL33 | Completed
J1277 | 2026-09-07 | CL33 | Completed
J1277 | 2026-09-08 | CL33 | Completed
J1277 | 2026-09-09 | CL33 | Completed
J1277 | 2026-09-14 | CL33 | Completed
J1277 | 2026-09-15 | CL33 | Completed
J1277 | 2026-09-16 | CL33 | Completed
J1277 | 2026-09-21 | CL33 | Completed
J1277 | 2026-09-22 | CL33 | Completed
J1277 | 2026-09-23 | CL33 | Completed
J1277 | 2026-09-28 | CL33 | Completed
J1277 | 2026-09-29 | CL33 | Completed
J1277 | 2026-09-30 | CL33 | Completed
J1277 | 2026-10-05 | CL33 | Completed
J1277 | 2026-10-06 | CL33 | Completed
J1277 | 2026-10-07 | CL33 | Completed
J1277 | 2026-10-12 | CL33 | Completed
J1277 | 2026-10-13 | CL33 | Completed
J1277 | 2026-10-14 | CL33 | Completed
J1277 | 2026-10-19 | CL33 | Completed
J1277 | 2026-10-20 | CL33 | Completed
J1277 | 2026-10-21 | CL33 | Completed
J1277 | 2026-10-26 | CL33 | Completed
J1277 | 2026-10-27 | CL33 | Completed
J1277 | 2026-10-28 | CL33 | Completed
J1278 | 2026-08-03 | CL17 | Completed
J1278 | 2026-08-04 | CL17 | Completed
J1278 | 2026-08-05 | CL17 | Completed
J1278 | 2026-08-06 | CL17 | Completed
J1278 | 2026-08-07 | CL17 | Completed
J1278 | 2026-08-10 | CL17 | Completed
J1278 | 2026-08-11 | CL17 | Completed
J1278 | 2026-08-12 | CL17 | Completed
J1278 | 2026-08-13 | CL17 | Completed
J1278 | 2026-08-14 | CL17 | Completed
J1278 | 2026-08-17 | CL17 | Completed
J1278 | 2026-08-18 | CL17 | Completed
J1278 | 2026-08-19 | CL17 | Completed
J1278 | 2026-08-20 | CL17 | Completed
J1278 | 2026-08-21 | CL17 | Completed
J1278 | 2026-08-24 | CL17 | Skipped
J1278 | 2026-08-25 | CL17 | Completed
J1278 | 2026-08-26 | CL17 | Completed
J1278 | 2026-08-27 | CL17 | Completed
J1278 | 2026-08-28 | CL17 | Completed
J1278 | 2026-08-31 | CL17 | Completed
J1278 | 2026-09-01 | CL17 | Completed
J1278 | 2026-09-02 | CL17 | Completed
J1278 | 2026-09-03 | CL17 | Completed
J1278 | 2026-09-04 | CL17 | Completed
J1278 | 2026-09-07 | CL17 | Completed
J1278 | 2026-09-08 | CL17 | Completed
J1278 | 2026-09-09 | CL17 | Completed
J1278 | 2026-09-10 | CL17 | Skipped
J1278 | 2026-09-11 | CL17 | Completed
J1278 | 2026-09-14 | CL17 | Completed
J1278 | 2026-09-15 | CL17 | Completed
J1278 | 2026-09-16 | CL17 | Completed
J1278 | 2026-09-17 | CL17 | Completed
J1278 | 2026-09-18 | CL17 | Completed
J1278 | 2026-09-21 | CL17 | Completed
J1278 | 2026-09-22 | CL17 | Completed
J1278 | 2026-09-23 | CL17 | Completed
J1278 | 2026-09-24 | CL17 | Completed
J1278 | 2026-09-25 | CL17 | Completed
J1278 | 2026-09-28 | CL17 | Completed
J1278 | 2026-09-29 | CL17 | Completed
J1278 | 2026-09-30 | CL17 | Completed
J1278 | 2026-10-01 | CL17 | Completed
J1278 | 2026-10-02 | CL17 | Completed
J1278 | 2026-10-05 | CL17 | Completed
J1278 | 2026-10-06 | CL17 | Completed
J1278 | 2026-10-07 | CL17 | Completed
J1278 | 2026-10-08 | CL17 | Completed
J1278 | 2026-10-09 | CL17 | Completed
J1278 | 2026-10-12 | CL17 | Completed
J1278 | 2026-10-13 | CL17 | Completed
J1278 | 2026-10-14 | CL17 | Completed
J1278 | 2026-10-15 | CL17 | Completed
J1278 | 2026-10-16 | CL17 | Completed
J1278 | 2026-10-19 | CL17 | Completed
J1278 | 2026-10-20 | CL17 | Completed
J1278 | 2026-10-21 | CL17 | Completed
J1278 | 2026-10-22 | CL17 | Completed
J1278 | 2026-10-23 | CL17 | Completed
J1278 | 2026-10-26 | CL17 | Completed
J1278 | 2026-10-27 | CL17 | Completed
J1278 | 2026-10-28 | CL17 | Completed
J1278 | 2026-10-29 | CL17 | Completed
J1278 | 2026-10-30 | CL17 | Skipped
J1279 | 2026-08-06 | CL25 | Completed
J1279 | 2026-08-07 | CL25 | Completed
J1279 | 2026-08-13 | CL25 | Completed
J1279 | 2026-08-14 | CL25 | Completed
J1279 | 2026-08-20 | CL25 | Completed
J1279 | 2026-08-21 | CL25 | Completed
J1279 | 2026-08-27 | CL25 | Completed
J1279 | 2026-08-28 | CL25 | Completed
J1279 | 2026-09-03 | CL25 | Completed
J1279 | 2026-09-04 | CL25 | Completed
J1279 | 2026-09-10 | CL25 | Completed
J1279 | 2026-09-11 | CL25 | Completed
J1279 | 2026-09-17 | CL25 | Completed
J1279 | 2026-09-18 | CL25 | Completed
J1279 | 2026-09-24 | CL25 | Completed
J1279 | 2026-09-25 | CL25 | Completed
J1279 | 2026-10-01 | CL25 | Completed
J1279 | 2026-10-02 | CL25 | Completed
J1279 | 2026-10-08 | CL25 | Completed
J1279 | 2026-10-09 | CL25 | Completed
J1279 | 2026-10-15 | CL25 | Completed
J1279 | 2026-10-16 | CL25 | Completed
J1279 | 2026-10-22 | CL25 | Completed
J1279 | 2026-10-23 | CL25 | Completed
J1279 | 2026-10-29 | CL25 | Completed
J1279 | 2026-10-30 | CL25 | Completed
J1280 | 2026-08-03 | CL50 | Completed
J1280 | 2026-08-04 | CL50 | Completed
J1280 | 2026-08-10 | CL50 | Completed
J1280 | 2026-08-11 | CL50 | Completed
J1280 | 2026-08-17 | CL50 | Completed
J1280 | 2026-08-18 | CL50 | Completed
J1280 | 2026-08-24 | CL50 | Completed
J1280 | 2026-08-25 | CL50 | Completed
J1280 | 2026-08-31 | CL50 | Completed
J1280 | 2026-09-01 | CL50 | Completed
J1280 | 2026-09-07 | CL50 | Completed
J1280 | 2026-09-08 | CL50 | Completed
J1280 | 2026-09-14 | CL50 | Completed
J1280 | 2026-09-15 | CL50 | Completed
J1280 | 2026-09-21 | CL50 | Completed
J1280 | 2026-09-22 | CL50 | Completed
J1280 | 2026-09-28 | CL50 | Completed
J1280 | 2026-09-29 | CL50 | Completed
J1280 | 2026-10-05 | CL50 | Completed
J1280 | 2026-10-06 | CL50 | Completed
J1280 | 2026-10-12 | CL50 | Completed
J1280 | 2026-10-13 | CL50 | Completed
J1280 | 2026-10-19 | CL50 | Completed
J1280 | 2026-10-20 | CL50 | Completed
J1280 | 2026-10-26 | CL50 | Completed
J1280 | 2026-10-27 | CL50 | Completed
J1281 | 2026-08-07 | CL20 | Completed
J1281 | 2026-08-14 | CL20 | Completed
J1281 | 2026-08-21 | CL20 | Completed
J1281 | 2026-08-28 | CL20 | Completed
J1281 | 2026-09-04 | CL20 | Completed
J1281 | 2026-09-11 | CL20 | Completed
J1281 | 2026-09-18 | CL20 | Completed
J1281 | 2026-09-25 | CL20 | Completed
J1281 | 2026-10-02 | CL20 | Completed
J1281 | 2026-10-09 | CL20 | Completed
J1281 | 2026-10-16 | CL20 | Completed
J1281 | 2026-10-23 | CL20 | Completed
J1281 | 2026-10-30 | CL20 | Completed
J1282 | 2026-08-25 | CL57 | Completed
J1282 | 2026-09-22 | CL57 | Completed
J1282 | 2026-10-20 | CL57 | Completed
J1283 | 2026-08-03 | CL06 | Skipped
J1283 | 2026-08-04 | CL06 | Completed
J1283 | 2026-08-05 | CL06 | Completed
J1283 | 2026-08-06 | CL06 | Completed
J1283 | 2026-08-07 | CL06 | Completed
J1283 | 2026-08-10 | CL06 | Completed
J1283 | 2026-08-11 | CL06 | Completed
J1283 | 2026-08-12 | CL06 | Completed
J1283 | 2026-08-13 | CL06 | Completed
J1283 | 2026-08-14 | CL06 | Completed
J1283 | 2026-08-17 | CL06 | Completed
J1283 | 2026-08-18 | CL06 | Completed
J1283 | 2026-08-19 | CL06 | Completed
J1283 | 2026-08-20 | CL06 | Completed
J1283 | 2026-08-21 | CL06 | Completed
J1283 | 2026-08-24 | CL06 | Completed
J1283 | 2026-08-25 | CL06 | Completed
J1283 | 2026-08-26 | CL06 | Completed
J1283 | 2026-08-27 | CL06 | Completed
J1283 | 2026-08-28 | CL06 | Completed
J1283 | 2026-08-31 | CL06 | Completed
J1283 | 2026-09-01 | CL06 | Completed
J1283 | 2026-09-02 | CL06 | Completed
J1283 | 2026-09-03 | CL06 | Completed
J1283 | 2026-09-04 | CL06 | Completed
J1283 | 2026-09-07 | CL06 | Completed
J1283 | 2026-09-08 | CL06 | Completed
J1283 | 2026-09-09 | CL06 | Completed
J1283 | 2026-09-10 | CL06 | Completed
J1283 | 2026-09-11 | CL06 | Completed
J1283 | 2026-09-14 | CL06 | Completed
J1283 | 2026-09-15 | CL06 | Completed
J1283 | 2026-09-16 | CL06 | Completed
J1283 | 2026-09-17 | CL06 | Completed
J1283 | 2026-09-18 | CL06 | Completed
J1283 | 2026-09-21 | CL06 | Completed
J1283 | 2026-09-22 | CL06 | Completed
J1283 | 2026-09-23 | CL06 | Completed
J1283 | 2026-09-24 | CL06 | Completed
J1283 | 2026-09-25 | CL06 | Completed
J1283 | 2026-09-28 | CL06 | Completed
J1283 | 2026-09-29 | CL06 | Completed
J1283 | 2026-09-30 | CL06 | Completed
J1283 | 2026-10-01 | CL06 | Completed
J1283 | 2026-10-02 | CL06 | Completed
J1283 | 2026-10-05 | CL06 | Completed
J1283 | 2026-10-06 | CL06 | Completed
J1283 | 2026-10-07 | CL06 | Completed
J1283 | 2026-10-08 | CL06 | Completed
J1283 | 2026-10-09 | CL06 | Completed
J1283 | 2026-10-12 | CL06 | Completed
J1283 | 2026-10-13 | CL06 | Completed
J1283 | 2026-10-14 | CL06 | Completed
J1283 | 2026-10-15 | CL06 | Completed
J1283 | 2026-10-16 | CL06 | Completed
J1283 | 2026-10-19 | CL06 | Completed
J1283 | 2026-10-20 | CL06 | Completed
J1283 | 2026-10-21 | CL06 | Completed
J1283 | 2026-10-22 | CL06 | Completed
J1283 | 2026-10-23 | CL06 | Completed
J1283 | 2026-10-26 | CL06 | Completed
J1283 | 2026-10-27 | CL06 | Completed
J1283 | 2026-10-28 | CL06 | Completed
J1283 | 2026-10-29 | CL06 | Completed
J1283 | 2026-10-30 | CL06 | Completed
J1284 | 2026-08-07 | CL54 | Completed
J1284 | 2026-09-04 | CL54 | Completed
J1284 | 2026-10-02 | CL54 | Completed
J1284 | 2026-10-30 | CL54 | Completed
J1285 | 2026-08-03 | CL38 | Completed
J1285 | 2026-08-04 | CL38 | Completed
J1285 | 2026-08-05 | CL38 | Completed
J1285 | 2026-08-06 | CL38 | Completed
J1285 | 2026-08-07 | CL38 | Completed
J1285 | 2026-08-10 | CL38 | Completed
J1285 | 2026-08-11 | CL38 | Completed
J1285 | 2026-08-12 | CL38 | Completed
J1285 | 2026-08-13 | CL38 | Completed
J1285 | 2026-08-14 | CL38 | Completed
J1285 | 2026-08-17 | CL38 | Completed
J1285 | 2026-08-18 | CL38 | Completed
J1285 | 2026-08-19 | CL38 | Completed
J1285 | 2026-08-20 | CL38 | Completed
J1285 | 2026-08-21 | CL38 | Completed
J1285 | 2026-08-24 | CL38 | Completed
J1285 | 2026-08-25 | CL38 | Completed
J1285 | 2026-08-26 | CL38 | Completed
J1285 | 2026-08-27 | CL38 | Completed
J1285 | 2026-08-28 | CL38 | Completed
J1285 | 2026-08-31 | CL38 | Completed
J1285 | 2026-09-01 | CL38 | Completed
J1285 | 2026-09-02 | CL38 | Completed
J1285 | 2026-09-03 | CL38 | Completed
J1285 | 2026-09-04 | CL38 | Completed
J1285 | 2026-09-07 | CL38 | Completed
J1285 | 2026-09-08 | CL38 | Completed
J1285 | 2026-09-09 | CL38 | Completed
J1285 | 2026-09-10 | CL38 | Completed
J1285 | 2026-09-11 | CL38 | Completed
J1285 | 2026-09-14 | CL38 | Completed
J1285 | 2026-09-15 | CL38 | Completed
J1285 | 2026-09-16 | CL38 | Completed
J1285 | 2026-09-17 | CL38 | Completed
J1285 | 2026-09-18 | CL38 | Completed
J1285 | 2026-09-21 | CL38 | Completed
J1285 | 2026-09-22 | CL38 | Completed
J1285 | 2026-09-23 | CL38 | Completed
J1285 | 2026-09-24 | CL38 | Completed
J1285 | 2026-09-25 | CL38 | Completed
J1285 | 2026-09-28 | CL38 | Completed
J1285 | 2026-09-29 | CL38 | Completed
J1285 | 2026-09-30 | CL38 | Completed
J1285 | 2026-10-01 | CL38 | Completed
J1285 | 2026-10-02 | CL38 | Completed
J1285 | 2026-10-05 | CL38 | Completed
J1285 | 2026-10-06 | CL38 | Completed
J1285 | 2026-10-07 | CL38 | Completed
J1285 | 2026-10-08 | CL38 | Completed
J1285 | 2026-10-09 | CL38 | Completed
J1285 | 2026-10-12 | CL38 | Completed
J1285 | 2026-10-13 | CL38 | Completed
J1285 | 2026-10-14 | CL38 | Completed
J1285 | 2026-10-15 | CL38 | Completed
J1285 | 2026-10-16 | CL38 | Completed
J1285 | 2026-10-19 | CL38 | Skipped
J1285 | 2026-10-20 | CL38 | Completed
J1285 | 2026-10-21 | CL38 | Completed
J1285 | 2026-10-22 | CL38 | Completed
J1285 | 2026-10-23 | CL38 | Completed
J1285 | 2026-10-26 | CL38 | Completed
J1285 | 2026-10-27 | CL38 | Completed
J1285 | 2026-10-28 | CL38 | Completed
J1285 | 2026-10-29 | CL38 | Completed
J1285 | 2026-10-30 | CL38 | Completed
J1286 | 2026-08-03 | CL02 | Completed
J1286 | 2026-08-04 | CL02 | Completed
J1286 | 2026-08-05 | CL02 | Skipped
J1286 | 2026-08-06 | CL02 | Completed
J1286 | 2026-08-07 | CL02 | Completed
J1286 | 2026-08-10 | CL02 | Completed
J1286 | 2026-08-11 | CL02 | Completed
J1286 | 2026-08-12 | CL02 | Completed
J1286 | 2026-08-13 | CL02 | Completed
J1286 | 2026-08-14 | CL02 | Completed
J1286 | 2026-08-17 | CL02 | Completed
J1286 | 2026-08-18 | CL02 | Completed
J1286 | 2026-08-19 | CL02 | Completed
J1286 | 2026-08-20 | CL02 | Completed
J1286 | 2026-08-21 | CL02 | Completed
J1286 | 2026-08-24 | CL02 | Completed
J1286 | 2026-08-25 | CL02 | Completed
J1286 | 2026-08-26 | CL02 | Completed
J1286 | 2026-08-27 | CL02 | Completed
J1286 | 2026-08-28 | CL02 | Completed
J1286 | 2026-08-31 | CL02 | Completed
J1286 | 2026-09-01 | CL02 | Completed
J1286 | 2026-09-02 | CL02 | Completed
J1286 | 2026-09-03 | CL02 | Completed
J1286 | 2026-09-04 | CL02 | Completed
J1286 | 2026-09-07 | CL02 | Completed
J1286 | 2026-09-08 | CL02 | Completed
J1286 | 2026-09-09 | CL02 | Completed
J1286 | 2026-09-10 | CL02 | Completed
J1286 | 2026-09-11 | CL02 | Completed
J1286 | 2026-09-14 | CL02 | Completed
J1286 | 2026-09-15 | CL02 | Skipped
J1286 | 2026-09-16 | CL02 | Completed
J1286 | 2026-09-17 | CL02 | Completed
J1286 | 2026-09-18 | CL02 | Completed
J1286 | 2026-09-21 | CL02 | Completed
J1286 | 2026-09-22 | CL02 | Completed
J1286 | 2026-09-23 | CL02 | Completed
J1286 | 2026-09-24 | CL02 | Completed
J1286 | 2026-09-25 | CL02 | Completed
J1286 | 2026-09-28 | CL02 | Completed
J1286 | 2026-09-29 | CL02 | Completed
J1286 | 2026-09-30 | CL02 | Completed
J1286 | 2026-10-01 | CL02 | Completed
J1286 | 2026-10-02 | CL02 | Completed
J1286 | 2026-10-05 | CL02 | Completed
J1286 | 2026-10-06 | CL02 | Completed
J1286 | 2026-10-07 | CL02 | Completed
J1286 | 2026-10-08 | CL02 | Completed
J1286 | 2026-10-09 | CL02 | Completed
J1286 | 2026-10-12 | CL02 | Completed
J1286 | 2026-10-13 | CL02 | Completed
J1286 | 2026-10-14 | CL02 | Completed
J1286 | 2026-10-15 | CL02 | Completed
J1286 | 2026-10-16 | CL02 | Completed
J1286 | 2026-10-19 | CL02 | Completed
J1286 | 2026-10-20 | CL02 | Completed
J1286 | 2026-10-21 | CL02 | Completed
J1286 | 2026-10-22 | CL02 | Completed
J1286 | 2026-10-23 | CL02 | Completed
J1286 | 2026-10-26 | CL02 | Completed
J1286 | 2026-10-27 | CL02 | Completed
J1286 | 2026-10-28 | CL02 | Completed
J1286 | 2026-10-29 | CL02 | Completed
J1286 | 2026-10-30 | CL02 | Completed
J1287 | 2026-08-03 | CL11 | Completed
J1287 | 2026-08-04 | CL11 | Completed
J1287 | 2026-08-05 | CL11 | Completed
J1287 | 2026-08-10 | CL11 | Completed
J1287 | 2026-08-11 | CL11 | Completed
J1287 | 2026-08-12 | CL11 | Completed
J1287 | 2026-08-17 | CL11 | Completed
J1287 | 2026-08-18 | CL11 | Completed
J1287 | 2026-08-19 | CL11 | Completed
J1287 | 2026-08-24 | CL11 | Completed
J1287 | 2026-08-25 | CL11 | Completed
J1287 | 2026-08-26 | CL11 | Completed
J1287 | 2026-08-31 | CL11 | Completed
J1287 | 2026-09-01 | CL11 | Completed
J1287 | 2026-09-02 | CL11 | Completed
J1287 | 2026-09-07 | CL11 | Completed
J1287 | 2026-09-08 | CL11 | Completed
J1287 | 2026-09-09 | CL11 | Completed
J1287 | 2026-09-14 | CL11 | Completed
J1287 | 2026-09-15 | CL11 | Completed
J1287 | 2026-09-16 | CL11 | Completed
J1287 | 2026-09-21 | CL11 | Completed
J1287 | 2026-09-22 | CL11 | Completed
J1287 | 2026-09-23 | CL11 | Completed
J1287 | 2026-09-28 | CL11 | Completed
J1287 | 2026-09-29 | CL11 | Completed
J1287 | 2026-09-30 | CL11 | Completed
J1287 | 2026-10-05 | CL11 | Completed
J1287 | 2026-10-06 | CL11 | Completed
J1287 | 2026-10-07 | CL11 | Completed
J1287 | 2026-10-12 | CL11 | Completed
J1287 | 2026-10-13 | CL11 | Completed
J1287 | 2026-10-14 | CL11 | Completed
J1287 | 2026-10-19 | CL11 | Completed
J1287 | 2026-10-20 | CL11 | Completed
J1287 | 2026-10-21 | CL11 | Completed
J1287 | 2026-10-26 | CL11 | Completed
J1287 | 2026-10-27 | CL11 | Completed
J1287 | 2026-10-28 | CL11 | Completed
J1288 | 2026-08-05 | CL34 | Completed
J1288 | 2026-08-06 | CL34 | Completed
J1288 | 2026-08-12 | CL34 | Completed
J1288 | 2026-08-13 | CL34 | Completed
J1288 | 2026-08-19 | CL34 | Completed
J1288 | 2026-08-20 | CL34 | Completed
J1288 | 2026-08-26 | CL34 | Completed
J1288 | 2026-08-27 | CL34 | Completed
J1288 | 2026-09-02 | CL34 | Completed
J1288 | 2026-09-03 | CL34 | Completed
J1288 | 2026-09-09 | CL34 | Completed
J1288 | 2026-09-10 | CL34 | Completed
J1288 | 2026-09-16 | CL34 | Completed
J1288 | 2026-09-17 | CL34 | Completed
J1288 | 2026-09-23 | CL34 | Completed
J1288 | 2026-09-24 | CL34 | Completed
J1288 | 2026-09-30 | CL34 | Completed
J1288 | 2026-10-01 | CL34 | Completed
J1288 | 2026-10-07 | CL34 | Completed
J1288 | 2026-10-08 | CL34 | Completed
J1288 | 2026-10-14 | CL34 | Completed
J1288 | 2026-10-15 | CL34 | Completed
J1288 | 2026-10-21 | CL34 | Completed
J1288 | 2026-10-22 | CL34 | Completed
J1288 | 2026-10-28 | CL34 | Completed
J1288 | 2026-10-29 | CL34 | Completed
J1289 | 2026-08-03 | CL30 | Completed
J1289 | 2026-08-04 | CL30 | Completed
J1289 | 2026-08-05 | CL30 | Completed
J1289 | 2026-08-06 | CL30 | Completed
J1289 | 2026-08-07 | CL30 | Completed
J1289 | 2026-08-10 | CL30 | Completed
J1289 | 2026-08-11 | CL30 | Completed
J1289 | 2026-08-12 | CL30 | Completed
J1289 | 2026-08-13 | CL30 | Completed
J1289 | 2026-08-14 | CL30 | Completed
J1289 | 2026-08-17 | CL30 | Completed
J1289 | 2026-08-18 | CL30 | Completed
J1289 | 2026-08-19 | CL30 | Completed
J1289 | 2026-08-20 | CL30 | Completed
J1289 | 2026-08-21 | CL30 | Completed
J1289 | 2026-08-24 | CL30 | Completed
J1289 | 2026-08-25 | CL30 | Completed
J1289 | 2026-08-26 | CL30 | Completed
J1289 | 2026-08-27 | CL30 | Completed
J1289 | 2026-08-28 | CL30 | Completed
J1289 | 2026-08-31 | CL30 | Completed
J1289 | 2026-09-01 | CL30 | Completed
J1289 | 2026-09-02 | CL30 | Completed
J1289 | 2026-09-03 | CL30 | Completed
J1289 | 2026-09-04 | CL30 | Completed
J1289 | 2026-09-07 | CL30 | Completed
J1289 | 2026-09-08 | CL30 | Completed
J1289 | 2026-09-09 | CL30 | Completed
J1289 | 2026-09-10 | CL30 | Completed
J1289 | 2026-09-11 | CL30 | Completed
J1289 | 2026-09-14 | CL30 | Completed
J1289 | 2026-09-15 | CL30 | Completed
J1289 | 2026-09-16 | CL30 | Completed
J1289 | 2026-09-17 | CL30 | Completed
J1289 | 2026-09-18 | CL30 | Completed
J1289 | 2026-09-21 | CL30 | Completed
J1289 | 2026-09-22 | CL30 | Completed
J1289 | 2026-09-23 | CL30 | Completed
J1289 | 2026-09-24 | CL30 | Completed
J1289 | 2026-09-25 | CL30 | Completed
J1289 | 2026-09-28 | CL30 | Completed
J1289 | 2026-09-29 | CL30 | Completed
J1289 | 2026-09-30 | CL30 | Completed
J1289 | 2026-10-01 | CL30 | Completed
J1289 | 2026-10-02 | CL30 | Completed
J1289 | 2026-10-05 | CL30 | Completed
J1289 | 2026-10-06 | CL30 | Completed
J1289 | 2026-10-07 | CL30 | Completed
J1289 | 2026-10-08 | CL30 | Completed
J1289 | 2026-10-09 | CL30 | Completed
J1289 | 2026-10-12 | CL30 | Completed
J1289 | 2026-10-13 | CL30 | Completed
J1289 | 2026-10-14 | CL30 | Completed
J1289 | 2026-10-15 | CL30 | Completed
J1289 | 2026-10-16 | CL30 | Completed
J1289 | 2026-10-19 | CL30 | Completed
J1289 | 2026-10-20 | CL30 | Completed
J1289 | 2026-10-21 | CL30 | Completed
J1289 | 2026-10-22 | CL30 | Completed
J1289 | 2026-10-23 | CL30 | Completed
J1289 | 2026-10-26 | CL30 | Completed
J1289 | 2026-10-27 | CL30 | Completed
J1289 | 2026-10-28 | CL30 | Completed
J1289 | 2026-10-29 | CL30 | Completed
J1289 | 2026-10-30 | CL30 | Completed
J1290 | 2026-08-10 | CL54 | Completed
J1290 | 2026-09-07 | CL54 | Completed
J1290 | 2026-10-05 | CL54 | Completed
J1291 | 2026-08-07 | CL54 | Completed
J1291 | 2026-09-04 | CL54 | Completed
J1291 | 2026-10-02 | CL54 | Completed
J1292 | 2026-08-03 | CL23 | Completed
J1292 | 2026-08-06 | CL23 | Completed
J1292 | 2026-08-10 | CL23 | Completed
J1292 | 2026-08-13 | CL23 | Completed
J1292 | 2026-08-17 | CL23 | Completed
J1292 | 2026-08-20 | CL23 | Completed
J1292 | 2026-08-24 | CL23 | Completed
J1292 | 2026-08-27 | CL23 | Completed
J1292 | 2026-08-31 | CL23 | Completed
J1292 | 2026-09-03 | CL23 | Completed
J1292 | 2026-09-07 | CL23 | Completed
J1292 | 2026-09-10 | CL23 | Completed
J1292 | 2026-09-14 | CL23 | Completed
J1292 | 2026-09-17 | CL23 | Completed
J1292 | 2026-09-21 | CL23 | Completed
J1292 | 2026-09-24 | CL23 | Completed
J1292 | 2026-09-28 | CL23 | Completed
J1292 | 2026-10-01 | CL23 | Completed
J1292 | 2026-10-05 | CL23 | Completed
J1292 | 2026-10-08 | CL23 | Completed
J1292 | 2026-10-12 | CL23 | Completed
J1292 | 2026-10-15 | CL23 | Completed
J1292 | 2026-10-19 | CL23 | Completed
J1292 | 2026-10-22 | CL23 | Completed
J1292 | 2026-10-26 | CL23 | Completed
J1292 | 2026-10-29 | CL23 | Completed
J1293 | 2026-08-20 | CL55 | Completed
J1293 | 2026-09-17 | CL55 | Completed
J1293 | 2026-10-15 | CL55 | Completed
J1294 | 2026-08-07 | CL47 | Completed
J1294 | 2026-08-14 | CL47 | Completed
J1294 | 2026-08-21 | CL47 | Skipped
J1294 | 2026-08-28 | CL47 | Completed
J1294 | 2026-09-04 | CL47 | Completed
J1294 | 2026-09-11 | CL47 | Completed
J1294 | 2026-09-18 | CL47 | Completed
J1294 | 2026-09-25 | CL47 | Completed
J1294 | 2026-10-02 | CL47 | Completed
J1294 | 2026-10-09 | CL47 | Completed
J1294 | 2026-10-16 | CL47 | Completed
J1294 | 2026-10-23 | CL47 | Completed
J1294 | 2026-10-30 | CL47 | Completed
J1295 | 2026-08-04 | CL55 | Completed
J1295 | 2026-09-01 | CL55 | Completed
J1295 | 2026-10-06 | CL55 | Completed
J1296 | 2026-08-06 | CL35 | Skipped
J1296 | 2026-08-13 | CL35 | Completed
J1296 | 2026-08-20 | CL35 | Completed
J1296 | 2026-08-27 | CL35 | Completed
J1296 | 2026-09-03 | CL35 | Skipped
J1296 | 2026-09-10 | CL35 | Completed
J1296 | 2026-09-17 | CL35 | Completed
J1296 | 2026-09-24 | CL35 | Completed
J1296 | 2026-10-01 | CL35 | Completed
J1296 | 2026-10-08 | CL35 | Completed
J1296 | 2026-10-15 | CL35 | Completed
J1296 | 2026-10-22 | CL35 | Completed
J1296 | 2026-10-29 | CL35 | Completed
J1297 | 2026-08-04 | CL03 | Completed
J1297 | 2026-08-05 | CL03 | Completed
J1297 | 2026-08-11 | CL03 | Completed
J1297 | 2026-08-12 | CL03 | Completed
J1297 | 2026-08-18 | CL03 | Completed
J1297 | 2026-08-19 | CL03 | Completed
J1297 | 2026-08-25 | CL03 | Completed
J1297 | 2026-08-26 | CL03 | Completed
J1297 | 2026-09-01 | CL03 | Completed
J1297 | 2026-09-02 | CL03 | Skipped
J1297 | 2026-09-08 | CL03 | Completed
J1297 | 2026-09-09 | CL03 | Completed
J1297 | 2026-09-15 | CL03 | Completed
J1297 | 2026-09-16 | CL03 | Completed
J1297 | 2026-09-22 | CL03 | Completed
J1297 | 2026-09-23 | CL03 | Completed
J1297 | 2026-09-29 | CL03 | Completed
J1297 | 2026-09-30 | CL03 | Completed
J1297 | 2026-10-06 | CL03 | Completed
J1297 | 2026-10-07 | CL03 | Completed
J1297 | 2026-10-13 | CL03 | Completed
J1297 | 2026-10-14 | CL03 | Completed
J1297 | 2026-10-20 | CL03 | Completed
J1297 | 2026-10-21 | CL03 | Completed
J1297 | 2026-10-27 | CL03 | Completed
J1297 | 2026-10-28 | CL03 | Completed
J1298 | 2026-08-04 | CL19 | Completed
J1298 | 2026-08-11 | CL19 | Completed
J1298 | 2026-08-18 | CL19 | Completed
J1298 | 2026-08-25 | CL19 | Completed
J1298 | 2026-09-01 | CL19 | Completed
J1298 | 2026-09-08 | CL19 | Completed
J1298 | 2026-09-15 | CL19 | Completed
J1298 | 2026-09-22 | CL19 | Completed
J1298 | 2026-09-29 | CL19 | Completed
J1298 | 2026-10-06 | CL19 | Completed
J1298 | 2026-10-13 | CL19 | Completed
J1298 | 2026-10-20 | CL19 | Completed
J1298 | 2026-10-27 | CL19 | Completed
J1299 | 2026-08-04 | CL43 | Completed
J1299 | 2026-08-11 | CL43 | Completed
J1299 | 2026-08-18 | CL43 | Completed
J1299 | 2026-08-25 | CL43 | Completed
J1299 | 2026-09-01 | CL43 | Completed
J1299 | 2026-09-08 | CL43 | Completed
J1299 | 2026-09-15 | CL43 | Completed
J1299 | 2026-09-22 | CL43 | Completed
J1299 | 2026-09-29 | CL43 | Completed
J1299 | 2026-10-06 | CL43 | Completed
J1299 | 2026-10-13 | CL43 | Completed
J1299 | 2026-10-20 | CL43 | Completed
J1299 | 2026-10-27 | CL43 | Completed
J1300 | 2026-08-03 | CL40 | Completed
J1300 | 2026-08-05 | CL40 | Completed
J1300 | 2026-08-07 | CL40 | Completed
J1300 | 2026-08-10 | CL40 | Completed
J1300 | 2026-08-12 | CL40 | Completed
J1300 | 2026-08-14 | CL40 | Completed
J1300 | 2026-08-17 | CL40 | Completed
J1300 | 2026-08-19 | CL40 | Completed
J1300 | 2026-08-21 | CL40 | Completed
J1300 | 2026-08-24 | CL40 | Completed
J1300 | 2026-08-26 | CL40 | Completed
J1300 | 2026-08-28 | CL40 | Completed
J1300 | 2026-08-31 | CL40 | Completed
J1300 | 2026-09-02 | CL40 | Completed
J1300 | 2026-09-04 | CL40 | Completed
J1300 | 2026-09-07 | CL40 | Completed
J1300 | 2026-09-09 | CL40 | Completed
J1300 | 2026-09-11 | CL40 | Completed
J1300 | 2026-09-14 | CL40 | Completed
J1300 | 2026-09-16 | CL40 | Completed
J1300 | 2026-09-18 | CL40 | Completed
J1300 | 2026-09-21 | CL40 | Completed
J1300 | 2026-09-23 | CL40 | Completed
J1300 | 2026-09-25 | CL40 | Completed
J1300 | 2026-09-28 | CL40 | Completed
J1300 | 2026-09-30 | CL40 | Completed
J1300 | 2026-10-02 | CL40 | Completed
J1300 | 2026-10-05 | CL40 | Completed
J1300 | 2026-10-07 | CL40 | Completed
J1300 | 2026-10-09 | CL40 | Completed
J1300 | 2026-10-12 | CL40 | Completed
J1300 | 2026-10-14 | CL40 | Completed
J1300 | 2026-10-16 | CL40 | Completed
J1300 | 2026-10-19 | CL40 | Completed
J1300 | 2026-10-21 | CL40 | Completed
J1300 | 2026-10-23 | CL40 | Completed
J1300 | 2026-10-26 | CL40 | Completed
J1300 | 2026-10-28 | CL40 | Completed
J1300 | 2026-10-30 | CL40 | Completed
J1301 | 2026-08-04 | CL29 | Completed
J1301 | 2026-08-06 | CL29 | Completed
J1301 | 2026-08-11 | CL29 | Skipped
J1301 | 2026-08-13 | CL29 | Completed
J1301 | 2026-08-18 | CL29 | Completed
J1301 | 2026-08-20 | CL29 | Completed
J1301 | 2026-08-25 | CL29 | Completed
J1301 | 2026-08-27 | CL29 | Completed
J1301 | 2026-09-01 | CL29 | Completed
J1301 | 2026-09-03 | CL29 | Completed
J1301 | 2026-09-08 | CL29 | Completed
J1301 | 2026-09-10 | CL29 | Completed
J1301 | 2026-09-15 | CL29 | Completed
J1301 | 2026-09-17 | CL29 | Completed
J1301 | 2026-09-22 | CL29 | Completed
J1301 | 2026-09-24 | CL29 | Completed
J1301 | 2026-09-29 | CL29 | Completed
J1301 | 2026-10-01 | CL29 | Completed
J1301 | 2026-10-06 | CL29 | Completed
J1301 | 2026-10-08 | CL29 | Completed
J1301 | 2026-10-13 | CL29 | Completed
J1301 | 2026-10-15 | CL29 | Completed
J1301 | 2026-10-20 | CL29 | Completed
J1301 | 2026-10-22 | CL29 | Completed
J1301 | 2026-10-27 | CL29 | Completed
J1301 | 2026-10-29 | CL29 | Completed
J1302 | 2026-08-07 | CL35 | Completed
J1302 | 2026-08-14 | CL35 | Completed
J1302 | 2026-08-21 | CL35 | Completed
J1302 | 2026-08-28 | CL35 | Completed
J1302 | 2026-09-04 | CL35 | Completed
J1302 | 2026-09-11 | CL35 | Completed
J1302 | 2026-09-18 | CL35 | Completed
J1302 | 2026-09-25 | CL35 | Completed
J1302 | 2026-10-02 | CL35 | Completed
J1302 | 2026-10-09 | CL35 | Completed
J1302 | 2026-10-16 | CL35 | Completed
J1302 | 2026-10-23 | CL35 | Completed
J1302 | 2026-10-30 | CL35 | Completed
J1303 | 2026-08-03 | CL48 | Completed
J1303 | 2026-08-04 | CL48 | Completed
J1303 | 2026-08-05 | CL48 | Completed
J1303 | 2026-08-06 | CL48 | Completed
J1303 | 2026-08-07 | CL48 | Completed
J1303 | 2026-08-10 | CL48 | Completed
J1303 | 2026-08-11 | CL48 | Completed
J1303 | 2026-08-12 | CL48 | Completed
J1303 | 2026-08-13 | CL48 | Completed
J1303 | 2026-08-14 | CL48 | Completed
J1303 | 2026-08-17 | CL48 | Completed
J1303 | 2026-08-18 | CL48 | Completed
J1303 | 2026-08-19 | CL48 | Completed
J1303 | 2026-08-20 | CL48 | Completed
J1303 | 2026-08-21 | CL48 | Completed
J1303 | 2026-08-24 | CL48 | Completed
J1303 | 2026-08-25 | CL48 | Completed
J1303 | 2026-08-26 | CL48 | Completed
J1303 | 2026-08-27 | CL48 | Completed
J1303 | 2026-08-28 | CL48 | Completed
J1303 | 2026-08-31 | CL48 | Completed
J1303 | 2026-09-01 | CL48 | Completed
J1303 | 2026-09-02 | CL48 | Completed
J1303 | 2026-09-03 | CL48 | Completed
J1303 | 2026-09-04 | CL48 | Completed
J1303 | 2026-09-07 | CL48 | Skipped
J1303 | 2026-09-08 | CL48 | Completed
J1303 | 2026-09-09 | CL48 | Completed
J1303 | 2026-09-10 | CL48 | Completed
J1303 | 2026-09-11 | CL48 | Completed
J1303 | 2026-09-14 | CL48 | Completed
J1303 | 2026-09-15 | CL48 | Completed
J1303 | 2026-09-16 | CL48 | Completed
J1303 | 2026-09-17 | CL48 | Completed
J1303 | 2026-09-18 | CL48 | Completed
J1303 | 2026-09-21 | CL48 | Completed
J1303 | 2026-09-22 | CL48 | Completed
J1303 | 2026-09-23 | CL48 | Completed
J1303 | 2026-09-24 | CL48 | Completed
J1303 | 2026-09-25 | CL48 | Completed
J1303 | 2026-09-28 | CL48 | Completed
J1303 | 2026-09-29 | CL48 | Completed
J1303 | 2026-09-30 | CL48 | Completed
J1303 | 2026-10-01 | CL48 | Completed
J1303 | 2026-10-02 | CL48 | Completed
J1303 | 2026-10-05 | CL48 | Completed
J1303 | 2026-10-06 | CL48 | Completed
J1303 | 2026-10-07 | CL48 | Completed
J1303 | 2026-10-08 | CL48 | Completed
J1303 | 2026-10-09 | CL48 | Completed
J1303 | 2026-10-12 | CL48 | Completed
J1303 | 2026-10-13 | CL48 | Completed
J1303 | 2026-10-14 | CL48 | Completed
J1303 | 2026-10-15 | CL48 | Completed
J1303 | 2026-10-16 | CL48 | Completed
J1303 | 2026-10-19 | CL48 | Completed
J1303 | 2026-10-20 | CL48 | Completed
J1303 | 2026-10-21 | CL48 | Completed
J1303 | 2026-10-22 | CL48 | Completed
J1303 | 2026-10-23 | CL48 | Completed
J1303 | 2026-10-26 | CL48 | Completed
J1303 | 2026-10-27 | CL48 | Completed
J1303 | 2026-10-28 | CL48 | Completed
J1303 | 2026-10-29 | CL48 | Completed
J1303 | 2026-10-30 | CL48 | Completed
J1304 | 2026-08-11 | CL55 | Skipped
J1304 | 2026-09-08 | CL55 | Completed
J1304 | 2026-10-06 | CL55 | Completed
J1305 | 2026-08-03 | CL42 | Completed
J1305 | 2026-08-04 | CL42 | Completed
J1305 | 2026-08-05 | CL42 | Completed
J1305 | 2026-08-06 | CL42 | Completed
J1305 | 2026-08-07 | CL42 | Completed
J1305 | 2026-08-10 | CL42 | Completed
J1305 | 2026-08-11 | CL42 | Completed
J1305 | 2026-08-12 | CL42 | Completed
J1305 | 2026-08-13 | CL42 | Completed
J1305 | 2026-08-14 | CL42 | Completed
J1305 | 2026-08-17 | CL42 | Completed
J1305 | 2026-08-18 | CL42 | Completed
J1305 | 2026-08-19 | CL42 | Completed
J1305 | 2026-08-20 | CL42 | Completed
J1305 | 2026-08-21 | CL42 | Completed
J1305 | 2026-08-24 | CL42 | Completed
J1305 | 2026-08-25 | CL42 | Completed
J1305 | 2026-08-26 | CL42 | Completed
J1305 | 2026-08-27 | CL42 | Completed
J1305 | 2026-08-28 | CL42 | Completed
J1305 | 2026-08-31 | CL42 | Completed
J1305 | 2026-09-01 | CL42 | Completed
J1305 | 2026-09-02 | CL42 | Completed
J1305 | 2026-09-03 | CL42 | Completed
J1305 | 2026-09-04 | CL42 | Completed
J1305 | 2026-09-07 | CL42 | Completed
J1305 | 2026-09-08 | CL42 | Completed
J1305 | 2026-09-09 | CL42 | Completed
J1305 | 2026-09-10 | CL42 | Completed
J1305 | 2026-09-11 | CL42 | Completed
J1305 | 2026-09-14 | CL42 | Completed
J1305 | 2026-09-15 | CL42 | Completed
J1305 | 2026-09-16 | CL42 | Completed
J1305 | 2026-09-17 | CL42 | Completed
J1305 | 2026-09-18 | CL42 | Completed
J1305 | 2026-09-21 | CL42 | Completed
J1305 | 2026-09-22 | CL42 | Completed
J1305 | 2026-09-23 | CL42 | Completed
J1305 | 2026-09-24 | CL42 | Completed
J1305 | 2026-09-25 | CL42 | Completed
J1305 | 2026-09-28 | CL42 | Completed
J1305 | 2026-09-29 | CL42 | Completed
J1305 | 2026-09-30 | CL42 | Skipped
J1305 | 2026-10-01 | CL42 | Completed
J1305 | 2026-10-02 | CL42 | Completed
J1305 | 2026-10-05 | CL42 | Completed
J1305 | 2026-10-06 | CL42 | Completed
J1305 | 2026-10-07 | CL42 | Completed
J1305 | 2026-10-08 | CL42 | Completed
J1305 | 2026-10-09 | CL42 | Completed
J1305 | 2026-10-12 | CL42 | Completed
J1305 | 2026-10-13 | CL42 | Completed
J1305 | 2026-10-14 | CL42 | Completed
J1305 | 2026-10-15 | CL42 | Completed
J1305 | 2026-10-16 | CL42 | Completed
J1305 | 2026-10-19 | CL42 | Completed
J1305 | 2026-10-20 | CL42 | Completed
J1305 | 2026-10-21 | CL42 | Completed
J1305 | 2026-10-22 | CL42 | Completed
J1305 | 2026-10-23 | CL42 | Completed
J1305 | 2026-10-26 | CL42 | Completed
J1305 | 2026-10-27 | CL42 | Completed
J1305 | 2026-10-28 | CL42 | Completed
J1305 | 2026-10-29 | CL42 | Completed
J1305 | 2026-10-30 | CL42 | Completed
J1306 | 2026-08-06 | CL55 | Completed
J1306 | 2026-09-03 | CL55 | Completed
J1306 | 2026-10-01 | CL55 | Completed
J1306 | 2026-10-29 | CL55 | Completed
J1307 | 2026-08-06 | CL56 | Completed
J1307 | 2026-09-03 | CL56 | Completed
J1307 | 2026-10-01 | CL56 | Completed
J1308 | 2026-08-03 | CL28 | Completed
J1308 | 2026-08-10 | CL28 | Completed
J1308 | 2026-08-17 | CL28 | Completed
J1308 | 2026-08-24 | CL28 | Completed
J1308 | 2026-08-31 | CL28 | Completed
J1308 | 2026-09-07 | CL28 | Completed
J1308 | 2026-09-14 | CL28 | Completed
J1308 | 2026-09-21 | CL28 | Completed
J1308 | 2026-09-28 | CL28 | Completed
J1308 | 2026-10-05 | CL28 | Completed
J1308 | 2026-10-12 | CL28 | Completed
J1308 | 2026-10-19 | CL28 | Completed
J1308 | 2026-10-26 | CL28 | Completed
J1309 | 2026-08-03 | CL54 | Completed
J1309 | 2026-08-31 | CL54 | Completed
J1309 | 2026-09-28 | CL54 | Completed
J1309 | 2026-10-26 | CL54 | Completed
J1310 | 2026-08-06 | CL54 | Completed
J1310 | 2026-09-03 | CL54 | Completed
J1310 | 2026-10-01 | CL54 | Completed
J1311 | 2026-08-03 | CL21 | Completed
J1311 | 2026-08-10 | CL21 | Completed
J1311 | 2026-08-17 | CL21 | Completed
J1311 | 2026-08-24 | CL21 | Completed
J1311 | 2026-08-31 | CL21 | Completed
J1311 | 2026-09-07 | CL21 | Completed
J1311 | 2026-09-14 | CL21 | Completed
J1311 | 2026-09-21 | CL21 | Completed
J1311 | 2026-09-28 | CL21 | Completed
J1311 | 2026-10-05 | CL21 | Completed
J1311 | 2026-10-12 | CL21 | Completed
J1311 | 2026-10-19 | CL21 | Completed
J1311 | 2026-10-26 | CL21 | Completed
J1312 | 2026-08-05 | CL44 | Completed
J1312 | 2026-08-07 | CL44 | Completed
J1312 | 2026-08-12 | CL44 | Completed
J1312 | 2026-08-14 | CL44 | Completed
J1312 | 2026-08-19 | CL44 | Completed
J1312 | 2026-08-21 | CL44 | Completed
J1312 | 2026-08-26 | CL44 | Completed
J1312 | 2026-08-28 | CL44 | Completed
J1312 | 2026-09-02 | CL44 | Completed
J1312 | 2026-09-04 | CL44 | Completed
J1312 | 2026-09-09 | CL44 | Completed
J1312 | 2026-09-11 | CL44 | Completed
J1312 | 2026-09-16 | CL44 | Completed
J1312 | 2026-09-18 | CL44 | Completed
J1312 | 2026-09-23 | CL44 | Completed
J1312 | 2026-09-25 | CL44 | Completed
J1312 | 2026-09-30 | CL44 | Completed
J1312 | 2026-10-02 | CL44 | Completed
J1312 | 2026-10-07 | CL44 | Completed
J1312 | 2026-10-09 | CL44 | Completed
J1312 | 2026-10-14 | CL44 | Completed
J1312 | 2026-10-16 | CL44 | Completed
J1312 | 2026-10-21 | CL44 | Completed
J1312 | 2026-10-23 | CL44 | Completed
J1312 | 2026-10-28 | CL44 | Completed
J1312 | 2026-10-30 | CL44 | Skipped
J1313 | 2026-08-05 | CL41 | Completed
J1313 | 2026-08-12 | CL41 | Completed
J1313 | 2026-08-19 | CL41 | Completed
J1313 | 2026-08-26 | CL41 | Completed
J1313 | 2026-09-02 | CL41 | Completed
J1313 | 2026-09-09 | CL41 | Completed
J1313 | 2026-09-16 | CL41 | Completed
J1313 | 2026-09-23 | CL41 | Completed
J1313 | 2026-09-30 | CL41 | Completed
J1313 | 2026-10-07 | CL41 | Completed
J1313 | 2026-10-14 | CL41 | Completed
J1313 | 2026-10-21 | CL41 | Completed
J1313 | 2026-10-28 | CL41 | Completed
J1314 | 2026-08-06 | CL46 | Completed
J1314 | 2026-08-07 | CL46 | Completed
J1314 | 2026-08-13 | CL46 | Completed
J1314 | 2026-08-14 | CL46 | Completed
J1314 | 2026-08-20 | CL46 | Completed
J1314 | 2026-08-21 | CL46 | Completed
J1314 | 2026-08-27 | CL46 | Completed
J1314 | 2026-08-28 | CL46 | Completed
J1314 | 2026-09-03 | CL46 | Completed
J1314 | 2026-09-04 | CL46 | Completed
J1314 | 2026-09-10 | CL46 | Completed
J1314 | 2026-09-11 | CL46 | Completed
J1314 | 2026-09-17 | CL46 | Completed
J1314 | 2026-09-18 | CL46 | Completed
J1314 | 2026-09-24 | CL46 | Completed
J1314 | 2026-09-25 | CL46 | Completed
J1314 | 2026-10-01 | CL46 | Completed
J1314 | 2026-10-02 | CL46 | Completed
J1314 | 2026-10-08 | CL46 | Completed
J1314 | 2026-10-09 | CL46 | Completed
J1314 | 2026-10-15 | CL46 | Completed
J1314 | 2026-10-16 | CL46 | Completed
J1314 | 2026-10-22 | CL46 | Completed
J1314 | 2026-10-23 | CL46 | Completed
J1314 | 2026-10-29 | CL46 | Completed
J1314 | 2026-10-30 | CL46 | Completed
J1315 | 2026-08-03 | CL49 | Completed
J1315 | 2026-08-04 | CL49 | Completed
J1315 | 2026-08-05 | CL49 | Completed
J1315 | 2026-08-06 | CL49 | Completed
J1315 | 2026-08-07 | CL49 | Completed
J1315 | 2026-08-10 | CL49 | Completed
J1315 | 2026-08-11 | CL49 | Completed
J1315 | 2026-08-12 | CL49 | Completed
J1315 | 2026-08-13 | CL49 | Completed
J1315 | 2026-08-14 | CL49 | Completed
J1315 | 2026-08-17 | CL49 | Completed
J1315 | 2026-08-18 | CL49 | Completed
J1315 | 2026-08-19 | CL49 | Completed
J1315 | 2026-08-20 | CL49 | Completed
J1315 | 2026-08-21 | CL49 | Completed
J1315 | 2026-08-24 | CL49 | Completed
J1315 | 2026-08-25 | CL49 | Completed
J1315 | 2026-08-26 | CL49 | Completed
J1315 | 2026-08-27 | CL49 | Completed
J1315 | 2026-08-28 | CL49 | Completed
J1315 | 2026-08-31 | CL49 | Skipped
J1315 | 2026-09-01 | CL49 | Completed
J1315 | 2026-09-02 | CL49 | Completed
J1315 | 2026-09-03 | CL49 | Completed
J1315 | 2026-09-04 | CL49 | Completed
J1315 | 2026-09-07 | CL49 | Completed
J1315 | 2026-09-08 | CL49 | Completed
J1315 | 2026-09-09 | CL49 | Completed
J1315 | 2026-09-10 | CL49 | Completed
J1315 | 2026-09-11 | CL49 | Completed
J1315 | 2026-09-14 | CL49 | Completed
J1315 | 2026-09-15 | CL49 | Completed
J1315 | 2026-09-16 | CL49 | Completed
J1315 | 2026-09-17 | CL49 | Completed
J1315 | 2026-09-18 | CL49 | Completed
J1315 | 2026-09-21 | CL49 | Completed
J1315 | 2026-09-22 | CL49 | Completed
J1315 | 2026-09-23 | CL49 | Completed
J1315 | 2026-09-24 | CL49 | Completed
J1315 | 2026-09-25 | CL49 | Completed
J1315 | 2026-09-28 | CL49 | Completed
J1315 | 2026-09-29 | CL49 | Completed
J1315 | 2026-09-30 | CL49 | Completed
J1315 | 2026-10-01 | CL49 | Completed
J1315 | 2026-10-02 | CL49 | Completed
J1315 | 2026-10-05 | CL49 | Completed
J1315 | 2026-10-06 | CL49 | Completed
J1315 | 2026-10-07 | CL49 | Completed
J1315 | 2026-10-08 | CL49 | Completed
J1315 | 2026-10-09 | CL49 | Completed
J1315 | 2026-10-12 | CL49 | Completed
J1315 | 2026-10-13 | CL49 | Completed
J1315 | 2026-10-14 | CL49 | Completed
J1315 | 2026-10-15 | CL49 | Completed
J1315 | 2026-10-16 | CL49 | Completed
J1315 | 2026-10-19 | CL49 | Completed
J1315 | 2026-10-20 | CL49 | Completed
J1315 | 2026-10-21 | CL49 | Completed
J1315 | 2026-10-22 | CL49 | Completed
J1315 | 2026-10-23 | CL49 | Completed
J1315 | 2026-10-26 | CL49 | Completed
J1315 | 2026-10-27 | CL49 | Completed
J1315 | 2026-10-28 | CL49 | Completed
J1315 | 2026-10-29 | CL49 | Completed
J1315 | 2026-10-30 | CL49 | Completed
J1316 | 2026-08-06 | CL55 | Completed
J1316 | 2026-09-03 | CL55 | Completed
J1316 | 2026-10-01 | CL55 | Completed
J1317 | 2026-08-04 | CL46 | Completed
J1317 | 2026-08-06 | CL46 | Completed
J1317 | 2026-08-11 | CL46 | Completed
J1317 | 2026-08-13 | CL46 | Completed
J1317 | 2026-08-18 | CL46 | Completed
J1317 | 2026-08-20 | CL46 | Completed
J1317 | 2026-08-25 | CL46 | Completed
J1317 | 2026-08-27 | CL46 | Completed
J1317 | 2026-09-01 | CL46 | Completed
J1317 | 2026-09-03 | CL46 | Completed
J1317 | 2026-09-08 | CL46 | Completed
J1317 | 2026-09-10 | CL46 | Completed
J1317 | 2026-09-15 | CL46 | Completed
J1317 | 2026-09-17 | CL46 | Completed
J1317 | 2026-09-22 | CL46 | Completed
J1317 | 2026-09-24 | CL46 | Completed
J1317 | 2026-09-29 | CL46 | Completed
J1317 | 2026-10-01 | CL46 | Completed
J1317 | 2026-10-06 | CL46 | Completed
J1317 | 2026-10-08 | CL46 | Completed
J1317 | 2026-10-13 | CL46 | Completed
J1317 | 2026-10-15 | CL46 | Completed
J1317 | 2026-10-20 | CL46 | Completed
J1317 | 2026-10-22 | CL46 | Completed
J1317 | 2026-10-27 | CL46 | Completed
J1317 | 2026-10-29 | CL46 | Completed
J1318 | 2026-08-18 | CL54 | Completed
J1318 | 2026-09-15 | CL54 | Completed
J1318 | 2026-10-13 | CL54 | Completed
J1319 | 2026-08-03 | CL43 | Completed
J1319 | 2026-08-07 | CL43 | Completed
J1319 | 2026-08-10 | CL43 | Completed
J1319 | 2026-08-14 | CL43 | Completed
J1319 | 2026-08-17 | CL43 | Completed
J1319 | 2026-08-21 | CL43 | Completed
J1319 | 2026-08-24 | CL43 | Completed
J1319 | 2026-08-28 | CL43 | Completed
J1319 | 2026-08-31 | CL43 | Completed
J1319 | 2026-09-04 | CL43 | Completed
J1319 | 2026-09-07 | CL43 | Completed
J1319 | 2026-09-11 | CL43 | Completed
J1319 | 2026-09-14 | CL43 | Completed
J1319 | 2026-09-18 | CL43 | Completed
J1319 | 2026-09-21 | CL43 | Completed
J1319 | 2026-09-25 | CL43 | Skipped
J1319 | 2026-09-28 | CL43 | Completed
J1319 | 2026-10-02 | CL43 | Completed
J1319 | 2026-10-05 | CL43 | Completed
J1319 | 2026-10-09 | CL43 | Completed
J1319 | 2026-10-12 | CL43 | Completed
J1319 | 2026-10-16 | CL43 | Completed
J1319 | 2026-10-19 | CL43 | Completed
J1319 | 2026-10-23 | CL43 | Completed
J1319 | 2026-10-26 | CL43 | Completed
J1319 | 2026-10-30 | CL43 | Completed
J1320 | 2026-08-06 | CL39 | Completed
J1320 | 2026-08-13 | CL39 | Completed
J1320 | 2026-08-20 | CL39 | Completed
J1320 | 2026-08-27 | CL39 | Completed
J1320 | 2026-09-03 | CL39 | Completed
J1320 | 2026-09-10 | CL39 | Completed
J1320 | 2026-09-17 | CL39 | Completed
J1320 | 2026-09-24 | CL39 | Completed
J1320 | 2026-10-01 | CL39 | Completed
J1320 | 2026-10-08 | CL39 | Completed
J1320 | 2026-10-15 | CL39 | Completed
J1320 | 2026-10-22 | CL39 | Completed
J1320 | 2026-10-29 | CL39 | Completed
J1321 | 2026-08-18 | CL55 | Completed
J1321 | 2026-09-15 | CL55 | Completed
J1321 | 2026-10-13 | CL55 | Completed
J1322 | 2026-08-03 | CL35 | Completed
J1322 | 2026-08-10 | CL35 | Completed
J1322 | 2026-08-17 | CL35 | Completed
J1322 | 2026-08-24 | CL35 | Completed
J1322 | 2026-08-31 | CL35 | Completed
J1322 | 2026-09-07 | CL35 | Completed
J1322 | 2026-09-14 | CL35 | Completed
J1322 | 2026-09-21 | CL35 | Completed
J1322 | 2026-09-28 | CL35 | Completed
J1322 | 2026-10-05 | CL35 | Completed
J1322 | 2026-10-12 | CL35 | Completed
J1322 | 2026-10-19 | CL35 | Completed
J1322 | 2026-10-26 | CL35 | Completed
J1323 | 2026-08-04 | CL45 | Completed
J1323 | 2026-08-11 | CL45 | Completed
J1323 | 2026-08-18 | CL45 | Completed
J1323 | 2026-08-25 | CL45 | Completed
J1323 | 2026-09-01 | CL45 | Completed
J1323 | 2026-09-08 | CL45 | Completed
J1323 | 2026-09-15 | CL45 | Completed
J1323 | 2026-09-22 | CL45 | Completed
J1323 | 2026-09-29 | CL45 | Completed
J1323 | 2026-10-06 | CL45 | Completed
J1323 | 2026-10-13 | CL45 | Completed
J1323 | 2026-10-20 | CL45 | Completed
J1323 | 2026-10-27 | CL45 | Completed
J1324 | 2026-08-05 | CL50 | Completed
J1324 | 2026-08-12 | CL50 | Completed
J1324 | 2026-08-19 | CL50 | Completed
J1324 | 2026-08-26 | CL50 | Completed
J1324 | 2026-09-02 | CL50 | Completed
J1324 | 2026-09-09 | CL50 | Completed
J1324 | 2026-09-16 | CL50 | Completed
J1324 | 2026-09-23 | CL50 | Completed
J1324 | 2026-09-30 | CL50 | Completed
J1324 | 2026-10-07 | CL50 | Completed
J1324 | 2026-10-14 | CL50 | Completed
J1324 | 2026-10-21 | CL50 | Completed
J1324 | 2026-10-28 | CL50 | Completed
J1325 | 2026-08-04 | CL31 | Completed
J1325 | 2026-08-07 | CL31 | Completed
J1325 | 2026-08-11 | CL31 | Completed
J1325 | 2026-08-14 | CL31 | Completed
J1325 | 2026-08-18 | CL31 | Completed
J1325 | 2026-08-21 | CL31 | Completed
J1325 | 2026-08-25 | CL31 | Completed
J1325 | 2026-08-28 | CL31 | Completed
J1325 | 2026-09-01 | CL31 | Completed
J1325 | 2026-09-04 | CL31 | Completed
J1325 | 2026-09-08 | CL31 | Completed
J1325 | 2026-09-11 | CL31 | Completed
J1325 | 2026-09-15 | CL31 | Completed
J1325 | 2026-09-18 | CL31 | Completed
J1325 | 2026-09-22 | CL31 | Skipped
J1325 | 2026-09-25 | CL31 | Completed
J1325 | 2026-09-29 | CL31 | Completed
J1325 | 2026-10-02 | CL31 | Completed
J1325 | 2026-10-06 | CL31 | Completed
J1325 | 2026-10-09 | CL31 | Completed
J1325 | 2026-10-13 | CL31 | Completed
J1325 | 2026-10-16 | CL31 | Completed
J1325 | 2026-10-20 | CL31 | Completed
J1325 | 2026-10-23 | CL31 | Completed
J1325 | 2026-10-27 | CL31 | Completed
J1325 | 2026-10-30 | CL31 | Completed
J1326 | 2026-08-03 | CL09 | Completed
J1326 | 2026-08-04 | CL09 | Completed
J1326 | 2026-08-05 | CL09 | Completed
J1326 | 2026-08-06 | CL09 | Completed
J1326 | 2026-08-07 | CL09 | Completed
J1326 | 2026-08-10 | CL09 | Completed
J1326 | 2026-08-11 | CL09 | Completed
J1326 | 2026-08-12 | CL09 | Completed
J1326 | 2026-08-13 | CL09 | Completed
J1326 | 2026-08-14 | CL09 | Completed
J1326 | 2026-08-17 | CL09 | Completed
J1326 | 2026-08-18 | CL09 | Completed
J1326 | 2026-08-19 | CL09 | Completed
J1326 | 2026-08-20 | CL09 | Completed
J1326 | 2026-08-21 | CL09 | Completed
J1326 | 2026-08-24 | CL09 | Completed
J1326 | 2026-08-25 | CL09 | Completed
J1326 | 2026-08-26 | CL09 | Completed
J1326 | 2026-08-27 | CL09 | Completed
J1326 | 2026-08-28 | CL09 | Completed
J1326 | 2026-08-31 | CL09 | Completed
J1326 | 2026-09-01 | CL09 | Completed
J1326 | 2026-09-02 | CL09 | Completed
J1326 | 2026-09-03 | CL09 | Completed
J1326 | 2026-09-04 | CL09 | Completed
J1326 | 2026-09-07 | CL09 | Completed
J1326 | 2026-09-08 | CL09 | Completed
J1326 | 2026-09-09 | CL09 | Completed
J1326 | 2026-09-10 | CL09 | Completed
J1326 | 2026-09-11 | CL09 | Completed
J1326 | 2026-09-14 | CL09 | Completed
J1326 | 2026-09-15 | CL09 | Completed
J1326 | 2026-09-16 | CL09 | Completed
J1326 | 2026-09-17 | CL09 | Completed
J1326 | 2026-09-18 | CL09 | Completed
J1326 | 2026-09-21 | CL09 | Completed
J1326 | 2026-09-22 | CL09 | Completed
J1326 | 2026-09-23 | CL09 | Completed
J1326 | 2026-09-24 | CL09 | Completed
J1326 | 2026-09-25 | CL09 | Completed
J1326 | 2026-09-28 | CL09 | Completed
J1326 | 2026-09-29 | CL09 | Completed
J1326 | 2026-09-30 | CL09 | Completed
J1326 | 2026-10-01 | CL09 | Completed
J1326 | 2026-10-02 | CL09 | Completed
J1326 | 2026-10-05 | CL09 | Completed
J1326 | 2026-10-06 | CL09 | Completed
J1326 | 2026-10-07 | CL09 | Completed
J1326 | 2026-10-08 | CL09 | Completed
J1326 | 2026-10-09 | CL09 | Completed
J1326 | 2026-10-12 | CL09 | Completed
J1326 | 2026-10-13 | CL09 | Completed
J1326 | 2026-10-14 | CL09 | Completed
J1326 | 2026-10-15 | CL09 | Completed
J1326 | 2026-10-16 | CL09 | Completed
J1326 | 2026-10-19 | CL09 | Completed
J1326 | 2026-10-20 | CL09 | Completed
J1326 | 2026-10-21 | CL09 | Completed
J1326 | 2026-10-22 | CL09 | Completed
J1326 | 2026-10-23 | CL09 | Completed
J1326 | 2026-10-26 | CL09 | Completed
J1326 | 2026-10-27 | CL09 | Completed
J1326 | 2026-10-28 | CL09 | Completed
J1326 | 2026-10-29 | CL09 | Completed
J1326 | 2026-10-30 | CL09 | Completed
J1327 | 2026-08-07 | CL47 | Completed
J1327 | 2026-08-14 | CL47 | Completed
J1327 | 2026-08-21 | CL47 | Completed
J1327 | 2026-08-28 | CL47 | Completed
J1327 | 2026-09-04 | CL47 | Completed
J1327 | 2026-09-11 | CL47 | Completed
J1327 | 2026-09-18 | CL47 | Completed
J1327 | 2026-09-25 | CL47 | Completed
J1327 | 2026-10-02 | CL47 | Completed
J1327 | 2026-10-09 | CL47 | Completed
J1327 | 2026-10-16 | CL47 | Completed
J1327 | 2026-10-23 | CL47 | Completed
J1327 | 2026-10-30 | CL47 | Completed
J1328 | 2026-08-05 | CL15 | Completed
J1328 | 2026-08-12 | CL15 | Completed
J1328 | 2026-08-19 | CL15 | Completed
J1328 | 2026-08-26 | CL15 | Completed
J1328 | 2026-09-02 | CL15 | Completed
J1328 | 2026-09-09 | CL15 | Completed
J1328 | 2026-09-16 | CL15 | Completed
J1328 | 2026-09-23 | CL15 | Completed
J1328 | 2026-09-30 | CL15 | Completed
J1328 | 2026-10-07 | CL15 | Completed
J1328 | 2026-10-14 | CL15 | Completed
J1328 | 2026-10-21 | CL15 | Completed
J1328 | 2026-10-28 | CL15 | Completed
J1329 | 2026-08-06 | CL54 | Completed
J1329 | 2026-09-03 | CL54 | Completed
J1329 | 2026-10-01 | CL54 | Completed
J1329 | 2026-10-29 | CL54 | Completed
J1330 | 2026-08-03 | CL15 | Completed
J1330 | 2026-08-06 | CL15 | Completed
J1330 | 2026-08-07 | CL15 | Completed
J1330 | 2026-08-10 | CL15 | Completed
J1330 | 2026-08-13 | CL15 | Completed
J1330 | 2026-08-14 | CL15 | Completed
J1330 | 2026-08-17 | CL15 | Completed
J1330 | 2026-08-20 | CL15 | Completed
J1330 | 2026-08-21 | CL15 | Completed
J1330 | 2026-08-24 | CL15 | Completed
J1330 | 2026-08-27 | CL15 | Completed
J1330 | 2026-08-28 | CL15 | Completed
J1330 | 2026-08-31 | CL15 | Completed
J1330 | 2026-09-03 | CL15 | Completed
J1330 | 2026-09-04 | CL15 | Completed
J1330 | 2026-09-07 | CL15 | Completed
J1330 | 2026-09-10 | CL15 | Completed
J1330 | 2026-09-11 | CL15 | Completed
J1330 | 2026-09-14 | CL15 | Completed
J1330 | 2026-09-17 | CL15 | Completed
J1330 | 2026-09-18 | CL15 | Completed
J1330 | 2026-09-21 | CL15 | Completed
J1330 | 2026-09-24 | CL15 | Completed
J1330 | 2026-09-25 | CL15 | Completed
J1330 | 2026-09-28 | CL15 | Completed
J1330 | 2026-10-01 | CL15 | Completed
J1330 | 2026-10-02 | CL15 | Completed
J1330 | 2026-10-05 | CL15 | Completed
J1330 | 2026-10-08 | CL15 | Completed
J1330 | 2026-10-09 | CL15 | Completed
J1330 | 2026-10-12 | CL15 | Completed
J1330 | 2026-10-15 | CL15 | Completed
J1330 | 2026-10-16 | CL15 | Completed
J1330 | 2026-10-19 | CL15 | Completed
J1330 | 2026-10-22 | CL15 | Completed
J1330 | 2026-10-23 | CL15 | Completed
J1330 | 2026-10-26 | CL15 | Completed
J1330 | 2026-10-29 | CL15 | Completed
J1330 | 2026-10-30 | CL15 | Completed
J1331 | 2026-08-04 | CL56 | Completed
J1331 | 2026-09-01 | CL56 | Completed
J1331 | 2026-10-06 | CL56 | Completed
J1332 | 2026-08-04 | CL04 | Completed
J1332 | 2026-08-05 | CL04 | Completed
J1332 | 2026-08-06 | CL04 | Completed
J1332 | 2026-08-11 | CL04 | Completed
J1332 | 2026-08-12 | CL04 | Completed
J1332 | 2026-08-13 | CL04 | Completed
J1332 | 2026-08-18 | CL04 | Completed
J1332 | 2026-08-19 | CL04 | Completed
J1332 | 2026-08-20 | CL04 | Completed
J1332 | 2026-08-25 | CL04 | Completed
J1332 | 2026-08-26 | CL04 | Completed
J1332 | 2026-08-27 | CL04 | Completed
J1332 | 2026-09-01 | CL04 | Completed
J1332 | 2026-09-02 | CL04 | Completed
J1332 | 2026-09-03 | CL04 | Completed
J1332 | 2026-09-08 | CL04 | Completed
J1332 | 2026-09-09 | CL04 | Completed
J1332 | 2026-09-10 | CL04 | Completed
J1332 | 2026-09-15 | CL04 | Completed
J1332 | 2026-09-16 | CL04 | Completed
J1332 | 2026-09-17 | CL04 | Completed
J1332 | 2026-09-22 | CL04 | Completed
J1332 | 2026-09-23 | CL04 | Completed
J1332 | 2026-09-24 | CL04 | Completed
J1332 | 2026-09-29 | CL04 | Completed
J1332 | 2026-09-30 | CL04 | Completed
J1332 | 2026-10-01 | CL04 | Completed
J1332 | 2026-10-06 | CL04 | Completed
J1332 | 2026-10-07 | CL04 | Completed
J1332 | 2026-10-08 | CL04 | Completed
J1332 | 2026-10-13 | CL04 | Completed
J1332 | 2026-10-14 | CL04 | Completed
J1332 | 2026-10-15 | CL04 | Completed
J1332 | 2026-10-20 | CL04 | Completed
J1332 | 2026-10-21 | CL04 | Completed
J1332 | 2026-10-22 | CL04 | Completed
J1332 | 2026-10-27 | CL04 | Completed
J1332 | 2026-10-28 | CL04 | Completed
J1332 | 2026-10-29 | CL04 | Completed
J1333 | 2026-08-03 | CL19 | Completed
J1333 | 2026-08-06 | CL19 | Completed
J1333 | 2026-08-10 | CL19 | Skipped
J1333 | 2026-08-13 | CL19 | Completed
J1333 | 2026-08-17 | CL19 | Completed
J1333 | 2026-08-20 | CL19 | Completed
J1333 | 2026-08-24 | CL19 | Completed
J1333 | 2026-08-27 | CL19 | Completed
J1333 | 2026-08-31 | CL19 | Completed
J1333 | 2026-09-03 | CL19 | Completed
J1333 | 2026-09-07 | CL19 | Completed
J1333 | 2026-09-10 | CL19 | Completed
J1333 | 2026-09-14 | CL19 | Completed
J1333 | 2026-09-17 | CL19 | Completed
J1333 | 2026-09-21 | CL19 | Completed
J1333 | 2026-09-24 | CL19 | Completed
J1333 | 2026-09-28 | CL19 | Completed
J1333 | 2026-10-01 | CL19 | Completed
J1333 | 2026-10-05 | CL19 | Completed
J1333 | 2026-10-08 | CL19 | Completed
J1333 | 2026-10-12 | CL19 | Completed
J1333 | 2026-10-15 | CL19 | Completed
J1333 | 2026-10-19 | CL19 | Skipped
J1333 | 2026-10-22 | CL19 | Completed
J1333 | 2026-10-26 | CL19 | Completed
J1333 | 2026-10-29 | CL19 | Completed
J1334 | 2026-08-05 | CL20 | Completed
J1334 | 2026-08-06 | CL20 | Completed
J1334 | 2026-08-12 | CL20 | Completed
J1334 | 2026-08-13 | CL20 | Completed
J1334 | 2026-08-19 | CL20 | Completed
J1334 | 2026-08-20 | CL20 | Completed
J1334 | 2026-08-26 | CL20 | Completed
J1334 | 2026-08-27 | CL20 | Completed
J1334 | 2026-09-02 | CL20 | Completed
J1334 | 2026-09-03 | CL20 | Completed
J1334 | 2026-09-09 | CL20 | Completed
J1334 | 2026-09-10 | CL20 | Completed
J1334 | 2026-09-16 | CL20 | Completed
J1334 | 2026-09-17 | CL20 | Completed
J1334 | 2026-09-23 | CL20 | Completed
J1334 | 2026-09-24 | CL20 | Completed
J1334 | 2026-09-30 | CL20 | Completed
J1334 | 2026-10-01 | CL20 | Completed
J1334 | 2026-10-07 | CL20 | Completed
J1334 | 2026-10-08 | CL20 | Completed
J1334 | 2026-10-14 | CL20 | Completed
J1334 | 2026-10-15 | CL20 | Completed
J1334 | 2026-10-21 | CL20 | Completed
J1334 | 2026-10-22 | CL20 | Completed
J1334 | 2026-10-28 | CL20 | Completed
J1334 | 2026-10-29 | CL20 | Completed
J1335 | 2026-08-07 | CL32 | Skipped
J1335 | 2026-08-14 | CL32 | Completed
J1335 | 2026-08-21 | CL32 | Completed
J1335 | 2026-08-28 | CL32 | Completed
J1335 | 2026-09-04 | CL32 | Completed
J1335 | 2026-09-11 | CL32 | Completed
J1335 | 2026-09-18 | CL32 | Completed
J1335 | 2026-09-25 | CL32 | Completed
J1335 | 2026-10-02 | CL32 | Completed
J1335 | 2026-10-09 | CL32 | Completed
J1335 | 2026-10-16 | CL32 | Completed
J1335 | 2026-10-23 | CL32 | Completed
J1335 | 2026-10-30 | CL32 | Completed
J1336 | 2026-08-06 | CL55 | Completed
J1336 | 2026-09-03 | CL55 | Completed
J1336 | 2026-10-01 | CL55 | Completed
J1336 | 2026-10-29 | CL55 | Completed
J1337 | 2026-08-03 | CL21 | Completed
J1337 | 2026-08-10 | CL21 | Completed
J1337 | 2026-08-17 | CL21 | Completed
J1337 | 2026-08-24 | CL21 | Completed
J1337 | 2026-08-31 | CL21 | Completed
J1337 | 2026-09-07 | CL21 | Completed
J1337 | 2026-09-14 | CL21 | Completed
J1337 | 2026-09-21 | CL21 | Completed
J1337 | 2026-09-28 | CL21 | Completed
J1337 | 2026-10-05 | CL21 | Completed
J1337 | 2026-10-12 | CL21 | Completed
J1337 | 2026-10-19 | CL21 | Completed
J1337 | 2026-10-26 | CL21 | Completed
J1338 | 2026-08-03 | CL18 | Completed
J1338 | 2026-08-10 | CL18 | Completed
J1338 | 2026-08-17 | CL18 | Completed
J1338 | 2026-08-24 | CL18 | Completed
J1338 | 2026-08-31 | CL18 | Completed
J1338 | 2026-09-07 | CL18 | Completed
J1338 | 2026-09-14 | CL18 | Completed
J1338 | 2026-09-21 | CL18 | Completed
J1338 | 2026-09-28 | CL18 | Completed
J1338 | 2026-10-05 | CL18 | Completed
J1338 | 2026-10-12 | CL18 | Completed
J1338 | 2026-10-19 | CL18 | Completed
J1338 | 2026-10-26 | CL18 | Completed
J1339 | 2026-08-04 | CL36 | Completed
J1339 | 2026-08-11 | CL36 | Completed
J1339 | 2026-08-18 | CL36 | Completed
J1339 | 2026-08-25 | CL36 | Completed
J1339 | 2026-09-01 | CL36 | Completed
J1339 | 2026-09-08 | CL36 | Completed
J1339 | 2026-09-15 | CL36 | Completed
J1339 | 2026-09-22 | CL36 | Completed
J1339 | 2026-09-29 | CL36 | Completed
J1339 | 2026-10-06 | CL36 | Completed
J1339 | 2026-10-13 | CL36 | Completed
J1339 | 2026-10-20 | CL36 | Completed
J1339 | 2026-10-27 | CL36 | Skipped

## QBO Customers
QBO customers (parents) and sub-customers (locations)
Work sample: realistic data, built to show how I approach this work.
QBO ID | Display name | Parent | Email | Active | Type | Templates
Q0001 | The Oakwood Vet Clinic |  | accounts@oakwoodvetclinic.example | true | Customer | 0
Q0002 | The Clearwater Dental Pty Ltd |  | accounts@clearwaterdental.example | true | Customer | 0
Q0003 | Riverside Insurance Brokers Pty Ltd |  | accounts@riversideinsuran.example | true | Customer | 0
Q0004 | Ironbark Pathology Pty Ltd |  | accounts@ironbarkpatholog.example | true | Customer | 0
Q0005 | WESTEND FITNESS PTY LTD |  | accounts@westendfitness.example | true | Customer | 0
Q0006 | Redgum Dental |  | accounts@redgumdental.example | true | Customer | 0
Q0007 | Elm Street Physiotherapy |  | accounts@elmstreetphysiot.example | true | Customer | 0
Q0008 | Wattle Grove Property Group |  | accounts@wattlegroveprope.example | true | Customer | 0
Q0009 | Hillcrest Physiotherapy P/L |  | accounts@hillcrestphysiot.example | true | Customer | 0
Q0010 | The Kingsley Real Estate |  | accounts@kingsleyrealesta.example | true | Customer | 0
Q0011 | Wattle Grove Medical Centre P/L |  | accounts@wattlegrovemedic.example | true | Customer | 0
Q0012 | BLUESTONE ENGINEERING |  | accounts@bluestoneenginee.example | true | Customer | 0
Q0013 | CLEARWATER INSURANCE BROKERS PTY LTD |  | accounts@clearwaterinsura.example | true | Customer | 0
Q0014 | REDGUM OPTOMETRISTS PTY LTD |  | accounts@redgumoptometris.example | true | Customer | 0
Q0015 | Northside Accountants |  | accounts@northsideaccount.example | true | Customer | 0
Q0016 | Oakwood Accountants Pty Ltd |  | accounts@oakwoodaccountan.example | true | Customer | 0
Q0017 | Northside Engineering Pty Ltd |  | accounts@northsideenginee.example | true | Customer | 0
Q0018 | Ashwood Early Learning |  | accounts@ashwoodearlylear.example | true | Customer | 0
Q0019 | SILVERTON PHARMACY |  | accounts@silvertonpharmac.example | true | Customer | 0
Q0020 | Brightside Podiatry |  | accounts@brightsidepodiat.example | true | Customer | 0
Q0021 | Ashwood Optometrists |  | accounts@ashwoodoptometri.example | true | Customer | 0
Q0022 | Parkside Accountants Pty Ltd |  | accounts@parksideaccounta.example | true | Customer | 0
Q0023 | Brightside Motors P/L |  | accounts@brightsidemotors.example | true | Customer | 0
Q0024 | Westend Motors Pty Ltd |  | accounts@westendmotors.example | true | Customer | 0
Q0025 | OAKWOOD LAWYERS PTY LTD |  | accounts@oakwoodlawyers.example | true | Customer | 0
Q0026 | Riverside Medical Centre |  | accounts@riversidemedical.example | true | Customer | 0
Q0027 | Riverside Motors |  | accounts@riversidemotors.example | true | Customer | 0
Q0028 | The Parkside Pathology Pty Ltd |  | accounts@parksidepatholog.example | true | Customer | 0
Q0029 | The Sunbury Accountants Pty Ltd |  | accounts@sunburyaccountan.example | true | Customer | 0
Q0030 | Sunbury Early Learning |  | accounts@sunburyearlylear.example | true | Customer | 0
Q0031 | The Silverton Lawyers Pty Ltd |  | accounts@silvertonlawyers.example | true | Customer | 0
Q0032 | Waverley Accountants Pty Ltd |  | accounts@waverleyaccounta.example | true | Customer | 0
Q0033 | The Westend Podiatry |  | accounts@westendpodiatry.example | true | Customer | 0
Q0034 | LAKESIDE ENGINEERING PTY LTD |  | accounts@lakesideengineer.example | true | Customer | 0
Q0035 | Kingsley Financial Planning |  | accounts@kingsleyfinancia.example | true | Customer | 0
Q0036 | The Wattle Grove Physiotherapy |  | accounts@wattlegrovephysi.example | true | Customer | 0
Q0037 | Elm Street Fitness |  | accounts@elmstreetfitness.example | true | Customer | 0
Q0038 | Wattle Grove Dental Pty Ltd |  | accounts@wattlegrovedenta.example | true | Customer | 0
Q0039 | The Lakeside Vet Clinic |  | accounts@lakesidevetclini.example | true | Customer | 0
Q0040 | Clearwater Property Group |  | accounts@clearwaterproper.example | true | Customer | 0
Q0041 | Eastwood Real Estate Pty Ltd |  | accounts@eastwoodrealesta.example | true | Customer | 0
Q0042 | Clearwater Physiotherapy |  | accounts@clearwaterphysio.example | true | Customer | 0
Q0043 | Greenway Physiotherapy |  | accounts@greenwayphysioth.example | true | Customer | 0
Q0044 | Fairfield Engineering Pty Ltd |  | accounts@fairfieldenginee.example | true | Customer | 0
Q0045 | Westend Optometrists P/L |  | accounts@westendoptometri.example | true | Customer | 0
Q0046 | Kingsley Insurance Brokers Pty Ltd |  | accounts@kingsleyinsuranc.example | true | Customer | 0
Q0047 | Bluestone Learning Centre Pty Ltd |  | accounts@bluestonelearnin.example | true | Customer | 0
Q0048 | Oakwood Logistics |  | accounts@oakwoodlogistics.example | true | Customer | 0
Q0049 | Banksia Insurance Brokers |  | accounts@banksiainsurance.example | true | Customer | 0
Q0050 | The Sunbury Lawyers Pty Ltd |  | accounts@sunburylawyers.example | true | Customer | 0
Q0051 | COBBLESTONE REAL ESTATE PTY LTD |  | accounts@cobblestonereale.example | true | Customer | 0
Q0052 | Bayview Engineering Pty Ltd |  | accounts@bayviewengineeri.example | true | Customer | 0
Q0053 | The Oakwood Financial Planning Pty Ltd |  | accounts@oakwoodfinancial.example | true | Customer | 0
Q0054 | The Brightside Dental Pty Ltd |  | accounts@brightsidedental.example | true | Customer | 0
Q0055 | Ashwood Physiotherapy |  | accounts@ashwoodphysiothe.example | true | Customer | 0
Q0056 | The Bluestone Dental |  | accounts@bluestonedental.example | true | Customer | 0
Q0057 | The Kingsley Accountants |  | accounts@kingsleyaccounta.example | true | Customer | 0
Q0058 | CLEARWATER EARLY LEARNING PTY LTD |  | accounts@clearwaterearlyl.example | true | Customer | 0
Q0059 | Banksia Pathology |  | accounts@banksiapathology.example | true | Customer | 0
Q0060 | SOUTHGATE FINANCIAL PLANNING PTY LTD |  | accounts@southgatefinanci.example | true | Customer | 0
Q0061 | BLUESTONE LAWYERS PTY LTD |  | accounts@bluestonelawyers.example | true | Customer | 0
Q0062 | Riverside Lawyers Pty Ltd |  | accounts@riversidelawyers.example | true | Customer | 0
Q0063 | Banksia Accountants |  | accounts@banksiaaccountan.example | true | Customer | 0
Q0064 | Ironbark Physiotherapy |  | accounts@ironbarkphysioth.example | true | Customer | 0
Q0065 | Wattle Grove Lawyers |  | accounts@wattlegrovelawye.example | true | Customer | 0
Q0066 | Kingsley Medical Centre Pty Ltd |  | accounts@kingsleymedicalc.example | true | Customer | 0
Q0067 | The Ashwood Engineering |  | accounts@ashwoodengineeri.example | true | Customer | 0
Q0068 | Sunbury Physiotherapy Pty Ltd |  | accounts@sunburyphysiothe.example | true | Customer | 0
Q0069 | Eastwood Pathology |  | accounts@eastwoodpatholog.example | true | Customer | 0
Q0070 | Waverley Fitness |  | accounts@waverleyfitness.example | true | Customer | 0
Q0071 | Clearwater Logistics |  | accounts@clearwaterlogist.example | true | Customer | 0
Q0072 | Wattle Grove Fitness |  | accounts@wattlegrovefitne.example | true | Customer | 0
Q0073 | Ashwood Medical Centre |  | accounts@ashwoodmedicalce.example | true | Customer | 0
Q0074 | Parkside Vet Clinic |  | accounts@parksidevetclini.example | true | Customer | 0
Q0075 | Wattle Grove Architects |  | accounts@wattlegrovearchi.example | true | Customer | 0
Q0076 | Bayview Pharmacy Pty Ltd |  | accounts@bayviewpharmacy.example | true | Customer | 0
Q0077 | Hillcrest Accountants Pty Ltd |  | accounts@hillcrestaccount.example | true | Customer | 0
Q0078 | Lakeside Architects |  | accounts@lakesidearchitec.example | true | Customer | 0
Q0079 | Ashwood Accountants |  | accounts@ashwoodaccountan.example | true | Customer | 0
Q0080 | Westend Property Group Pty Ltd |  | accounts@westendpropertyg.example | true | Customer | 0
Q0081 | Eastwood Optometrists |  | accounts@eastwoodoptometr.example | true | Customer | 0
Q0082 | The Westend Medical Centre |  | accounts@westendmedicalce.example | true | Customer | 0
Q0083 | Riverside Learning Centre |  | accounts@riversidelearnin.example | true | Customer | 0
Q0084 | Silverton Insurance Brokers P/L |  | accounts@silvertoninsuran.example | true | Customer | 0
Q0085 | Greenway Podiatry P/L |  | accounts@greenwaypodiatry.example | true | Customer | 0
Q0086 | Banksia Logistics Pty Ltd |  | accounts@banksialogistics.example | true | Customer | 0
Q0087 | Sunbury Architects P/L |  | accounts@sunburyarchitect.example | true | Customer | 0
Q0088 | Cobblestone Physiotherapy P/L |  | accounts@cobblestonephysi.example | true | Customer | 0
Q0089 | Banksia Real Estate |  | accounts@banksiarealestat.example | true | Customer | 0
Q0090 | The Northside Pathology Pty Ltd |  | accounts@northsidepatholo.example | true | Customer | 0
Q0091 | Harbourside Lawyers |  | accounts@harboursidelawye.example | true | Customer | 0
Q0092 | Kingsley Fitness Pty Ltd |  | accounts@kingsleyfitness.example | true | Customer | 0
Q0093 | LAKESIDE OPTOMETRISTS |  | accounts@lakesideoptometr.example | true | Customer | 0
Q0094 | Southgate Dental Pty Ltd |  | accounts@southgatedental.example | true | Customer | 0
Q0095 | SUNBURY OPTOMETRISTS |  | accounts@sunburyoptometri.example | true | Customer | 0
Q0096 | Bayview Vet Clinic |  | accounts@bayviewvetclinic.example | true | Customer | 0
Q0097 | The Redgum Pathology Pty Ltd |  | accounts@redgumpathology.example | true | Customer | 0
Q0098 | Greenway Medical Centre Pty Ltd |  | accounts@greenwaymedicalc.example | true | Customer | 0
Q0099 | Westend Physiotherapy Pty Ltd |  | accounts@westendphysiothe.example | true | Customer | 0
Q0100 | Riverside Podiatry Pty Ltd |  | accounts@riversidepodiatr.example | true | Customer | 0
Q0101 | The Northside Learning Centre |  | accounts@northsidelearnin.example | true | Customer | 0
Q0102 | The Harbourside Logistics Pty Ltd |  | accounts@harboursidelogis.example | true | Customer | 0
Q0103 | Redgum Podiatry |  | accounts@redgumpodiatry.example | true | Customer | 0
Q0104 | Harbourside Chiropractic |  | accounts@harboursidechiro.example | true | Customer | 0
Q0105 | Hillcrest Lawyers |  | accounts@hillcrestlawyers.example | true | Customer | 0
Q0106 | Silverton Logistics Pty Ltd |  | accounts@silvertonlogisti.example | true | Customer | 0
Q0107 | The Hillcrest Motors Pty Ltd |  | accounts@hillcrestmotors.example | true | Customer | 0
Q0108 | Southgate Pathology Pty Ltd |  | accounts@southgatepatholo.example | true | Customer | 0
Q0109 | Westend Engineering |  | accounts@westendengineeri.example | true | Customer | 0
Q0110 | Lakeside Real Estate |  | accounts@lakesiderealesta.example | true | Customer | 0
Q0111 | Harbourside Pharmacy Pty Ltd |  | accounts@harboursidepharm.example | true | Customer | 0
Q0112 | Brightside Early Learning |  | accounts@brightsideearlyl.example | true | Customer | 0
Q0113 | Southgate Engineering |  | accounts@southgateenginee.example | true | Customer | 0
Q0114 | Riverside Dental Pty Ltd |  | accounts@riversidedental.example | true | Customer | 0
Q0115 | Bayview Early Learning Pty Ltd |  | accounts@bayviewearlylear.example | true | Customer | 0
Q0116 | Elm Street Financial Planning Pty Ltd |  | accounts@elmstreetfinanci.example | true | Customer | 0
Q0117 | Ashwood Property Group |  | accounts@ashwoodpropertyg.example | true | Customer | 0
Q0118 | The Northside Early Learning Pty Ltd |  | accounts@northsideearlyle.example | true | Customer | 0
Q0119 | Brightside Logistics Pty Ltd |  | accounts@brightsidelogist.example | true | Customer | 0
Q0120 | Elm Street Early Learning |  | accounts@elmstreetearlyle.example | true | Customer | 0
Q0121 | Redgum Financial Planning |  | accounts@redgumfinancialp.example | true | Customer | 0
Q0122 | The Lakeside Fitness Pty Ltd |  | accounts@lakesidefitness.example | true | Customer | 0
Q0123 | Elm Street Logistics P/L |  | accounts@elmstreetlogisti.example | true | Customer | 0
Q0124 | LAKESIDE INSURANCE BROKERS |  | accounts@lakesideinsuranc.example | true | Customer | 0
Q0125 | Elm Street Pathology Pty Ltd |  | accounts@elmstreetpatholo.example | true | Customer | 0
Q0126 | The Fairfield Accountants Pty Ltd |  | accounts@fairfieldaccount.example | true | Customer | 0
Q0127 | Fairfield Dental |  | accounts@fairfielddental.example | true | Customer | 0
Q0128 | The Oakwood Medical Centre Pty Ltd |  | accounts@oakwoodmedicalce.example | true | Customer | 0
Q0129 | Banksia Architects |  | accounts@banksiaarchitect.example | true | Customer | 0
Q0130 | The Ironbark Engineering Pty Ltd |  | accounts@ironbarkengineer.example | true | Customer | 0
Q0131 | Wattle Grove Financial Planning |  | accounts@wattlegrovefinan.example | true | Customer | 0
Q0132 | Parkside Fitness |  | accounts@parksidefitness.example | true | Customer | 0
Q0133 | Greenway Chiropractic P/L |  | accounts@greenwaychiropra.example | true | Customer | 0
Q0134 | Bayview Real Estate |  | accounts@bayviewrealestat.example | true | Customer | 0
Q0135 | RIVERSIDE PHARMACY |  | accounts@riversidepharmac.example | true | Customer | 0
Q0136 | Elm Street Chiropractic Pty Ltd |  | accounts@elmstreetchiropr.example | true | Customer | 0
Q0137 | Ironbark Real Estate Pty Ltd |  | accounts@ironbarkrealesta.example | true | Customer | 0
Q0138 | ELM STREET MOTORS |  | accounts@elmstreetmotors.example | true | Customer | 0
Q0139 | Sunbury Engineering Pty Ltd |  | accounts@sunburyengineeri.example | true | Customer | 0
Q0140 | Ashwood Dental Pty Ltd |  | accounts@ashwooddental.example | true | Customer | 0
Q0141 | Bluestone Early Learning P/L |  | accounts@bluestoneearlyle.example | true | Customer | 0
Q0142 | Harbourside Property Group |  | accounts@harboursideprope.example | true | Customer | 0
Q0143 | RIVERSIDE ENGINEERING PTY LTD |  | accounts@riversideenginee.example | true | Customer | 0
Q0144 | ASHWOOD LAWYERS |  | accounts@ashwoodlawyers.example | true | Customer | 0
Q0145 | Bayview Fitness P/L |  | accounts@bayviewfitness.example | true | Customer | 0
Q0146 | The Ironbark Property Group Pty Ltd |  | accounts@ironbarkproperty.example | true | Customer | 0
Q0147 | Oakwood Engineering |  | accounts@oakwoodengineeri.example | true | Customer | 0
Q0148 | Waverley Physiotherapy |  | accounts@waverleyphysioth.example | true | Customer | 0
Q0149 | Harbourside Insurance Brokers Pty Ltd |  | accounts@harboursideinsur.example | true | Customer | 0
Q0150 | Harbourside Real Estate |  | accounts@harboursidereale.example | true | Customer | 0
Q0151 | Eastwood Podiatry |  | accounts@eastwoodpodiatry.example | true | Customer | 0
Q0152 | The Cityside Real Estate |  | accounts@citysiderealesta.example | true | Customer | 0
Q0153 | Parkside Dental |  | accounts@parksidedental.example | true | Customer | 0
Q0154 | Parkside Dental Group |  | accounts@parksidedentalgr2.example | true | Customer | 0
Q0155 | Northside Physiotherapy |  | accounts@northsidephysiot.example | true | Customer | 0
Q0156 | North Side Physiotherapy |  | accounts@northsidephysiot2.example | true | Customer | 0
Q0157 | Bayview Accountants |  | accounts@bayviewaccountan.example | true | Customer | 0
Q0158 | BAY VIEW ACCOUNTANTS |  | accounts@bayviewaccountan2.example | true | Customer | 0
Q0159 | Northside Enginering - Accounts |  |  | true | Customer | 0
Q0160 | Hillcrest Accontants - Accounts |  | accounts@hillcrestaccount.example | true | Customer | 0
Q0161 | Kngsley Fitness |  | accounts@kingsleyfitness.example | true | Customer | 0
Q0162 | Fairfield Engineerng |  |  | true | Customer | 0
Q0163 | Westend Poiatry - Accounts |  | accounts@westendpodiatry.example | true | Customer | 0
Q0164 | Banksia Logistics - Accounts |  | accounts@banksialogistics.example | true | Customer | 0
Q0165 | Elm Street Lgistics - Accounts |  |  | true | Customer | 0
Q0166 | Lakeside Inusrance Brokers - Accounts |  | accounts@lakesideinsuranc.example | true | Customer | 0
Q0167 | Ashwod Medical Centre - Accounts |  | accounts@ashwoodmedicalce.example | true | Customer | 0
Q0168 | Harbourside Chiorpractic - Accounts |  |  | true | Customer | 0
Q0169 | 218 High Road, Bentleigh | Q0001 |  | true | Location | 1
Q0170 | 162 Station Pde, Oakleigh | Q0001 |  | true | Location | 1
Q0171 | 273 Albert Road, Deer Park | Q0002 |  | true | Location | 1
Q0172 | 59 Station Parade, Bundoora | Q0003 |  | true | Location | 1
Q0173 | 224 Ballarat Pde, Footscray | Q0004 |  | true | Location | 1
Q0174 | 77 Ballarat Pde, Brighton | Q0005 |  | true | Location | 1
Q0175 | 290A Ballarat Hwy, Bundoora | Q0006 |  | true | Location | 1
Q0176 | 359 Glenferrie Ave, Werribee | Q0006 |  | true | Location | 1
Q0177 | 315 Park Parade, Oakleigh | Q0007 |  | true | Location | 1
Q0178 | 359 Albert Street, Point Cook | Q0007 |  | true | Location | 0
Q0179 | 169 King St, Hawthorn | Q0008 |  | true | Location | 1
Q0180 | 396 Park Hwy, Epping | Q0009 |  | true | Location | 1
Q0181 | 214A Nepean Parade, Thornbury | Q0009 |  | true | Location | 1
Q0182 | 208 Main Ave, Mitcham | Q0010 |  | true | Location | 2
Q0183 | 208 High Ave, Kew | Q0010 |  | true | Location | 1
Q0184 | 462 Mason Rd, Clayton | Q0011 |  | true | Location | 0
Q0185 | 201 Plenty Ave, Coburg | Q0012 |  | true | Location | 1
Q0186 | 164 Whitehorse St, Mentone | Q0013 |  | true | Location | 1
Q0187 | 480 King Ave, Camberwell | Q0014 |  | true | Location | 2
Q0188 | 426 Mason St, Cheltenham | Q0015 |  | true | Location | 2
Q0189 | 351 Burke Road, Oakleigh | Q0015 |  | true | Location | 1
Q0190 | 354 High Street, Clayton | Q0015 |  | true | Location | 1
Q0191 | 54 Mason Parade, Reservoir | Q0016 |  | true | Location | 1
Q0192 | 430 Victoria Road, St Kilda | Q0159 |  | true | Location | 1
Q0193 | 195/12 Railway Hwy, Bentleigh | Q0017 |  | true | Location | 1
Q0194 | 10 Queen Hwy, Deer Park | Q0017 |  | true | Location | 1
Q0195 | 17 Park Avenue, St Kilda | Q0159 |  | true | Location | 1
Q0196 | 378 Plenty St, Camberwell | Q0018 |  | true | Location | 1
Q0197 | 266 Union Ave, Point Cook | Q0019 |  | true | Location | 1
Q0198 | 98 Park Road, Kew | Q0019 |  | true | Location | 0
Q0199 | 107 Barkly Hwy, Bundoora | Q0019 |  | true | Location | 1
Q0200 | 298 Main Rd, Footscray | Q0019 |  | true | Location | 2
Q0201 | 142 Plenty Rd, Camberwell | Q0020 |  | true | Location | 1
Q0202 | 195 Nicholson Road, Ringwood | Q0021 |  | true | Location | 1
Q0203 | 245 Ballarat Avenue, Ringwood | Q0021 |  | true | Location | 1
Q0204 | 22 Hopkins Road, Bundoora | Q0022 |  | true | Location | 1
Q0205 | 356 Albert Ave, Northcote | Q0022 |  | true | Location | 2
Q0206 | 364/12 High Rd, Heidelberg | Q0023 |  | true | Location | 0
Q0207 | 417 Main Rd, Sunshine | Q0024 |  | true | Location | 1
Q0208 | 37 Nicholson Highway, Williamstown | Q0024 |  | true | Location | 1
Q0209 | 117 Railway Hwy, Epping | Q0024 |  | true | Location | 1
Q0210 | 453 Plenty Pde, Moorabbin | Q0025 |  | true | Location | 0
Q0211 | 188 Nicholson Rd, Essendon | Q0025 |  | true | Location | 1
Q0212 | 300 Sydney Hwy, Camberwell | Q0026 |  | true | Location | 0
Q0213 | 205 Railway St, Altona | Q0027 |  | true | Location | 1
Q0214 | 359 King Rd, Yarraville | Q0028 |  | true | Location | 1
Q0215 | 313A Queen Street, Camberwell | Q0029 |  | true | Location | 0
Q0216 | 386 Nepean Rd, Glen Waverley | Q0030 |  | true | Location | 1
Q0217 | 255 Glenferrie Pde, Thornbury | Q0031 |  | true | Location | 0
Q0218 | 23A Ballarat Street, Brunswick | Q0032 |  | true | Location | 0
Q0219 | 310 Ballarat Ave, Brunswick | Q0163 |  | true | Location | 2
Q0220 | 269 Victoria Avenue, Thornbury | Q0163 |  | true | Location | 2
Q0221 | 332A Glenferrie Pde, Essendon | Q0163 |  | true | Location | 1
Q0222 | 157 Whitehorse Parade, Deer Park | Q0034 |  | true | Location | 1
Q0223 | 439 Sydney Pde, Maribyrnong | Q0034 |  | true | Location | 1
Q0224 | 204 Bridge Highway, Oakleigh | Q0035 |  | true | Location | 2
Q0225 | 48 Ballarat Pde, Cheltenham | Q0036 |  | true | Location | 1
Q0226 | 479 Mason Parade, Hawthorn | Q0037 |  | true | Location | 1
Q0227 | 450 King Rd, Doncaster | Q0037 |  | true | Location | 1
Q0228 | 259 Union Ave, Hawthorn | Q0038 |  | true | Location | 1
Q0229 | 426 Ballarat Pde, Point Cook | Q0039 |  | true | Location | 1
Q0230 | 164 Nicholson St, Laverton | Q0039 |  | true | Location | 2
Q0231 | 143/12 Nepean Street, Frankston | Q0040 |  | true | Location | 3
Q0232 | 380 Nepean Pde, Laverton | Q0040 |  | true | Location | 1
Q0233 | 296 Barkly Hwy, Hawthorn | Q0041 |  | true | Location | 3
Q0234 | 46 Main Ave, Bentleigh | Q0042 |  | true | Location | 2
Q0235 | 211 Union Road, Burwood | Q0042 |  | true | Location | 1
Q0236 | 418 Nicholson Ave, Burwood | Q0043 |  | true | Location | 1
Q0237 | 43 Plenty Ave, Bentleigh | Q0044 |  | true | Location | 1
Q0238 | 27 Railway Avenue, Cheltenham | Q0162 |  | true | Location | 2
Q0239 | 225/12 Glenferrie Pde, Mentone | Q0045 |  | true | Location | 1
Q0240 | 225 Park Ave, Reservoir | Q0046 |  | true | Location | 3
Q0241 | 410 Burke Hwy, Point Cook | Q0046 |  | true | Location | 1
Q0242 | 205 Burke Highway, Glen Waverley | Q0047 |  | true | Location | 1
Q0243 | 189 Union Highway, Hawthorn | Q0048 |  | true | Location | 2
Q0244 | 128 Victoria Road, Blackburn | Q0048 |  | true | Location | 0
Q0245 | 375 Station Hwy, Cheltenham | Q0048 |  | true | Location | 2
Q0246 | 378 Burke Highway, Box Hill | Q0048 |  | true | Location | 1
Q0247 | 185 Church Parade, Burwood | Q0049 |  | true | Location | 2
Q0248 | 115 Nepean Pde, Reservoir | Q0050 |  | true | Location | 1
Q0249 | 96A Glenferrie Pde, Essendon | Q0050 |  | true | Location | 1
Q0250 | 158 Station St, Mentone | Q0050 |  | true | Location | 1
Q0251 | 476 Sydney Hwy, Frankston | Q0051 |  | true | Location | 1
Q0252 | 436/12 Nepean Highway, Sunshine | Q0052 |  | true | Location | 1
Q0253 | 394 Ballarat Avenue, Brighton | Q0053 |  | true | Location | 2
Q0254 | 135 Victoria Pde, Dandenong | Q0054 |  | true | Location | 1
Q0255 | 472 Barkly Pde, Moorabbin | Q0054 |  | true | Location | 1
Q0256 | 151 Nicholson Street, Point Cook | Q0055 |  | true | Location | 1
Q0257 | 4A Gilbert Rd, Camberwell | Q0055 |  | true | Location | 1
Q0258 | 144 Burke Avenue, Coburg | Q0055 |  | true | Location | 1
Q0259 | 182 King Ave, Footscray | Q0055 |  | true | Location | 1
Q0260 | 79/12 Glenferrie Pde, Camberwell | Q0056 |  | true | Location | 1
Q0261 | 401 Park Highway, Burwood | Q0056 |  | true | Location | 2
Q0262 | 401 Burke St, Burwood | Q0056 |  | true | Location | 1
Q0263 | 11 Hopkins Ave, Ringwood | Q0056 |  | true | Location | 1
Q0264 | 263 Nepean Highway, Altona | Q0057 |  | true | Location | 1
Q0265 | 288 Main Hwy, Northcote | Q0058 |  | true | Location | 2
Q0266 | 459 Park Ave, Deer Park | Q0059 |  | true | Location | 1
Q0267 | 464 Barkly Rd, Blackburn | Q0060 |  | true | Location | 1
Q0268 | 90A Albert Pde, Bentleigh | Q0060 |  | true | Location | 1
Q0269 | 29 Burke Pde, Burwood | Q0061 |  | true | Location | 1
Q0270 | 23 Station Pde, Glen Waverley | Q0062 |  | true | Location | 2
Q0271 | 251 Union Ave, Altona | Q0063 |  | true | Location | 1
Q0272 | 270 Station Rd, Doncaster | Q0063 |  | true | Location | 2
Q0273 | 463 Gilbert Street, Glen Waverley | Q0063 |  | true | Location | 1
Q0274 | 59 King Hwy, Point Cook | Q0064 |  | true | Location | 1
Q0275 | 61 Church Street, Point Cook | Q0064 |  | true | Location | 2
Q0276 | 280 Railway Road, Point Cook | Q0065 |  | true | Location | 2
Q0277 | 149 Main Road, Point Cook | Q0066 |  | true | Location | 2
Q0278 | 313 King Rd, Hawthorn | Q0066 |  | true | Location | 1
Q0279 | 155 Hopkins Road, Glen Waverley | Q0067 |  | true | Location | 2
Q0280 | 284 Park Pde, Point Cook | Q0068 |  | true | Location | 1
Q0281 | 85 Nepean Road, Frankston | Q0068 |  | true | Location | 1
Q0282 | 231 Church Hwy, Hawthorn | Q0068 |  | true | Location | 1
Q0283 | 223A Nicholson Parade, Werribee | Q0069 |  | true | Location | 2
Q0284 | 382 Hopkins Street, Footscray | Q0070 |  | true | Location | 1
Q0285 | 443 Station Rd, Footscray | Q0070 |  | true | Location | 2
Q0286 | 127 Main Highway, Reservoir | Q0071 |  | true | Location | 1
Q0287 | 68 Church Pde, Essendon | Q0072 |  | true | Location | 0
Q0288 | 102 Union Rd, St Kilda | Q0072 |  | true | Location | 2
Q0289 | 61 Church Rd, Bundoora | Q0167 |  | true | Location | 1
Q0290 | 287 Whitehorse Hwy, Deer Park | Q0074 |  | true | Location | 1
Q0291 | 289 Nepean Street, Bentleigh | Q0075 |  | true | Location | 1
Q0292 | 221 Plenty Ave, Footscray | Q0076 |  | true | Location | 1
Q0293 | 77 Mason Hwy, Mitcham | Q0160 |  | true | Location | 1
Q0294 | 170 Railway Hwy, Reservoir | Q0078 |  | true | Location | 1
Q0295 | 208 Glenferrie Rd, Mitcham | Q0078 |  | true | Location | 1
Q0296 | 212 Sydney Avenue, Yarraville | Q0079 |  | true | Location | 2
Q0297 | 268 Sydney Road, Heidelberg | Q0080 |  | true | Location | 2
Q0298 | 369 Station Road, Burwood | Q0081 |  | true | Location | 1
Q0299 | 264 Queen Pde, Mitcham | Q0081 |  | true | Location | 1
Q0300 | 130 Barkly Rd, Sunshine | Q0082 |  | true | Location | 1
Q0301 | 180 Union Ave, Mentone | Q0083 |  | true | Location | 1
Q0302 | 148 Plenty Street, Cheltenham | Q0083 |  | true | Location | 1
Q0303 | 4A Main Hwy, Moorabbin | Q0083 |  | true | Location | 1
Q0304 | 165 Hopkins Rd, Cheltenham | Q0084 |  | true | Location | 1
Q0305 | 245 Victoria Rd, Frankston | Q0084 |  | true | Location | 1
Q0306 | 274 Gilbert Ave, Glen Waverley | Q0084 |  | true | Location | 2
Q0307 | 198 Station Avenue, Burwood | Q0085 |  | true | Location | 0
Q0308 | 387 Burke Parade, Northcote | Q0086 |  | true | Location | 1
Q0309 | 467 High Avenue, Northcote | Q0086 |  | true | Location | 1
Q0310 | 458 Glenferrie Pde, Thornbury | Q0086 |  | true | Location | 1
Q0311 | 111A Plenty St, Epping | Q0087 |  | true | Location | 2
Q0312 | 12 Sydney Road, Bundoora | Q0088 |  | true | Location | 2
Q0313 | 272 Gilbert St, Maribyrnong | Q0089 |  | true | Location | 2
Q0314 | 416 Park Road, Ringwood | Q0090 |  | true | Location | 1
Q0315 | 1 Mason Pde, Glen Waverley | Q0091 |  | true | Location | 1
Q0316 | 460 Sydney Hwy, Werribee | Q0161 |  | true | Location | 2
Q0317 | 35 Nepean Ave, Footscray | Q0093 |  | true | Location | 2
Q0318 | 271 Victoria Ave, Hawthorn | Q0094 |  | true | Location | 1
Q0319 | 375 Railway Rd, Altona | Q0095 |  | true | Location | 0
Q0320 | 186 Sydney Ave, Coburg | Q0096 |  | true | Location | 1
Q0321 | 399 Whitehorse Road, Reservoir | Q0096 |  | true | Location | 1
Q0322 | 453 Railway Pde, Camberwell | Q0097 |  | true | Location | 1
Q0323 | 326 Main Highway, Glen Waverley | Q0098 |  | true | Location | 2
Q0324 | 306 Bridge Rd, Glen Waverley | Q0099 |  | true | Location | 1
Q0325 | 79 Ballarat Street, Point Cook | Q0100 |  | true | Location | 0
Q0326 | 145 Church Ave, Brighton | Q0100 |  | true | Location | 1
Q0327 | 190 Nicholson Ave, Camberwell | Q0101 |  | true | Location | 1
Q0328 | 387 Barkly Highway, Hawthorn | Q0102 |  | true | Location | 2
Q0329 | 5 Park Hwy, Kew | Q0102 |  | true | Location | 1
Q0330 | 204 Mason Pde, Williamstown | Q0103 |  | true | Location | 1
Q0331 | 445 Barkly Ave, Cheltenham | Q0103 |  | true | Location | 1
Q0332 | 151 Glenferrie Hwy, Oakleigh | Q0104 |  | true | Location | 1
Q0333 | 284 Mason Hwy, Moorabbin | Q0168 |  | true | Location | 2
Q0334 | 218 Burke St, St Kilda | Q0168 |  | true | Location | 0
Q0335 | 362 Barkly Avenue, Mentone | Q0105 |  | true | Location | 1
Q0336 | 418 Main Ave, Northcote | Q0105 |  | true | Location | 2
Q0337 | 176 High Highway, Brunswick | Q0106 |  | true | Location | 2
Q0338 | 356 Glenferrie Pde, Frankston | Q0106 |  | true | Location | 1
Q0339 | 64 Glenferrie Pde, Bentleigh | Q0107 |  | true | Location | 2
Q0340 | 433 Mason Pde, Brunswick | Q0108 |  | true | Location | 1
Q0341 | 291 Burke Highway, Hawthorn | Q0108 |  | true | Location | 1
Q0342 | 186 Plenty Street, Altona | Q0108 |  | true | Location | 2
Q0343 | 279 Nicholson Avenue, Deer Park | Q0109 |  | true | Location | 1
Q0344 | 313 Victoria Road, Reservoir | Q0109 |  | true | Location | 1
Q0345 | 44 Nepean Pde, Brunswick | Q0110 |  | true | Location | 1
Q0346 | 67 Glenferrie Rd, Preston | Q0110 |  | true | Location | 1
Q0347 | 6 Whitehorse Street, Mitcham | Q0110 |  | true | Location | 2
Q0348 | 267 Nepean St, Yarraville | Q0111 |  | true | Location | 1
Q0349 | 266 Park Rd, Williamstown | Q0111 |  | true | Location | 0
Q0350 | 158 Nepean Avenue, Footscray | Q0112 |  | true | Location | 1
Q0351 | 135 Main Ave, Frankston | Q0113 |  | true | Location | 0
Q0352 | 256 Albert Parade, Northcote | Q0114 |  | true | Location | 0
Q0353 | 215 Barkly St, Laverton | Q0115 |  | true | Location | 2
Q0354 | 329 Station Ave, Brighton | Q0115 |  | true | Location | 1
Q0355 | 462A Victoria Road, Yarraville | Q0116 |  | true | Location | 1
Q0356 | 248 Sydney St, Cheltenham | Q0117 |  | true | Location | 0
Q0357 | 251 Plenty Hwy, Bentleigh | Q0118 |  | true | Location | 1
Q0358 | 148 Nepean Street, Bentleigh | Q0119 |  | true | Location | 2
Q0359 | 431 Union Ave, Hawthorn | Q0120 |  | true | Location | 1
Q0360 | 356 Main Rd, Camberwell | Q0120 |  | true | Location | 0
Q0361 | 422 Nicholson Parade, Glen Waverley | Q0120 |  | true | Location | 2
Q0362 | 455 Railway Rd, Williamstown | Q0121 |  | true | Location | 0
Q0363 | 217 King Street, Epping | Q0121 |  | true | Location | 1
Q0364 | 58 Station Rd, Mitcham | Q0122 |  | true | Location | 1
Q0365 | 343 Sydney St, Kew | Q0165 |  | true | Location | 1
Q0366 | 399 Plenty Ave, Ringwood | Q0165 |  | true | Location | 0
Q0367 | 256 Station St, Blackburn | Q0123 |  | true | Location | 2
Q0368 | 459 Whitehorse Pde, Sunshine | Q0124 |  | true | Location | 1
Q0369 | 87 Main Ave, Maribyrnong | Q0125 |  | true | Location | 1
Q0370 | 313/12 Union Avenue, Dandenong | Q0126 |  | true | Location | 0
Q0371 | 354 King Avenue, Moorabbin | Q0126 |  | true | Location | 2
Q0372 | 122 Main Avenue, Box Hill | Q0127 |  | true | Location | 1
Q0373 | 64 Bridge Street, Coburg | Q0128 |  | true | Location | 1
Q0374 | 213 Church Pde, Frankston | Q0129 |  | true | Location | 1
Q0375 | 420 Railway Parade, Preston | Q0130 |  | true | Location | 1
Q0376 | 301 Whitehorse Hwy, Thornbury | Q0130 |  | true | Location | 0
Q0377 | 294 Victoria Ave, Northcote | Q0131 |  | true | Location | 0
Q0378 | 81 Nepean Road, Burwood | Q0132 |  | true | Location | 2
Q0379 | 440 Bridge Street, Maribyrnong | Q0132 |  | true | Location | 2
Q0380 | 347 High Highway, Ringwood | Q0133 |  | true | Location | 2
Q0381 | 250 Hopkins Hwy, Kew | Q0133 |  | true | Location | 0
Q0382 | 191 Albert Avenue, Burwood | Q0133 |  | true | Location | 1
Q0383 | 414 Sydney Avenue, Brighton | Q0134 |  | true | Location | 1
Q0384 | 472 Hopkins Hwy, Box Hill | Q0135 |  | true | Location | 2
Q0385 | 410 Queen Hwy, Glen Waverley | Q0135 |  | true | Location | 2
Q0386 | 348 Railway St, Mentone | Q0136 |  | true | Location | 2
Q0387 | 4 Sydney Hwy, Cheltenham | Q0136 |  | true | Location | 2
Q0388 | 395 Plenty Ave, Oakleigh | Q0137 |  | true | Location | 1
Q0389 | 32 Park Avenue, Oakleigh | Q0137 |  | true | Location | 0
Q0390 | 333 Albert Parade, Brighton | Q0138 |  | true | Location | 1
Q0391 | 280 Station St, Oakleigh | Q0138 |  | true | Location | 0
Q0392 | 87/12 Victoria Rd, Point Cook | Q0139 |  | true | Location | 1
Q0393 | 241 Mason Road, Northcote | Q0140 |  | true | Location | 0
Q0394 | 448 Barkly Avenue, Mentone | Q0140 |  | true | Location | 0
Q0395 | 351 High Street, Altona | Q0141 |  | true | Location | 1
Q0396 | 477 Hopkins Avenue, Hawthorn | Q0141 |  | true | Location | 3
Q0397 | 428 Church Pde, Maribyrnong | Q0142 |  | true | Location | 3
Q0398 | 253A Glenferrie St, Bundoora | Q0143 |  | true | Location | 1
Q0399 | 466 Main St, Werribee | Q0144 |  | true | Location | 1
Q0400 | 367 Station Pde, Thornbury | Q0145 |  | true | Location | 0
Q0401 | 266/12 Albert Avenue, Mitcham | Q0146 |  | true | Location | 1
Q0402 | 479 Burke Rd, Reservoir | Q0146 |  | true | Location | 1
Q0403 | 216 Plenty Road, Burwood | Q0147 |  | true | Location | 2
Q0404 | 42 Queen Ave, Bentleigh | Q0148 |  | true | Location | 0
Q0405 | 438 Church Hwy, Bentleigh | Q0148 |  | true | Location | 2
Q0406 | 337 Plenty Pde, St Kilda | Q0148 |  | true | Location | 1
Q0407 | 314 Plenty St, Northcote | Q0149 |  | true | Location | 1
Q0408 | 121 High Pde, Glen Waverley | Q0150 |  | true | Location | 1
Q0409 | 317 Victoria Parade, Clayton | Q0150 |  | true | Location | 2
Q0410 | 273/12 Plenty Pde, Coburg | Q0151 |  | true | Location | 1
Q0411 | 200 Nepean Avenue, Moorabbin | Q0152 |  | true | Location | 0
Q0412 | 455 Nicholson Highway, Moorabbin | Q0152 |  | true | Location | 2
Q0413 | 400 Albert Street, Mentone | Q0153 |  | true | Location | 2
Q0414 | 257 Hopkins Pde, Point Cook | Q0154 |  | true | Location | 1
Q0415 | 139 Glenferrie Parade, Brighton | Q0155 |  | true | Location | 1
Q0416 | 250 Bridge Hwy, Werribee | Q0155 |  | true | Location | 1
Q0417 | 284A Park Rd, Point Cook | Q0156 |  | true | Location | 2
Q0418 | 163 Barkly Highway, Essendon | Q0156 |  | true | Location | 1
Q0419 | 448 Nicholson Street, Kew | Q0157 |  | true | Location | 1
Q0420 | 360 Burke St, Maribyrnong | Q0158 |  | true | Location | 1

## QBO Templates
QBO recurring invoice templates
Work sample: realistic data, built to show how I approach this work.
Template | Name | Customer ID | Interval | Amount | Description | Next date | Active | Created by | Jobber job | Counted
T0001 | Oakleigh - Kitchen and bathrooms | Q0170 | Monthly | 251.33 | Kitchen and bathrooms at 162 Station Parade, Oakleigh | 2026-11-01 | true | Office | J1002 | 1
T0002 | Deer Park - Kitchen and bathrooms | Q0171 | Monthly | 284 | Kitchen and bathrooms at 273 Albert Road, Deer Park | 2026-11-01 | true | Office | J1004 | 1
T0003 | Bundoora - Window clean | Q0172 | Every 4 weeks | 156 | Window clean at 59 Station Parade, Bundoora | 2026-12-03 | true | Office | J1006 | 1
T0004 | Footscray - Kitchen and bathrooms | Q0173 | Monthly | 598 | Kitchen and bathrooms at 224 Ballarat Pde, Footscray | 2026-11-01 | true | Bookkeeper | J1007 | 1
T0005 | Brighton - Office clean | Q0174 | Monthly | 2093 | Office clean at 77 Ballarat Parade, Brighton | 2026-11-01 | true | Owner | J1008 | 1
T0006 | Bundoora - Office clean | Q0175 | Monthly | 1135.33 | Office clean at 290A Ballarat Highway, Bundoora | 2026-11-01 | true | Office | J1009 | 1
T0007 | Werribee - Office clean | Q0176 | Monthly | 1768 | Office clean at 359 Glenferrie Ave, Werribee | 2026-11-01 | true | Office | J1010 | 1
T0008 | Oakleigh - Office clean | Q0177 | Monthly | 277.33 | Office clean at 315 Park Parade, Oakleigh | 2026-11-01 | true | Owner | J1011 | 1
T0009 | Hawthorn - Washroom service | Q0179 | Monthly | 88 | Washroom service at 169 King Street, Hawthorn | 2026-11-01 | true | Office | J1015 | 1
T0010 | Epping - Kitchen and bathrooms | Q0180 | Monthly | 1386.67 | Kitchen and bathrooms at 396 Park Hwy, Epping | 2026-11-01 | true | Owner | J1016 | 1
T0011 | Thornbury - Office clean | Q0181 | Monthly | 832 | Office clean at 214A Nepean Pde, Thornbury | 2026-11-01 | true | Office | J1017 | 1
T0012 | Mitcham - Office clean | Q0182 | Monthly | 390 | Office clean at 208 Main Avenue, Mitcham | 2026-11-01 | true | Owner | J1018 | 1
T0013 | Kew - Office clean | Q0183 | Monthly | 442 | Office clean at 208 High Avenue, Kew | 2026-11-01 | true | Bookkeeper | J1019 | 1
T0014 | Coburg - Office clean | Q0185 | Monthly | 1352 | Office clean at 201 Plenty Ave, Coburg | 2026-11-01 | true | Bookkeeper | J1021 | 1
T0015 | Mentone - Office clean | Q0186 | Monthly | 819 | Office clean at 164 Whitehorse St, Mentone | 2026-11-01 | true | Owner | J1022 | 1
T0016 | Camberwell - Office clean | Q0187 | Monthly | 1256.67 | Office clean at 480 King Ave, Camberwell | 2026-11-01 | true | Owner | J1023 | 1
T0017 | Camberwell - Carpet steam clean | Q0187 | Every 4 weeks | 218 | Carpet steam clean at 480 King Ave, Camberwell | 2026-12-11 | true | Owner | J1024 | 1
T0018 | Cheltenham - Kitchen and bathrooms | Q0188 | Monthly | 303.33 | Kitchen and bathrooms at 426 Mason Street, Cheltenham | 2026-11-01 | true | Office | J1025 | 1
T0019 | Cheltenham - Window clean | Q0188 | Every 4 weeks | 218 | Window clean at 426 Mason Street, Cheltenham | 2026-11-17 | true | Owner | J1026 | 1
T0020 | Oakleigh - Office clean | Q0189 | Monthly | 1464 | Office clean at 351 Burke Road, Oakleigh | 2026-11-01 | true | Owner | J1027 | 1
T0021 | Clayton - Kitchen and bathrooms | Q0190 | Monthly | 537.33 | Kitchen and bathrooms at 354 High Street, Clayton | 2026-11-01 | true | Owner | J1028 | 1
T0022 | Reservoir - Office clean | Q0191 | Monthly | 442 | Office clean at 54 Mason Parade, Reservoir | 2026-11-01 | true | Office | J1029 | 1
T0023 | St Kilda - Office clean | Q0192 | Monthly | 884 | Office clean at 430 Victoria Road, St Kilda | 2026-11-01 | true | Bookkeeper | J1030 | 1
T0024 | Bentleigh - Office clean | Q0193 | Monthly | 806 | Office clean at 195/12 Railway Hwy, Bentleigh | 2026-11-01 | true | Owner | J1031 | 1
T0025 | Deer Park - Office clean | Q0194 | Monthly | 4051.67 | Office clean at 10 Queen Hwy, Deer Park | 2026-11-01 | true | Bookkeeper | J1033 | 1
T0026 | St Kilda - Kitchen and bathrooms | Q0195 | Monthly | 560 | Kitchen and bathrooms at 17 Park Ave, St Kilda | 2026-11-01 | true | Owner | J1034 | 1
T0027 | Camberwell - Window clean | Q0196 | Every 4 weeks | 203 | Window clean at 378 Plenty St, Camberwell | 2026-12-08 | true | Bookkeeper | J1036 | 1
T0028 | Point Cook - Office clean | Q0197 | Monthly | 286 | Office clean at 266 Union Ave, Point Cook | 2026-11-01 | true | Office | J1037 | 1
T0029 | Bundoora - Office clean | Q0199 | Monthly | 748 | Office clean at 107 Barkly Highway, Bundoora | 2026-11-01 | true | Office | J1039 | 1
T0030 | Footscray - Office clean | Q0200 | Monthly | 840.67 | Office clean at 298 Main Rd, Footscray | 2026-11-01 | true | Office | J1040 | 1
T0031 | Footscray - Carpet steam clean | Q0200 | Every 4 weeks | 135 | Carpet steam clean at 298 Main Road, Footscray | 2026-11-30 | true | Office | J1041 | 1
T0032 | Camberwell - Kitchen and bathrooms | Q0201 | Monthly | 138.67 | Kitchen and bathrooms at 142 Plenty Rd, Camberwell | 2026-11-01 | true | Bookkeeper | J1042 | 1
T0033 | Ringwood - Window clean | Q0202 | Every 4 weeks | 109 | Window clean at 195 Nicholson Rd, Ringwood | 2026-12-08 | true | Owner | J1044 | 1
T0034 | Ringwood - Washroom service | Q0203 | Monthly | 125 | Washroom service at 245 Ballarat Avenue, Ringwood | 2026-11-01 | true | Office | J1046 | 1
T0035 | Bundoora - Kitchen and bathrooms | Q0204 | Monthly | 260 | Kitchen and bathrooms at 22 Hopkins Road, Bundoora | 2026-11-01 | true | Office | J1047 | 1
T0036 | Northcote - Office clean | Q0205 | Monthly | 836.33 | Office clean at 356 Albert Ave, Northcote | 2026-11-01 | true | Owner | J1048 | 1
T0037 | Northcote - Carpet steam clean | Q0205 | Every 4 weeks | 130 | Carpet steam clean at 356 Albert Avenue, Northcote | 2026-11-24 | true | Owner | J1049 | 1
T0038 | Sunshine - Office clean | Q0207 | Monthly | 923 | Office clean at 417 Main Road, Sunshine | 2026-11-01 | true | Office | J1051 | 1
T0039 | Williamstown - Office clean | Q0208 | Monthly | 1542.67 | Office clean at 37 Nicholson Highway, Williamstown | 2026-11-01 | true | Owner | J1052 | 1
T0040 | Epping - Office clean | Q0209 | Monthly | 697.67 | Office clean at 117 Railway Hwy, Epping | 2026-11-01 | true | Bookkeeper | J1053 | 1
T0041 | Essendon - Office clean | Q0211 | Monthly | 1768 | Office clean at 188 Nicholson Road, Essendon | 2026-11-01 | true | Owner | J1055 | 1
T0042 | Altona - Office clean | Q0213 | Monthly | 524.33 | Office clean at 205 Railway Street, Altona | 2026-11-01 | true | Bookkeeper | J1057 | 1
T0043 | Yarraville - Office clean | Q0214 | Monthly | 975 | Office clean at 359 King Rd, Yarraville | 2026-11-01 | true | Owner | J1058 | 1
T0044 | Glen Waverley - Office clean | Q0216 | Monthly | 1542.67 | Office clean at 386 Nepean Road, Glen Waverley | 2026-11-01 | true | Owner | J1060 | 1
T0045 | Brunswick - Office clean | Q0219 | Monthly | 1352 | Office clean at 310 Ballarat Ave, Brunswick | 2026-11-01 | true | Office | J1064 | 1
T0046 | Brunswick - Carpet steam clean | Q0219 | Every 4 weeks | 130 | Carpet steam clean at 310 Ballarat Ave, Brunswick | 2026-11-25 | true | Bookkeeper | J1065 | 1
T0047 | Thornbury - Office clean | Q0220 | Monthly | 2093 | Office clean at 269 Victoria Avenue, Thornbury | 2026-11-01 | true | Bookkeeper | J1066 | 1
T0048 | Thornbury - Window clean | Q0220 | Every 4 weeks | 116 | Window clean at 269 Victoria Avenue, Thornbury | 2026-11-23 | true | Owner | J1067 | 1
T0049 | Essendon - Office clean | Q0221 | Monthly | 654.33 | Office clean at 332A Glenferrie Pde, Essendon | 2026-11-01 | true | Bookkeeper | J1068 | 1
T0050 | Deer Park - Office clean | Q0222 | Monthly | 897 | Office clean at 157 Whitehorse Pde, Deer Park | 2026-11-01 | true | Office | J1069 | 1
T0051 | Maribyrnong - Kitchen and bathrooms | Q0223 | Monthly | 598 | Kitchen and bathrooms at 439 Sydney Parade, Maribyrnong | 2026-11-01 | true | Owner | J1070 | 1
T0052 | Oakleigh - Office clean | Q0224 | Monthly | 784.33 | Office clean at 204 Bridge Highway, Oakleigh | 2026-11-01 | true | Office | J1071 | 1
T0053 | Oakleigh office clean (copy) | Q0224 | Monthly | 784.33 | Office clean at 204 Bridge Hwy, Oakleigh | 2026-11-01 | true | Owner | J1071 | 1
T0054 | Cheltenham - Office clean | Q0225 | Monthly | 580.67 | Office clean at 48 Ballarat Pde, Cheltenham | 2026-11-01 | true | Owner | J1072 | 1
T0055 | Hawthorn - Kitchen and bathrooms | Q0226 | Monthly | 273 | Kitchen and bathrooms at 479 Mason Parade, Hawthorn | 2026-11-01 | true | Bookkeeper | J1073 | 1
T0056 | Doncaster - Window clean | Q0227 | Every 4 weeks | 102 | Window clean at 450 King Road, Doncaster | 2026-11-19 | true | Owner | J1076 | 1
T0057 | Point Cook - Office clean | Q0229 | Monthly | 273 | Office clean at 426 Ballarat Parade, Point Cook | 2026-11-01 | true | Bookkeeper | J1078 | 1
T0058 | Laverton - Office clean | Q0230 | Monthly | 286 | Office clean at 164 Nicholson Street, Laverton | 2026-11-01 | true | Owner | J1079 | 1
T0059 | Laverton - Window clean | Q0230 | Every 4 weeks | 109 | Window clean at 164 Nicholson St, Laverton | 2026-11-23 | true | Owner | J1080 | 1
T0060 | Frankston - Office clean | Q0231 | Monthly | 1690 | Office clean at 143/12 Nepean Street, Frankston | 2026-11-01 | true | Owner | J1081 | 1
T0061 | Frankston office clean (copy) | Q0231 | Monthly | 1690 | Office clean at 143/12 Nepean St, Frankston | 2026-11-01 | true | Bookkeeper | J1081 | 1
T0062 | Frankston - Washroom service | Q0231 | Monthly | 151 | Washroom service at 143/12 Nepean Street, Frankston | 2026-11-01 | true | Owner | J1082 | 1
T0063 | Laverton - Office clean | Q0232 | Monthly | 1625 | Office clean at 380 Nepean Pde, Laverton | 2026-11-01 | true | Bookkeeper | J1083 | 1
T0064 | Hawthorn - Office clean | Q0233 | Monthly | 1672.67 | Office clean at 296 Barkly Hwy, Hawthorn | 2026-11-01 | true | Office | J1085 | 1
T0065 | Hawthorn - Window clean | Q0233 | Every 4 weeks | 109 | Window clean at 296 Barkly Hwy, Hawthorn | 2026-11-26 | true | Bookkeeper | J1086 | 1
T0066 | Hawthorn - Washroom service | Q0233 | Monthly | 145 | Washroom service at 296 Barkly Highway, Hawthorn | 2026-11-01 | true | Office | J1087 | 1
T0067 | Bentleigh - Carpet steam clean | Q0234 | Every 4 weeks | 109 | Carpet steam clean at 46 Main Avenue, Bentleigh | 2026-12-02 | true | Bookkeeper | J1089 | 1
T0068 | Bentleigh - Washroom service | Q0234 | Monthly | 151 | Washroom service at 46 Main Ave, Bentleigh | 2026-11-01 | true | Office | J1090 | 1
T0069 | Burwood - Kitchen and bathrooms | Q0235 | Monthly | 520 | Kitchen and bathrooms at 211 Union Rd, Burwood | 2026-11-01 | true | Bookkeeper | J1091 | 1
T0070 | Burwood - Office clean | Q0236 | Monthly | 884 | Office clean at 418 Nicholson Avenue, Burwood | 2026-11-01 | true | Owner | J1092 | 1
T0071 | Bentleigh - Office clean | Q0237 | Monthly | 559 | Office clean at 43 Plenty Ave, Bentleigh | 2026-11-01 | true | Owner | J1093 | 1
T0072 | Cheltenham - Office clean | Q0238 | Monthly | 806 | Office clean at 27 Railway Avenue, Cheltenham | 2026-11-01 | true | Bookkeeper | J1094 | 1
T0073 | Cheltenham - Window clean | Q0238 | Every 4 weeks | 102 | Window clean at 27 Railway Ave, Cheltenham | 2026-11-24 | true | Bookkeeper | J1095 | 1
T0074 | Mentone - Office clean | Q0239 | Monthly | 1755 | Office clean at 225/12 Glenferrie Parade, Mentone | 2026-11-01 | true | Office | J1096 | 1
T0075 | Reservoir - Office clean | Q0240 | Monthly | 1716 | Office clean at 225 Park Ave, Reservoir | 2026-11-01 | true | Bookkeeper | J1097 | 1
T0076 | Reservoir - Carpet steam clean | Q0240 | Every 4 weeks | 112 | Carpet steam clean at 225 Park Ave, Reservoir | 2026-11-19 | true | Office | J1098 | 1
T0077 | Reservoir - Washroom service | Q0240 | Monthly | 125 | Washroom service at 225 Park Avenue, Reservoir | 2026-11-01 | true | Bookkeeper | J1099 | 1
T0078 | Point Cook - Office clean | Q0241 | Monthly | 1005.33 | Office clean at 410 Burke Hwy, Point Cook | 2026-11-01 | true | Owner | J1100 | 1
T0079 | Glen Waverley - Washroom service | Q0242 | Monthly | 85 | Washroom service at 205 Burke Highway, Glen Waverley | 2026-11-01 | true | Owner | J1103 | 1
T0080 | Hawthorn - Office clean | Q0243 | Monthly | 464 | Office clean at 189 Union Hwy, Hawthorn | 2026-11-01 | true | Bookkeeper | J1104 | 1
T0081 | Hawthorn - Carpet steam clean | Q0243 | Every 4 weeks | 218 | Carpet steam clean at 189 Union Hwy, Hawthorn | 2026-11-25 | true | Office | J1105 | 1
T0082 | Cheltenham - Office clean | Q0245 | Monthly | 2440 | Office clean at 375 Station Highway, Cheltenham | 2026-11-01 | true | Owner | J1107 | 1
T0083 | Cheltenham - Window clean | Q0245 | Every 4 weeks | 116 | Window clean at 375 Station Highway, Cheltenham | 2026-12-07 | true | Bookkeeper | J1108 | 1
T0084 | Box Hill - Office clean | Q0246 | Monthly | 606.67 | Office clean at 378 Burke Hwy, Box Hill | 2026-11-01 | true | Owner | J1109 | 1
T0085 | Burwood - Office clean | Q0247 | Monthly | 2123.33 | Office clean at 185 Church Parade, Burwood | 2026-11-01 | true | Owner | J1110 | 1
T0086 | Burwood - Window clean | Q0247 | Every 4 weeks | 105 | Window clean at 185 Church Pde, Burwood | 2026-11-19 | true | Bookkeeper | J1111 | 1
T0087 | Reservoir - Kitchen and bathrooms | Q0248 | Monthly | 130 | Kitchen and bathrooms at 115 Nepean Parade, Reservoir | 2026-11-01 | true | Office | J1112 | 1
T0088 | Essendon - Washroom service | Q0249 | Monthly | 125 | Washroom service at 96A Glenferrie Parade, Essendon | 2026-11-01 | true | Owner | J1114 | 1
T0089 | Mentone - Kitchen and bathrooms | Q0250 | Monthly | 325 | Kitchen and bathrooms at 158 Station Street, Mentone | 2026-11-01 | true | Office | J1115 | 1
T0090 | Frankston - Office clean | Q0251 | Monthly | 801.67 | Office clean at 476 Sydney Hwy, Frankston | 2026-11-01 | true | Bookkeeper | J1116 | 1
T0091 | Sunshine - Office clean | Q0252 | Monthly | 1100.67 | Office clean at 436/12 Nepean Hwy, Sunshine | 2026-11-01 | true | Bookkeeper | J1117 | 1
T0092 | Brighton - Office clean | Q0253 | Monthly | 748 | Office clean at 394 Ballarat Avenue, Brighton | 2026-11-01 | true | Office | J1118 | 1
T0093 | Brighton - Carpet steam clean | Q0253 | Every 4 weeks | 116 | Carpet steam clean at 394 Ballarat Ave, Brighton | 2026-11-24 | true | Bookkeeper | J1119 | 1
T0094 | Dandenong - Office clean | Q0254 | Monthly | 502.67 | Office clean at 135 Victoria Parade, Dandenong | 2026-11-01 | true | Owner | J1120 | 1
T0095 | Moorabbin - Kitchen and bathrooms | Q0255 | Monthly | 134.33 | Kitchen and bathrooms at 472 Barkly Pde, Moorabbin | 2026-11-01 | true | Office | J1121 | 1
T0096 | Point Cook - Kitchen and bathrooms | Q0256 | Monthly | 559 | Kitchen and bathrooms at 151 Nicholson Street, Point Cook | 2026-11-01 | true | Bookkeeper | J1122 | 1
T0097 | Camberwell - Office clean | Q0257 | Monthly | 580.67 | Office clean at 4A Gilbert Road, Camberwell | 2026-11-01 | true | Bookkeeper | J1124 | 1
T0098 | Coburg - Office clean | Q0258 | Monthly | 1300 | Office clean at 144 Burke Ave, Coburg | 2026-11-01 | true | Owner | J1125 | 1
T0099 | Footscray - Office clean | Q0259 | Monthly | 1395.33 | Office clean at 182 King Ave, Footscray | 2026-11-01 | true | Office | J1127 | 1
T0100 | Camberwell - Kitchen and bathrooms | Q0260 | Monthly | 650 | Kitchen and bathrooms at 79/12 Glenferrie Parade, Camberwell | 2026-11-01 | true | Office | J1128 | 1
T0101 | Burwood - Office clean | Q0261 | Monthly | 550.33 | Office clean at 401 Park Highway, Burwood | 2026-11-01 | true | Office | J1129 | 1
T0102 | Burwood - Carpet steam clean | Q0261 | Every 4 weeks | 203 | Carpet steam clean at 401 Park Highway, Burwood | 2026-11-23 | true | Bookkeeper | J1130 | 1
T0103 | Burwood - Office clean | Q0262 | Monthly | 589.33 | Office clean at 401 Burke St, Burwood | 2026-11-01 | true | Bookkeeper | J1131 | 1
T0104 | Ringwood - Carpet steam clean | Q0263 | Every 4 weeks | 218 | Carpet steam clean at 11 Hopkins Ave, Ringwood | 2026-11-20 | true | Owner | J1133 | 1
T0105 | Altona - Office clean | Q0264 | Monthly | 251.33 | Office clean at 263 Nepean Highway, Altona | 2026-11-01 | true | Owner | J1134 | 1
T0106 | Northcote - Office clean | Q0265 | Monthly | 1438.67 | Office clean at 288 Main Hwy, Northcote | 2026-11-01 | true | Owner | J1135 | 1
T0107 | Northcote - Window clean | Q0265 | Every 4 weeks | 156 | Window clean at 288 Main Hwy, Northcote | 2026-12-07 | true | Office | J1136 | 1
T0108 | Deer Park - Office clean | Q0266 | Monthly | 502.67 | Office clean at 459 Park Ave, Deer Park | 2026-11-01 | true | Office | J1137 | 1
T0109 | Blackburn - Office clean | Q0267 | Monthly | 632.67 | Office clean at 464 Barkly Road, Blackburn | 2026-11-01 | true | Office | J1138 | 1
T0110 | Bentleigh - Office clean | Q0268 | Monthly | 1170 | Office clean at 90A Albert Pde, Bentleigh | 2026-11-01 | true | Bookkeeper | J1139 | 1
T0111 | Burwood - Office clean | Q0269 | Monthly | 650 | Office clean at 29 Burke Parade, Burwood | 2026-11-01 | true | Owner | J1140 | 1
T0112 | Glen Waverley - Office clean | Q0270 | Monthly | 294.67 | Office clean at 23 Station Pde, Glen Waverley | 2026-11-01 | true | Owner | J1141 | 1
T0113 | Glen Waverley - Washroom service | Q0270 | Monthly | 99 | Washroom service at 23 Station Pde, Glen Waverley | 2026-11-01 | true | Bookkeeper | J1142 | 1
T0114 | Altona - Office clean | Q0271 | Monthly | 1092 | Office clean at 251 Union Ave, Altona | 2026-11-01 | true | Bookkeeper | J1143 | 1
T0115 | Doncaster - Office clean | Q0272 | Monthly | 676 | Office clean at 270 Station Rd, Doncaster | 2026-11-01 | true | Owner | J1144 | 1
T0116 | Doncaster - Window clean | Q0272 | Every 4 weeks | 109 | Window clean at 270 Station Rd, Doncaster | 2026-11-16 | true | Owner | J1145 | 1
T0117 | Glen Waverley - Kitchen and bathrooms | Q0273 | Monthly | 251.33 | Kitchen and bathrooms at 463 Gilbert Street, Glen Waverley | 2026-11-01 | true | Office | J1146 | 1
T0118 | Point Cook - Office clean | Q0274 | Monthly | 923 | Office clean at 59 King Highway, Point Cook | 2026-11-01 | true | Owner | J1147 | 1
T0119 | Point Cook - Office clean | Q0275 | Monthly | 277.33 | Office clean at 61 Church St, Point Cook | 2026-11-01 | true | Bookkeeper | J1148 | 1
T0120 | Point Cook - Window clean | Q0275 | Every 4 weeks | 135 | Window clean at 61 Church St, Point Cook | 2026-11-17 | true | Office | J1149 | 1
T0121 | Point Cook - Kitchen and bathrooms | Q0276 | Monthly | 936 | Kitchen and bathrooms at 280 Railway Rd, Point Cook | 2026-11-01 | true | Owner | J1150 | 1
T0122 | Point Cook - Window clean | Q0276 | Every 4 weeks | 203 | Window clean at 280 Railway Road, Point Cook | 2026-11-27 | true | Owner | J1151 | 1
T0123 | Point Cook - Office clean | Q0277 | Monthly | 1568.67 | Office clean at 149 Main Rd, Point Cook | 2026-11-01 | true | Bookkeeper | J1152 | 1
T0124 | Point Cook - Washroom service | Q0277 | Monthly | 95 | Washroom service at 149 Main Rd, Point Cook | 2026-11-01 | true | Bookkeeper | J1153 | 1
T0125 | Hawthorn - Office clean | Q0278 | Monthly | 437.67 | Office clean at 313 King Rd, Hawthorn | 2026-11-01 | true | Owner | J1154 | 1
T0126 | Glen Waverley - Office clean | Q0279 | Monthly | 528.67 | Office clean at 155 Hopkins Road, Glen Waverley | 2026-11-01 | true | Owner | J1155 | 1
T0127 | Glen Waverley office clean (copy) | Q0279 | Monthly | 528.67 | Office clean at 155 Hopkins Road, Glen Waverley | 2026-11-01 | true | Office | J1155 | 1
T0128 | Point Cook - Office clean | Q0280 | Monthly | 1655.33 | Office clean at 284 Park Pde, Point Cook | 2026-11-01 | true | Bookkeeper | J1156 | 1
T0129 | Frankston - Office clean | Q0281 | Monthly | 1752 | Office clean at 85 Nepean Rd, Frankston | 2026-11-01 | true | Office | J1157 | 1
T0130 | Hawthorn - Office clean | Q0282 | Monthly | 1213.33 | Office clean at 231 Church Highway, Hawthorn | 2026-11-01 | true | Owner | J1158 | 1
T0131 | Werribee - Kitchen and bathrooms | Q0283 | Monthly | 277.33 | Kitchen and bathrooms at 223A Nicholson Pde, Werribee | 2026-11-01 | true | Owner | J1159 | 1
T0132 | Werribee - Washroom service | Q0283 | Monthly | 85 | Washroom service at 223A Nicholson Parade, Werribee | 2026-11-01 | true | Bookkeeper | J1160 | 1
T0133 | Footscray - Office clean | Q0284 | Monthly | 268.67 | Office clean at 382 Hopkins Street, Footscray | 2026-11-01 | true | Bookkeeper | J1161 | 1
T0134 | Footscray - Office clean | Q0285 | Monthly | 585 | Office clean at 443 Station Road, Footscray | 2026-11-01 | true | Owner | J1162 | 1
T0135 | Reservoir - Carpet steam clean | Q0286 | Every 4 weeks | 146 | Carpet steam clean at 127 Main Hwy, Reservoir | 2026-12-09 | true | Office | J1164 | 1
T0136 | St Kilda - Office clean | Q0288 | Monthly | 1438.67 | Office clean at 102 Union Road, St Kilda | 2026-11-01 | true | Office | J1166 | 1
T0137 | Bundoora - Kitchen and bathrooms | Q0289 | Monthly | 307.67 | Kitchen and bathrooms at 61 Church Rd, Bundoora | 2026-11-01 | true | Owner | J1167 | 1
T0138 | Deer Park - Office clean | Q0290 | Monthly | 1560 | Office clean at 287 Whitehorse Hwy, Deer Park | 2026-11-01 | true | Bookkeeper | J1169 | 1
T0139 | Bentleigh - Kitchen and bathrooms | Q0291 | Monthly | 251.33 | Kitchen and bathrooms at 289 Nepean St, Bentleigh | 2026-11-01 | true | Office | J1170 | 1
T0140 | Footscray - Office clean | Q0292 | Monthly | 2513.33 | Office clean at 221 Plenty Avenue, Footscray | 2026-11-01 | true | Owner | J1171 | 1
T0141 | Mitcham - Kitchen and bathrooms | Q0293 | Monthly | 1343.33 | Kitchen and bathrooms at 77 Mason Highway, Mitcham | 2026-11-01 | true | Owner | J1172 | 1
T0142 | Reservoir - Office clean | Q0294 | Monthly | 806 | Office clean at 170 Railway Hwy, Reservoir | 2026-11-01 | true | Bookkeeper | J1174 | 1
T0143 | Mitcham - Office clean | Q0295 | Monthly | 420.33 | Office clean at 208 Glenferrie Road, Mitcham | 2026-11-01 | true | Bookkeeper | J1175 | 1
T0144 | Yarraville - Office clean | Q0296 | Monthly | 316.33 | Office clean at 212 Sydney Avenue, Yarraville | 2026-11-01 | true | Bookkeeper | J1176 | 1
T0145 | Yarraville office clean (copy) | Q0296 | Monthly | 303.33 | Office clean at 212 Sydney Avenue, Yarraville | 2026-11-01 | true | Bookkeeper | J1176 | 1
T0146 | Heidelberg - Kitchen and bathrooms | Q0297 | Monthly | 296 | Kitchen and bathrooms at 268 Sydney Rd, Heidelberg | 2026-11-01 | true | Owner | J1177 | 1
T0147 | Heidelberg - Carpet steam clean | Q0297 | Every 4 weeks | 135 | Carpet steam clean at 268 Sydney Rd, Heidelberg | 2026-12-11 | true | Owner | J1178 | 1
T0148 | Burwood - Office clean | Q0298 | Monthly | 488 | Office clean at 369 Station Road, Burwood | 2026-11-01 | true | Bookkeeper | J1179 | 1
T0149 | Mitcham - Kitchen and bathrooms | Q0299 | Monthly | 1516.67 | Kitchen and bathrooms at 264 Queen Pde, Mitcham | 2026-11-01 | true | Office | J1180 | 1
T0150 | Sunshine - Office clean | Q0300 | Monthly | 884 | Office clean at 130 Barkly Rd, Sunshine | 2026-11-01 | true | Owner | J1181 | 1
T0151 | Mentone - Office clean | Q0301 | Monthly | 654.33 | Office clean at 180 Union Ave, Mentone | 2026-11-01 | true | Office | J1182 | 1
T0152 | Cheltenham - Office clean | Q0302 | Monthly | 1083.33 | Office clean at 148 Plenty Street, Cheltenham | 2026-11-01 | true | Bookkeeper | J1183 | 1
T0153 | Moorabbin - Office clean | Q0303 | Monthly | 1352 | Office clean at 4A Main Highway, Moorabbin | 2026-11-01 | true | Bookkeeper | J1184 | 1
T0154 | Cheltenham - Office clean | Q0304 | Monthly | 541.67 | Office clean at 165 Hopkins Rd, Cheltenham | 2026-11-01 | true | Bookkeeper | J1186 | 1
T0155 | Frankston - Office clean | Q0305 | Monthly | 546 | Office clean at 245 Victoria Road, Frankston | 2026-11-01 | true | Office | J1187 | 1
T0156 | Glen Waverley - Office clean | Q0306 | Monthly | 1057.33 | Office clean at 274 Gilbert Ave, Glen Waverley | 2026-11-01 | true | Office | J1188 | 1
T0157 | Glen Waverley - Washroom service | Q0306 | Monthly | 88 | Washroom service at 274 Gilbert Avenue, Glen Waverley | 2026-11-01 | true | Office | J1189 | 1
T0158 | Northcote - Office clean | Q0308 | Monthly | 376 | Office clean at 387 Burke Pde, Northcote | 2026-11-01 | true | Office | J1191 | 1
T0159 | Northcote - Office clean | Q0309 | Monthly | 862.33 | Office clean at 467 High Ave, Northcote | 2026-11-01 | true | Bookkeeper | J1192 | 1
T0160 | Thornbury - Office clean | Q0310 | Monthly | 463.67 | Office clean at 458 Glenferrie Pde, Thornbury | 2026-11-01 | true | Bookkeeper | J1193 | 1
T0161 | Epping - Kitchen and bathrooms | Q0311 | Monthly | 1386.67 | Kitchen and bathrooms at 111A Plenty Street, Epping | 2026-11-01 | true | Owner | J1194 | 1
T0162 | Bundoora - Kitchen and bathrooms | Q0312 | Monthly | 156 | Kitchen and bathrooms at 12 Sydney Road, Bundoora | 2026-11-01 | true | Office | J1195 | 1
T0163 | Bundoora kitchen and bathrooms (copy) | Q0312 | Monthly | 151.67 | Kitchen and bathrooms at 12 Sydney Road, Bundoora | 2026-11-01 | true | Office | J1195 | 1
T0164 | Maribyrnong - Office clean | Q0313 | Monthly | 1204.67 | Office clean at 272 Gilbert St, Maribyrnong | 2026-11-01 | true | Owner | J1196 | 1
T0165 | Maribyrnong - Window clean | Q0313 | Every 4 weeks | 218 | Window clean at 272 Gilbert Street, Maribyrnong | 2026-12-09 | true | Owner | J1197 | 1
T0166 | Ringwood - Office clean | Q0314 | Monthly | 580.67 | Office clean at 416 Park Rd, Ringwood | 2026-11-01 | true | Owner | J1198 | 1
T0167 | Glen Waverley - Kitchen and bathrooms | Q0315 | Monthly | 320.67 | Kitchen and bathrooms at 1 Mason Parade, Glen Waverley | 2026-11-01 | true | Bookkeeper | J1199 | 1
T0168 | Werribee - Kitchen and bathrooms | Q0316 | Monthly | 251.33 | Kitchen and bathrooms at 460 Sydney Hwy, Werribee | 2026-11-01 | true | Bookkeeper | J1200 | 1
T0169 | Footscray - Office clean | Q0317 | Monthly | 563.33 | Office clean at 35 Nepean Avenue, Footscray | 2026-11-01 | true | Bookkeeper | J1201 | 1
T0170 | Footscray - Carpet steam clean | Q0317 | Every 4 weeks | 234 | Carpet steam clean at 35 Nepean Ave, Footscray | 2026-11-19 | true | Bookkeeper | J1202 | 1
T0171 | Hawthorn - Office clean | Q0318 | Monthly | 1352 | Office clean at 271 Victoria Ave, Hawthorn | 2026-11-01 | true | Office | J1203 | 1
T0172 | Coburg - Office clean | Q0320 | Monthly | 1261 | Office clean at 186 Sydney Avenue, Coburg | 2026-11-01 | true | Office | J1205 | 1
T0173 | Reservoir - Window clean | Q0321 | Every 4 weeks | 218 | Window clean at 399 Whitehorse Rd, Reservoir | 2026-11-16 | true | Office | J1208 | 1
T0174 | Camberwell - Office clean | Q0322 | Monthly | 858 | Office clean at 453 Railway Pde, Camberwell | 2026-11-01 | true | Bookkeeper | J1209 | 1
T0175 | Glen Waverley - Office clean | Q0323 | Monthly | 392 | Office clean at 326 Main Hwy, Glen Waverley | 2026-11-01 | true | Bookkeeper | J1210 | 1
T0176 | Glen Waverley - Carpet steam clean | Q0323 | Every 4 weeks | 218 | Carpet steam clean at 326 Main Highway, Glen Waverley | 2026-11-20 | true | Owner | J1211 | 1
T0177 | Glen Waverley - Office clean | Q0324 | Monthly | 3320 | Office clean at 306 Bridge Rd, Glen Waverley | 2026-11-01 | true | Office | J1212 | 1
T0178 | Brighton - Office clean | Q0326 | Monthly | 463.67 | Office clean at 145 Church Avenue, Brighton | 2026-11-01 | true | Office | J1214 | 1
T0179 | Camberwell - Office clean | Q0327 | Monthly | 1495 | Office clean at 190 Nicholson Avenue, Camberwell | 2026-11-01 | true | Owner | J1215 | 1
T0180 | Hawthorn - Office clean | Q0328 | Monthly | 1261 | Office clean at 387 Barkly Highway, Hawthorn | 2026-11-01 | true | Owner | J1216 | 1
T0181 | Kew - Office clean | Q0329 | Monthly | 572 | Office clean at 5 Park Hwy, Kew | 2026-11-01 | true | Office | J1217 | 1
T0182 | Williamstown - Office clean | Q0330 | Monthly | 814.67 | Office clean at 204 Mason Pde, Williamstown | 2026-11-01 | true | Office | J1218 | 1
T0183 | Cheltenham - Office clean | Q0331 | Monthly | 901.33 | Office clean at 445 Barkly Ave, Cheltenham | 2026-11-01 | true | Office | J1219 | 1
T0184 | Oakleigh - Office clean | Q0332 | Monthly | 780 | Office clean at 151 Glenferrie Highway, Oakleigh | 2026-11-01 | true | Bookkeeper | J1221 | 1
T0185 | Moorabbin - Office clean | Q0333 | Monthly | 928 | Office clean at 284 Mason Hwy, Moorabbin | 2026-11-01 | true | Bookkeeper | J1222 | 1
T0186 | Moorabbin - Carpet steam clean | Q0333 | Every 4 weeks | 135 | Carpet steam clean at 284 Mason Highway, Moorabbin | 2026-12-11 | true | Office | J1223 | 1
T0187 | Mentone - Office clean | Q0335 | Monthly | 520 | Office clean at 362 Barkly Ave, Mentone | 2026-11-01 | true | Bookkeeper | J1225 | 1
T0188 | Northcote - Office clean | Q0336 | Monthly | 2210 | Office clean at 418 Main Avenue, Northcote | 2026-11-01 | true | Owner | J1226 | 1
T0189 | Brunswick - Kitchen and bathrooms | Q0337 | Monthly | 512 | Kitchen and bathrooms at 176 High Highway, Brunswick | 2026-11-01 | true | Office | J1227 | 1
T0190 | Brunswick - Window clean | Q0337 | Every 4 weeks | 146 | Window clean at 176 High Hwy, Brunswick | 2026-12-02 | true | Bookkeeper | J1228 | 1
T0191 | Frankston - Kitchen and bathrooms | Q0338 | Monthly | 116 | Kitchen and bathrooms at 356 Glenferrie Pde, Frankston | 2026-11-01 | true | Owner | J1229 | 1
T0192 | Bentleigh - Office clean | Q0339 | Monthly | 580.67 | Office clean at 64 Glenferrie Parade, Bentleigh | 2026-11-01 | true | Office | J1230 | 1
T0193 | Bentleigh - Carpet steam clean | Q0339 | Every 4 weeks | 218 | Carpet steam clean at 64 Glenferrie Pde, Bentleigh | 2026-12-02 | true | Office | J1231 | 1
T0194 | Brunswick - Office clean | Q0340 | Monthly | 1672.67 | Office clean at 433 Mason Parade, Brunswick | 2026-11-01 | true | Bookkeeper | J1232 | 1
T0195 | Hawthorn - Office clean | Q0341 | Monthly | 1395.33 | Office clean at 291 Burke Highway, Hawthorn | 2026-11-01 | true | Bookkeeper | J1233 | 1
T0196 | Altona - Kitchen and bathrooms | Q0342 | Monthly | 806 | Kitchen and bathrooms at 186 Plenty Street, Altona | 2026-11-01 | true | Office | J1234 | 1
T0197 | Deer Park - Office clean | Q0343 | Monthly | 1092 | Office clean at 279 Nicholson Avenue, Deer Park | 2026-11-01 | true | Office | J1235 | 1
T0198 | Reservoir - Kitchen and bathrooms | Q0344 | Monthly | 832 | Kitchen and bathrooms at 313 Victoria Rd, Reservoir | 2026-11-01 | true | Office | J1236 | 1
T0199 | Brunswick - Office clean | Q0345 | Monthly | 910 | Office clean at 44 Nepean Parade, Brunswick | 2026-11-01 | true | Bookkeeper | J1238 | 1
T0200 | Preston - Office clean | Q0346 | Monthly | 1248 | Office clean at 67 Glenferrie Road, Preston | 2026-11-01 | true | Office | J1239 | 1
T0201 | Mitcham - Window clean | Q0347 | Every 4 weeks | 146 | Window clean at 6 Whitehorse St, Mitcham | 2026-12-07 | true | Office | J1241 | 1
T0202 | Mitcham - Washroom service | Q0347 | Monthly | 99 | Washroom service at 6 Whitehorse Street, Mitcham | 2026-11-01 | true | Office | J1242 | 1
T0203 | Yarraville - Office clean | Q0348 | Monthly | 1161.33 | Office clean at 267 Nepean Street, Yarraville | 2026-11-01 | true | Office | J1243 | 1
T0204 | Footscray - Office clean | Q0350 | Monthly | 1950 | Office clean at 158 Nepean Ave, Footscray | 2026-11-01 | true | Office | J1245 | 1
T0205 | Laverton - Office clean | Q0353 | Monthly | 390 | Office clean at 215 Barkly St, Laverton | 2026-11-01 | true | Bookkeeper | J1248 | 1
T0206 | Laverton - Window clean | Q0353 | Every 4 weeks | 116 | Window clean at 215 Barkly Street, Laverton | 2026-12-10 | true | Owner | J1249 | 1
T0207 | Brighton - Office clean | Q0354 | Monthly | 312 | Office clean at 329 Station Avenue, Brighton | 2026-11-01 | true | Bookkeeper | J1250 | 1
T0208 | Yarraville - Kitchen and bathrooms | Q0355 | Monthly | 615.33 | Kitchen and bathrooms at 462A Victoria Road, Yarraville | 2026-11-01 | true | Owner | J1251 | 1
T0209 | Bentleigh - Kitchen and bathrooms | Q0357 | Monthly | 554.67 | Kitchen and bathrooms at 251 Plenty Highway, Bentleigh | 2026-11-01 | true | Owner | J1254 | 1
T0210 | Bentleigh - Office clean | Q0358 | Monthly | 875.33 | Office clean at 148 Nepean St, Bentleigh | 2026-11-01 | true | Office | J1255 | 1
T0211 | Hawthorn - Office clean | Q0359 | Monthly | 1516.67 | Office clean at 431 Union Avenue, Hawthorn | 2026-11-01 | true | Bookkeeper | J1256 | 1
T0212 | Glen Waverley - Office clean | Q0361 | Monthly | 849.33 | Office clean at 422 Nicholson Parade, Glen Waverley | 2026-11-01 | true | Owner | J1258 | 1
T0213 | Glen Waverley - Window clean | Q0361 | Every 4 weeks | 218 | Window clean at 422 Nicholson Parade, Glen Waverley | 2026-11-16 | true | Office | J1259 | 1
T0214 | Epping - Office clean | Q0363 | Monthly | 849.33 | Office clean at 217 King St, Epping | 2026-11-01 | true | Office | J1262 | 1
T0215 | Mitcham - Office clean | Q0364 | Monthly | 901.33 | Office clean at 58 Station Rd, Mitcham | 2026-11-01 | true | Owner | J1263 | 1
T0216 | Kew - Office clean | Q0365 | Monthly | 2101.67 | Office clean at 343 Sydney St, Kew | 2026-11-01 | true | Bookkeeper | J1264 | 1
T0217 | Blackburn - Office clean | Q0367 | Monthly | 1280 | Office clean at 256 Station Street, Blackburn | 2026-11-01 | true | Owner | J1266 | 1
T0218 | Blackburn - Window clean | Q0367 | Every 4 weeks | 203 | Window clean at 256 Station St, Blackburn | 2026-12-11 | true | Owner | J1267 | 1
T0219 | Sunshine - Carpet steam clean | Q0368 | Every 4 weeks | 156 | Carpet steam clean at 459 Whitehorse Pde, Sunshine | 2026-12-01 | true | Bookkeeper | J1269 | 1
T0220 | Maribyrnong - Kitchen and bathrooms | Q0369 | Monthly | 1495 | Kitchen and bathrooms at 87 Main Ave, Maribyrnong | 2026-11-01 | true | Office | J1270 | 1
T0221 | Moorabbin - Office clean | Q0371 | Monthly | 754 | Office clean at 354 King Avenue, Moorabbin | 2026-11-01 | true | Owner | J1272 | 1
T0222 | Moorabbin - Window clean | Q0371 | Every 4 weeks | 109 | Window clean at 354 King Avenue, Moorabbin | 2026-11-26 | true | Owner | J1273 | 1
T0223 | Box Hill - Office clean | Q0372 | Monthly | 1265.33 | Office clean at 122 Main Ave, Box Hill | 2026-11-01 | true | Bookkeeper | J1274 | 1
T0224 | Frankston - Office clean | Q0374 | Monthly | 2327 | Office clean at 213 Church Pde, Frankston | 2026-11-01 | true | Bookkeeper | J1276 | 1
T0225 | Preston - Office clean | Q0375 | Monthly | 1287 | Office clean at 420 Railway Pde, Preston | 2026-11-01 | true | Office | J1277 | 1
T0226 | Burwood - Office clean | Q0378 | Monthly | 780 | Office clean at 81 Nepean Rd, Burwood | 2026-11-01 | true | Office | J1280 | 1
T0227 | Burwood office clean (copy) | Q0378 | Monthly | 754 | Office clean at 81 Nepean Road, Burwood | 2026-11-01 | true | Bookkeeper | J1280 | 1
T0228 | Maribyrnong - Office clean | Q0379 | Monthly | 325 | Office clean at 440 Bridge St, Maribyrnong | 2026-11-01 | true | Owner | J1281 | 1
T0229 | Maribyrnong - Window clean | Q0379 | Every 4 weeks | 146 | Window clean at 440 Bridge St, Maribyrnong | 2026-11-17 | true | Owner | J1282 | 1
T0230 | Ringwood - Office clean | Q0380 | Monthly | 2015 | Office clean at 347 High Highway, Ringwood | 2026-11-01 | true | Office | J1283 | 1
T0231 | Ringwood - Window clean | Q0380 | Every 4 weeks | 218 | Window clean at 347 High Hwy, Ringwood | 2026-11-27 | true | Office | J1284 | 1
T0232 | Burwood - Office clean | Q0382 | Monthly | 2513.33 | Office clean at 191 Albert Avenue, Burwood | 2026-11-01 | true | Office | J1286 | 1
T0233 | Brighton - Office clean | Q0383 | Monthly | 1326 | Office clean at 414 Sydney Ave, Brighton | 2026-11-01 | true | Bookkeeper | J1287 | 1
T0234 | Box Hill - Kitchen and bathrooms | Q0384 | Monthly | 572 | Kitchen and bathrooms at 472 Hopkins Highway, Box Hill | 2026-11-01 | true | Bookkeeper | J1288 | 1
T0235 | Box Hill kitchen and bathrooms (copy) | Q0384 | Monthly | 572 | Kitchen and bathrooms at 472 Hopkins Highway, Box Hill | 2026-11-01 | true | Owner | J1288 | 1
T0236 | Glen Waverley - Window clean | Q0385 | Every 4 weeks | 225 | Window clean at 410 Queen Hwy, Glen Waverley | 2026-11-30 | true | Bookkeeper | J1290 | 1
T0237 | Glen Waverley - Washroom service | Q0385 | Monthly | 99 | Washroom service at 410 Queen Hwy, Glen Waverley | 2026-11-01 | true | Office | J1291 | 1
T0238 | Mentone - Office clean | Q0386 | Monthly | 1005.33 | Office clean at 348 Railway Street, Mentone | 2026-11-01 | true | Owner | J1292 | 1
T0239 | Mentone - Window clean | Q0386 | Every 4 weeks | 116 | Window clean at 348 Railway Street, Mentone | 2026-12-10 | true | Owner | J1293 | 1
T0240 | Cheltenham - Office clean | Q0387 | Monthly | 671.67 | Office clean at 4 Sydney Highway, Cheltenham | 2026-11-01 | true | Office | J1294 | 1
T0241 | Cheltenham - Washroom service | Q0387 | Monthly | 151 | Washroom service at 4 Sydney Hwy, Cheltenham | 2026-11-01 | true | Office | J1295 | 1
T0242 | Oakleigh - Office clean | Q0388 | Monthly | 303.33 | Office clean at 395 Plenty Ave, Oakleigh | 2026-11-01 | true | Owner | J1296 | 1
T0243 | Brighton - Office clean | Q0390 | Monthly | 810.33 | Office clean at 333 Albert Parade, Brighton | 2026-11-01 | true | Bookkeeper | J1298 | 1
T0244 | Point Cook - Office clean | Q0392 | Monthly | 923 | Office clean at 87/12 Victoria Road, Point Cook | 2026-11-01 | true | Office | J1300 | 1
T0245 | Altona - Window clean | Q0395 | Every 4 weeks | 135 | Window clean at 351 High Street, Altona | 2026-12-01 | true | Bookkeeper | J1304 | 1
T0246 | Hawthorn - Office clean | Q0396 | Monthly | 2015 | Office clean at 477 Hopkins Avenue, Hawthorn | 2026-11-01 | true | Owner | J1305 | 1
T0247 | Hawthorn - Window clean | Q0396 | Every 4 weeks | 146 | Window clean at 477 Hopkins Ave, Hawthorn | 2026-11-26 | true | Bookkeeper | J1306 | 1
T0248 | Hawthorn - Washroom service | Q0396 | Monthly | 88 | Washroom service at 477 Hopkins Ave, Hawthorn | 2026-11-01 | true | Bookkeeper | J1307 | 1
T0249 | Maribyrnong - Carpet steam clean | Q0397 | Every 4 weeks | 146 | Carpet steam clean at 428 Church Pde, Maribyrnong | 2026-11-23 | true | Owner | J1309 | 1
T0250 | Maribyrnong carpet steam clean (copy) | Q0397 | Every 4 weeks | 146 | Carpet steam clean at 428 Church Pde, Maribyrnong | 2026-11-23 | true | Office | J1309 | 1
T0251 | Maribyrnong - Washroom service | Q0397 | Monthly | 99 | Washroom service at 428 Church Parade, Maribyrnong | 2026-11-01 | true | Bookkeeper | J1310 | 1
T0252 | Bundoora - Office clean | Q0398 | Monthly | 294.67 | Office clean at 253A Glenferrie Street, Bundoora | 2026-11-01 | true | Bookkeeper | J1311 | 1
T0253 | Werribee - Kitchen and bathrooms | Q0399 | Monthly | 589.33 | Kitchen and bathrooms at 466 Main Street, Werribee | 2026-11-01 | true | Office | J1312 | 1
T0254 | Mitcham - Kitchen and bathrooms | Q0401 | Monthly | 364 | Kitchen and bathrooms at 266/12 Albert Avenue, Mitcham | 2026-11-01 | true | Owner | J1314 | 1
T0255 | Reservoir - Washroom service | Q0402 | Monthly | 151 | Washroom service at 479 Burke Rd, Reservoir | 2026-11-01 | true | Office | J1316 | 1
T0256 | Burwood - Office clean | Q0403 | Monthly | 1048.67 | Office clean at 216 Plenty Road, Burwood | 2026-11-01 | true | Office | J1317 | 1
T0257 | Burwood - Window clean | Q0403 | Every 4 weeks | 218 | Window clean at 216 Plenty Road, Burwood | 2026-12-08 | true | Owner | J1318 | 1
T0258 | Bentleigh - Office clean | Q0405 | Monthly | 719.33 | Office clean at 438 Church Hwy, Bentleigh | 2026-11-01 | true | Bookkeeper | J1320 | 1
T0259 | Bentleigh - Carpet steam clean | Q0405 | Every 4 weeks | 203 | Carpet steam clean at 438 Church Highway, Bentleigh | 2026-12-08 | true | Office | J1321 | 1
T0260 | St Kilda - Office clean | Q0406 | Monthly | 671.67 | Office clean at 337 Plenty Pde, St Kilda | 2026-11-01 | true | Owner | J1322 | 1
T0261 | Northcote - Office clean | Q0407 | Monthly | 754 | Office clean at 314 Plenty Street, Northcote | 2026-11-01 | true | Bookkeeper | J1323 | 1
T0262 | Glen Waverley - Office clean | Q0408 | Monthly | 437.67 | Office clean at 121 High Pde, Glen Waverley | 2026-11-01 | true | Office | J1324 | 1
T0263 | Clayton - Office clean | Q0409 | Monthly | 1672.67 | Office clean at 317 Victoria Pde, Clayton | 2026-11-01 | true | Bookkeeper | J1325 | 1
T0264 | Coburg - Office clean | Q0410 | Monthly | 2621.67 | Office clean at 273/12 Plenty Pde, Coburg | 2026-11-01 | true | Bookkeeper | J1326 | 1
T0265 | Moorabbin - Office clean | Q0412 | Monthly | 416 | Office clean at 455 Nicholson Hwy, Moorabbin | 2026-11-01 | true | Bookkeeper | J1328 | 1
T0266 | Moorabbin - Window clean | Q0412 | Every 4 weeks | 112 | Window clean at 455 Nicholson Hwy, Moorabbin | 2026-11-26 | true | Bookkeeper | J1329 | 1
T0267 | Mentone - Office clean | Q0413 | Monthly | 1212 | Office clean at 400 Albert St, Mentone | 2026-11-01 | true | Bookkeeper | J1330 | 1
T0268 | Mentone - Washroom service | Q0413 | Monthly | 151 | Washroom service at 400 Albert St, Mentone | 2026-11-01 | true | Owner | J1331 | 1
T0269 | Point Cook - Office clean | Q0414 | Monthly | 1391 | Office clean at 257 Hopkins Pde, Point Cook | 2026-11-01 | true | Bookkeeper | J1332 | 1
T0270 | Brighton - Kitchen and bathrooms | Q0415 | Monthly | 598 | Kitchen and bathrooms at 139 Glenferrie Parade, Brighton | 2026-11-01 | true | Bookkeeper | J1333 | 1
T0271 | Werribee - Office clean | Q0416 | Monthly | 1664 | Office clean at 250 Bridge Highway, Werribee | 2026-11-01 | true | Office | J1334 | 1
T0272 | Point Cook - Office clean | Q0417 | Monthly | 567.67 | Office clean at 284A Park Road, Point Cook | 2026-11-01 | true | Office | J1335 | 1
T0273 | Point Cook - Window clean | Q0417 | Every 4 weeks | 203 | Window clean at 284A Park Road, Point Cook | 2026-11-26 | true | Bookkeeper | J1336 | 1
T0274 | Essendon - Office clean | Q0418 | Monthly | 801.67 | Office clean at 163 Barkly Highway, Essendon | 2026-11-01 | true | Owner | J1337 | 1
T0275 | Kew - Office clean | Q0419 | Monthly | 429 | Office clean at 448 Nicholson Street, Kew | 2026-11-01 | true | Bookkeeper | J1338 | 1
T0276 | Maribyrnong - Office clean | Q0420 | Monthly | 546 | Office clean at 360 Burke Street, Maribyrnong | 2026-11-01 | true | Bookkeeper | J1339 | 1
T0277 | Coburg - Office clean | Q0373 | Monthly | 377 | Office clean at 64 Bridge St, Coburg | 2026-11-01 | true | Office | J1340 | 1
T0278 | Werribee - Office clean | Q0316 | Monthly | 264.33 | Office clean at 460 Sydney Highway, Werribee | 2026-11-01 | true | Office | J1341 | 1
T0279 | St Kilda - Office clean | Q0288 | Monthly | 771.33 | Office clean at 102 Union Road, St Kilda | 2026-11-01 | true | Bookkeeper | J1342 | 1
T0280 | Altona - Office clean | Q0342 | Monthly | 1040 | Office clean at 186 Plenty St, Altona | 2026-11-01 | true | Office | J1343 | 1
T0281 | Bentleigh - Office clean | Q0169 | Monthly | 546 | Office clean at 218 High Rd, Bentleigh | 2026-11-01 | true | Office | J1344 | 1
T0282 | Northcote - Office clean | Q0336 | Monthly | 823.33 | Office clean at 418 Main Avenue, Northcote | 2026-11-01 | true | Owner | J1345 | 1
T0283 | Epping - Office clean | Q0311 | Monthly | 1274 | Office clean at 111A Plenty St, Epping | 2026-11-01 | true | Office | J1346 | 1
T0284 | Mitcham - Consumables supply | Q0182 | Monthly | 65 | Paper towel, soap and bin liners at 208 Main Avenue, Mitcham | 2026-11-01 | true | Owner | (none) | 1
T0285 | Clayton - Consumables supply | Q0409 | Monthly | 65 | Paper towel, soap and bin liners at 317 Victoria Parade, Clayton | 2026-11-01 | true | Owner | (none) | 1
T0286 | Bentleigh - Consumables supply | Q0358 | Monthly | 80 | Paper towel, soap and bin liners at 148 Nepean Street, Bentleigh | 2026-11-01 | true | Owner | (none) | 1
T0287 | Hawthorn - Consumables supply | Q0328 | Monthly | 80 | Paper towel, soap and bin liners at 387 Barkly Highway, Hawthorn | 2026-11-01 | true | Owner | (none) | 1
T0288 | Footscray - Consumables supply | Q0285 | Monthly | 65 | Paper towel, soap and bin liners at 443 Station Road, Footscray | 2026-11-01 | true | Owner | (none) | 1
T0289 | Hawthorn - Consumables supply | Q0228 | Monthly | 110 | Paper towel, soap and bin liners at 259 Union Avenue, Hawthorn | 2026-11-01 | true | Owner | (none) | 1

## QBO Invoices
QBO invoices Aug-Oct 2026 (from recurring templates)
Work sample: realistic data, built to show how I approach this work.
Invoice | Template | Customer ID | Date | Amount | Month | Job (or template)
10450 | T0001 | Q0170 | 2026-08-01 | 251.33 | 2026-08 | J1002
10451 | T0001 | Q0170 | 2026-09-01 | 251.33 | 2026-09 | J1002
10452 | T0001 | Q0170 | 2026-10-01 | 251.33 | 2026-10 | J1002
10453 | T0002 | Q0171 | 2026-08-01 | 284 | 2026-08 | J1004
10454 | T0002 | Q0171 | 2026-09-01 | 284 | 2026-09 | J1004
10455 | T0002 | Q0171 | 2026-10-01 | 284 | 2026-10 | J1004
10456 | T0003 | Q0172 | 2026-08-13 | 156 | 2026-08 | J1006
10457 | T0003 | Q0172 | 2026-09-10 | 156 | 2026-09 | J1006
10458 | T0003 | Q0172 | 2026-10-08 | 156 | 2026-10 | J1006
10459 | T0004 | Q0173 | 2026-08-01 | 598 | 2026-08 | J1007
10460 | T0004 | Q0173 | 2026-09-01 | 598 | 2026-09 | J1007
10461 | T0004 | Q0173 | 2026-10-01 | 598 | 2026-10 | J1007
10462 | T0005 | Q0174 | 2026-08-01 | 2093 | 2026-08 | J1008
10463 | T0005 | Q0174 | 2026-09-01 | 2093 | 2026-09 | J1008
10464 | T0005 | Q0174 | 2026-10-01 | 2093 | 2026-10 | J1008
10465 | T0006 | Q0175 | 2026-08-01 | 1135.33 | 2026-08 | J1009
10466 | T0006 | Q0175 | 2026-09-01 | 1135.33 | 2026-09 | J1009
10467 | T0006 | Q0175 | 2026-10-01 | 1135.33 | 2026-10 | J1009
10468 | T0007 | Q0176 | 2026-08-01 | 1768 | 2026-08 | J1010
10469 | T0007 | Q0176 | 2026-09-01 | 1768 | 2026-09 | J1010
10470 | T0007 | Q0176 | 2026-10-01 | 1768 | 2026-10 | J1010
10471 | T0008 | Q0177 | 2026-08-01 | 277.33 | 2026-08 | J1011
10472 | T0008 | Q0177 | 2026-09-01 | 277.33 | 2026-09 | J1011
10473 | T0008 | Q0177 | 2026-10-01 | 277.33 | 2026-10 | J1011
10474 | T0009 | Q0179 | 2026-08-01 | 88 | 2026-08 | J1015
10475 | T0009 | Q0179 | 2026-09-01 | 88 | 2026-09 | J1015
10476 | T0009 | Q0179 | 2026-10-01 | 88 | 2026-10 | J1015
10477 | T0010 | Q0180 | 2026-08-01 | 1386.67 | 2026-08 | J1016
10478 | T0010 | Q0180 | 2026-09-01 | 1386.67 | 2026-09 | J1016
10479 | T0010 | Q0180 | 2026-10-01 | 1386.67 | 2026-10 | J1016
10480 | T0011 | Q0181 | 2026-08-01 | 832 | 2026-08 | J1017
10481 | T0011 | Q0181 | 2026-09-01 | 832 | 2026-09 | J1017
10482 | T0011 | Q0181 | 2026-10-01 | 832 | 2026-10 | J1017
10483 | T0012 | Q0182 | 2026-08-01 | 390 | 2026-08 | J1018
10484 | T0012 | Q0182 | 2026-09-01 | 390 | 2026-09 | J1018
10485 | T0012 | Q0182 | 2026-10-01 | 390 | 2026-10 | J1018
10486 | T0013 | Q0183 | 2026-08-01 | 442 | 2026-08 | J1019
10487 | T0013 | Q0183 | 2026-09-01 | 442 | 2026-09 | J1019
10488 | T0013 | Q0183 | 2026-10-01 | 442 | 2026-10 | J1019
10489 | T0014 | Q0185 | 2026-08-01 | 1352 | 2026-08 | J1021
10490 | T0014 | Q0185 | 2026-09-01 | 1352 | 2026-09 | J1021
10491 | T0014 | Q0185 | 2026-10-01 | 1352 | 2026-10 | J1021
10492 | T0015 | Q0186 | 2026-08-01 | 819 | 2026-08 | J1022
10493 | T0015 | Q0186 | 2026-09-01 | 819 | 2026-09 | J1022
10494 | T0015 | Q0186 | 2026-10-01 | 819 | 2026-10 | J1022
10495 | T0016 | Q0187 | 2026-08-01 | 1256.67 | 2026-08 | J1023
10496 | T0016 | Q0187 | 2026-09-01 | 1256.67 | 2026-09 | J1023
10497 | T0016 | Q0187 | 2026-10-01 | 1256.67 | 2026-10 | J1023
10498 | T0017 | Q0187 | 2026-08-21 | 218 | 2026-08 | J1024
10499 | T0017 | Q0187 | 2026-09-18 | 218 | 2026-09 | J1024
10500 | T0017 | Q0187 | 2026-10-16 | 218 | 2026-10 | J1024
10501 | T0018 | Q0188 | 2026-08-01 | 303.33 | 2026-08 | J1025
10502 | T0018 | Q0188 | 2026-09-01 | 303.33 | 2026-09 | J1025
10503 | T0018 | Q0188 | 2026-10-01 | 303.33 | 2026-10 | J1025
10504 | T0019 | Q0188 | 2026-08-25 | 218 | 2026-08 | J1026
10505 | T0019 | Q0188 | 2026-09-22 | 218 | 2026-09 | J1026
10506 | T0019 | Q0188 | 2026-10-20 | 218 | 2026-10 | J1026
10507 | T0020 | Q0189 | 2026-08-01 | 1464 | 2026-08 | J1027
10508 | T0020 | Q0189 | 2026-09-01 | 1464 | 2026-09 | J1027
10509 | T0020 | Q0189 | 2026-10-01 | 1464 | 2026-10 | J1027
10510 | T0021 | Q0190 | 2026-08-01 | 537.33 | 2026-08 | J1028
10511 | T0021 | Q0190 | 2026-09-01 | 537.33 | 2026-09 | J1028
10512 | T0021 | Q0190 | 2026-10-01 | 537.33 | 2026-10 | J1028
10513 | T0022 | Q0191 | 2026-08-01 | 442 | 2026-08 | J1029
10514 | T0022 | Q0191 | 2026-09-01 | 442 | 2026-09 | J1029
10515 | T0022 | Q0191 | 2026-10-01 | 442 | 2026-10 | J1029
10516 | T0023 | Q0192 | 2026-08-01 | 884 | 2026-08 | J1030
10517 | T0023 | Q0192 | 2026-09-01 | 884 | 2026-09 | J1030
10518 | T0023 | Q0192 | 2026-10-01 | 884 | 2026-10 | J1030
10519 | T0024 | Q0193 | 2026-08-01 | 806 | 2026-08 | J1031
10520 | T0024 | Q0193 | 2026-09-01 | 806 | 2026-09 | J1031
10521 | T0024 | Q0193 | 2026-10-01 | 806 | 2026-10 | J1031
10522 | T0025 | Q0194 | 2026-08-01 | 4051.67 | 2026-08 | J1033
10523 | T0025 | Q0194 | 2026-09-01 | 4051.67 | 2026-09 | J1033
10524 | T0025 | Q0194 | 2026-10-01 | 4051.67 | 2026-10 | J1033
10525 | T0026 | Q0195 | 2026-08-01 | 560 | 2026-08 | J1034
10526 | T0026 | Q0195 | 2026-09-01 | 560 | 2026-09 | J1034
10527 | T0026 | Q0195 | 2026-10-01 | 560 | 2026-10 | J1034
10528 | T0027 | Q0196 | 2026-08-18 | 203 | 2026-08 | J1036
10529 | T0027 | Q0196 | 2026-09-15 | 203 | 2026-09 | J1036
10530 | T0027 | Q0196 | 2026-10-13 | 203 | 2026-10 | J1036
10531 | T0028 | Q0197 | 2026-08-01 | 286 | 2026-08 | J1037
10532 | T0028 | Q0197 | 2026-09-01 | 286 | 2026-09 | J1037
10533 | T0028 | Q0197 | 2026-10-01 | 286 | 2026-10 | J1037
10534 | T0029 | Q0199 | 2026-08-01 | 748 | 2026-08 | J1039
10535 | T0029 | Q0199 | 2026-09-01 | 748 | 2026-09 | J1039
10536 | T0029 | Q0199 | 2026-10-01 | 748 | 2026-10 | J1039
10537 | T0030 | Q0200 | 2026-08-01 | 840.67 | 2026-08 | J1040
10538 | T0030 | Q0200 | 2026-09-01 | 840.67 | 2026-09 | J1040
10539 | T0030 | Q0200 | 2026-10-01 | 840.67 | 2026-10 | J1040
10540 | T0031 | Q0200 | 2026-08-10 | 135 | 2026-08 | J1041
10541 | T0031 | Q0200 | 2026-09-07 | 135 | 2026-09 | J1041
10542 | T0031 | Q0200 | 2026-10-05 | 135 | 2026-10 | J1041
10543 | T0032 | Q0201 | 2026-08-01 | 138.67 | 2026-08 | J1042
10544 | T0032 | Q0201 | 2026-09-01 | 138.67 | 2026-09 | J1042
10545 | T0032 | Q0201 | 2026-10-01 | 138.67 | 2026-10 | J1042
10546 | T0033 | Q0202 | 2026-08-18 | 109 | 2026-08 | J1044
10547 | T0033 | Q0202 | 2026-09-15 | 109 | 2026-09 | J1044
10548 | T0033 | Q0202 | 2026-10-13 | 109 | 2026-10 | J1044
10549 | T0034 | Q0203 | 2026-08-01 | 125 | 2026-08 | J1046
10550 | T0034 | Q0203 | 2026-09-01 | 125 | 2026-09 | J1046
10551 | T0034 | Q0203 | 2026-10-01 | 125 | 2026-10 | J1046
10552 | T0035 | Q0204 | 2026-08-01 | 260 | 2026-08 | J1047
10553 | T0035 | Q0204 | 2026-09-01 | 260 | 2026-09 | J1047
10554 | T0035 | Q0204 | 2026-10-01 | 260 | 2026-10 | J1047
10555 | T0036 | Q0205 | 2026-08-01 | 836.33 | 2026-08 | J1048
10556 | T0036 | Q0205 | 2026-09-01 | 836.33 | 2026-09 | J1048
10557 | T0036 | Q0205 | 2026-10-01 | 836.33 | 2026-10 | J1048
10558 | T0037 | Q0205 | 2026-08-04 | 130 | 2026-08 | J1049
10559 | T0037 | Q0205 | 2026-09-01 | 130 | 2026-09 | J1049
10560 | T0037 | Q0205 | 2026-09-29 | 130 | 2026-09 | J1049
10561 | T0037 | Q0205 | 2026-10-27 | 130 | 2026-10 | J1049
10562 | T0038 | Q0207 | 2026-08-01 | 923 | 2026-08 | J1051
10563 | T0038 | Q0207 | 2026-09-01 | 923 | 2026-09 | J1051
10564 | T0038 | Q0207 | 2026-10-01 | 923 | 2026-10 | J1051
10565 | T0039 | Q0208 | 2026-08-01 | 1542.67 | 2026-08 | J1052
10566 | T0039 | Q0208 | 2026-09-01 | 1542.67 | 2026-09 | J1052
10567 | T0039 | Q0208 | 2026-10-01 | 1542.67 | 2026-10 | J1052
10568 | T0040 | Q0209 | 2026-08-01 | 697.67 | 2026-08 | J1053
10569 | T0040 | Q0209 | 2026-09-01 | 697.67 | 2026-09 | J1053
10570 | T0040 | Q0209 | 2026-10-01 | 697.67 | 2026-10 | J1053
10571 | T0041 | Q0211 | 2026-08-01 | 1768 | 2026-08 | J1055
10572 | T0041 | Q0211 | 2026-09-01 | 1768 | 2026-09 | J1055
10573 | T0041 | Q0211 | 2026-10-01 | 1768 | 2026-10 | J1055
10574 | T0042 | Q0213 | 2026-08-01 | 524.33 | 2026-08 | J1057
10575 | T0042 | Q0213 | 2026-09-01 | 524.33 | 2026-09 | J1057
10576 | T0042 | Q0213 | 2026-10-01 | 524.33 | 2026-10 | J1057
10577 | T0043 | Q0214 | 2026-08-01 | 975 | 2026-08 | J1058
10578 | T0043 | Q0214 | 2026-09-01 | 975 | 2026-09 | J1058
10579 | T0043 | Q0214 | 2026-10-01 | 975 | 2026-10 | J1058
10580 | T0044 | Q0216 | 2026-08-01 | 1542.67 | 2026-08 | J1060
10581 | T0044 | Q0216 | 2026-09-01 | 1542.67 | 2026-09 | J1060
10582 | T0044 | Q0216 | 2026-10-01 | 1542.67 | 2026-10 | J1060
10583 | T0045 | Q0219 | 2026-08-01 | 1352 | 2026-08 | J1064
10584 | T0045 | Q0219 | 2026-09-01 | 1352 | 2026-09 | J1064
10585 | T0045 | Q0219 | 2026-10-01 | 1352 | 2026-10 | J1064
10586 | T0046 | Q0219 | 2026-08-05 | 130 | 2026-08 | J1065
10587 | T0046 | Q0219 | 2026-09-02 | 130 | 2026-09 | J1065
10588 | T0046 | Q0219 | 2026-09-30 | 130 | 2026-09 | J1065
10589 | T0046 | Q0219 | 2026-10-28 | 130 | 2026-10 | J1065
10590 | T0047 | Q0220 | 2026-08-01 | 2093 | 2026-08 | J1066
10591 | T0047 | Q0220 | 2026-09-01 | 2093 | 2026-09 | J1066
10592 | T0047 | Q0220 | 2026-10-01 | 2093 | 2026-10 | J1066
10593 | T0048 | Q0220 | 2026-08-03 | 116 | 2026-08 | J1067
10594 | T0048 | Q0220 | 2026-08-31 | 116 | 2026-08 | J1067
10595 | T0048 | Q0220 | 2026-09-28 | 116 | 2026-09 | J1067
10596 | T0048 | Q0220 | 2026-10-26 | 116 | 2026-10 | J1067
10597 | T0049 | Q0221 | 2026-08-01 | 654.33 | 2026-08 | J1068
10598 | T0049 | Q0221 | 2026-09-01 | 654.33 | 2026-09 | J1068
10599 | T0049 | Q0221 | 2026-10-01 | 654.33 | 2026-10 | J1068
10600 | T0050 | Q0222 | 2026-08-01 | 897 | 2026-08 | J1069
10601 | T0050 | Q0222 | 2026-09-01 | 897 | 2026-09 | J1069
10602 | T0050 | Q0222 | 2026-10-01 | 897 | 2026-10 | J1069
10603 | T0051 | Q0223 | 2026-08-01 | 598 | 2026-08 | J1070
10604 | T0051 | Q0223 | 2026-09-01 | 598 | 2026-09 | J1070
10605 | T0051 | Q0223 | 2026-10-01 | 598 | 2026-10 | J1070
10606 | T0052 | Q0224 | 2026-08-01 | 784.33 | 2026-08 | J1071
10607 | T0052 | Q0224 | 2026-09-01 | 784.33 | 2026-09 | J1071
10608 | T0052 | Q0224 | 2026-10-01 | 784.33 | 2026-10 | J1071
10609 | T0053 | Q0224 | 2026-08-01 | 784.33 | 2026-08 | J1071
10610 | T0053 | Q0224 | 2026-09-01 | 784.33 | 2026-09 | J1071
10611 | T0053 | Q0224 | 2026-10-01 | 784.33 | 2026-10 | J1071
10612 | T0054 | Q0225 | 2026-08-01 | 580.67 | 2026-08 | J1072
10613 | T0054 | Q0225 | 2026-09-01 | 580.67 | 2026-09 | J1072
10614 | T0054 | Q0225 | 2026-10-01 | 580.67 | 2026-10 | J1072
10615 | T0055 | Q0226 | 2026-08-01 | 273 | 2026-08 | J1073
10616 | T0055 | Q0226 | 2026-09-01 | 273 | 2026-09 | J1073
10617 | T0055 | Q0226 | 2026-10-01 | 273 | 2026-10 | J1073
10618 | T0056 | Q0227 | 2026-08-27 | 102 | 2026-08 | J1076
10619 | T0056 | Q0227 | 2026-09-24 | 102 | 2026-09 | J1076
10620 | T0056 | Q0227 | 2026-10-22 | 102 | 2026-10 | J1076
10621 | T0057 | Q0229 | 2026-08-01 | 273 | 2026-08 | J1078
10622 | T0057 | Q0229 | 2026-09-01 | 273 | 2026-09 | J1078
10623 | T0057 | Q0229 | 2026-10-01 | 273 | 2026-10 | J1078
10624 | T0058 | Q0230 | 2026-08-01 | 286 | 2026-08 | J1079
10625 | T0058 | Q0230 | 2026-09-01 | 286 | 2026-09 | J1079
10626 | T0058 | Q0230 | 2026-10-01 | 286 | 2026-10 | J1079
10627 | T0059 | Q0230 | 2026-08-03 | 109 | 2026-08 | J1080
10628 | T0059 | Q0230 | 2026-08-31 | 109 | 2026-08 | J1080
10629 | T0059 | Q0230 | 2026-09-28 | 109 | 2026-09 | J1080
10630 | T0059 | Q0230 | 2026-10-26 | 109 | 2026-10 | J1080
10631 | T0060 | Q0231 | 2026-08-01 | 1690 | 2026-08 | J1081
10632 | T0060 | Q0231 | 2026-09-01 | 1690 | 2026-09 | J1081
10633 | T0060 | Q0231 | 2026-10-01 | 1690 | 2026-10 | J1081
10634 | T0061 | Q0231 | 2026-08-01 | 1690 | 2026-08 | J1081
10635 | T0061 | Q0231 | 2026-09-01 | 1690 | 2026-09 | J1081
10636 | T0061 | Q0231 | 2026-10-01 | 1690 | 2026-10 | J1081
10637 | T0062 | Q0231 | 2026-08-01 | 151 | 2026-08 | J1082
10638 | T0062 | Q0231 | 2026-09-01 | 151 | 2026-09 | J1082
10639 | T0062 | Q0231 | 2026-10-01 | 151 | 2026-10 | J1082
10640 | T0063 | Q0232 | 2026-08-01 | 1625 | 2026-08 | J1083
10641 | T0063 | Q0232 | 2026-09-01 | 1625 | 2026-09 | J1083
10642 | T0063 | Q0232 | 2026-10-01 | 1625 | 2026-10 | J1083
10643 | T0064 | Q0233 | 2026-08-01 | 1672.67 | 2026-08 | J1085
10644 | T0064 | Q0233 | 2026-09-01 | 1672.67 | 2026-09 | J1085
10645 | T0064 | Q0233 | 2026-10-01 | 1672.67 | 2026-10 | J1085
10646 | T0065 | Q0233 | 2026-08-06 | 109 | 2026-08 | J1086
10647 | T0065 | Q0233 | 2026-09-03 | 109 | 2026-09 | J1086
10648 | T0065 | Q0233 | 2026-10-01 | 109 | 2026-10 | J1086
10649 | T0065 | Q0233 | 2026-10-29 | 109 | 2026-10 | J1086
10650 | T0066 | Q0233 | 2026-08-01 | 145 | 2026-08 | J1087
10651 | T0066 | Q0233 | 2026-09-01 | 145 | 2026-09 | J1087
10652 | T0066 | Q0233 | 2026-10-01 | 145 | 2026-10 | J1087
10653 | T0067 | Q0234 | 2026-08-12 | 109 | 2026-08 | J1089
10654 | T0067 | Q0234 | 2026-09-09 | 109 | 2026-09 | J1089
10655 | T0067 | Q0234 | 2026-10-07 | 109 | 2026-10 | J1089
10656 | T0068 | Q0234 | 2026-08-01 | 151 | 2026-08 | J1090
10657 | T0068 | Q0234 | 2026-09-01 | 151 | 2026-09 | J1090
10658 | T0068 | Q0234 | 2026-10-01 | 151 | 2026-10 | J1090
10659 | T0069 | Q0235 | 2026-08-01 | 520 | 2026-08 | J1091
10660 | T0069 | Q0235 | 2026-09-01 | 520 | 2026-09 | J1091
10661 | T0069 | Q0235 | 2026-10-01 | 520 | 2026-10 | J1091
10662 | T0070 | Q0236 | 2026-08-01 | 884 | 2026-08 | J1092
10663 | T0070 | Q0236 | 2026-09-01 | 884 | 2026-09 | J1092
10664 | T0070 | Q0236 | 2026-10-01 | 884 | 2026-10 | J1092
10665 | T0071 | Q0237 | 2026-08-01 | 559 | 2026-08 | J1093
10666 | T0071 | Q0237 | 2026-09-01 | 559 | 2026-09 | J1093
10667 | T0071 | Q0237 | 2026-10-01 | 559 | 2026-10 | J1093
10668 | T0072 | Q0238 | 2026-08-01 | 806 | 2026-08 | J1094
10669 | T0072 | Q0238 | 2026-09-01 | 806 | 2026-09 | J1094
10670 | T0072 | Q0238 | 2026-10-01 | 806 | 2026-10 | J1094
10671 | T0073 | Q0238 | 2026-08-04 | 102 | 2026-08 | J1095
10672 | T0073 | Q0238 | 2026-09-01 | 102 | 2026-09 | J1095
10673 | T0073 | Q0238 | 2026-09-29 | 102 | 2026-09 | J1095
10674 | T0073 | Q0238 | 2026-10-27 | 102 | 2026-10 | J1095
10675 | T0074 | Q0239 | 2026-08-01 | 1755 | 2026-08 | J1096
10676 | T0074 | Q0239 | 2026-09-01 | 1755 | 2026-09 | J1096
10677 | T0074 | Q0239 | 2026-10-01 | 1755 | 2026-10 | J1096
10678 | T0075 | Q0240 | 2026-08-01 | 1716 | 2026-08 | J1097
10679 | T0075 | Q0240 | 2026-09-01 | 1716 | 2026-09 | J1097
10680 | T0075 | Q0240 | 2026-10-01 | 1716 | 2026-10 | J1097
10681 | T0076 | Q0240 | 2026-08-27 | 112 | 2026-08 | J1098
10682 | T0076 | Q0240 | 2026-09-24 | 112 | 2026-09 | J1098
10683 | T0076 | Q0240 | 2026-10-22 | 112 | 2026-10 | J1098
10684 | T0077 | Q0240 | 2026-08-01 | 125 | 2026-08 | J1099
10685 | T0077 | Q0240 | 2026-09-01 | 125 | 2026-09 | J1099
10686 | T0077 | Q0240 | 2026-10-01 | 125 | 2026-10 | J1099
10687 | T0078 | Q0241 | 2026-08-01 | 1005.33 | 2026-08 | J1100
10688 | T0078 | Q0241 | 2026-09-01 | 1005.33 | 2026-09 | J1100
10689 | T0078 | Q0241 | 2026-10-01 | 1005.33 | 2026-10 | J1100
10690 | T0079 | Q0242 | 2026-08-01 | 85 | 2026-08 | J1103
10691 | T0079 | Q0242 | 2026-09-01 | 85 | 2026-09 | J1103
10692 | T0079 | Q0242 | 2026-10-01 | 85 | 2026-10 | J1103
10693 | T0080 | Q0243 | 2026-08-01 | 464 | 2026-08 | J1104
10694 | T0080 | Q0243 | 2026-09-01 | 464 | 2026-09 | J1104
10695 | T0080 | Q0243 | 2026-10-01 | 464 | 2026-10 | J1104
10696 | T0081 | Q0243 | 2026-08-05 | 218 | 2026-08 | J1105
10697 | T0081 | Q0243 | 2026-09-02 | 218 | 2026-09 | J1105
10698 | T0081 | Q0243 | 2026-09-30 | 218 | 2026-09 | J1105
10699 | T0081 | Q0243 | 2026-10-28 | 218 | 2026-10 | J1105
10700 | T0082 | Q0245 | 2026-08-01 | 2440 | 2026-08 | J1107
10701 | T0082 | Q0245 | 2026-09-01 | 2440 | 2026-09 | J1107
10702 | T0082 | Q0245 | 2026-10-01 | 2440 | 2026-10 | J1107
10703 | T0083 | Q0245 | 2026-08-17 | 116 | 2026-08 | J1108
10704 | T0083 | Q0245 | 2026-09-14 | 116 | 2026-09 | J1108
10705 | T0083 | Q0245 | 2026-10-12 | 116 | 2026-10 | J1108
10706 | T0084 | Q0246 | 2026-08-01 | 606.67 | 2026-08 | J1109
10707 | T0084 | Q0246 | 2026-09-01 | 606.67 | 2026-09 | J1109
10708 | T0084 | Q0246 | 2026-10-01 | 606.67 | 2026-10 | J1109
10709 | T0085 | Q0247 | 2026-08-01 | 2123.33 | 2026-08 | J1110
10710 | T0085 | Q0247 | 2026-09-01 | 2123.33 | 2026-09 | J1110
10711 | T0085 | Q0247 | 2026-10-01 | 2123.33 | 2026-10 | J1110
10712 | T0086 | Q0247 | 2026-08-27 | 105 | 2026-08 | J1111
10713 | T0086 | Q0247 | 2026-09-24 | 105 | 2026-09 | J1111
10714 | T0086 | Q0247 | 2026-10-22 | 105 | 2026-10 | J1111
10715 | T0087 | Q0248 | 2026-08-01 | 130 | 2026-08 | J1112
10716 | T0087 | Q0248 | 2026-09-01 | 130 | 2026-09 | J1112
10717 | T0087 | Q0248 | 2026-10-01 | 130 | 2026-10 | J1112
10718 | T0088 | Q0249 | 2026-08-01 | 125 | 2026-08 | J1114
10719 | T0088 | Q0249 | 2026-09-01 | 125 | 2026-09 | J1114
10720 | T0088 | Q0249 | 2026-10-01 | 125 | 2026-10 | J1114
10721 | T0089 | Q0250 | 2026-08-01 | 325 | 2026-08 | J1115
10722 | T0089 | Q0250 | 2026-09-01 | 325 | 2026-09 | J1115
10723 | T0089 | Q0250 | 2026-10-01 | 325 | 2026-10 | J1115
10724 | T0090 | Q0251 | 2026-08-01 | 801.67 | 2026-08 | J1116
10725 | T0090 | Q0251 | 2026-09-01 | 801.67 | 2026-09 | J1116
10726 | T0090 | Q0251 | 2026-10-01 | 801.67 | 2026-10 | J1116
10727 | T0091 | Q0252 | 2026-08-01 | 1100.67 | 2026-08 | J1117
10728 | T0091 | Q0252 | 2026-09-01 | 1100.67 | 2026-09 | J1117
10729 | T0091 | Q0252 | 2026-10-01 | 1100.67 | 2026-10 | J1117
10730 | T0092 | Q0253 | 2026-08-01 | 748 | 2026-08 | J1118
10731 | T0092 | Q0253 | 2026-09-01 | 748 | 2026-09 | J1118
10732 | T0092 | Q0253 | 2026-10-01 | 748 | 2026-10 | J1118
10733 | T0093 | Q0253 | 2026-08-04 | 116 | 2026-08 | J1119
10734 | T0093 | Q0253 | 2026-09-01 | 116 | 2026-09 | J1119
10735 | T0093 | Q0253 | 2026-09-29 | 116 | 2026-09 | J1119
10736 | T0093 | Q0253 | 2026-10-27 | 116 | 2026-10 | J1119
10737 | T0094 | Q0254 | 2026-08-01 | 502.67 | 2026-08 | J1120
10738 | T0094 | Q0254 | 2026-09-01 | 502.67 | 2026-09 | J1120
10739 | T0094 | Q0254 | 2026-10-01 | 502.67 | 2026-10 | J1120
10740 | T0095 | Q0255 | 2026-08-01 | 134.33 | 2026-08 | J1121
10741 | T0095 | Q0255 | 2026-09-01 | 134.33 | 2026-09 | J1121
10742 | T0095 | Q0255 | 2026-10-01 | 134.33 | 2026-10 | J1121
10743 | T0096 | Q0256 | 2026-08-01 | 559 | 2026-08 | J1122
10744 | T0096 | Q0256 | 2026-09-01 | 559 | 2026-09 | J1122
10745 | T0096 | Q0256 | 2026-10-01 | 559 | 2026-10 | J1122
10746 | T0097 | Q0257 | 2026-08-01 | 580.67 | 2026-08 | J1124
10747 | T0097 | Q0257 | 2026-09-01 | 580.67 | 2026-09 | J1124
10748 | T0097 | Q0257 | 2026-10-01 | 580.67 | 2026-10 | J1124
10749 | T0098 | Q0258 | 2026-08-01 | 1300 | 2026-08 | J1125
10750 | T0098 | Q0258 | 2026-09-01 | 1300 | 2026-09 | J1125
10751 | T0098 | Q0258 | 2026-10-01 | 1300 | 2026-10 | J1125
10752 | T0099 | Q0259 | 2026-08-01 | 1395.33 | 2026-08 | J1127
10753 | T0099 | Q0259 | 2026-09-01 | 1395.33 | 2026-09 | J1127
10754 | T0099 | Q0259 | 2026-10-01 | 1395.33 | 2026-10 | J1127
10755 | T0100 | Q0260 | 2026-08-01 | 650 | 2026-08 | J1128
10756 | T0100 | Q0260 | 2026-09-01 | 650 | 2026-09 | J1128
10757 | T0100 | Q0260 | 2026-10-01 | 650 | 2026-10 | J1128
10758 | T0101 | Q0261 | 2026-08-01 | 550.33 | 2026-08 | J1129
10759 | T0101 | Q0261 | 2026-09-01 | 550.33 | 2026-09 | J1129
10760 | T0101 | Q0261 | 2026-10-01 | 550.33 | 2026-10 | J1129
10761 | T0102 | Q0261 | 2026-08-03 | 203 | 2026-08 | J1130
10762 | T0102 | Q0261 | 2026-08-31 | 203 | 2026-08 | J1130
10763 | T0102 | Q0261 | 2026-09-28 | 203 | 2026-09 | J1130
10764 | T0102 | Q0261 | 2026-10-26 | 203 | 2026-10 | J1130
10765 | T0103 | Q0262 | 2026-08-01 | 589.33 | 2026-08 | J1131
10766 | T0103 | Q0262 | 2026-09-01 | 589.33 | 2026-09 | J1131
10767 | T0103 | Q0262 | 2026-10-01 | 589.33 | 2026-10 | J1131
10768 | T0104 | Q0263 | 2026-08-28 | 218 | 2026-08 | J1133
10769 | T0104 | Q0263 | 2026-09-25 | 218 | 2026-09 | J1133
10770 | T0104 | Q0263 | 2026-10-23 | 218 | 2026-10 | J1133
10771 | T0105 | Q0264 | 2026-08-01 | 251.33 | 2026-08 | J1134
10772 | T0105 | Q0264 | 2026-09-01 | 251.33 | 2026-09 | J1134
10773 | T0105 | Q0264 | 2026-10-01 | 251.33 | 2026-10 | J1134
10774 | T0106 | Q0265 | 2026-08-01 | 1438.67 | 2026-08 | J1135
10775 | T0106 | Q0265 | 2026-09-01 | 1438.67 | 2026-09 | J1135
10776 | T0106 | Q0265 | 2026-10-01 | 1438.67 | 2026-10 | J1135
10777 | T0107 | Q0265 | 2026-08-17 | 156 | 2026-08 | J1136
10778 | T0107 | Q0265 | 2026-09-14 | 156 | 2026-09 | J1136
10779 | T0107 | Q0265 | 2026-10-12 | 156 | 2026-10 | J1136
10780 | T0108 | Q0266 | 2026-08-01 | 502.67 | 2026-08 | J1137
10781 | T0108 | Q0266 | 2026-09-01 | 502.67 | 2026-09 | J1137
10782 | T0108 | Q0266 | 2026-10-01 | 502.67 | 2026-10 | J1137
10783 | T0109 | Q0267 | 2026-08-01 | 632.67 | 2026-08 | J1138
10784 | T0109 | Q0267 | 2026-09-01 | 632.67 | 2026-09 | J1138
10785 | T0109 | Q0267 | 2026-10-01 | 632.67 | 2026-10 | J1138
10786 | T0110 | Q0268 | 2026-08-01 | 1170 | 2026-08 | J1139
10787 | T0110 | Q0268 | 2026-09-01 | 1170 | 2026-09 | J1139
10788 | T0110 | Q0268 | 2026-10-01 | 1170 | 2026-10 | J1139
10789 | T0111 | Q0269 | 2026-08-01 | 650 | 2026-08 | J1140
10790 | T0111 | Q0269 | 2026-09-01 | 650 | 2026-09 | J1140
10791 | T0111 | Q0269 | 2026-10-01 | 650 | 2026-10 | J1140
10792 | T0112 | Q0270 | 2026-08-01 | 294.67 | 2026-08 | J1141
10793 | T0112 | Q0270 | 2026-09-01 | 294.67 | 2026-09 | J1141
10794 | T0112 | Q0270 | 2026-10-01 | 294.67 | 2026-10 | J1141
10795 | T0113 | Q0270 | 2026-08-01 | 99 | 2026-08 | J1142
10796 | T0113 | Q0270 | 2026-09-01 | 99 | 2026-09 | J1142
10797 | T0113 | Q0270 | 2026-10-01 | 99 | 2026-10 | J1142
10798 | T0114 | Q0271 | 2026-08-01 | 1092 | 2026-08 | J1143
10799 | T0114 | Q0271 | 2026-09-01 | 1092 | 2026-09 | J1143
10800 | T0114 | Q0271 | 2026-10-01 | 1092 | 2026-10 | J1143
10801 | T0115 | Q0272 | 2026-08-01 | 676 | 2026-08 | J1144
10802 | T0115 | Q0272 | 2026-09-01 | 676 | 2026-09 | J1144
10803 | T0115 | Q0272 | 2026-10-01 | 676 | 2026-10 | J1144
10804 | T0116 | Q0272 | 2026-08-24 | 109 | 2026-08 | J1145
10805 | T0116 | Q0272 | 2026-09-21 | 109 | 2026-09 | J1145
10806 | T0116 | Q0272 | 2026-10-19 | 109 | 2026-10 | J1145
10807 | T0117 | Q0273 | 2026-08-01 | 251.33 | 2026-08 | J1146
10808 | T0117 | Q0273 | 2026-09-01 | 251.33 | 2026-09 | J1146
10809 | T0117 | Q0273 | 2026-10-01 | 251.33 | 2026-10 | J1146
10810 | T0118 | Q0274 | 2026-08-01 | 923 | 2026-08 | J1147
10811 | T0118 | Q0274 | 2026-09-01 | 923 | 2026-09 | J1147
10812 | T0118 | Q0274 | 2026-10-01 | 923 | 2026-10 | J1147
10813 | T0119 | Q0275 | 2026-08-01 | 277.33 | 2026-08 | J1148
10814 | T0119 | Q0275 | 2026-09-01 | 277.33 | 2026-09 | J1148
10815 | T0119 | Q0275 | 2026-10-01 | 277.33 | 2026-10 | J1148
10816 | T0120 | Q0275 | 2026-08-25 | 135 | 2026-08 | J1149
10817 | T0120 | Q0275 | 2026-09-22 | 135 | 2026-09 | J1149
10818 | T0120 | Q0275 | 2026-10-20 | 135 | 2026-10 | J1149
10819 | T0121 | Q0276 | 2026-08-01 | 936 | 2026-08 | J1150
10820 | T0121 | Q0276 | 2026-09-01 | 936 | 2026-09 | J1150
10821 | T0121 | Q0276 | 2026-10-01 | 936 | 2026-10 | J1150
10822 | T0122 | Q0276 | 2026-08-07 | 203 | 2026-08 | J1151
10823 | T0122 | Q0276 | 2026-09-04 | 203 | 2026-09 | J1151
10824 | T0122 | Q0276 | 2026-10-02 | 203 | 2026-10 | J1151
10825 | T0122 | Q0276 | 2026-10-30 | 203 | 2026-10 | J1151
10826 | T0123 | Q0277 | 2026-08-01 | 1568.67 | 2026-08 | J1152
10827 | T0123 | Q0277 | 2026-09-01 | 1568.67 | 2026-09 | J1152
10828 | T0123 | Q0277 | 2026-10-01 | 1568.67 | 2026-10 | J1152
10829 | T0124 | Q0277 | 2026-08-01 | 95 | 2026-08 | J1153
10830 | T0124 | Q0277 | 2026-09-01 | 95 | 2026-09 | J1153
10831 | T0124 | Q0277 | 2026-10-01 | 95 | 2026-10 | J1153
10832 | T0125 | Q0278 | 2026-08-01 | 437.67 | 2026-08 | J1154
10833 | T0125 | Q0278 | 2026-09-01 | 437.67 | 2026-09 | J1154
10834 | T0125 | Q0278 | 2026-10-01 | 437.67 | 2026-10 | J1154
10835 | T0126 | Q0279 | 2026-08-01 | 528.67 | 2026-08 | J1155
10836 | T0126 | Q0279 | 2026-09-01 | 528.67 | 2026-09 | J1155
10837 | T0126 | Q0279 | 2026-10-01 | 528.67 | 2026-10 | J1155
10838 | T0127 | Q0279 | 2026-08-01 | 528.67 | 2026-08 | J1155
10839 | T0127 | Q0279 | 2026-09-01 | 528.67 | 2026-09 | J1155
10840 | T0127 | Q0279 | 2026-10-01 | 528.67 | 2026-10 | J1155
10841 | T0128 | Q0280 | 2026-08-01 | 1655.33 | 2026-08 | J1156
10842 | T0128 | Q0280 | 2026-09-01 | 1655.33 | 2026-09 | J1156
10843 | T0128 | Q0280 | 2026-10-01 | 1655.33 | 2026-10 | J1156
10844 | T0129 | Q0281 | 2026-08-01 | 1752 | 2026-08 | J1157
10845 | T0129 | Q0281 | 2026-09-01 | 1752 | 2026-09 | J1157
10846 | T0129 | Q0281 | 2026-10-01 | 1752 | 2026-10 | J1157
10847 | T0130 | Q0282 | 2026-08-01 | 1213.33 | 2026-08 | J1158
10848 | T0130 | Q0282 | 2026-09-01 | 1213.33 | 2026-09 | J1158
10849 | T0130 | Q0282 | 2026-10-01 | 1213.33 | 2026-10 | J1158
10850 | T0131 | Q0283 | 2026-08-01 | 277.33 | 2026-08 | J1159
10851 | T0131 | Q0283 | 2026-09-01 | 277.33 | 2026-09 | J1159
10852 | T0131 | Q0283 | 2026-10-01 | 277.33 | 2026-10 | J1159
10853 | T0132 | Q0283 | 2026-08-01 | 85 | 2026-08 | J1160
10854 | T0132 | Q0283 | 2026-09-01 | 85 | 2026-09 | J1160
10855 | T0132 | Q0283 | 2026-10-01 | 85 | 2026-10 | J1160
10856 | T0133 | Q0284 | 2026-08-01 | 268.67 | 2026-08 | J1161
10857 | T0133 | Q0284 | 2026-09-01 | 268.67 | 2026-09 | J1161
10858 | T0133 | Q0284 | 2026-10-01 | 268.67 | 2026-10 | J1161
10859 | T0134 | Q0285 | 2026-08-01 | 585 | 2026-08 | J1162
10860 | T0134 | Q0285 | 2026-09-01 | 585 | 2026-09 | J1162
10861 | T0134 | Q0285 | 2026-10-01 | 585 | 2026-10 | J1162
10862 | T0135 | Q0286 | 2026-08-19 | 146 | 2026-08 | J1164
10863 | T0135 | Q0286 | 2026-09-16 | 146 | 2026-09 | J1164
10864 | T0135 | Q0286 | 2026-10-14 | 146 | 2026-10 | J1164
10865 | T0136 | Q0288 | 2026-08-01 | 1438.67 | 2026-08 | J1166
10866 | T0136 | Q0288 | 2026-09-01 | 1438.67 | 2026-09 | J1166
10867 | T0136 | Q0288 | 2026-10-01 | 1438.67 | 2026-10 | J1166
10868 | T0137 | Q0289 | 2026-08-01 | 307.67 | 2026-08 | J1167
10869 | T0137 | Q0289 | 2026-09-01 | 307.67 | 2026-09 | J1167
10870 | T0137 | Q0289 | 2026-10-01 | 307.67 | 2026-10 | J1167
10871 | T0138 | Q0290 | 2026-08-01 | 1560 | 2026-08 | J1169
10872 | T0138 | Q0290 | 2026-09-01 | 1560 | 2026-09 | J1169
10873 | T0138 | Q0290 | 2026-10-01 | 1560 | 2026-10 | J1169
10874 | T0139 | Q0291 | 2026-08-01 | 251.33 | 2026-08 | J1170
10875 | T0139 | Q0291 | 2026-09-01 | 251.33 | 2026-09 | J1170
10876 | T0139 | Q0291 | 2026-10-01 | 251.33 | 2026-10 | J1170
10877 | T0140 | Q0292 | 2026-08-01 | 2513.33 | 2026-08 | J1171
10878 | T0140 | Q0292 | 2026-09-01 | 2513.33 | 2026-09 | J1171
10879 | T0140 | Q0292 | 2026-10-01 | 2513.33 | 2026-10 | J1171
10880 | T0141 | Q0293 | 2026-08-01 | 1343.33 | 2026-08 | J1172
10881 | T0141 | Q0293 | 2026-09-01 | 1343.33 | 2026-09 | J1172
10882 | T0141 | Q0293 | 2026-10-01 | 1343.33 | 2026-10 | J1172
10883 | T0142 | Q0294 | 2026-08-01 | 806 | 2026-08 | J1174
10884 | T0142 | Q0294 | 2026-09-01 | 806 | 2026-09 | J1174
10885 | T0142 | Q0294 | 2026-10-01 | 806 | 2026-10 | J1174
10886 | T0143 | Q0295 | 2026-08-01 | 420.33 | 2026-08 | J1175
10887 | T0143 | Q0295 | 2026-09-01 | 420.33 | 2026-09 | J1175
10888 | T0143 | Q0295 | 2026-10-01 | 420.33 | 2026-10 | J1175
10889 | T0144 | Q0296 | 2026-08-01 | 316.33 | 2026-08 | J1176
10890 | T0144 | Q0296 | 2026-09-01 | 316.33 | 2026-09 | J1176
10891 | T0144 | Q0296 | 2026-10-01 | 316.33 | 2026-10 | J1176
10892 | T0145 | Q0296 | 2026-08-01 | 303.33 | 2026-08 | J1176
10893 | T0145 | Q0296 | 2026-09-01 | 303.33 | 2026-09 | J1176
10894 | T0145 | Q0296 | 2026-10-01 | 303.33 | 2026-10 | J1176
10895 | T0146 | Q0297 | 2026-08-01 | 296 | 2026-08 | J1177
10896 | T0146 | Q0297 | 2026-09-01 | 296 | 2026-09 | J1177
10897 | T0146 | Q0297 | 2026-10-01 | 296 | 2026-10 | J1177
10898 | T0147 | Q0297 | 2026-08-21 | 135 | 2026-08 | J1178
10899 | T0147 | Q0297 | 2026-09-18 | 135 | 2026-09 | J1178
10900 | T0147 | Q0297 | 2026-10-16 | 135 | 2026-10 | J1178
10901 | T0148 | Q0298 | 2026-08-01 | 488 | 2026-08 | J1179
10902 | T0148 | Q0298 | 2026-09-01 | 488 | 2026-09 | J1179
10903 | T0148 | Q0298 | 2026-10-01 | 488 | 2026-10 | J1179
10904 | T0149 | Q0299 | 2026-08-01 | 1516.67 | 2026-08 | J1180
10905 | T0149 | Q0299 | 2026-09-01 | 1516.67 | 2026-09 | J1180
10906 | T0149 | Q0299 | 2026-10-01 | 1516.67 | 2026-10 | J1180
10907 | T0150 | Q0300 | 2026-08-01 | 884 | 2026-08 | J1181
10908 | T0150 | Q0300 | 2026-09-01 | 884 | 2026-09 | J1181
10909 | T0150 | Q0300 | 2026-10-01 | 884 | 2026-10 | J1181
10910 | T0151 | Q0301 | 2026-08-01 | 654.33 | 2026-08 | J1182
10911 | T0151 | Q0301 | 2026-09-01 | 654.33 | 2026-09 | J1182
10912 | T0151 | Q0301 | 2026-10-01 | 654.33 | 2026-10 | J1182
10913 | T0152 | Q0302 | 2026-08-01 | 1083.33 | 2026-08 | J1183
10914 | T0152 | Q0302 | 2026-09-01 | 1083.33 | 2026-09 | J1183
10915 | T0152 | Q0302 | 2026-10-01 | 1083.33 | 2026-10 | J1183
10916 | T0153 | Q0303 | 2026-08-01 | 1352 | 2026-08 | J1184
10917 | T0153 | Q0303 | 2026-09-01 | 1352 | 2026-09 | J1184
10918 | T0153 | Q0303 | 2026-10-01 | 1352 | 2026-10 | J1184
10919 | T0154 | Q0304 | 2026-08-01 | 541.67 | 2026-08 | J1186
10920 | T0154 | Q0304 | 2026-09-01 | 541.67 | 2026-09 | J1186
10921 | T0154 | Q0304 | 2026-10-01 | 541.67 | 2026-10 | J1186
10922 | T0155 | Q0305 | 2026-08-01 | 546 | 2026-08 | J1187
10923 | T0155 | Q0305 | 2026-09-01 | 546 | 2026-09 | J1187
10924 | T0155 | Q0305 | 2026-10-01 | 546 | 2026-10 | J1187
10925 | T0156 | Q0306 | 2026-08-01 | 1057.33 | 2026-08 | J1188
10926 | T0156 | Q0306 | 2026-09-01 | 1057.33 | 2026-09 | J1188
10927 | T0156 | Q0306 | 2026-10-01 | 1057.33 | 2026-10 | J1188
10928 | T0157 | Q0306 | 2026-08-01 | 88 | 2026-08 | J1189
10929 | T0157 | Q0306 | 2026-09-01 | 88 | 2026-09 | J1189
10930 | T0157 | Q0306 | 2026-10-01 | 88 | 2026-10 | J1189
10931 | T0158 | Q0308 | 2026-08-01 | 376 | 2026-08 | J1191
10932 | T0158 | Q0308 | 2026-09-01 | 376 | 2026-09 | J1191
10933 | T0158 | Q0308 | 2026-10-01 | 376 | 2026-10 | J1191
10934 | T0159 | Q0309 | 2026-08-01 | 862.33 | 2026-08 | J1192
10935 | T0159 | Q0309 | 2026-09-01 | 862.33 | 2026-09 | J1192
10936 | T0159 | Q0309 | 2026-10-01 | 862.33 | 2026-10 | J1192
10937 | T0160 | Q0310 | 2026-08-01 | 463.67 | 2026-08 | J1193
10938 | T0160 | Q0310 | 2026-09-01 | 463.67 | 2026-09 | J1193
10939 | T0160 | Q0310 | 2026-10-01 | 463.67 | 2026-10 | J1193
10940 | T0161 | Q0311 | 2026-08-01 | 1386.67 | 2026-08 | J1194
10941 | T0161 | Q0311 | 2026-09-01 | 1386.67 | 2026-09 | J1194
10942 | T0161 | Q0311 | 2026-10-01 | 1386.67 | 2026-10 | J1194
10943 | T0162 | Q0312 | 2026-08-01 | 156 | 2026-08 | J1195
10944 | T0162 | Q0312 | 2026-09-01 | 156 | 2026-09 | J1195
10945 | T0162 | Q0312 | 2026-10-01 | 156 | 2026-10 | J1195
10946 | T0163 | Q0312 | 2026-08-01 | 151.67 | 2026-08 | J1195
10947 | T0163 | Q0312 | 2026-09-01 | 151.67 | 2026-09 | J1195
10948 | T0163 | Q0312 | 2026-10-01 | 151.67 | 2026-10 | J1195
10949 | T0164 | Q0313 | 2026-08-01 | 1204.67 | 2026-08 | J1196
10950 | T0164 | Q0313 | 2026-09-01 | 1204.67 | 2026-09 | J1196
10951 | T0164 | Q0313 | 2026-10-01 | 1204.67 | 2026-10 | J1196
10952 | T0165 | Q0313 | 2026-08-19 | 218 | 2026-08 | J1197
10953 | T0165 | Q0313 | 2026-09-16 | 218 | 2026-09 | J1197
10954 | T0165 | Q0313 | 2026-10-14 | 218 | 2026-10 | J1197
10955 | T0166 | Q0314 | 2026-08-01 | 580.67 | 2026-08 | J1198
10956 | T0166 | Q0314 | 2026-09-01 | 580.67 | 2026-09 | J1198
10957 | T0166 | Q0314 | 2026-10-01 | 580.67 | 2026-10 | J1198
10958 | T0167 | Q0315 | 2026-08-01 | 320.67 | 2026-08 | J1199
10959 | T0167 | Q0315 | 2026-09-01 | 320.67 | 2026-09 | J1199
10960 | T0167 | Q0315 | 2026-10-01 | 320.67 | 2026-10 | J1199
10961 | T0168 | Q0316 | 2026-08-01 | 251.33 | 2026-08 | J1200
10962 | T0168 | Q0316 | 2026-09-01 | 251.33 | 2026-09 | J1200
10963 | T0168 | Q0316 | 2026-10-01 | 251.33 | 2026-10 | J1200
10964 | T0169 | Q0317 | 2026-08-01 | 563.33 | 2026-08 | J1201
10965 | T0169 | Q0317 | 2026-09-01 | 563.33 | 2026-09 | J1201
10966 | T0169 | Q0317 | 2026-10-01 | 563.33 | 2026-10 | J1201
10967 | T0170 | Q0317 | 2026-08-27 | 234 | 2026-08 | J1202
10968 | T0170 | Q0317 | 2026-09-24 | 234 | 2026-09 | J1202
10969 | T0170 | Q0317 | 2026-10-22 | 234 | 2026-10 | J1202
10970 | T0171 | Q0318 | 2026-08-01 | 1352 | 2026-08 | J1203
10971 | T0171 | Q0318 | 2026-09-01 | 1352 | 2026-09 | J1203
10972 | T0171 | Q0318 | 2026-10-01 | 1352 | 2026-10 | J1203
10973 | T0172 | Q0320 | 2026-08-01 | 1261 | 2026-08 | J1205
10974 | T0172 | Q0320 | 2026-09-01 | 1261 | 2026-09 | J1205
10975 | T0172 | Q0320 | 2026-10-01 | 1261 | 2026-10 | J1205
10976 | T0173 | Q0321 | 2026-08-24 | 218 | 2026-08 | J1208
10977 | T0173 | Q0321 | 2026-09-21 | 218 | 2026-09 | J1208
10978 | T0173 | Q0321 | 2026-10-19 | 218 | 2026-10 | J1208
10979 | T0174 | Q0322 | 2026-08-01 | 858 | 2026-08 | J1209
10980 | T0174 | Q0322 | 2026-09-01 | 858 | 2026-09 | J1209
10981 | T0174 | Q0322 | 2026-10-01 | 858 | 2026-10 | J1209
10982 | T0175 | Q0323 | 2026-08-01 | 392 | 2026-08 | J1210
10983 | T0175 | Q0323 | 2026-09-01 | 392 | 2026-09 | J1210
10984 | T0175 | Q0323 | 2026-10-01 | 392 | 2026-10 | J1210
10985 | T0176 | Q0323 | 2026-08-28 | 218 | 2026-08 | J1211
10986 | T0176 | Q0323 | 2026-09-25 | 218 | 2026-09 | J1211
10987 | T0176 | Q0323 | 2026-10-23 | 218 | 2026-10 | J1211
10988 | T0177 | Q0324 | 2026-08-01 | 3320 | 2026-08 | J1212
10989 | T0177 | Q0324 | 2026-09-01 | 3320 | 2026-09 | J1212
10990 | T0177 | Q0324 | 2026-10-01 | 3320 | 2026-10 | J1212
10991 | T0178 | Q0326 | 2026-08-01 | 463.67 | 2026-08 | J1214
10992 | T0178 | Q0326 | 2026-09-01 | 463.67 | 2026-09 | J1214
10993 | T0178 | Q0326 | 2026-10-01 | 463.67 | 2026-10 | J1214
10994 | T0179 | Q0327 | 2026-08-01 | 1495 | 2026-08 | J1215
10995 | T0179 | Q0327 | 2026-09-01 | 1495 | 2026-09 | J1215
10996 | T0179 | Q0327 | 2026-10-01 | 1495 | 2026-10 | J1215
10997 | T0180 | Q0328 | 2026-08-01 | 1261 | 2026-08 | J1216
10998 | T0180 | Q0328 | 2026-09-01 | 1261 | 2026-09 | J1216
10999 | T0180 | Q0328 | 2026-10-01 | 1261 | 2026-10 | J1216
11000 | T0181 | Q0329 | 2026-08-01 | 572 | 2026-08 | J1217
11001 | T0181 | Q0329 | 2026-09-01 | 572 | 2026-09 | J1217
11002 | T0181 | Q0329 | 2026-10-01 | 572 | 2026-10 | J1217
11003 | T0182 | Q0330 | 2026-08-01 | 814.67 | 2026-08 | J1218
11004 | T0182 | Q0330 | 2026-09-01 | 814.67 | 2026-09 | J1218
11005 | T0182 | Q0330 | 2026-10-01 | 814.67 | 2026-10 | J1218
11006 | T0183 | Q0331 | 2026-08-01 | 901.33 | 2026-08 | J1219
11007 | T0183 | Q0331 | 2026-09-01 | 901.33 | 2026-09 | J1219
11008 | T0183 | Q0331 | 2026-10-01 | 901.33 | 2026-10 | J1219
11009 | T0184 | Q0332 | 2026-08-01 | 780 | 2026-08 | J1221
11010 | T0184 | Q0332 | 2026-09-01 | 780 | 2026-09 | J1221
11011 | T0184 | Q0332 | 2026-10-01 | 780 | 2026-10 | J1221
11012 | T0185 | Q0333 | 2026-08-01 | 928 | 2026-08 | J1222
11013 | T0185 | Q0333 | 2026-09-01 | 928 | 2026-09 | J1222
11014 | T0185 | Q0333 | 2026-10-01 | 928 | 2026-10 | J1222
11015 | T0186 | Q0333 | 2026-08-21 | 135 | 2026-08 | J1223
11016 | T0186 | Q0333 | 2026-09-18 | 135 | 2026-09 | J1223
11017 | T0186 | Q0333 | 2026-10-16 | 135 | 2026-10 | J1223
11018 | T0187 | Q0335 | 2026-08-01 | 520 | 2026-08 | J1225
11019 | T0187 | Q0335 | 2026-09-01 | 520 | 2026-09 | J1225
11020 | T0187 | Q0335 | 2026-10-01 | 520 | 2026-10 | J1225
11021 | T0188 | Q0336 | 2026-08-01 | 2210 | 2026-08 | J1226
11022 | T0188 | Q0336 | 2026-09-01 | 2210 | 2026-09 | J1226
11023 | T0188 | Q0336 | 2026-10-01 | 2210 | 2026-10 | J1226
11024 | T0189 | Q0337 | 2026-08-01 | 512 | 2026-08 | J1227
11025 | T0189 | Q0337 | 2026-09-01 | 512 | 2026-09 | J1227
11026 | T0189 | Q0337 | 2026-10-01 | 512 | 2026-10 | J1227
11027 | T0190 | Q0337 | 2026-08-12 | 146 | 2026-08 | J1228
11028 | T0190 | Q0337 | 2026-09-09 | 146 | 2026-09 | J1228
11029 | T0190 | Q0337 | 2026-10-07 | 146 | 2026-10 | J1228
11030 | T0191 | Q0338 | 2026-08-01 | 116 | 2026-08 | J1229
11031 | T0191 | Q0338 | 2026-09-01 | 116 | 2026-09 | J1229
11032 | T0191 | Q0338 | 2026-10-01 | 116 | 2026-10 | J1229
11033 | T0192 | Q0339 | 2026-08-01 | 580.67 | 2026-08 | J1230
11034 | T0192 | Q0339 | 2026-09-01 | 580.67 | 2026-09 | J1230
11035 | T0192 | Q0339 | 2026-10-01 | 580.67 | 2026-10 | J1230
11036 | T0193 | Q0339 | 2026-08-12 | 218 | 2026-08 | J1231
11037 | T0193 | Q0339 | 2026-09-09 | 218 | 2026-09 | J1231
11038 | T0193 | Q0339 | 2026-10-07 | 218 | 2026-10 | J1231
11039 | T0194 | Q0340 | 2026-08-01 | 1672.67 | 2026-08 | J1232
11040 | T0194 | Q0340 | 2026-09-01 | 1672.67 | 2026-09 | J1232
11041 | T0194 | Q0340 | 2026-10-01 | 1672.67 | 2026-10 | J1232
11042 | T0195 | Q0341 | 2026-08-01 | 1395.33 | 2026-08 | J1233
11043 | T0195 | Q0341 | 2026-09-01 | 1395.33 | 2026-09 | J1233
11044 | T0195 | Q0341 | 2026-10-01 | 1395.33 | 2026-10 | J1233
11045 | T0196 | Q0342 | 2026-08-01 | 806 | 2026-08 | J1234
11046 | T0196 | Q0342 | 2026-09-01 | 806 | 2026-09 | J1234
11047 | T0196 | Q0342 | 2026-10-01 | 806 | 2026-10 | J1234
11048 | T0197 | Q0343 | 2026-08-01 | 1092 | 2026-08 | J1235
11049 | T0197 | Q0343 | 2026-09-01 | 1092 | 2026-09 | J1235
11050 | T0197 | Q0343 | 2026-10-01 | 1092 | 2026-10 | J1235
11051 | T0198 | Q0344 | 2026-08-01 | 832 | 2026-08 | J1236
11052 | T0198 | Q0344 | 2026-09-01 | 832 | 2026-09 | J1236
11053 | T0198 | Q0344 | 2026-10-01 | 832 | 2026-10 | J1236
11054 | T0199 | Q0345 | 2026-08-01 | 910 | 2026-08 | J1238
11055 | T0199 | Q0345 | 2026-09-01 | 910 | 2026-09 | J1238
11056 | T0199 | Q0345 | 2026-10-01 | 910 | 2026-10 | J1238
11057 | T0200 | Q0346 | 2026-08-01 | 1248 | 2026-08 | J1239
11058 | T0200 | Q0346 | 2026-09-01 | 1248 | 2026-09 | J1239
11059 | T0200 | Q0346 | 2026-10-01 | 1248 | 2026-10 | J1239
11060 | T0201 | Q0347 | 2026-08-17 | 146 | 2026-08 | J1241
11061 | T0201 | Q0347 | 2026-09-14 | 146 | 2026-09 | J1241
11062 | T0201 | Q0347 | 2026-10-12 | 146 | 2026-10 | J1241
11063 | T0202 | Q0347 | 2026-08-01 | 99 | 2026-08 | J1242
11064 | T0202 | Q0347 | 2026-09-01 | 99 | 2026-09 | J1242
11065 | T0202 | Q0347 | 2026-10-01 | 99 | 2026-10 | J1242
11066 | T0203 | Q0348 | 2026-08-01 | 1161.33 | 2026-08 | J1243
11067 | T0203 | Q0348 | 2026-09-01 | 1161.33 | 2026-09 | J1243
11068 | T0203 | Q0348 | 2026-10-01 | 1161.33 | 2026-10 | J1243
11069 | T0204 | Q0350 | 2026-08-01 | 1950 | 2026-08 | J1245
11070 | T0204 | Q0350 | 2026-09-01 | 1950 | 2026-09 | J1245
11071 | T0204 | Q0350 | 2026-10-01 | 1950 | 2026-10 | J1245
11072 | T0205 | Q0353 | 2026-08-01 | 390 | 2026-08 | J1248
11073 | T0205 | Q0353 | 2026-09-01 | 390 | 2026-09 | J1248
11074 | T0205 | Q0353 | 2026-10-01 | 390 | 2026-10 | J1248
11075 | T0206 | Q0353 | 2026-08-20 | 116 | 2026-08 | J1249
11076 | T0206 | Q0353 | 2026-09-17 | 116 | 2026-09 | J1249
11077 | T0206 | Q0353 | 2026-10-15 | 116 | 2026-10 | J1249
11078 | T0207 | Q0354 | 2026-08-01 | 312 | 2026-08 | J1250
11079 | T0207 | Q0354 | 2026-09-01 | 312 | 2026-09 | J1250
11080 | T0207 | Q0354 | 2026-10-01 | 312 | 2026-10 | J1250
11081 | T0208 | Q0355 | 2026-08-01 | 615.33 | 2026-08 | J1251
11082 | T0208 | Q0355 | 2026-09-01 | 615.33 | 2026-09 | J1251
11083 | T0208 | Q0355 | 2026-10-01 | 615.33 | 2026-10 | J1251
11084 | T0209 | Q0357 | 2026-08-01 | 554.67 | 2026-08 | J1254
11085 | T0209 | Q0357 | 2026-09-01 | 554.67 | 2026-09 | J1254
11086 | T0209 | Q0357 | 2026-10-01 | 554.67 | 2026-10 | J1254
11087 | T0210 | Q0358 | 2026-08-01 | 875.33 | 2026-08 | J1255
11088 | T0210 | Q0358 | 2026-09-01 | 875.33 | 2026-09 | J1255
11089 | T0210 | Q0358 | 2026-10-01 | 875.33 | 2026-10 | J1255
11090 | T0211 | Q0359 | 2026-08-01 | 1516.67 | 2026-08 | J1256
11091 | T0211 | Q0359 | 2026-09-01 | 1516.67 | 2026-09 | J1256
11092 | T0211 | Q0359 | 2026-10-01 | 1516.67 | 2026-10 | J1256
11093 | T0212 | Q0361 | 2026-08-01 | 849.33 | 2026-08 | J1258
11094 | T0212 | Q0361 | 2026-09-01 | 849.33 | 2026-09 | J1258
11095 | T0212 | Q0361 | 2026-10-01 | 849.33 | 2026-10 | J1258
11096 | T0213 | Q0361 | 2026-08-24 | 218 | 2026-08 | J1259
11097 | T0213 | Q0361 | 2026-09-21 | 218 | 2026-09 | J1259
11098 | T0213 | Q0361 | 2026-10-19 | 218 | 2026-10 | J1259
11099 | T0214 | Q0363 | 2026-08-01 | 849.33 | 2026-08 | J1262
11100 | T0214 | Q0363 | 2026-09-01 | 849.33 | 2026-09 | J1262
11101 | T0214 | Q0363 | 2026-10-01 | 849.33 | 2026-10 | J1262
11102 | T0215 | Q0364 | 2026-08-01 | 901.33 | 2026-08 | J1263
11103 | T0215 | Q0364 | 2026-09-01 | 901.33 | 2026-09 | J1263
11104 | T0215 | Q0364 | 2026-10-01 | 901.33 | 2026-10 | J1263
11105 | T0216 | Q0365 | 2026-08-01 | 2101.67 | 2026-08 | J1264
11106 | T0216 | Q0365 | 2026-09-01 | 2101.67 | 2026-09 | J1264
11107 | T0216 | Q0365 | 2026-10-01 | 2101.67 | 2026-10 | J1264
11108 | T0217 | Q0367 | 2026-08-01 | 1280 | 2026-08 | J1266
11109 | T0217 | Q0367 | 2026-09-01 | 1280 | 2026-09 | J1266
11110 | T0217 | Q0367 | 2026-10-01 | 1280 | 2026-10 | J1266
11111 | T0218 | Q0367 | 2026-08-21 | 203 | 2026-08 | J1267
11112 | T0218 | Q0367 | 2026-09-18 | 203 | 2026-09 | J1267
11113 | T0218 | Q0367 | 2026-10-16 | 203 | 2026-10 | J1267
11114 | T0219 | Q0368 | 2026-08-11 | 156 | 2026-08 | J1269
11115 | T0219 | Q0368 | 2026-09-08 | 156 | 2026-09 | J1269
11116 | T0219 | Q0368 | 2026-10-06 | 156 | 2026-10 | J1269
11117 | T0220 | Q0369 | 2026-08-01 | 1495 | 2026-08 | J1270
11118 | T0220 | Q0369 | 2026-09-01 | 1495 | 2026-09 | J1270
11119 | T0220 | Q0369 | 2026-10-01 | 1495 | 2026-10 | J1270
11120 | T0221 | Q0371 | 2026-08-01 | 754 | 2026-08 | J1272
11121 | T0221 | Q0371 | 2026-09-01 | 754 | 2026-09 | J1272
11122 | T0221 | Q0371 | 2026-10-01 | 754 | 2026-10 | J1272
11123 | T0222 | Q0371 | 2026-08-06 | 109 | 2026-08 | J1273
11124 | T0222 | Q0371 | 2026-09-03 | 109 | 2026-09 | J1273
11125 | T0222 | Q0371 | 2026-10-01 | 109 | 2026-10 | J1273
11126 | T0222 | Q0371 | 2026-10-29 | 109 | 2026-10 | J1273
11127 | T0223 | Q0372 | 2026-08-01 | 1265.33 | 2026-08 | J1274
11128 | T0223 | Q0372 | 2026-09-01 | 1265.33 | 2026-09 | J1274
11129 | T0223 | Q0372 | 2026-10-01 | 1265.33 | 2026-10 | J1274
11130 | T0224 | Q0374 | 2026-08-01 | 2327 | 2026-08 | J1276
11131 | T0224 | Q0374 | 2026-09-01 | 2327 | 2026-09 | J1276
11132 | T0224 | Q0374 | 2026-10-01 | 2327 | 2026-10 | J1276
11133 | T0225 | Q0375 | 2026-08-01 | 1287 | 2026-08 | J1277
11134 | T0225 | Q0375 | 2026-09-01 | 1287 | 2026-09 | J1277
11135 | T0225 | Q0375 | 2026-10-01 | 1287 | 2026-10 | J1277
11136 | T0226 | Q0378 | 2026-08-01 | 780 | 2026-08 | J1280
11137 | T0226 | Q0378 | 2026-09-01 | 780 | 2026-09 | J1280
11138 | T0226 | Q0378 | 2026-10-01 | 780 | 2026-10 | J1280
11139 | T0227 | Q0378 | 2026-08-01 | 754 | 2026-08 | J1280
11140 | T0227 | Q0378 | 2026-09-01 | 754 | 2026-09 | J1280
11141 | T0227 | Q0378 | 2026-10-01 | 754 | 2026-10 | J1280
11142 | T0228 | Q0379 | 2026-08-01 | 325 | 2026-08 | J1281
11143 | T0228 | Q0379 | 2026-09-01 | 325 | 2026-09 | J1281
11144 | T0228 | Q0379 | 2026-10-01 | 325 | 2026-10 | J1281
11145 | T0229 | Q0379 | 2026-08-25 | 146 | 2026-08 | J1282
11146 | T0229 | Q0379 | 2026-09-22 | 146 | 2026-09 | J1282
11147 | T0229 | Q0379 | 2026-10-20 | 146 | 2026-10 | J1282
11148 | T0230 | Q0380 | 2026-08-01 | 2015 | 2026-08 | J1283
11149 | T0230 | Q0380 | 2026-09-01 | 2015 | 2026-09 | J1283
11150 | T0230 | Q0380 | 2026-10-01 | 2015 | 2026-10 | J1283
11151 | T0231 | Q0380 | 2026-08-07 | 218 | 2026-08 | J1284
11152 | T0231 | Q0380 | 2026-09-04 | 218 | 2026-09 | J1284
11153 | T0231 | Q0380 | 2026-10-02 | 218 | 2026-10 | J1284
11154 | T0231 | Q0380 | 2026-10-30 | 218 | 2026-10 | J1284
11155 | T0232 | Q0382 | 2026-08-01 | 2513.33 | 2026-08 | J1286
11156 | T0232 | Q0382 | 2026-09-01 | 2513.33 | 2026-09 | J1286
11157 | T0232 | Q0382 | 2026-10-01 | 2513.33 | 2026-10 | J1286
11158 | T0233 | Q0383 | 2026-08-01 | 1326 | 2026-08 | J1287
11159 | T0233 | Q0383 | 2026-09-01 | 1326 | 2026-09 | J1287
11160 | T0233 | Q0383 | 2026-10-01 | 1326 | 2026-10 | J1287
11161 | T0234 | Q0384 | 2026-08-01 | 572 | 2026-08 | J1288
11162 | T0234 | Q0384 | 2026-09-01 | 572 | 2026-09 | J1288
11163 | T0234 | Q0384 | 2026-10-01 | 572 | 2026-10 | J1288
11164 | T0235 | Q0384 | 2026-08-01 | 572 | 2026-08 | J1288
11165 | T0235 | Q0384 | 2026-09-01 | 572 | 2026-09 | J1288
11166 | T0235 | Q0384 | 2026-10-01 | 572 | 2026-10 | J1288
11167 | T0236 | Q0385 | 2026-08-10 | 225 | 2026-08 | J1290
11168 | T0236 | Q0385 | 2026-09-07 | 225 | 2026-09 | J1290
11169 | T0236 | Q0385 | 2026-10-05 | 225 | 2026-10 | J1290
11170 | T0237 | Q0385 | 2026-08-01 | 99 | 2026-08 | J1291
11171 | T0237 | Q0385 | 2026-09-01 | 99 | 2026-09 | J1291
11172 | T0237 | Q0385 | 2026-10-01 | 99 | 2026-10 | J1291
11173 | T0238 | Q0386 | 2026-08-01 | 1005.33 | 2026-08 | J1292
11174 | T0238 | Q0386 | 2026-09-01 | 1005.33 | 2026-09 | J1292
11175 | T0238 | Q0386 | 2026-10-01 | 1005.33 | 2026-10 | J1292
11176 | T0239 | Q0386 | 2026-08-20 | 116 | 2026-08 | J1293
11177 | T0239 | Q0386 | 2026-09-17 | 116 | 2026-09 | J1293
11178 | T0239 | Q0386 | 2026-10-15 | 116 | 2026-10 | J1293
11179 | T0240 | Q0387 | 2026-08-01 | 671.67 | 2026-08 | J1294
11180 | T0240 | Q0387 | 2026-09-01 | 671.67 | 2026-09 | J1294
11181 | T0240 | Q0387 | 2026-10-01 | 671.67 | 2026-10 | J1294
11182 | T0241 | Q0387 | 2026-08-01 | 151 | 2026-08 | J1295
11183 | T0241 | Q0387 | 2026-09-01 | 151 | 2026-09 | J1295
11184 | T0241 | Q0387 | 2026-10-01 | 151 | 2026-10 | J1295
11185 | T0242 | Q0388 | 2026-08-01 | 303.33 | 2026-08 | J1296
11186 | T0242 | Q0388 | 2026-09-01 | 303.33 | 2026-09 | J1296
11187 | T0242 | Q0388 | 2026-10-01 | 303.33 | 2026-10 | J1296
11188 | T0243 | Q0390 | 2026-08-01 | 810.33 | 2026-08 | J1298
11189 | T0243 | Q0390 | 2026-09-01 | 810.33 | 2026-09 | J1298
11190 | T0243 | Q0390 | 2026-10-01 | 810.33 | 2026-10 | J1298
11191 | T0244 | Q0392 | 2026-08-01 | 923 | 2026-08 | J1300
11192 | T0244 | Q0392 | 2026-09-01 | 923 | 2026-09 | J1300
11193 | T0244 | Q0392 | 2026-10-01 | 923 | 2026-10 | J1300
11194 | T0245 | Q0395 | 2026-08-11 | 135 | 2026-08 | J1304
11195 | T0245 | Q0395 | 2026-09-08 | 135 | 2026-09 | J1304
11196 | T0245 | Q0395 | 2026-10-06 | 135 | 2026-10 | J1304
11197 | T0246 | Q0396 | 2026-08-01 | 2015 | 2026-08 | J1305
11198 | T0246 | Q0396 | 2026-09-01 | 2015 | 2026-09 | J1305
11199 | T0246 | Q0396 | 2026-10-01 | 2015 | 2026-10 | J1305
11200 | T0247 | Q0396 | 2026-08-06 | 146 | 2026-08 | J1306
11201 | T0247 | Q0396 | 2026-09-03 | 146 | 2026-09 | J1306
11202 | T0247 | Q0396 | 2026-10-01 | 146 | 2026-10 | J1306
11203 | T0247 | Q0396 | 2026-10-29 | 146 | 2026-10 | J1306
11204 | T0248 | Q0396 | 2026-08-01 | 88 | 2026-08 | J1307
11205 | T0248 | Q0396 | 2026-09-01 | 88 | 2026-09 | J1307
11206 | T0248 | Q0396 | 2026-10-01 | 88 | 2026-10 | J1307
11207 | T0249 | Q0397 | 2026-08-03 | 146 | 2026-08 | J1309
11208 | T0249 | Q0397 | 2026-08-31 | 146 | 2026-08 | J1309
11209 | T0249 | Q0397 | 2026-09-28 | 146 | 2026-09 | J1309
11210 | T0249 | Q0397 | 2026-10-26 | 146 | 2026-10 | J1309
11211 | T0250 | Q0397 | 2026-08-03 | 146 | 2026-08 | J1309
11212 | T0250 | Q0397 | 2026-08-31 | 146 | 2026-08 | J1309
11213 | T0250 | Q0397 | 2026-09-28 | 146 | 2026-09 | J1309
11214 | T0250 | Q0397 | 2026-10-26 | 146 | 2026-10 | J1309
11215 | T0251 | Q0397 | 2026-08-01 | 99 | 2026-08 | J1310
11216 | T0251 | Q0397 | 2026-09-01 | 99 | 2026-09 | J1310
11217 | T0251 | Q0397 | 2026-10-01 | 99 | 2026-10 | J1310
11218 | T0252 | Q0398 | 2026-08-01 | 294.67 | 2026-08 | J1311
11219 | T0252 | Q0398 | 2026-09-01 | 294.67 | 2026-09 | J1311
11220 | T0252 | Q0398 | 2026-10-01 | 294.67 | 2026-10 | J1311
11221 | T0253 | Q0399 | 2026-08-01 | 589.33 | 2026-08 | J1312
11222 | T0253 | Q0399 | 2026-09-01 | 589.33 | 2026-09 | J1312
11223 | T0253 | Q0399 | 2026-10-01 | 589.33 | 2026-10 | J1312
11224 | T0254 | Q0401 | 2026-08-01 | 364 | 2026-08 | J1314
11225 | T0254 | Q0401 | 2026-09-01 | 364 | 2026-09 | J1314
11226 | T0254 | Q0401 | 2026-10-01 | 364 | 2026-10 | J1314
11227 | T0255 | Q0402 | 2026-08-01 | 151 | 2026-08 | J1316
11228 | T0255 | Q0402 | 2026-09-01 | 151 | 2026-09 | J1316
11229 | T0255 | Q0402 | 2026-10-01 | 151 | 2026-10 | J1316
11230 | T0256 | Q0403 | 2026-08-01 | 1048.67 | 2026-08 | J1317
11231 | T0256 | Q0403 | 2026-09-01 | 1048.67 | 2026-09 | J1317
11232 | T0256 | Q0403 | 2026-10-01 | 1048.67 | 2026-10 | J1317
11233 | T0257 | Q0403 | 2026-08-18 | 218 | 2026-08 | J1318
11234 | T0257 | Q0403 | 2026-09-15 | 218 | 2026-09 | J1318
11235 | T0257 | Q0403 | 2026-10-13 | 218 | 2026-10 | J1318
11236 | T0258 | Q0405 | 2026-08-01 | 719.33 | 2026-08 | J1320
11237 | T0258 | Q0405 | 2026-09-01 | 719.33 | 2026-09 | J1320
11238 | T0258 | Q0405 | 2026-10-01 | 719.33 | 2026-10 | J1320
11239 | T0259 | Q0405 | 2026-08-18 | 203 | 2026-08 | J1321
11240 | T0259 | Q0405 | 2026-09-15 | 203 | 2026-09 | J1321
11241 | T0259 | Q0405 | 2026-10-13 | 203 | 2026-10 | J1321
11242 | T0260 | Q0406 | 2026-08-01 | 671.67 | 2026-08 | J1322
11243 | T0260 | Q0406 | 2026-09-01 | 671.67 | 2026-09 | J1322
11244 | T0260 | Q0406 | 2026-10-01 | 671.67 | 2026-10 | J1322
11245 | T0261 | Q0407 | 2026-08-01 | 754 | 2026-08 | J1323
11246 | T0261 | Q0407 | 2026-09-01 | 754 | 2026-09 | J1323
11247 | T0261 | Q0407 | 2026-10-01 | 754 | 2026-10 | J1323
11248 | T0262 | Q0408 | 2026-08-01 | 437.67 | 2026-08 | J1324
11249 | T0262 | Q0408 | 2026-09-01 | 437.67 | 2026-09 | J1324
11250 | T0262 | Q0408 | 2026-10-01 | 437.67 | 2026-10 | J1324
11251 | T0263 | Q0409 | 2026-08-01 | 1672.67 | 2026-08 | J1325
11252 | T0263 | Q0409 | 2026-09-01 | 1672.67 | 2026-09 | J1325
11253 | T0263 | Q0409 | 2026-10-01 | 1672.67 | 2026-10 | J1325
11254 | T0264 | Q0410 | 2026-08-01 | 2621.67 | 2026-08 | J1326
11255 | T0264 | Q0410 | 2026-09-01 | 2621.67 | 2026-09 | J1326
11256 | T0264 | Q0410 | 2026-10-01 | 2621.67 | 2026-10 | J1326
11257 | T0265 | Q0412 | 2026-08-01 | 416 | 2026-08 | J1328
11258 | T0265 | Q0412 | 2026-09-01 | 416 | 2026-09 | J1328
11259 | T0265 | Q0412 | 2026-10-01 | 416 | 2026-10 | J1328
11260 | T0266 | Q0412 | 2026-08-06 | 112 | 2026-08 | J1329
11261 | T0266 | Q0412 | 2026-09-03 | 112 | 2026-09 | J1329
11262 | T0266 | Q0412 | 2026-10-01 | 112 | 2026-10 | J1329
11263 | T0266 | Q0412 | 2026-10-29 | 112 | 2026-10 | J1329
11264 | T0267 | Q0413 | 2026-08-01 | 1212 | 2026-08 | J1330
11265 | T0267 | Q0413 | 2026-09-01 | 1212 | 2026-09 | J1330
11266 | T0267 | Q0413 | 2026-10-01 | 1212 | 2026-10 | J1330
11267 | T0268 | Q0413 | 2026-08-01 | 151 | 2026-08 | J1331
11268 | T0268 | Q0413 | 2026-09-01 | 151 | 2026-09 | J1331
11269 | T0268 | Q0413 | 2026-10-01 | 151 | 2026-10 | J1331
11270 | T0269 | Q0414 | 2026-08-01 | 1391 | 2026-08 | J1332
11271 | T0269 | Q0414 | 2026-09-01 | 1391 | 2026-09 | J1332
11272 | T0269 | Q0414 | 2026-10-01 | 1391 | 2026-10 | J1332
11273 | T0270 | Q0415 | 2026-08-01 | 598 | 2026-08 | J1333
11274 | T0270 | Q0415 | 2026-09-01 | 598 | 2026-09 | J1333
11275 | T0270 | Q0415 | 2026-10-01 | 598 | 2026-10 | J1333
11276 | T0271 | Q0416 | 2026-08-01 | 1664 | 2026-08 | J1334
11277 | T0271 | Q0416 | 2026-09-01 | 1664 | 2026-09 | J1334
11278 | T0271 | Q0416 | 2026-10-01 | 1664 | 2026-10 | J1334
11279 | T0272 | Q0417 | 2026-08-01 | 567.67 | 2026-08 | J1335
11280 | T0272 | Q0417 | 2026-09-01 | 567.67 | 2026-09 | J1335
11281 | T0272 | Q0417 | 2026-10-01 | 567.67 | 2026-10 | J1335
11282 | T0273 | Q0417 | 2026-08-06 | 203 | 2026-08 | J1336
11283 | T0273 | Q0417 | 2026-09-03 | 203 | 2026-09 | J1336
11284 | T0273 | Q0417 | 2026-10-01 | 203 | 2026-10 | J1336
11285 | T0273 | Q0417 | 2026-10-29 | 203 | 2026-10 | J1336
11286 | T0274 | Q0418 | 2026-08-01 | 801.67 | 2026-08 | J1337
11287 | T0274 | Q0418 | 2026-09-01 | 801.67 | 2026-09 | J1337
11288 | T0274 | Q0418 | 2026-10-01 | 801.67 | 2026-10 | J1337
11289 | T0275 | Q0419 | 2026-08-01 | 429 | 2026-08 | J1338
11290 | T0275 | Q0419 | 2026-09-01 | 429 | 2026-09 | J1338
11291 | T0275 | Q0419 | 2026-10-01 | 429 | 2026-10 | J1338
11292 | T0276 | Q0420 | 2026-08-01 | 546 | 2026-08 | J1339
11293 | T0276 | Q0420 | 2026-09-01 | 546 | 2026-09 | J1339
11294 | T0276 | Q0420 | 2026-10-01 | 546 | 2026-10 | J1339
11295 | T0277 | Q0373 | 2026-08-01 | 377 | 2026-08 | J1340
11296 | T0277 | Q0373 | 2026-09-01 | 377 | 2026-09 | J1340
11297 | T0277 | Q0373 | 2026-10-01 | 377 | 2026-10 | J1340
11298 | T0278 | Q0316 | 2026-08-01 | 264.33 | 2026-08 | J1341
11299 | T0278 | Q0316 | 2026-09-01 | 264.33 | 2026-09 | J1341
11300 | T0278 | Q0316 | 2026-10-01 | 264.33 | 2026-10 | J1341
11301 | T0279 | Q0288 | 2026-08-01 | 771.33 | 2026-08 | J1342
11302 | T0279 | Q0288 | 2026-09-01 | 771.33 | 2026-09 | J1342
11303 | T0279 | Q0288 | 2026-10-01 | 771.33 | 2026-10 | J1342
11304 | T0280 | Q0342 | 2026-08-01 | 1040 | 2026-08 | J1343
11305 | T0280 | Q0342 | 2026-09-01 | 1040 | 2026-09 | J1343
11306 | T0280 | Q0342 | 2026-10-01 | 1040 | 2026-10 | J1343
11307 | T0281 | Q0169 | 2026-08-01 | 546 | 2026-08 | J1344
11308 | T0281 | Q0169 | 2026-09-01 | 546 | 2026-09 | J1344
11309 | T0281 | Q0169 | 2026-10-01 | 546 | 2026-10 | J1344
11310 | T0282 | Q0336 | 2026-08-01 | 823.33 | 2026-08 | J1345
11311 | T0282 | Q0336 | 2026-09-01 | 823.33 | 2026-09 | J1345
11312 | T0282 | Q0336 | 2026-10-01 | 823.33 | 2026-10 | J1345
11313 | T0283 | Q0311 | 2026-08-01 | 1274 | 2026-08 | J1346
11314 | T0283 | Q0311 | 2026-09-01 | 1274 | 2026-09 | J1346
11315 | T0283 | Q0311 | 2026-10-01 | 1274 | 2026-10 | J1346
11316 | T0284 | Q0182 | 2026-08-01 | 65 | 2026-08 | T0284
11317 | T0284 | Q0182 | 2026-09-01 | 65 | 2026-09 | T0284
11318 | T0284 | Q0182 | 2026-10-01 | 65 | 2026-10 | T0284
11319 | T0285 | Q0409 | 2026-08-01 | 65 | 2026-08 | T0285
11320 | T0285 | Q0409 | 2026-09-01 | 65 | 2026-09 | T0285
11321 | T0285 | Q0409 | 2026-10-01 | 65 | 2026-10 | T0285
11322 | T0286 | Q0358 | 2026-08-01 | 80 | 2026-08 | T0286
11323 | T0286 | Q0358 | 2026-09-01 | 80 | 2026-09 | T0286
11324 | T0286 | Q0358 | 2026-10-01 | 80 | 2026-10 | T0286
11325 | T0287 | Q0328 | 2026-08-01 | 80 | 2026-08 | T0287
11326 | T0287 | Q0328 | 2026-09-01 | 80 | 2026-09 | T0287
11327 | T0287 | Q0328 | 2026-10-01 | 80 | 2026-10 | T0287
11328 | T0288 | Q0285 | 2026-08-01 | 65 | 2026-08 | T0288
11329 | T0288 | Q0285 | 2026-09-01 | 65 | 2026-09 | T0288
11330 | T0288 | Q0285 | 2026-10-01 | 65 | 2026-10 | T0288
11331 | T0289 | Q0228 | 2026-08-01 | 110 | 2026-08 | T0289
11332 | T0289 | Q0228 | 2026-09-01 | 110 | 2026-09 | T0289
11333 | T0289 | Q0228 | 2026-10-01 | 110 | 2026-10 | T0289

## Customer Match
QBO parent customers matched to Jobber clients
Work sample: realistic data, built to show how I approach this work.
QBO ID | QBO name | Email | Client ID | Jobber client | Rule | Action | Client exists | Sub-customers
Q0001 | The Oakwood Vet Clinic | accounts@oakwoodvetclinic.example | JC0001 | Oakwood Vet Clinic | N1 same name | Keep | 1 | 2
Q0002 | The Clearwater Dental Pty Ltd | accounts@clearwaterdental.example | JC0002 | Clearwater Dental Pty Ltd | N1 same name | Keep | 1 | 1
Q0003 | Riverside Insurance Brokers Pty Ltd | accounts@riversideinsuran.example | JC0003 | Riverside Insurance Brokers Pty Ltd | N1 same name | Keep | 1 | 1
Q0004 | Ironbark Pathology Pty Ltd | accounts@ironbarkpatholog.example | JC0004 | Ironbark Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0005 | WESTEND FITNESS PTY LTD | accounts@westendfitness.example | JC0005 | Westend Fitness Pty Ltd | N1 same name | Keep | 1 | 1
Q0006 | Redgum Dental | accounts@redgumdental.example | JC0006 | Redgum Dental | N1 same name | Keep | 1 | 2
Q0007 | Elm Street Physiotherapy | accounts@elmstreetphysiot.example | JC0007 | Elm Street Physiotherapy | N1 same name | Keep | 1 | 2
Q0008 | Wattle Grove Property Group | accounts@wattlegroveprope.example | JC0008 | Wattle Grove Property Group | N1 same name | Keep | 1 | 1
Q0009 | Hillcrest Physiotherapy P/L | accounts@hillcrestphysiot.example | JC0009 | Hillcrest Physiotherapy Pty Ltd | N1 same name | Keep | 1 | 2
Q0010 | The Kingsley Real Estate | accounts@kingsleyrealesta.example | JC0010 | Kingsley Real Estate | N1 same name | Keep | 1 | 2
Q0011 | Wattle Grove Medical Centre P/L | accounts@wattlegrovemedic.example | JC0011 | Wattle Grove Medical Centre Pty Ltd | N1 same name | Keep | 1 | 1
Q0012 | BLUESTONE ENGINEERING | accounts@bluestoneenginee.example | JC0012 | Bluestone Engineering | N1 same name | Keep | 1 | 1
Q0013 | CLEARWATER INSURANCE BROKERS PTY LTD | accounts@clearwaterinsura.example | JC0013 | Clearwater Insurance Brokers Pty Ltd | N1 same name | Keep | 1 | 1
Q0014 | REDGUM OPTOMETRISTS PTY LTD | accounts@redgumoptometris.example | JC0014 | Redgum Optometrists Pty Ltd | N1 same name | Keep | 1 | 1
Q0015 | Northside Accountants | accounts@northsideaccount.example | JC0015 | Northside Accountants Pty Ltd | N1 same name | Keep | 1 | 3
Q0016 | Oakwood Accountants Pty Ltd | accounts@oakwoodaccountan.example | JC0016 | Oakwood Accountants Pty Ltd | N1 same name | Keep | 1 | 1
Q0017 | Northside Engineering Pty Ltd | accounts@northsideenginee.example | JC0017 | Northside Engineering Pty Ltd | N1 same name | Keep | 1 | 2
Q0018 | Ashwood Early Learning | accounts@ashwoodearlylear.example | JC0018 | Ashwood Early Learning | N1 same name | Keep | 1 | 1
Q0019 | SILVERTON PHARMACY | accounts@silvertonpharmac.example | JC0019 | Silverton Pharmacy | N1 same name | Keep | 1 | 4
Q0020 | Brightside Podiatry | accounts@brightsidepodiat.example | JC0020 | Brightside Podiatry | N1 same name | Keep | 1 | 1
Q0021 | Ashwood Optometrists | accounts@ashwoodoptometri.example | JC0021 | Ashwood Optometrists | N1 same name | Keep | 1 | 2
Q0022 | Parkside Accountants Pty Ltd | accounts@parksideaccounta.example | JC0022 | Parkside Accountants | N1 same name | Keep | 1 | 2
Q0023 | Brightside Motors P/L | accounts@brightsidemotors.example | JC0023 | Brightside Motors Pty Ltd | N1 same name | Keep | 1 | 1
Q0024 | Westend Motors Pty Ltd | accounts@westendmotors.example | JC0024 | Westend Motors Pty Ltd | N1 same name | Keep | 1 | 3
Q0025 | OAKWOOD LAWYERS PTY LTD | accounts@oakwoodlawyers.example | JC0025 | Oakwood Lawyers Pty Ltd | N1 same name | Keep | 1 | 2
Q0026 | Riverside Medical Centre | accounts@riversidemedical.example | JC0026 | Riverside Medical Centre | N1 same name | Keep | 1 | 1
Q0027 | Riverside Motors | accounts@riversidemotors.example | JC0027 | Riverside Motors Pty Ltd | N1 same name | Keep | 1 | 1
Q0028 | The Parkside Pathology Pty Ltd | accounts@parksidepatholog.example | JC0028 | Parkside Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0029 | The Sunbury Accountants Pty Ltd | accounts@sunburyaccountan.example | JC0029 | Sunbury Accountants Pty Ltd | N1 same name | Keep | 1 | 1
Q0030 | Sunbury Early Learning | accounts@sunburyearlylear.example | JC0030 | Sunbury Early Learning | N1 same name | Keep | 1 | 1
Q0031 | The Silverton Lawyers Pty Ltd | accounts@silvertonlawyers.example | JC0031 | Silverton Lawyers Pty Ltd | N1 same name | Keep | 1 | 1
Q0032 | Waverley Accountants Pty Ltd | accounts@waverleyaccounta.example | JC0032 | Waverley Accountants Pty Ltd | N1 same name | Keep | 1 | 1
Q0033 | The Westend Podiatry | accounts@westendpodiatry.example | JC0033 | Westend Podiatry | N1 same name | Keep | 1 | 0
Q0034 | LAKESIDE ENGINEERING PTY LTD | accounts@lakesideengineer.example | JC0034 | Lakeside Engineering Pty Ltd | N1 same name | Keep | 1 | 2
Q0035 | Kingsley Financial Planning | accounts@kingsleyfinancia.example | JC0035 | Kingsley Financial Planning | N1 same name | Keep | 1 | 1
Q0036 | The Wattle Grove Physiotherapy | accounts@wattlegrovephysi.example | JC0036 | Wattle Grove Physiotherapy | N1 same name | Keep | 1 | 1
Q0037 | Elm Street Fitness | accounts@elmstreetfitness.example | JC0037 | Elm Street Fitness Pty Ltd | N1 same name | Keep | 1 | 2
Q0038 | Wattle Grove Dental Pty Ltd | accounts@wattlegrovedenta.example | JC0038 | Wattle Grove Dental | N1 same name | Keep | 1 | 1
Q0039 | The Lakeside Vet Clinic | accounts@lakesidevetclini.example | JC0039 | Lakeside Vet Clinic | N1 same name | Keep | 1 | 2
Q0040 | Clearwater Property Group | accounts@clearwaterproper.example | JC0040 | Clearwater Property Group Pty Ltd | N1 same name | Keep | 1 | 2
Q0041 | Eastwood Real Estate Pty Ltd | accounts@eastwoodrealesta.example | JC0041 | Eastwood Real Estate Pty Ltd | N1 same name | Keep | 1 | 1
Q0042 | Clearwater Physiotherapy | accounts@clearwaterphysio.example | JC0042 | Clearwater Physiotherapy | N1 same name | Keep | 1 | 2
Q0043 | Greenway Physiotherapy | accounts@greenwayphysioth.example | JC0043 | Greenway Physiotherapy | N1 same name | Keep | 1 | 1
Q0044 | Fairfield Engineering Pty Ltd | accounts@fairfieldenginee.example | JC0044 | Fairfield Engineering Pty Ltd | N1 same name | Keep | 1 | 1
Q0045 | Westend Optometrists P/L | accounts@westendoptometri.example | JC0045 | Westend Optometrists Pty Ltd | N1 same name | Keep | 1 | 1
Q0046 | Kingsley Insurance Brokers Pty Ltd | accounts@kingsleyinsuranc.example | JC0046 | Kingsley Insurance Brokers | N1 same name | Keep | 1 | 2
Q0047 | Bluestone Learning Centre Pty Ltd | accounts@bluestonelearnin.example | JC0047 | Bluestone Learning Centre Pty Ltd | N1 same name | Keep | 1 | 1
Q0048 | Oakwood Logistics | accounts@oakwoodlogistics.example | JC0048 | Oakwood Logistics | N1 same name | Keep | 1 | 4
Q0049 | Banksia Insurance Brokers | accounts@banksiainsurance.example | JC0049 | Banksia Insurance Brokers | N1 same name | Keep | 1 | 1
Q0050 | The Sunbury Lawyers Pty Ltd | accounts@sunburylawyers.example | JC0050 | Sunbury Lawyers Pty Ltd | N1 same name | Keep | 1 | 3
Q0051 | COBBLESTONE REAL ESTATE PTY LTD | accounts@cobblestonereale.example | JC0051 | Cobblestone Real Estate Pty Ltd | N1 same name | Keep | 1 | 1
Q0052 | Bayview Engineering Pty Ltd | accounts@bayviewengineeri.example | JC0052 | Bayview Engineering Pty Ltd | N1 same name | Keep | 1 | 1
Q0053 | The Oakwood Financial Planning Pty Ltd | accounts@oakwoodfinancial.example | JC0053 | Oakwood Financial Planning Pty Ltd | N1 same name | Keep | 1 | 1
Q0054 | The Brightside Dental Pty Ltd | accounts@brightsidedental.example | JC0054 | Brightside Dental Pty Ltd | N1 same name | Keep | 1 | 2
Q0055 | Ashwood Physiotherapy | accounts@ashwoodphysiothe.example | JC0055 | Ashwood Physiotherapy | N1 same name | Keep | 1 | 4
Q0056 | The Bluestone Dental | accounts@bluestonedental.example | JC0056 | Bluestone Dental | N1 same name | Keep | 1 | 4
Q0057 | The Kingsley Accountants | accounts@kingsleyaccounta.example | JC0057 | Kingsley Accountants | N1 same name | Keep | 1 | 1
Q0058 | CLEARWATER EARLY LEARNING PTY LTD | accounts@clearwaterearlyl.example | JC0058 | Clearwater Early Learning Pty Ltd | N1 same name | Keep | 1 | 1
Q0059 | Banksia Pathology | accounts@banksiapathology.example | JC0059 | Banksia Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0060 | SOUTHGATE FINANCIAL PLANNING PTY LTD | accounts@southgatefinanci.example | JC0060 | Southgate Financial Planning Pty Ltd | N1 same name | Keep | 1 | 2
Q0061 | BLUESTONE LAWYERS PTY LTD | accounts@bluestonelawyers.example | JC0061 | Bluestone Lawyers Pty Ltd | N1 same name | Keep | 1 | 1
Q0062 | Riverside Lawyers Pty Ltd | accounts@riversidelawyers.example | JC0062 | Riverside Lawyers Pty Ltd | N1 same name | Keep | 1 | 1
Q0063 | Banksia Accountants | accounts@banksiaaccountan.example | JC0063 | Banksia Accountants | N1 same name | Keep | 1 | 3
Q0064 | Ironbark Physiotherapy | accounts@ironbarkphysioth.example | JC0064 | Ironbark Physiotherapy Pty Ltd | N1 same name | Keep | 1 | 2
Q0065 | Wattle Grove Lawyers | accounts@wattlegrovelawye.example | JC0065 | Wattle Grove Lawyers Pty Ltd | N1 same name | Keep | 1 | 1
Q0066 | Kingsley Medical Centre Pty Ltd | accounts@kingsleymedicalc.example | JC0066 | Kingsley Medical Centre Pty Ltd | N1 same name | Keep | 1 | 2
Q0067 | The Ashwood Engineering | accounts@ashwoodengineeri.example | JC0067 | Ashwood Engineering | N1 same name | Keep | 1 | 1
Q0068 | Sunbury Physiotherapy Pty Ltd | accounts@sunburyphysiothe.example | JC0068 | Sunbury Physiotherapy Pty Ltd | N1 same name | Keep | 1 | 3
Q0069 | Eastwood Pathology | accounts@eastwoodpatholog.example | JC0069 | Eastwood Pathology | N1 same name | Keep | 1 | 1
Q0070 | Waverley Fitness | accounts@waverleyfitness.example | JC0070 | Waverley Fitness Pty Ltd | N1 same name | Keep | 1 | 2
Q0071 | Clearwater Logistics | accounts@clearwaterlogist.example | JC0071 | Clearwater Logistics | N1 same name | Keep | 1 | 1
Q0072 | Wattle Grove Fitness | accounts@wattlegrovefitne.example | JC0072 | Wattle Grove Fitness | N1 same name | Keep | 1 | 2
Q0073 | Ashwood Medical Centre | accounts@ashwoodmedicalce.example | JC0073 | Ashwood Medical Centre | N1 same name | Keep | 1 | 0
Q0074 | Parkside Vet Clinic | accounts@parksidevetclini.example | JC0074 | Parkside Vet Clinic | N1 same name | Keep | 1 | 1
Q0075 | Wattle Grove Architects | accounts@wattlegrovearchi.example | JC0075 | Wattle Grove Architects | N1 same name | Keep | 1 | 1
Q0076 | Bayview Pharmacy Pty Ltd | accounts@bayviewpharmacy.example | JC0076 | Bayview Pharmacy Pty Ltd | N1 same name | Keep | 1 | 1
Q0077 | Hillcrest Accountants Pty Ltd | accounts@hillcrestaccount.example | JC0077 | Hillcrest Accountants | N1 same name | Keep | 1 | 0
Q0078 | Lakeside Architects | accounts@lakesidearchitec.example | JC0078 | Lakeside Architects | N1 same name | Keep | 1 | 2
Q0079 | Ashwood Accountants | accounts@ashwoodaccountan.example | JC0079 | Ashwood Accountants | N1 same name | Keep | 1 | 1
Q0080 | Westend Property Group Pty Ltd | accounts@westendpropertyg.example | JC0080 | Westend Property Group | N1 same name | Keep | 1 | 1
Q0081 | Eastwood Optometrists | accounts@eastwoodoptometr.example | JC0081 | Eastwood Optometrists | N1 same name | Keep | 1 | 2
Q0082 | The Westend Medical Centre | accounts@westendmedicalce.example | JC0082 | Westend Medical Centre | N1 same name | Keep | 1 | 1
Q0083 | Riverside Learning Centre | accounts@riversidelearnin.example | JC0083 | Riverside Learning Centre | N1 same name | Keep | 1 | 3
Q0084 | Silverton Insurance Brokers P/L | accounts@silvertoninsuran.example | JC0084 | Silverton Insurance Brokers Pty Ltd | N1 same name | Keep | 1 | 3
Q0085 | Greenway Podiatry P/L | accounts@greenwaypodiatry.example | JC0085 | Greenway Podiatry Pty Ltd | N1 same name | Keep | 1 | 1
Q0086 | Banksia Logistics Pty Ltd | accounts@banksialogistics.example | JC0086 | Banksia Logistics | N1 same name | Keep | 1 | 3
Q0087 | Sunbury Architects P/L | accounts@sunburyarchitect.example | JC0087 | Sunbury Architects Pty Ltd | N1 same name | Keep | 1 | 1
Q0088 | Cobblestone Physiotherapy P/L | accounts@cobblestonephysi.example | JC0088 | Cobblestone Physiotherapy Pty Ltd | N1 same name | Keep | 1 | 1
Q0089 | Banksia Real Estate | accounts@banksiarealestat.example | JC0089 | Banksia Real Estate | N1 same name | Keep | 1 | 1
Q0090 | The Northside Pathology Pty Ltd | accounts@northsidepatholo.example | JC0090 | Northside Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0091 | Harbourside Lawyers | accounts@harboursidelawye.example | JC0091 | Harbourside Lawyers | N1 same name | Keep | 1 | 1
Q0092 | Kingsley Fitness Pty Ltd | accounts@kingsleyfitness.example | JC0092 | Kingsley Fitness Pty Ltd | N1 same name | Keep | 1 | 0
Q0093 | LAKESIDE OPTOMETRISTS | accounts@lakesideoptometr.example | JC0093 | Lakeside Optometrists | N1 same name | Keep | 1 | 1
Q0094 | Southgate Dental Pty Ltd | accounts@southgatedental.example | JC0094 | Southgate Dental | N1 same name | Keep | 1 | 1
Q0095 | SUNBURY OPTOMETRISTS | accounts@sunburyoptometri.example | JC0095 | Sunbury Optometrists | N1 same name | Keep | 1 | 1
Q0096 | Bayview Vet Clinic | accounts@bayviewvetclinic.example | JC0096 | Bayview Vet Clinic | N1 same name | Keep | 1 | 2
Q0097 | The Redgum Pathology Pty Ltd | accounts@redgumpathology.example | JC0097 | Redgum Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0098 | Greenway Medical Centre Pty Ltd | accounts@greenwaymedicalc.example | JC0098 | Greenway Medical Centre Pty Ltd | N1 same name | Keep | 1 | 1
Q0099 | Westend Physiotherapy Pty Ltd | accounts@westendphysiothe.example | JC0099 | Westend Physiotherapy | N1 same name | Keep | 1 | 1
Q0100 | Riverside Podiatry Pty Ltd | accounts@riversidepodiatr.example | JC0100 | Riverside Podiatry | N1 same name | Keep | 1 | 2
Q0101 | The Northside Learning Centre | accounts@northsidelearnin.example | JC0101 | Northside Learning Centre | N1 same name | Keep | 1 | 1
Q0102 | The Harbourside Logistics Pty Ltd | accounts@harboursidelogis.example | JC0102 | Harbourside Logistics Pty Ltd | N1 same name | Keep | 1 | 2
Q0103 | Redgum Podiatry | accounts@redgumpodiatry.example | JC0103 | Redgum Podiatry | N1 same name | Keep | 1 | 2
Q0104 | Harbourside Chiropractic | accounts@harboursidechiro.example | JC0104 | Harbourside Chiropractic | N1 same name | Keep | 1 | 1
Q0105 | Hillcrest Lawyers | accounts@hillcrestlawyers.example | JC0105 | Hillcrest Lawyers | N1 same name | Keep | 1 | 2
Q0106 | Silverton Logistics Pty Ltd | accounts@silvertonlogisti.example | JC0106 | Silverton Logistics Pty Ltd | N1 same name | Keep | 1 | 2
Q0107 | The Hillcrest Motors Pty Ltd | accounts@hillcrestmotors.example | JC0107 | Hillcrest Motors Pty Ltd | N1 same name | Keep | 1 | 1
Q0108 | Southgate Pathology Pty Ltd | accounts@southgatepatholo.example | JC0108 | Southgate Pathology | N1 same name | Keep | 1 | 3
Q0109 | Westend Engineering | accounts@westendengineeri.example | JC0109 | Westend Engineering | N1 same name | Keep | 1 | 2
Q0110 | Lakeside Real Estate | accounts@lakesiderealesta.example | JC0110 | Lakeside Real Estate Pty Ltd | N1 same name | Keep | 1 | 3
Q0111 | Harbourside Pharmacy Pty Ltd | accounts@harboursidepharm.example | JC0111 | Harbourside Pharmacy Pty Ltd | N1 same name | Keep | 1 | 2
Q0112 | Brightside Early Learning | accounts@brightsideearlyl.example | JC0112 | Brightside Early Learning Pty Ltd | N1 same name | Keep | 1 | 1
Q0113 | Southgate Engineering | accounts@southgateenginee.example | JC0113 | Southgate Engineering | N1 same name | Keep | 1 | 1
Q0114 | Riverside Dental Pty Ltd | accounts@riversidedental.example | JC0114 | Riverside Dental Pty Ltd | N1 same name | Keep | 1 | 1
Q0115 | Bayview Early Learning Pty Ltd | accounts@bayviewearlylear.example | JC0115 | Bayview Early Learning | N1 same name | Keep | 1 | 2
Q0116 | Elm Street Financial Planning Pty Ltd | accounts@elmstreetfinanci.example | JC0116 | Elm Street Financial Planning Pty Ltd | N1 same name | Keep | 1 | 1
Q0117 | Ashwood Property Group | accounts@ashwoodpropertyg.example | JC0117 | Ashwood Property Group | N1 same name | Keep | 1 | 1
Q0118 | The Northside Early Learning Pty Ltd | accounts@northsideearlyle.example | JC0118 | Northside Early Learning Pty Ltd | N1 same name | Keep | 1 | 1
Q0119 | Brightside Logistics Pty Ltd | accounts@brightsidelogist.example | JC0119 | Brightside Logistics Pty Ltd | N1 same name | Keep | 1 | 1
Q0120 | Elm Street Early Learning | accounts@elmstreetearlyle.example | JC0120 | Elm Street Early Learning | N1 same name | Keep | 1 | 3
Q0121 | Redgum Financial Planning | accounts@redgumfinancialp.example | JC0121 | Redgum Financial Planning | N1 same name | Keep | 1 | 2
Q0122 | The Lakeside Fitness Pty Ltd | accounts@lakesidefitness.example | JC0122 | Lakeside Fitness Pty Ltd | N1 same name | Keep | 1 | 1
Q0123 | Elm Street Logistics P/L | accounts@elmstreetlogisti.example | JC0123 | Elm Street Logistics Pty Ltd | N1 same name | Keep | 1 | 1
Q0124 | LAKESIDE INSURANCE BROKERS | accounts@lakesideinsuranc.example | JC0124 | Lakeside Insurance Brokers | N1 same name | Keep | 1 | 1
Q0125 | Elm Street Pathology Pty Ltd | accounts@elmstreetpatholo.example | JC0125 | Elm Street Pathology Pty Ltd | N1 same name | Keep | 1 | 1
Q0126 | The Fairfield Accountants Pty Ltd | accounts@fairfieldaccount.example | JC0126 | Fairfield Accountants Pty Ltd | N1 same name | Keep | 1 | 2
Q0127 | Fairfield Dental | accounts@fairfielddental.example | JC0127 | Fairfield Dental | N1 same name | Keep | 1 | 1
Q0128 | The Oakwood Medical Centre Pty Ltd | accounts@oakwoodmedicalce.example | JC0128 | Oakwood Medical Centre Pty Ltd | N1 same name | Keep | 1 | 1
Q0129 | Banksia Architects | accounts@banksiaarchitect.example | JC0129 | Banksia Architects Pty Ltd | N1 same name | Keep | 1 | 1
Q0130 | The Ironbark Engineering Pty Ltd | accounts@ironbarkengineer.example | JC0130 | Ironbark Engineering Pty Ltd | N1 same name | Keep | 1 | 2
Q0131 | Wattle Grove Financial Planning | accounts@wattlegrovefinan.example | JC0131 | Wattle Grove Financial Planning | N1 same name | Keep | 1 | 1
Q0132 | Parkside Fitness | accounts@parksidefitness.example | JC0132 | Parkside Fitness Pty Ltd | N1 same name | Keep | 1 | 2
Q0133 | Greenway Chiropractic P/L | accounts@greenwaychiropra.example | JC0133 | Greenway Chiropractic Pty Ltd | N1 same name | Keep | 1 | 3
Q0134 | Bayview Real Estate | accounts@bayviewrealestat.example | JC0134 | Bayview Real Estate Pty Ltd | N1 same name | Keep | 1 | 1
Q0135 | RIVERSIDE PHARMACY | accounts@riversidepharmac.example | JC0135 | Riverside Pharmacy | N1 same name | Keep | 1 | 2
Q0136 | Elm Street Chiropractic Pty Ltd | accounts@elmstreetchiropr.example | JC0136 | Elm Street Chiropractic Pty Ltd | N1 same name | Keep | 1 | 2
Q0137 | Ironbark Real Estate Pty Ltd | accounts@ironbarkrealesta.example | JC0137 | Ironbark Real Estate Pty Ltd | N1 same name | Keep | 1 | 2
Q0138 | ELM STREET MOTORS | accounts@elmstreetmotors.example | JC0138 | Elm Street Motors | N1 same name | Keep | 1 | 2
Q0139 | Sunbury Engineering Pty Ltd | accounts@sunburyengineeri.example | JC0139 | Sunbury Engineering | N1 same name | Keep | 1 | 1
Q0140 | Ashwood Dental Pty Ltd | accounts@ashwooddental.example | JC0140 | Ashwood Dental Pty Ltd | N1 same name | Keep | 1 | 2
Q0141 | Bluestone Early Learning P/L | accounts@bluestoneearlyle.example | JC0141 | Bluestone Early Learning Pty Ltd | N1 same name | Keep | 1 | 2
Q0142 | Harbourside Property Group | accounts@harboursideprope.example | JC0142 | Harbourside Property Group | N1 same name | Keep | 1 | 1
Q0143 | RIVERSIDE ENGINEERING PTY LTD | accounts@riversideenginee.example | JC0143 | Riverside Engineering Pty Ltd | N1 same name | Keep | 1 | 1
Q0144 | ASHWOOD LAWYERS | accounts@ashwoodlawyers.example | JC0144 | Ashwood Lawyers | N1 same name | Keep | 1 | 1
Q0145 | Bayview Fitness P/L | accounts@bayviewfitness.example | JC0145 | Bayview Fitness Pty Ltd | N1 same name | Keep | 1 | 1
Q0146 | The Ironbark Property Group Pty Ltd | accounts@ironbarkproperty.example | JC0146 | Ironbark Property Group Pty Ltd | N1 same name | Keep | 1 | 2
Q0147 | Oakwood Engineering | accounts@oakwoodengineeri.example | JC0147 | Oakwood Engineering | N1 same name | Keep | 1 | 1
Q0148 | Waverley Physiotherapy | accounts@waverleyphysioth.example | JC0148 | Waverley Physiotherapy Pty Ltd | N1 same name | Keep | 1 | 3
Q0149 | Harbourside Insurance Brokers Pty Ltd | accounts@harboursideinsur.example | JC0149 | Harbourside Insurance Brokers Pty Ltd | N1 same name | Keep | 1 | 1
Q0150 | Harbourside Real Estate | accounts@harboursidereale.example | JC0150 | Harbourside Real Estate | N1 same name | Keep | 1 | 2
Q0151 | Eastwood Podiatry | accounts@eastwoodpodiatry.example | JC0151 | Eastwood Podiatry | N1 same name | Keep | 1 | 1
Q0152 | The Cityside Real Estate | accounts@citysiderealesta.example | JC0152 | Cityside Real Estate | N1 same name | Keep | 1 | 2
Q0153 | Parkside Dental | accounts@parksidedental.example | JC0153 | Parkside Dental | N1 same name | Keep | 1 | 1
Q0154 | Parkside Dental Group | accounts@parksidedentalgr2.example | JC0154 | Parkside Dental Group | N1 same name | Keep | 1 | 1
Q0155 | Northside Physiotherapy | accounts@northsidephysiot.example | JC0155 | Northside Physiotherapy | N1 same name | Keep | 1 | 2
Q0156 | North Side Physiotherapy | accounts@northsidephysiot2.example | JC0156 | North Side Physiotherapy | N1 same name | Keep | 1 | 2
Q0157 | Bayview Accountants | accounts@bayviewaccountan.example | JC0157 | Bayview Accountants | N1 same name | Keep | 1 | 1
Q0158 | BAY VIEW ACCOUNTANTS | accounts@bayviewaccountan2.example | JC0158 | Bay View Accountants | N1 same name | Keep | 1 | 1
Q0159 | Northside Enginering - Accounts |  | JC0017 | Northside Engineering Pty Ltd | F1 name 0.93+, clear winner | Merge into Q0017 | 1 | 2
Q0160 | Hillcrest Accontants - Accounts | accounts@hillcrestaccount.example | JC0077 | Hillcrest Accountants | E1 same email, name 0.85+ | Merge into Q0077 | 1 | 1
Q0161 | Kngsley Fitness | accounts@kingsleyfitness.example | JC0092 | Kingsley Fitness Pty Ltd | E1 same email, name 0.85+ | Merge into Q0092 | 1 | 1
Q0162 | Fairfield Engineerng |  | JC0044 | Fairfield Engineering Pty Ltd | F1 name 0.93+, clear winner | Merge into Q0044 | 1 | 1
Q0163 | Westend Poiatry - Accounts | accounts@westendpodiatry.example | JC0033 | Westend Podiatry | E1 same email, name 0.85+ | Merge into Q0033 | 1 | 3
Q0164 | Banksia Logistics - Accounts | accounts@banksialogistics.example | JC0086 | Banksia Logistics | N1 same name | Merge into Q0086 | 1 | 0
Q0165 | Elm Street Lgistics - Accounts |  | JC0123 | Elm Street Logistics Pty Ltd | F1 name 0.93+, clear winner | Merge into Q0123 | 1 | 2
Q0166 | Lakeside Inusrance Brokers - Accounts | accounts@lakesideinsuranc.example | JC0124 | Lakeside Insurance Brokers | E1 same email, name 0.85+ | Merge into Q0124 | 1 | 0
Q0167 | Ashwod Medical Centre - Accounts | accounts@ashwoodmedicalce.example | JC0073 | Ashwood Medical Centre | E1 same email, name 0.85+ | Merge into Q0073 | 1 | 1
Q0168 | Harbourside Chiorpractic - Accounts |  | JC0104 | Harbourside Chiropractic | F1 name 0.93+, clear winner | Merge into Q0104 | 1 | 2

## Property Match
QBO sub-customers matched to Jobber properties
Work sample: realistic data, built to show how I approach this work.
QBO ID | QBO location | Parent | Client ID | Property ID | Rule | Property exists
Q0169 | 218 High Road, Bentleigh | Q0001 | JC0001 | JP0001 | Address, normalised | 1
Q0170 | 162 Station Pde, Oakleigh | Q0001 | JC0001 | JP0002 | Address, normalised | 1
Q0171 | 273 Albert Road, Deer Park | Q0002 | JC0002 | JP0003 | Address, normalised | 1
Q0172 | 59 Station Parade, Bundoora | Q0003 | JC0003 | JP0004 | Address, normalised | 1
Q0173 | 224 Ballarat Pde, Footscray | Q0004 | JC0004 | JP0005 | Address, normalised | 1
Q0174 | 77 Ballarat Pde, Brighton | Q0005 | JC0005 | JP0006 | Address, normalised | 1
Q0175 | 290A Ballarat Hwy, Bundoora | Q0006 | JC0006 | JP0007 | Address, normalised | 1
Q0176 | 359 Glenferrie Ave, Werribee | Q0006 | JC0006 | JP0008 | Address, normalised | 1
Q0177 | 315 Park Parade, Oakleigh | Q0007 | JC0007 | JP0009 | Address, normalised | 1
Q0178 | 359 Albert Street, Point Cook | Q0007 | JC0007 | JP0010 | Address, normalised | 1
Q0179 | 169 King St, Hawthorn | Q0008 | JC0008 | JP0011 | Address, normalised | 1
Q0180 | 396 Park Hwy, Epping | Q0009 | JC0009 | JP0012 | Address, normalised | 1
Q0181 | 214A Nepean Parade, Thornbury | Q0009 | JC0009 | JP0013 | Address, normalised | 1
Q0182 | 208 Main Ave, Mitcham | Q0010 | JC0010 | JP0014 | Address, normalised | 1
Q0183 | 208 High Ave, Kew | Q0010 | JC0010 | JP0015 | Address, normalised | 1
Q0184 | 462 Mason Rd, Clayton | Q0011 | JC0011 | JP0016 | Address, normalised | 1
Q0185 | 201 Plenty Ave, Coburg | Q0012 | JC0012 | JP0017 | Address, normalised | 1
Q0186 | 164 Whitehorse St, Mentone | Q0013 | JC0013 | JP0018 | Address, normalised | 1
Q0187 | 480 King Ave, Camberwell | Q0014 | JC0014 | JP0019 | Address, normalised | 1
Q0188 | 426 Mason St, Cheltenham | Q0015 | JC0015 | JP0020 | Address, normalised | 1
Q0189 | 351 Burke Road, Oakleigh | Q0015 | JC0015 | JP0021 | Address, normalised | 1
Q0190 | 354 High Street, Clayton | Q0015 | JC0015 | JP0022 | Address, normalised | 1
Q0191 | 54 Mason Parade, Reservoir | Q0016 | JC0016 | JP0023 | Address, normalised | 1
Q0192 | 430 Victoria Road, St Kilda | Q0159 | JC0017 | JP0024 | Address, normalised | 1
Q0193 | 195/12 Railway Hwy, Bentleigh | Q0017 | JC0017 | JP0025 | Address, normalised | 1
Q0194 | 10 Queen Hwy, Deer Park | Q0017 | JC0017 | JP0026 | Address, normalised | 1
Q0195 | 17 Park Avenue, St Kilda | Q0159 | JC0017 | JP0027 | Address, normalised | 1
Q0196 | 378 Plenty St, Camberwell | Q0018 | JC0018 | JP0028 | Address, normalised | 1
Q0197 | 266 Union Ave, Point Cook | Q0019 | JC0019 | JP0029 | Address, normalised | 1
Q0198 | 98 Park Road, Kew | Q0019 | JC0019 | JP0030 | Address, normalised | 1
Q0199 | 107 Barkly Hwy, Bundoora | Q0019 | JC0019 | JP0031 | Address, normalised | 1
Q0200 | 298 Main Rd, Footscray | Q0019 | JC0019 | JP0032 | Address, normalised | 1
Q0201 | 142 Plenty Rd, Camberwell | Q0020 | JC0020 | JP0033 | Address, normalised | 1
Q0202 | 195 Nicholson Road, Ringwood | Q0021 | JC0021 | JP0034 | Address, normalised | 1
Q0203 | 245 Ballarat Avenue, Ringwood | Q0021 | JC0021 | JP0035 | Address, normalised | 1
Q0204 | 22 Hopkins Road, Bundoora | Q0022 | JC0022 | JP0036 | Address, normalised | 1
Q0205 | 356 Albert Ave, Northcote | Q0022 | JC0022 | JP0037 | Address, normalised | 1
Q0206 | 364/12 High Rd, Heidelberg | Q0023 | JC0023 | JP0038 | Address, normalised | 1
Q0207 | 417 Main Rd, Sunshine | Q0024 | JC0024 | JP0039 | Address, normalised | 1
Q0208 | 37 Nicholson Highway, Williamstown | Q0024 | JC0024 | JP0040 | Address, normalised | 1
Q0209 | 117 Railway Hwy, Epping | Q0024 | JC0024 | JP0041 | Address, normalised | 1
Q0210 | 453 Plenty Pde, Moorabbin | Q0025 | JC0025 | JP0042 | Address, normalised | 1
Q0211 | 188 Nicholson Rd, Essendon | Q0025 | JC0025 | JP0043 | Address, normalised | 1
Q0212 | 300 Sydney Hwy, Camberwell | Q0026 | JC0026 | JP0044 | Address, normalised | 1
Q0213 | 205 Railway St, Altona | Q0027 | JC0027 | JP0045 | Address, normalised | 1
Q0214 | 359 King Rd, Yarraville | Q0028 | JC0028 | JP0046 | Address, normalised | 1
Q0215 | 313A Queen Street, Camberwell | Q0029 | JC0029 | JP0047 | Address, normalised | 1
Q0216 | 386 Nepean Rd, Glen Waverley | Q0030 | JC0030 | JP0048 | Address, normalised | 1
Q0217 | 255 Glenferrie Pde, Thornbury | Q0031 | JC0031 | JP0049 | Address, normalised | 1
Q0218 | 23A Ballarat Street, Brunswick | Q0032 | JC0032 | JP0050 | Address, normalised | 1
Q0219 | 310 Ballarat Ave, Brunswick | Q0163 | JC0033 | JP0051 | Address, normalised | 1
Q0220 | 269 Victoria Avenue, Thornbury | Q0163 | JC0033 | JP0052 | Address, normalised | 1
Q0221 | 332A Glenferrie Pde, Essendon | Q0163 | JC0033 | JP0053 | Address, normalised | 1
Q0222 | 157 Whitehorse Parade, Deer Park | Q0034 | JC0034 | JP0054 | Address, normalised | 1
Q0223 | 439 Sydney Pde, Maribyrnong | Q0034 | JC0034 | JP0055 | Address, normalised | 1
Q0224 | 204 Bridge Highway, Oakleigh | Q0035 | JC0035 | JP0056 | Address, normalised | 1
Q0225 | 48 Ballarat Pde, Cheltenham | Q0036 | JC0036 | JP0057 | Address, normalised | 1
Q0226 | 479 Mason Parade, Hawthorn | Q0037 | JC0037 | JP0058 | Address, normalised | 1
Q0227 | 450 King Rd, Doncaster | Q0037 | JC0037 | JP0059 | Address, normalised | 1
Q0228 | 259 Union Ave, Hawthorn | Q0038 | JC0038 | JP0060 | Address, normalised | 1
Q0229 | 426 Ballarat Pde, Point Cook | Q0039 | JC0039 | JP0061 | Address, normalised | 1
Q0230 | 164 Nicholson St, Laverton | Q0039 | JC0039 | JP0062 | Address, normalised | 1
Q0231 | 143/12 Nepean Street, Frankston | Q0040 | JC0040 | JP0063 | Address, normalised | 1
Q0232 | 380 Nepean Pde, Laverton | Q0040 | JC0040 | JP0064 | Address, normalised | 1
Q0233 | 296 Barkly Hwy, Hawthorn | Q0041 | JC0041 | JP0065 | Address, normalised | 1
Q0234 | 46 Main Ave, Bentleigh | Q0042 | JC0042 | JP0066 | Address, normalised | 1
Q0235 | 211 Union Road, Burwood | Q0042 | JC0042 | JP0067 | Address, normalised | 1
Q0236 | 418 Nicholson Ave, Burwood | Q0043 | JC0043 | JP0068 | Address, normalised | 1
Q0237 | 43 Plenty Ave, Bentleigh | Q0044 | JC0044 | JP0069 | Address, normalised | 1
Q0238 | 27 Railway Avenue, Cheltenham | Q0162 | JC0044 | JP0070 | Address, normalised | 1
Q0239 | 225/12 Glenferrie Pde, Mentone | Q0045 | JC0045 | JP0071 | Address, normalised | 1
Q0240 | 225 Park Ave, Reservoir | Q0046 | JC0046 | JP0072 | Address, normalised | 1
Q0241 | 410 Burke Hwy, Point Cook | Q0046 | JC0046 | JP0073 | Address, normalised | 1
Q0242 | 205 Burke Highway, Glen Waverley | Q0047 | JC0047 | JP0074 | Address, normalised | 1
Q0243 | 189 Union Highway, Hawthorn | Q0048 | JC0048 | JP0075 | Address, normalised | 1
Q0244 | 128 Victoria Road, Blackburn | Q0048 | JC0048 | JP0076 | Address, normalised | 1
Q0245 | 375 Station Hwy, Cheltenham | Q0048 | JC0048 | JP0077 | Address, normalised | 1
Q0246 | 378 Burke Highway, Box Hill | Q0048 | JC0048 | JP0078 | Address, normalised | 1
Q0247 | 185 Church Parade, Burwood | Q0049 | JC0049 | JP0079 | Address, normalised | 1
Q0248 | 115 Nepean Pde, Reservoir | Q0050 | JC0050 | JP0080 | Address, normalised | 1
Q0249 | 96A Glenferrie Pde, Essendon | Q0050 | JC0050 | JP0081 | Address, normalised | 1
Q0250 | 158 Station St, Mentone | Q0050 | JC0050 | JP0082 | Address, normalised | 1
Q0251 | 476 Sydney Hwy, Frankston | Q0051 | JC0051 | JP0083 | Address, normalised | 1
Q0252 | 436/12 Nepean Highway, Sunshine | Q0052 | JC0052 | JP0084 | Address, normalised | 1
Q0253 | 394 Ballarat Avenue, Brighton | Q0053 | JC0053 | JP0085 | Address, normalised | 1
Q0254 | 135 Victoria Pde, Dandenong | Q0054 | JC0054 | JP0086 | Address, normalised | 1
Q0255 | 472 Barkly Pde, Moorabbin | Q0054 | JC0054 | JP0087 | Address, normalised | 1
Q0256 | 151 Nicholson Street, Point Cook | Q0055 | JC0055 | JP0088 | Address, normalised | 1
Q0257 | 4A Gilbert Rd, Camberwell | Q0055 | JC0055 | JP0089 | Address, normalised | 1
Q0258 | 144 Burke Avenue, Coburg | Q0055 | JC0055 | JP0090 | Address, normalised | 1
Q0259 | 182 King Ave, Footscray | Q0055 | JC0055 | JP0091 | Address, normalised | 1
Q0260 | 79/12 Glenferrie Pde, Camberwell | Q0056 | JC0056 | JP0092 | Address, normalised | 1
Q0261 | 401 Park Highway, Burwood | Q0056 | JC0056 | JP0093 | Address, normalised | 1
Q0262 | 401 Burke St, Burwood | Q0056 | JC0056 | JP0094 | Address, normalised | 1
Q0263 | 11 Hopkins Ave, Ringwood | Q0056 | JC0056 | JP0095 | Address, normalised | 1
Q0264 | 263 Nepean Highway, Altona | Q0057 | JC0057 | JP0096 | Address, normalised | 1
Q0265 | 288 Main Hwy, Northcote | Q0058 | JC0058 | JP0097 | Address, normalised | 1
Q0266 | 459 Park Ave, Deer Park | Q0059 | JC0059 | JP0098 | Address, normalised | 1
Q0267 | 464 Barkly Rd, Blackburn | Q0060 | JC0060 | JP0099 | Address, normalised | 1
Q0268 | 90A Albert Pde, Bentleigh | Q0060 | JC0060 | JP0100 | Address, normalised | 1
Q0269 | 29 Burke Pde, Burwood | Q0061 | JC0061 | JP0101 | Address, normalised | 1
Q0270 | 23 Station Pde, Glen Waverley | Q0062 | JC0062 | JP0102 | Address, normalised | 1
Q0271 | 251 Union Ave, Altona | Q0063 | JC0063 | JP0103 | Address, normalised | 1
Q0272 | 270 Station Rd, Doncaster | Q0063 | JC0063 | JP0104 | Address, normalised | 1
Q0273 | 463 Gilbert Street, Glen Waverley | Q0063 | JC0063 | JP0105 | Address, normalised | 1
Q0274 | 59 King Hwy, Point Cook | Q0064 | JC0064 | JP0106 | Address, normalised | 1
Q0275 | 61 Church Street, Point Cook | Q0064 | JC0064 | JP0107 | Address, normalised | 1
Q0276 | 280 Railway Road, Point Cook | Q0065 | JC0065 | JP0108 | Address, normalised | 1
Q0277 | 149 Main Road, Point Cook | Q0066 | JC0066 | JP0109 | Address, normalised | 1
Q0278 | 313 King Rd, Hawthorn | Q0066 | JC0066 | JP0110 | Address, normalised | 1
Q0279 | 155 Hopkins Road, Glen Waverley | Q0067 | JC0067 | JP0111 | Address, normalised | 1
Q0280 | 284 Park Pde, Point Cook | Q0068 | JC0068 | JP0112 | Address, normalised | 1
Q0281 | 85 Nepean Road, Frankston | Q0068 | JC0068 | JP0113 | Address, normalised | 1
Q0282 | 231 Church Hwy, Hawthorn | Q0068 | JC0068 | JP0114 | Address, normalised | 1
Q0283 | 223A Nicholson Parade, Werribee | Q0069 | JC0069 | JP0115 | Address, normalised | 1
Q0284 | 382 Hopkins Street, Footscray | Q0070 | JC0070 | JP0116 | Address, normalised | 1
Q0285 | 443 Station Rd, Footscray | Q0070 | JC0070 | JP0117 | Address, normalised | 1
Q0286 | 127 Main Highway, Reservoir | Q0071 | JC0071 | JP0118 | Address, normalised | 1
Q0287 | 68 Church Pde, Essendon | Q0072 | JC0072 | JP0119 | Address, normalised | 1
Q0288 | 102 Union Rd, St Kilda | Q0072 | JC0072 | JP0120 | Address, normalised | 1
Q0289 | 61 Church Rd, Bundoora | Q0167 | JC0073 | JP0121 | Address, normalised | 1
Q0290 | 287 Whitehorse Hwy, Deer Park | Q0074 | JC0074 | JP0122 | Address, normalised | 1
Q0291 | 289 Nepean Street, Bentleigh | Q0075 | JC0075 | JP0123 | Address, normalised | 1
Q0292 | 221 Plenty Ave, Footscray | Q0076 | JC0076 | JP0124 | Address, normalised | 1
Q0293 | 77 Mason Hwy, Mitcham | Q0160 | JC0077 | JP0125 | Address, normalised | 1
Q0294 | 170 Railway Hwy, Reservoir | Q0078 | JC0078 | JP0126 | Address, normalised | 1
Q0295 | 208 Glenferrie Rd, Mitcham | Q0078 | JC0078 | JP0127 | Address, normalised | 1
Q0296 | 212 Sydney Avenue, Yarraville | Q0079 | JC0079 | JP0128 | Address, normalised | 1
Q0297 | 268 Sydney Road, Heidelberg | Q0080 | JC0080 | JP0129 | Address, normalised | 1
Q0298 | 369 Station Road, Burwood | Q0081 | JC0081 | JP0130 | Address, normalised | 1
Q0299 | 264 Queen Pde, Mitcham | Q0081 | JC0081 | JP0131 | Address, normalised | 1
Q0300 | 130 Barkly Rd, Sunshine | Q0082 | JC0082 | JP0132 | Address, normalised | 1
Q0301 | 180 Union Ave, Mentone | Q0083 | JC0083 | JP0133 | Address, normalised | 1
Q0302 | 148 Plenty Street, Cheltenham | Q0083 | JC0083 | JP0134 | Address, normalised | 1
Q0303 | 4A Main Hwy, Moorabbin | Q0083 | JC0083 | JP0135 | Address, normalised | 1
Q0304 | 165 Hopkins Rd, Cheltenham | Q0084 | JC0084 | JP0136 | Address, normalised | 1
Q0305 | 245 Victoria Rd, Frankston | Q0084 | JC0084 | JP0137 | Address, normalised | 1
Q0306 | 274 Gilbert Ave, Glen Waverley | Q0084 | JC0084 | JP0138 | Address, normalised | 1
Q0307 | 198 Station Avenue, Burwood | Q0085 | JC0085 | JP0139 | Address, normalised | 1
Q0308 | 387 Burke Parade, Northcote | Q0086 | JC0086 | JP0140 | Address, normalised | 1
Q0309 | 467 High Avenue, Northcote | Q0086 | JC0086 | JP0141 | Address, normalised | 1
Q0310 | 458 Glenferrie Pde, Thornbury | Q0086 | JC0086 | JP0142 | Address, normalised | 1
Q0311 | 111A Plenty St, Epping | Q0087 | JC0087 | JP0143 | Address, normalised | 1
Q0312 | 12 Sydney Road, Bundoora | Q0088 | JC0088 | JP0144 | Address, normalised | 1
Q0313 | 272 Gilbert St, Maribyrnong | Q0089 | JC0089 | JP0145 | Address, normalised | 1
Q0314 | 416 Park Road, Ringwood | Q0090 | JC0090 | JP0146 | Address, normalised | 1
Q0315 | 1 Mason Pde, Glen Waverley | Q0091 | JC0091 | JP0147 | Address, normalised | 1
Q0316 | 460 Sydney Hwy, Werribee | Q0161 | JC0092 | JP0148 | Address, normalised | 1
Q0317 | 35 Nepean Ave, Footscray | Q0093 | JC0093 | JP0149 | Address, normalised | 1
Q0318 | 271 Victoria Ave, Hawthorn | Q0094 | JC0094 | JP0150 | Address, normalised | 1
Q0319 | 375 Railway Rd, Altona | Q0095 | JC0095 | JP0151 | Address, normalised | 1
Q0320 | 186 Sydney Ave, Coburg | Q0096 | JC0096 | JP0152 | Address, normalised | 1
Q0321 | 399 Whitehorse Road, Reservoir | Q0096 | JC0096 | JP0153 | Address, normalised | 1
Q0322 | 453 Railway Pde, Camberwell | Q0097 | JC0097 | JP0154 | Address, normalised | 1
Q0323 | 326 Main Highway, Glen Waverley | Q0098 | JC0098 | JP0155 | Address, normalised | 1
Q0324 | 306 Bridge Rd, Glen Waverley | Q0099 | JC0099 | JP0156 | Address, normalised | 1
Q0325 | 79 Ballarat Street, Point Cook | Q0100 | JC0100 | JP0157 | Address, normalised | 1
Q0326 | 145 Church Ave, Brighton | Q0100 | JC0100 | JP0158 | Address, normalised | 1
Q0327 | 190 Nicholson Ave, Camberwell | Q0101 | JC0101 | JP0159 | Address, normalised | 1
Q0328 | 387 Barkly Highway, Hawthorn | Q0102 | JC0102 | JP0160 | Address, normalised | 1
Q0329 | 5 Park Hwy, Kew | Q0102 | JC0102 | JP0161 | Address, normalised | 1
Q0330 | 204 Mason Pde, Williamstown | Q0103 | JC0103 | JP0162 | Address, normalised | 1
Q0331 | 445 Barkly Ave, Cheltenham | Q0103 | JC0103 | JP0163 | Address, normalised | 1
Q0332 | 151 Glenferrie Hwy, Oakleigh | Q0104 | JC0104 | JP0164 | Address, normalised | 1
Q0333 | 284 Mason Hwy, Moorabbin | Q0168 | JC0104 | JP0165 | Address, normalised | 1
Q0334 | 218 Burke St, St Kilda | Q0168 | JC0104 | JP0166 | Address, normalised | 1
Q0335 | 362 Barkly Avenue, Mentone | Q0105 | JC0105 | JP0167 | Address, normalised | 1
Q0336 | 418 Main Ave, Northcote | Q0105 | JC0105 | JP0168 | Address, normalised | 1
Q0337 | 176 High Highway, Brunswick | Q0106 | JC0106 | JP0169 | Address, normalised | 1
Q0338 | 356 Glenferrie Pde, Frankston | Q0106 | JC0106 | JP0170 | Address, normalised | 1
Q0339 | 64 Glenferrie Pde, Bentleigh | Q0107 | JC0107 | JP0171 | Address, normalised | 1
Q0340 | 433 Mason Pde, Brunswick | Q0108 | JC0108 | JP0172 | Address, normalised | 1
Q0341 | 291 Burke Highway, Hawthorn | Q0108 | JC0108 | JP0173 | Address, normalised | 1
Q0342 | 186 Plenty Street, Altona | Q0108 | JC0108 | JP0174 | Address, normalised | 1
Q0343 | 279 Nicholson Avenue, Deer Park | Q0109 | JC0109 | JP0175 | Address, normalised | 1
Q0344 | 313 Victoria Road, Reservoir | Q0109 | JC0109 | JP0176 | Address, normalised | 1
Q0345 | 44 Nepean Pde, Brunswick | Q0110 | JC0110 | JP0177 | Address, normalised | 1
Q0346 | 67 Glenferrie Rd, Preston | Q0110 | JC0110 | JP0178 | Address, normalised | 1
Q0347 | 6 Whitehorse Street, Mitcham | Q0110 | JC0110 | JP0179 | Address, normalised | 1
Q0348 | 267 Nepean St, Yarraville | Q0111 | JC0111 | JP0180 | Address, normalised | 1
Q0349 | 266 Park Rd, Williamstown | Q0111 | JC0111 | JP0181 | Address, normalised | 1
Q0350 | 158 Nepean Avenue, Footscray | Q0112 | JC0112 | JP0182 | Address, normalised | 1
Q0351 | 135 Main Ave, Frankston | Q0113 | JC0113 | JP0183 | Address, normalised | 1
Q0352 | 256 Albert Parade, Northcote | Q0114 | JC0114 | JP0184 | Address, normalised | 1
Q0353 | 215 Barkly St, Laverton | Q0115 | JC0115 | JP0185 | Address, normalised | 1
Q0354 | 329 Station Ave, Brighton | Q0115 | JC0115 | JP0186 | Address, normalised | 1
Q0355 | 462A Victoria Road, Yarraville | Q0116 | JC0116 | JP0187 | Address, normalised | 1
Q0356 | 248 Sydney St, Cheltenham | Q0117 | JC0117 | JP0188 | Address, normalised | 1
Q0357 | 251 Plenty Hwy, Bentleigh | Q0118 | JC0118 | JP0189 | Address, normalised | 1
Q0358 | 148 Nepean Street, Bentleigh | Q0119 | JC0119 | JP0190 | Address, normalised | 1
Q0359 | 431 Union Ave, Hawthorn | Q0120 | JC0120 | JP0191 | Address, normalised | 1
Q0360 | 356 Main Rd, Camberwell | Q0120 | JC0120 | JP0192 | Address, normalised | 1
Q0361 | 422 Nicholson Parade, Glen Waverley | Q0120 | JC0120 | JP0193 | Address, normalised | 1
Q0362 | 455 Railway Rd, Williamstown | Q0121 | JC0121 | JP0194 | Address, normalised | 1
Q0363 | 217 King Street, Epping | Q0121 | JC0121 | JP0195 | Address, normalised | 1
Q0364 | 58 Station Rd, Mitcham | Q0122 | JC0122 | JP0196 | Address, normalised | 1
Q0365 | 343 Sydney St, Kew | Q0165 | JC0123 | JP0197 | Address, normalised | 1
Q0366 | 399 Plenty Ave, Ringwood | Q0165 | JC0123 | JP0198 | Address, normalised | 1
Q0367 | 256 Station St, Blackburn | Q0123 | JC0123 | JP0199 | Address, normalised | 1
Q0368 | 459 Whitehorse Pde, Sunshine | Q0124 | JC0124 | JP0200 | Address, normalised | 1
Q0369 | 87 Main Ave, Maribyrnong | Q0125 | JC0125 | JP0201 | Address, normalised | 1
Q0370 | 313/12 Union Avenue, Dandenong | Q0126 | JC0126 | JP0202 | Address, normalised | 1
Q0371 | 354 King Avenue, Moorabbin | Q0126 | JC0126 | JP0203 | Address, normalised | 1
Q0372 | 122 Main Avenue, Box Hill | Q0127 | JC0127 | JP0204 | Address, normalised | 1
Q0373 | 64 Bridge Street, Coburg | Q0128 | JC0128 | JP0205 | Address, normalised | 1
Q0374 | 213 Church Pde, Frankston | Q0129 | JC0129 | JP0206 | Address, normalised | 1
Q0375 | 420 Railway Parade, Preston | Q0130 | JC0130 | JP0207 | Address, normalised | 1
Q0376 | 301 Whitehorse Hwy, Thornbury | Q0130 | JC0130 | JP0208 | Address, normalised | 1
Q0377 | 294 Victoria Ave, Northcote | Q0131 | JC0131 | JP0209 | Address, normalised | 1
Q0378 | 81 Nepean Road, Burwood | Q0132 | JC0132 | JP0210 | Address, normalised | 1
Q0379 | 440 Bridge Street, Maribyrnong | Q0132 | JC0132 | JP0211 | Address, normalised | 1
Q0380 | 347 High Highway, Ringwood | Q0133 | JC0133 | JP0212 | Address, normalised | 1
Q0381 | 250 Hopkins Hwy, Kew | Q0133 | JC0133 | JP0213 | Address, normalised | 1
Q0382 | 191 Albert Avenue, Burwood | Q0133 | JC0133 | JP0214 | Address, normalised | 1
Q0383 | 414 Sydney Avenue, Brighton | Q0134 | JC0134 | JP0215 | Address, normalised | 1
Q0384 | 472 Hopkins Hwy, Box Hill | Q0135 | JC0135 | JP0216 | Address, normalised | 1
Q0385 | 410 Queen Hwy, Glen Waverley | Q0135 | JC0135 | JP0217 | Address, normalised | 1
Q0386 | 348 Railway St, Mentone | Q0136 | JC0136 | JP0218 | Address, normalised | 1
Q0387 | 4 Sydney Hwy, Cheltenham | Q0136 | JC0136 | JP0219 | Address, normalised | 1
Q0388 | 395 Plenty Ave, Oakleigh | Q0137 | JC0137 | JP0220 | Address, normalised | 1
Q0389 | 32 Park Avenue, Oakleigh | Q0137 | JC0137 | JP0221 | Address, normalised | 1
Q0390 | 333 Albert Parade, Brighton | Q0138 | JC0138 | JP0222 | Address, normalised | 1
Q0391 | 280 Station St, Oakleigh | Q0138 | JC0138 | JP0223 | Address, normalised | 1
Q0392 | 87/12 Victoria Rd, Point Cook | Q0139 | JC0139 | JP0224 | Address, normalised | 1
Q0393 | 241 Mason Road, Northcote | Q0140 | JC0140 | JP0225 | Address, normalised | 1
Q0394 | 448 Barkly Avenue, Mentone | Q0140 | JC0140 | JP0226 | Address, normalised | 1
Q0395 | 351 High Street, Altona | Q0141 | JC0141 | JP0227 | Address, normalised | 1
Q0396 | 477 Hopkins Avenue, Hawthorn | Q0141 | JC0141 | JP0228 | Address, normalised | 1
Q0397 | 428 Church Pde, Maribyrnong | Q0142 | JC0142 | JP0229 | Address, normalised | 1
Q0398 | 253A Glenferrie St, Bundoora | Q0143 | JC0143 | JP0230 | Address, normalised | 1
Q0399 | 466 Main St, Werribee | Q0144 | JC0144 | JP0231 | Address, normalised | 1
Q0400 | 367 Station Pde, Thornbury | Q0145 | JC0145 | JP0232 | Address, normalised | 1
Q0401 | 266/12 Albert Avenue, Mitcham | Q0146 | JC0146 | JP0233 | Address, normalised | 1
Q0402 | 479 Burke Rd, Reservoir | Q0146 | JC0146 | JP0234 | Address, normalised | 1
Q0403 | 216 Plenty Road, Burwood | Q0147 | JC0147 | JP0235 | Address, normalised | 1
Q0404 | 42 Queen Ave, Bentleigh | Q0148 | JC0148 | JP0236 | Address, normalised | 1
Q0405 | 438 Church Hwy, Bentleigh | Q0148 | JC0148 | JP0237 | Address, normalised | 1
Q0406 | 337 Plenty Pde, St Kilda | Q0148 | JC0148 | JP0238 | Address, normalised | 1
Q0407 | 314 Plenty St, Northcote | Q0149 | JC0149 | JP0239 | Address, normalised | 1
Q0408 | 121 High Pde, Glen Waverley | Q0150 | JC0150 | JP0240 | Address, normalised | 1
Q0409 | 317 Victoria Parade, Clayton | Q0150 | JC0150 | JP0241 | Address, normalised | 1
Q0410 | 273/12 Plenty Pde, Coburg | Q0151 | JC0151 | JP0242 | Address, normalised | 1
Q0411 | 200 Nepean Avenue, Moorabbin | Q0152 | JC0152 | JP0243 | Address, normalised | 1
Q0412 | 455 Nicholson Highway, Moorabbin | Q0152 | JC0152 | JP0244 | Address, normalised | 1
Q0413 | 400 Albert Street, Mentone | Q0153 | JC0153 | JP0245 | Address, normalised | 1
Q0414 | 257 Hopkins Pde, Point Cook | Q0154 | JC0154 | JP0246 | Address, normalised | 1
Q0415 | 139 Glenferrie Parade, Brighton | Q0155 | JC0155 | JP0247 | Address, normalised | 1
Q0416 | 250 Bridge Hwy, Werribee | Q0155 | JC0155 | JP0248 | Address, normalised | 1
Q0417 | 284A Park Rd, Point Cook | Q0156 | JC0156 | JP0249 | Address, normalised | 1
Q0418 | 163 Barkly Highway, Essendon | Q0156 | JC0156 | JP0250 | Address, normalised | 1
Q0419 | 448 Nicholson Street, Kew | Q0157 | JC0157 | JP0251 | Address, normalised | 1
Q0420 | 360 Burke St, Maribyrnong | Q0158 | JC0158 | JP0252 | Address, normalised | 1

## Template Match
QBO templates matched to Jobber jobs (property + service, amount when two jobs share an address)
Work sample: realistic data, built to show how I approach this work.
Template | Name | Property | Service | Jobber job | Rule | Job exists
T0001 | Oakleigh - Kitchen and bathrooms | JP0002 | kitchen and bathrooms | J1002 | Property + service | 1
T0002 | Deer Park - Kitchen and bathrooms | JP0003 | kitchen and bathrooms | J1004 | Property + service | 1
T0003 | Bundoora - Window clean | JP0004 | window clean | J1006 | Property + service | 1
T0004 | Footscray - Kitchen and bathrooms | JP0005 | kitchen and bathrooms | J1007 | Property + service | 1
T0005 | Brighton - Office clean | JP0006 | office clean | J1008 | Property + service | 1
T0006 | Bundoora - Office clean | JP0007 | office clean | J1009 | Property + service | 1
T0007 | Werribee - Office clean | JP0008 | office clean | J1010 | Property + service | 1
T0008 | Oakleigh - Office clean | JP0009 | office clean | J1011 | Property + service | 1
T0009 | Hawthorn - Washroom service | JP0011 | washroom service | J1015 | Property + service | 1
T0010 | Epping - Kitchen and bathrooms | JP0012 | kitchen and bathrooms | J1016 | Property + service | 1
T0011 | Thornbury - Office clean | JP0013 | office clean | J1017 | Property + service | 1
T0012 | Mitcham - Office clean | JP0014 | office clean | J1018 | Property + service | 1
T0013 | Kew - Office clean | JP0015 | office clean | J1019 | Property + service | 1
T0014 | Coburg - Office clean | JP0017 | office clean | J1021 | Property + service | 1
T0015 | Mentone - Office clean | JP0018 | office clean | J1022 | Property + service | 1
T0016 | Camberwell - Office clean | JP0019 | office clean | J1023 | Property + service | 1
T0017 | Camberwell - Carpet steam clean | JP0019 | carpet steam clean | J1024 | Property + service | 1
T0018 | Cheltenham - Kitchen and bathrooms | JP0020 | kitchen and bathrooms | J1025 | Property + service | 1
T0019 | Cheltenham - Window clean | JP0020 | window clean | J1026 | Property + service | 1
T0020 | Oakleigh - Office clean | JP0021 | office clean | J1027 | Property + service | 1
T0021 | Clayton - Kitchen and bathrooms | JP0022 | kitchen and bathrooms | J1028 | Property + service | 1
T0022 | Reservoir - Office clean | JP0023 | office clean | J1029 | Property + service + amount | 1
T0023 | St Kilda - Office clean | JP0024 | office clean | J1030 | Property + service + amount | 1
T0024 | Bentleigh - Office clean | JP0025 | office clean | J1031 | Property + service | 1
T0025 | Deer Park - Office clean | JP0026 | office clean | J1033 | Property + service | 1
T0026 | St Kilda - Kitchen and bathrooms | JP0027 | kitchen and bathrooms | J1034 | Property + service | 1
T0027 | Camberwell - Window clean | JP0028 | window clean | J1036 | Property + service | 1
T0028 | Point Cook - Office clean | JP0029 | office clean | J1037 | Property + service | 1
T0029 | Bundoora - Office clean | JP0031 | office clean | J1039 | Property + service | 1
T0030 | Footscray - Office clean | JP0032 | office clean | J1040 | Property + service | 1
T0031 | Footscray - Carpet steam clean | JP0032 | carpet steam clean | J1041 | Property + service | 1
T0032 | Camberwell - Kitchen and bathrooms | JP0033 | kitchen and bathrooms | J1042 | Property + service | 1
T0033 | Ringwood - Window clean | JP0034 | window clean | J1044 | Property + service | 1
T0034 | Ringwood - Washroom service | JP0035 | washroom service | J1046 | Property + service | 1
T0035 | Bundoora - Kitchen and bathrooms | JP0036 | kitchen and bathrooms | J1047 | Property + service | 1
T0036 | Northcote - Office clean | JP0037 | office clean | J1048 | Property + service | 1
T0037 | Northcote - Carpet steam clean | JP0037 | carpet steam clean | J1049 | Property + service | 1
T0038 | Sunshine - Office clean | JP0039 | office clean | J1051 | Property + service | 1
T0039 | Williamstown - Office clean | JP0040 | office clean | J1052 | Property + service | 1
T0040 | Epping - Office clean | JP0041 | office clean | J1053 | Property + service | 1
T0041 | Essendon - Office clean | JP0043 | office clean | J1055 | Property + service | 1
T0042 | Altona - Office clean | JP0045 | office clean | J1057 | Property + service | 1
T0043 | Yarraville - Office clean | JP0046 | office clean | J1058 | Property + service | 1
T0044 | Glen Waverley - Office clean | JP0048 | office clean | J1060 | Property + service | 1
T0045 | Brunswick - Office clean | JP0051 | office clean | J1064 | Property + service | 1
T0046 | Brunswick - Carpet steam clean | JP0051 | carpet steam clean | J1065 | Property + service | 1
T0047 | Thornbury - Office clean | JP0052 | office clean | J1066 | Property + service | 1
T0048 | Thornbury - Window clean | JP0052 | window clean | J1067 | Property + service | 1
T0049 | Essendon - Office clean | JP0053 | office clean | J1068 | Property + service | 1
T0050 | Deer Park - Office clean | JP0054 | office clean | J1069 | Property + service | 1
T0051 | Maribyrnong - Kitchen and bathrooms | JP0055 | kitchen and bathrooms | J1070 | Property + service | 1
T0052 | Oakleigh - Office clean | JP0056 | office clean | J1071 | Property + service | 1
T0053 | Oakleigh office clean (copy) | JP0056 | office clean | J1071 | Property + service | 1
T0054 | Cheltenham - Office clean | JP0057 | office clean | J1072 | Property + service | 1
T0055 | Hawthorn - Kitchen and bathrooms | JP0058 | kitchen and bathrooms | J1073 | Property + service | 1
T0056 | Doncaster - Window clean | JP0059 | window clean | J1076 | Property + service | 1
T0057 | Point Cook - Office clean | JP0061 | office clean | J1078 | Property + service | 1
T0058 | Laverton - Office clean | JP0062 | office clean | J1079 | Property + service | 1
T0059 | Laverton - Window clean | JP0062 | window clean | J1080 | Property + service | 1
T0060 | Frankston - Office clean | JP0063 | office clean | J1081 | Property + service + amount | 1
T0061 | Frankston office clean (copy) | JP0063 | office clean | J1081 | Property + service + amount | 1
T0062 | Frankston - Washroom service | JP0063 | washroom service | J1082 | Property + service | 1
T0063 | Laverton - Office clean | JP0064 | office clean | J1083 | Property + service | 1
T0064 | Hawthorn - Office clean | JP0065 | office clean | J1085 | Property + service | 1
T0065 | Hawthorn - Window clean | JP0065 | window clean | J1086 | Property + service | 1
T0066 | Hawthorn - Washroom service | JP0065 | washroom service | J1087 | Property + service | 1
T0067 | Bentleigh - Carpet steam clean | JP0066 | carpet steam clean | J1089 | Property + service | 1
T0068 | Bentleigh - Washroom service | JP0066 | washroom service | J1090 | Property + service | 1
T0069 | Burwood - Kitchen and bathrooms | JP0067 | kitchen and bathrooms | J1091 | Property + service | 1
T0070 | Burwood - Office clean | JP0068 | office clean | J1092 | Property + service | 1
T0071 | Bentleigh - Office clean | JP0069 | office clean | J1093 | Property + service | 1
T0072 | Cheltenham - Office clean | JP0070 | office clean | J1094 | Property + service | 1
T0073 | Cheltenham - Window clean | JP0070 | window clean | J1095 | Property + service | 1
T0074 | Mentone - Office clean | JP0071 | office clean | J1096 | Property + service | 1
T0075 | Reservoir - Office clean | JP0072 | office clean | J1097 | Property + service + amount | 1
T0076 | Reservoir - Carpet steam clean | JP0072 | carpet steam clean | J1098 | Property + service | 1
T0077 | Reservoir - Washroom service | JP0072 | washroom service | J1099 | Property + service | 1
T0078 | Point Cook - Office clean | JP0073 | office clean | J1100 | Property + service | 1
T0079 | Glen Waverley - Washroom service | JP0074 | washroom service | J1103 | Property + service | 1
T0080 | Hawthorn - Office clean | JP0075 | office clean | J1104 | Property + service | 1
T0081 | Hawthorn - Carpet steam clean | JP0075 | carpet steam clean | J1105 | Property + service | 1
T0082 | Cheltenham - Office clean | JP0077 | office clean | J1107 | Property + service | 1
T0083 | Cheltenham - Window clean | JP0077 | window clean | J1108 | Property + service | 1
T0084 | Box Hill - Office clean | JP0078 | office clean | J1109 | Property + service | 1
T0085 | Burwood - Office clean | JP0079 | office clean | J1110 | Property + service | 1
T0086 | Burwood - Window clean | JP0079 | window clean | J1111 | Property + service | 1
T0087 | Reservoir - Kitchen and bathrooms | JP0080 | kitchen and bathrooms | J1112 | Property + service | 1
T0088 | Essendon - Washroom service | JP0081 | washroom service | J1114 | Property + service | 1
T0089 | Mentone - Kitchen and bathrooms | JP0082 | kitchen and bathrooms | J1115 | Property + service | 1
T0090 | Frankston - Office clean | JP0083 | office clean | J1116 | Property + service | 1
T0091 | Sunshine - Office clean | JP0084 | office clean | J1117 | Property + service | 1
T0092 | Brighton - Office clean | JP0085 | office clean | J1118 | Property + service | 1
T0093 | Brighton - Carpet steam clean | JP0085 | carpet steam clean | J1119 | Property + service | 1
T0094 | Dandenong - Office clean | JP0086 | office clean | J1120 | Property + service | 1
T0095 | Moorabbin - Kitchen and bathrooms | JP0087 | kitchen and bathrooms | J1121 | Property + service | 1
T0096 | Point Cook - Kitchen and bathrooms | JP0088 | kitchen and bathrooms | J1122 | Property + service | 1
T0097 | Camberwell - Office clean | JP0089 | office clean | J1124 | Property + service + amount | 1
T0098 | Coburg - Office clean | JP0090 | office clean | J1125 | Property + service | 1
T0099 | Footscray - Office clean | JP0091 | office clean | J1127 | Property + service | 1
T0100 | Camberwell - Kitchen and bathrooms | JP0092 | kitchen and bathrooms | J1128 | Property + service | 1
T0101 | Burwood - Office clean | JP0093 | office clean | J1129 | Property + service | 1
T0102 | Burwood - Carpet steam clean | JP0093 | carpet steam clean | J1130 | Property + service | 1
T0103 | Burwood - Office clean | JP0094 | office clean | J1131 | Property + service | 1
T0104 | Ringwood - Carpet steam clean | JP0095 | carpet steam clean | J1133 | Property + service | 1
T0105 | Altona - Office clean | JP0096 | office clean | J1134 | Property + service | 1
T0106 | Northcote - Office clean | JP0097 | office clean | J1135 | Property + service | 1
T0107 | Northcote - Window clean | JP0097 | window clean | J1136 | Property + service | 1
T0108 | Deer Park - Office clean | JP0098 | office clean | J1137 | Property + service | 1
T0109 | Blackburn - Office clean | JP0099 | office clean | J1138 | Property + service | 1
T0110 | Bentleigh - Office clean | JP0100 | office clean | J1139 | Property + service | 1
T0111 | Burwood - Office clean | JP0101 | office clean | J1140 | Property + service | 1
T0112 | Glen Waverley - Office clean | JP0102 | office clean | J1141 | Property + service | 1
T0113 | Glen Waverley - Washroom service | JP0102 | washroom service | J1142 | Property + service | 1
T0114 | Altona - Office clean | JP0103 | office clean | J1143 | Property + service | 1
T0115 | Doncaster - Office clean | JP0104 | office clean | J1144 | Property + service | 1
T0116 | Doncaster - Window clean | JP0104 | window clean | J1145 | Property + service | 1
T0117 | Glen Waverley - Kitchen and bathrooms | JP0105 | kitchen and bathrooms | J1146 | Property + service | 1
T0118 | Point Cook - Office clean | JP0106 | office clean | J1147 | Property + service | 1
T0119 | Point Cook - Office clean | JP0107 | office clean | J1148 | Property + service | 1
T0120 | Point Cook - Window clean | JP0107 | window clean | J1149 | Property + service | 1
T0121 | Point Cook - Kitchen and bathrooms | JP0108 | kitchen and bathrooms | J1150 | Property + service | 1
T0122 | Point Cook - Window clean | JP0108 | window clean | J1151 | Property + service | 1
T0123 | Point Cook - Office clean | JP0109 | office clean | J1152 | Property + service | 1
T0124 | Point Cook - Washroom service | JP0109 | washroom service | J1153 | Property + service | 1
T0125 | Hawthorn - Office clean | JP0110 | office clean | J1154 | Property + service | 1
T0126 | Glen Waverley - Office clean | JP0111 | office clean | J1155 | Property + service | 1
T0127 | Glen Waverley office clean (copy) | JP0111 | office clean | J1155 | Property + service | 1
T0128 | Point Cook - Office clean | JP0112 | office clean | J1156 | Property + service | 1
T0129 | Frankston - Office clean | JP0113 | office clean | J1157 | Property + service | 1
T0130 | Hawthorn - Office clean | JP0114 | office clean | J1158 | Property + service | 1
T0131 | Werribee - Kitchen and bathrooms | JP0115 | kitchen and bathrooms | J1159 | Property + service | 1
T0132 | Werribee - Washroom service | JP0115 | washroom service | J1160 | Property + service | 1
T0133 | Footscray - Office clean | JP0116 | office clean | J1161 | Property + service | 1
T0134 | Footscray - Office clean | JP0117 | office clean | J1162 | Property + service | 1
T0135 | Reservoir - Carpet steam clean | JP0118 | carpet steam clean | J1164 | Property + service | 1
T0136 | St Kilda - Office clean | JP0120 | office clean | J1166 | Property + service + amount | 1
T0137 | Bundoora - Kitchen and bathrooms | JP0121 | kitchen and bathrooms | J1167 | Property + service | 1
T0138 | Deer Park - Office clean | JP0122 | office clean | J1169 | Property + service | 1
T0139 | Bentleigh - Kitchen and bathrooms | JP0123 | kitchen and bathrooms | J1170 | Property + service | 1
T0140 | Footscray - Office clean | JP0124 | office clean | J1171 | Property + service | 1
T0141 | Mitcham - Kitchen and bathrooms | JP0125 | kitchen and bathrooms | J1172 | Property + service | 1
T0142 | Reservoir - Office clean | JP0126 | office clean | J1174 | Property + service | 1
T0143 | Mitcham - Office clean | JP0127 | office clean | J1175 | Property + service + amount | 1
T0144 | Yarraville - Office clean | JP0128 | office clean | J1176 | Property + service | 1
T0145 | Yarraville office clean (copy) | JP0128 | office clean | J1176 | Property + service | 1
T0146 | Heidelberg - Kitchen and bathrooms | JP0129 | kitchen and bathrooms | J1177 | Property + service | 1
T0147 | Heidelberg - Carpet steam clean | JP0129 | carpet steam clean | J1178 | Property + service | 1
T0148 | Burwood - Office clean | JP0130 | office clean | J1179 | Property + service | 1
T0149 | Mitcham - Kitchen and bathrooms | JP0131 | kitchen and bathrooms | J1180 | Property + service | 1
T0150 | Sunshine - Office clean | JP0132 | office clean | J1181 | Property + service | 1
T0151 | Mentone - Office clean | JP0133 | office clean | J1182 | Property + service | 1
T0152 | Cheltenham - Office clean | JP0134 | office clean | J1183 | Property + service + amount | 1
T0153 | Moorabbin - Office clean | JP0135 | office clean | J1184 | Property + service | 1
T0154 | Cheltenham - Office clean | JP0136 | office clean | J1186 | Property + service | 1
T0155 | Frankston - Office clean | JP0137 | office clean | J1187 | Property + service | 1
T0156 | Glen Waverley - Office clean | JP0138 | office clean | J1188 | Property + service | 1
T0157 | Glen Waverley - Washroom service | JP0138 | washroom service | J1189 | Property + service | 1
T0158 | Northcote - Office clean | JP0140 | office clean | J1191 | Property + service | 1
T0159 | Northcote - Office clean | JP0141 | office clean | J1192 | Property + service | 1
T0160 | Thornbury - Office clean | JP0142 | office clean | J1193 | Property + service | 1
T0161 | Epping - Kitchen and bathrooms | JP0143 | kitchen and bathrooms | J1194 | Property + service | 1
T0162 | Bundoora - Kitchen and bathrooms | JP0144 | kitchen and bathrooms | J1195 | Property + service | 1
T0163 | Bundoora kitchen and bathrooms (copy) | JP0144 | kitchen and bathrooms | J1195 | Property + service | 1
T0164 | Maribyrnong - Office clean | JP0145 | office clean | J1196 | Property + service | 1
T0165 | Maribyrnong - Window clean | JP0145 | window clean | J1197 | Property + service | 1
T0166 | Ringwood - Office clean | JP0146 | office clean | J1198 | Property + service | 1
T0167 | Glen Waverley - Kitchen and bathrooms | JP0147 | kitchen and bathrooms | J1199 | Property + service | 1
T0168 | Werribee - Kitchen and bathrooms | JP0148 | kitchen and bathrooms | J1200 | Property + service | 1
T0169 | Footscray - Office clean | JP0149 | office clean | J1201 | Property + service | 1
T0170 | Footscray - Carpet steam clean | JP0149 | carpet steam clean | J1202 | Property + service | 1
T0171 | Hawthorn - Office clean | JP0150 | office clean | J1203 | Property + service | 1
T0172 | Coburg - Office clean | JP0152 | office clean | J1205 | Property + service | 1
T0173 | Reservoir - Window clean | JP0153 | window clean | J1208 | Property + service | 1
T0174 | Camberwell - Office clean | JP0154 | office clean | J1209 | Property + service | 1
T0175 | Glen Waverley - Office clean | JP0155 | office clean | J1210 | Property + service | 1
T0176 | Glen Waverley - Carpet steam clean | JP0155 | carpet steam clean | J1211 | Property + service | 1
T0177 | Glen Waverley - Office clean | JP0156 | office clean | J1212 | Property + service | 1
T0178 | Brighton - Office clean | JP0158 | office clean | J1214 | Property + service | 1
T0179 | Camberwell - Office clean | JP0159 | office clean | J1215 | Property + service | 1
T0180 | Hawthorn - Office clean | JP0160 | office clean | J1216 | Property + service | 1
T0181 | Kew - Office clean | JP0161 | office clean | J1217 | Property + service | 1
T0182 | Williamstown - Office clean | JP0162 | office clean | J1218 | Property + service + amount | 1
T0183 | Cheltenham - Office clean | JP0163 | office clean | J1219 | Property + service | 1
T0184 | Oakleigh - Office clean | JP0164 | office clean | J1221 | Property + service | 1
T0185 | Moorabbin - Office clean | JP0165 | office clean | J1222 | Property + service | 1
T0186 | Moorabbin - Carpet steam clean | JP0165 | carpet steam clean | J1223 | Property + service | 1
T0187 | Mentone - Office clean | JP0167 | office clean | J1225 | Property + service | 1
T0188 | Northcote - Office clean | JP0168 | office clean | J1226 | Property + service + amount | 1
T0189 | Brunswick - Kitchen and bathrooms | JP0169 | kitchen and bathrooms | J1227 | Property + service | 1
T0190 | Brunswick - Window clean | JP0169 | window clean | J1228 | Property + service | 1
T0191 | Frankston - Kitchen and bathrooms | JP0170 | kitchen and bathrooms | J1229 | Property + service | 1
T0192 | Bentleigh - Office clean | JP0171 | office clean | J1230 | Property + service | 1
T0193 | Bentleigh - Carpet steam clean | JP0171 | carpet steam clean | J1231 | Property + service | 1
T0194 | Brunswick - Office clean | JP0172 | office clean | J1232 | Property + service | 1
T0195 | Hawthorn - Office clean | JP0173 | office clean | J1233 | Property + service | 1
T0196 | Altona - Kitchen and bathrooms | JP0174 | kitchen and bathrooms | J1234 | Property + service | 1
T0197 | Deer Park - Office clean | JP0175 | office clean | J1235 | Property + service | 1
T0198 | Reservoir - Kitchen and bathrooms | JP0176 | kitchen and bathrooms | J1236 | Property + service | 1
T0199 | Brunswick - Office clean | JP0177 | office clean | J1238 | Property + service + amount | 1
T0200 | Preston - Office clean | JP0178 | office clean | J1239 | Property + service | 1
T0201 | Mitcham - Window clean | JP0179 | window clean | J1241 | Property + service | 1
T0202 | Mitcham - Washroom service | JP0179 | washroom service | J1242 | Property + service | 1
T0203 | Yarraville - Office clean | JP0180 | office clean | J1243 | Property + service | 1
T0204 | Footscray - Office clean | JP0182 | office clean | J1245 | Property + service | 1
T0205 | Laverton - Office clean | JP0185 | office clean | J1248 | Property + service | 1
T0206 | Laverton - Window clean | JP0185 | window clean | J1249 | Property + service | 1
T0207 | Brighton - Office clean | JP0186 | office clean | J1250 | Property + service | 1
T0208 | Yarraville - Kitchen and bathrooms | JP0187 | kitchen and bathrooms | J1251 | Property + service | 1
T0209 | Bentleigh - Kitchen and bathrooms | JP0189 | kitchen and bathrooms | J1254 | Property + service | 1
T0210 | Bentleigh - Office clean | JP0190 | office clean | J1255 | Property + service | 1
T0211 | Hawthorn - Office clean | JP0191 | office clean | J1256 | Property + service + amount | 1
T0212 | Glen Waverley - Office clean | JP0193 | office clean | J1258 | Property + service | 1
T0213 | Glen Waverley - Window clean | JP0193 | window clean | J1259 | Property + service | 1
T0214 | Epping - Office clean | JP0195 | office clean | J1262 | Property + service | 1
T0215 | Mitcham - Office clean | JP0196 | office clean | J1263 | Property + service | 1
T0216 | Kew - Office clean | JP0197 | office clean | J1264 | Property + service | 1
T0217 | Blackburn - Office clean | JP0199 | office clean | J1266 | Property + service | 1
T0218 | Blackburn - Window clean | JP0199 | window clean | J1267 | Property + service | 1
T0219 | Sunshine - Carpet steam clean | JP0200 | carpet steam clean | J1269 | Property + service | 1
T0220 | Maribyrnong - Kitchen and bathrooms | JP0201 | kitchen and bathrooms | J1270 | Property + service | 1
T0221 | Moorabbin - Office clean | JP0203 | office clean | J1272 | Property + service | 1
T0222 | Moorabbin - Window clean | JP0203 | window clean | J1273 | Property + service | 1
T0223 | Box Hill - Office clean | JP0204 | office clean | J1274 | Property + service | 1
T0224 | Frankston - Office clean | JP0206 | office clean | J1276 | Property + service | 1
T0225 | Preston - Office clean | JP0207 | office clean | J1277 | Property + service | 1
T0226 | Burwood - Office clean | JP0210 | office clean | J1280 | Property + service | 1
T0227 | Burwood office clean (copy) | JP0210 | office clean | J1280 | Property + service | 1
T0228 | Maribyrnong - Office clean | JP0211 | office clean | J1281 | Property + service | 1
T0229 | Maribyrnong - Window clean | JP0211 | window clean | J1282 | Property + service | 1
T0230 | Ringwood - Office clean | JP0212 | office clean | J1283 | Property + service | 1
T0231 | Ringwood - Window clean | JP0212 | window clean | J1284 | Property + service | 1
T0232 | Burwood - Office clean | JP0214 | office clean | J1286 | Property + service | 1
T0233 | Brighton - Office clean | JP0215 | office clean | J1287 | Property + service | 1
T0234 | Box Hill - Kitchen and bathrooms | JP0216 | kitchen and bathrooms | J1288 | Property + service | 1
T0235 | Box Hill kitchen and bathrooms (copy) | JP0216 | kitchen and bathrooms | J1288 | Property + service | 1
T0236 | Glen Waverley - Window clean | JP0217 | window clean | J1290 | Property + service | 1
T0237 | Glen Waverley - Washroom service | JP0217 | washroom service | J1291 | Property + service | 1
T0238 | Mentone - Office clean | JP0218 | office clean | J1292 | Property + service | 1
T0239 | Mentone - Window clean | JP0218 | window clean | J1293 | Property + service | 1
T0240 | Cheltenham - Office clean | JP0219 | office clean | J1294 | Property + service + amount | 1
T0241 | Cheltenham - Washroom service | JP0219 | washroom service | J1295 | Property + service | 1
T0242 | Oakleigh - Office clean | JP0220 | office clean | J1296 | Property + service | 1
T0243 | Brighton - Office clean | JP0222 | office clean | J1298 | Property + service | 1
T0244 | Point Cook - Office clean | JP0224 | office clean | J1300 | Property + service | 1
T0245 | Altona - Window clean | JP0227 | window clean | J1304 | Property + service | 1
T0246 | Hawthorn - Office clean | JP0228 | office clean | J1305 | Property + service | 1
T0247 | Hawthorn - Window clean | JP0228 | window clean | J1306 | Property + service | 1
T0248 | Hawthorn - Washroom service | JP0228 | washroom service | J1307 | Property + service | 1
T0249 | Maribyrnong - Carpet steam clean | JP0229 | carpet steam clean | J1309 | Property + service | 1
T0250 | Maribyrnong carpet steam clean (copy) | JP0229 | carpet steam clean | J1309 | Property + service | 1
T0251 | Maribyrnong - Washroom service | JP0229 | washroom service | J1310 | Property + service | 1
T0252 | Bundoora - Office clean | JP0230 | office clean | J1311 | Property + service | 1
T0253 | Werribee - Kitchen and bathrooms | JP0231 | kitchen and bathrooms | J1312 | Property + service | 1
T0254 | Mitcham - Kitchen and bathrooms | JP0233 | kitchen and bathrooms | J1314 | Property + service | 1
T0255 | Reservoir - Washroom service | JP0234 | washroom service | J1316 | Property + service | 1
T0256 | Burwood - Office clean | JP0235 | office clean | J1317 | Property + service | 1
T0257 | Burwood - Window clean | JP0235 | window clean | J1318 | Property + service | 1
T0258 | Bentleigh - Office clean | JP0237 | office clean | J1320 | Property + service | 1
T0259 | Bentleigh - Carpet steam clean | JP0237 | carpet steam clean | J1321 | Property + service | 1
T0260 | St Kilda - Office clean | JP0238 | office clean | J1322 | Property + service | 1
T0261 | Northcote - Office clean | JP0239 | office clean | J1323 | Property + service | 1
T0262 | Glen Waverley - Office clean | JP0240 | office clean | J1324 | Property + service | 1
T0263 | Clayton - Office clean | JP0241 | office clean | J1325 | Property + service | 1
T0264 | Coburg - Office clean | JP0242 | office clean | J1326 | Property + service | 1
T0265 | Moorabbin - Office clean | JP0244 | office clean | J1328 | Property + service | 1
T0266 | Moorabbin - Window clean | JP0244 | window clean | J1329 | Property + service | 1
T0267 | Mentone - Office clean | JP0245 | office clean | J1330 | Property + service | 1
T0268 | Mentone - Washroom service | JP0245 | washroom service | J1331 | Property + service | 1
T0269 | Point Cook - Office clean | JP0246 | office clean | J1332 | Property + service | 1
T0270 | Brighton - Kitchen and bathrooms | JP0247 | kitchen and bathrooms | J1333 | Property + service | 1
T0271 | Werribee - Office clean | JP0248 | office clean | J1334 | Property + service | 1
T0272 | Point Cook - Office clean | JP0249 | office clean | J1335 | Property + service | 1
T0273 | Point Cook - Window clean | JP0249 | window clean | J1336 | Property + service | 1
T0274 | Essendon - Office clean | JP0250 | office clean | J1337 | Property + service | 1
T0275 | Kew - Office clean | JP0251 | office clean | J1338 | Property + service | 1
T0276 | Maribyrnong - Office clean | JP0252 | office clean | J1339 | Property + service | 1
T0277 | Coburg - Office clean | JP0205 | office clean | J1340 | Property + service + amount | 1
T0278 | Werribee - Office clean | JP0148 | office clean | J1341 | Property + service | 1
T0279 | St Kilda - Office clean | JP0120 | office clean | J1342 | Property + service + amount | 1
T0280 | Altona - Office clean | JP0174 | office clean | J1343 | Property + service | 1
T0281 | Bentleigh - Office clean | JP0001 | office clean | J1344 | Property + service + amount | 1
T0282 | Northcote - Office clean | JP0168 | office clean | J1345 | Property + service + amount | 1
T0283 | Epping - Office clean | JP0143 | office clean | J1346 | Property + service | 1
T0284 | Mitcham - Consumables supply | JP0014 | paper towel, soap and bin liners | (none) | Not in Jobber | 0
T0285 | Clayton - Consumables supply | JP0241 | paper towel, soap and bin liners | (none) | Not in Jobber | 0
T0286 | Bentleigh - Consumables supply | JP0190 | paper towel, soap and bin liners | (none) | Not in Jobber | 0
T0287 | Hawthorn - Consumables supply | JP0160 | paper towel, soap and bin liners | (none) | Not in Jobber | 0
T0288 | Footscray - Consumables supply | JP0117 | paper towel, soap and bin liners | (none) | Not in Jobber | 0
T0289 | Hawthorn - Consumables supply | JP0060 | paper towel, soap and bin liners | (none) | Not in Jobber | 0

## Rate Reconciliation
Rate reconciliation: Jobber job vs QBO recurring templates (status by formula)
Work sample: realistic data, built to show how I approach this work.
Job | Client | Location | Service | Frequency | Visits/wk | Rate | Jobber status | Invoicing | QBO templates | Jobber monthly | Active templates | QBO monthly | Difference | Status | Engine status | Next action | Owner | Wave | Sign-off
J1001 | Oakwood Vet Clinic | 218 High Road, Bentleigh | Office clean | Weekly | 1 | 127 | Active | Auto |  | 550.33 | 0 | 0 | -550.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1002 | Oakwood Vet Clinic | 162 Station Parade, Oakleigh | Kitchen and bathrooms | Weekly | 1 | 58 | Active | Outside Jobber | T0001 | 251.33 | 1 | 251.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1003 | Oakwood Vet Clinic | 162 Station Parade, Oakleigh | Window clean | Every 4 weeks | 0 | 218 | Active | Auto |  | 218 | 0 | 0 | -218 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1004 | Clearwater Dental Pty Ltd | 273 Albert Road, Deer Park | Kitchen and bathrooms | Weekly | 1 | 71 | Active | Outside Jobber | T0002 | 307.67 | 1 | 284 | -23.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 4 West
J1005 | Riverside Insurance Brokers Pty Ltd | 59 Station Parade, Bundoora | Kitchen and bathrooms | Weekly | 2 | 70 | Active | Auto |  | 606.67 | 0 | 0 | -606.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1006 | Riverside Insurance Brokers Pty Ltd | 59 Station Parade, Bundoora | Window clean | Every 4 weeks | 0 | 156 | Active | Outside Jobber | T0003 | 156 | 1 | 156 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1007 | Ironbark Pathology Pty Ltd | 224 Ballarat Parade, Footscray | Kitchen and bathrooms | Weekly | 2 | 69 | Active | Outside Jobber | T0004 | 598 | 1 | 598 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1008 | Westend Fitness Pty Ltd | 77 Ballarat Parade, Brighton | Office clean | Weekly | 3 | 161 | Active | Outside Jobber | T0005 | 2093 | 1 | 2093 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1009 | Redgum Dental | 290A Ballarat Highway, Bundoora | Office clean | Weekly | 2 | 131 | Active | Outside Jobber | T0006 | 1135.33 | 1 | 1135.33 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1010 | Redgum Dental | 359 Glenferrie Avenue, Werribee | Office clean | Weekly | 2 | 204 | Active | Outside Jobber | T0007 | 1768 | 1 | 1768 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1011 | Elm Street Physiotherapy | 315 Park Parade, Oakleigh | Office clean | Weekly | 1 | 64 | Active | Outside Jobber | T0008 | 277.33 | 1 | 277.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1012 | Elm Street Physiotherapy | 359 Albert Street, Point Cook | Office clean | Weekly | 2 | 73 | Active | Auto |  | 632.67 | 0 | 0 | -632.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1013 | Elm Street Physiotherapy | 359 Albert Street, Point Cook | Washroom service | Monthly | 0 | 99 | Active | Auto |  | 99 | 0 | 0 | -99 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1014 | Wattle Grove Property Group | 169 King Street, Hawthorn | Office clean | Weekly | 2 | 68 | Active | Auto |  | 589.33 | 0 | 0 | -589.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1015 | Wattle Grove Property Group | 169 King Street, Hawthorn | Washroom service | Monthly | 0 | 88 | Active | Outside Jobber | T0009 | 88 | 1 | 88 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1016 | Hillcrest Physiotherapy Pty Ltd | 396 Park Highway, Epping | Kitchen and bathrooms | Weekly | 5 | 64 | Active | Outside Jobber | T0010 | 1386.67 | 1 | 1386.67 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1017 | Hillcrest Physiotherapy Pty Ltd | 214A Nepean Parade, Thornbury | Office clean | Weekly | 2 | 96 | Active | Outside Jobber | T0011 | 832 | 1 | 832 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1018 | Kingsley Real Estate | 208 Main Avenue, Mitcham | Office clean | Weekly | 1 | 90 | Active | Outside Jobber | T0012 | 390 | 1 | 390 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1019 | Kingsley Real Estate | 208 High Avenue, Kew | Office clean | Weekly | 1 | 102 | Active | Outside Jobber | T0013 | 442 | 1 | 442 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1020 | Wattle Grove Medical Centre Pty Ltd | 462 Mason Road, Clayton | Office clean | Weekly | 1 | 186 | Active | Auto |  | 806 | 0 | 0 | -806 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1021 | Bluestone Engineering | 201 Plenty Avenue, Coburg | Office clean | Weekly | 2 | 156 | Active | Outside Jobber | T0014 | 1352 | 1 | 1352 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1022 | Clearwater Insurance Brokers Pty Ltd | 164 Whitehorse Street, Mentone | Office clean | Weekly | 3 | 63 | Active | Outside Jobber | T0015 | 819 | 1 | 819 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1023 | Redgum Optometrists Pty Ltd | 480 King Avenue, Camberwell | Office clean | Weekly | 2 | 151 | Active | Outside Jobber | T0016 | 1308.67 | 1 | 1256.67 | -52 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1024 | Redgum Optometrists Pty Ltd | 480 King Avenue, Camberwell | Carpet steam clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0017 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1025 | Northside Accountants Pty Ltd | 426 Mason Street, Cheltenham | Kitchen and bathrooms | Weekly | 2 | 35 | Active | Outside Jobber | T0018 | 303.33 | 1 | 303.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1026 | Northside Accountants Pty Ltd | 426 Mason Street, Cheltenham | Window clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0019 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1027 | Northside Accountants Pty Ltd | 351 Burke Road, Oakleigh | Office clean | Weekly | 3 | 122 | Active | Outside Jobber | T0020 | 1586 | 1 | 1464 | -122 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1028 | Northside Accountants Pty Ltd | 354 High Street, Clayton | Kitchen and bathrooms | Weekly | 2 | 62 | Active | Outside Jobber | T0021 | 537.33 | 1 | 537.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1029 | Oakwood Accountants Pty Ltd | 54 Mason Parade, Reservoir | Office clean | Weekly | 1 | 102 | Active | Outside Jobber | T0022 | 442 | 1 | 442 | 0 | Matched | Matched | Move as is | Office | Pilot
J1030 | Northside Engineering Pty Ltd | 430 Victoria Road, St Kilda | Office clean | Weekly | 2 | 102 | Active | Outside Jobber | T0023 | 884 | 1 | 884 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1031 | Northside Engineering Pty Ltd | 195/12 Railway Highway, Bentleigh | Office clean | Weekly | 2 | 93 | Active | Auto | T0024 | 806 | 1 | 806 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 3 South
J1032 | Northside Engineering Pty Ltd | 195/12 Railway Highway, Bentleigh | Carpet steam clean | Every 4 weeks | 0 | 234 | Active | Auto |  | 234 | 0 | 0 | -234 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1033 | Northside Engineering Pty Ltd | 10 Queen Highway, Deer Park | Office clean | Weekly | 5 | 187 | Active | Outside Jobber | T0025 | 4051.67 | 1 | 4051.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1034 | Northside Engineering Pty Ltd | 17 Park Avenue, St Kilda | Kitchen and bathrooms | Weekly | 2 | 70 | Active | Outside Jobber | T0026 | 606.67 | 1 | 560 | -46.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1035 | Ashwood Early Learning | 378 Plenty Street, Camberwell | Office clean | Weekly | 3 | 70 | Active | Outside Jobber |  | 910 | 0 | 0 | -910 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 2 East
J1036 | Ashwood Early Learning | 378 Plenty Street, Camberwell | Window clean | Every 4 weeks | 0 | 203 | Active | Auto | T0027 | 203 | 1 | 203 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1037 | Silverton Pharmacy | 266 Union Avenue, Point Cook | Office clean | Weekly | 1 | 66 | Active | Outside Jobber | T0028 | 286 | 1 | 286 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1038 | Silverton Pharmacy | 98 Park Road, Kew | Office clean | Weekly | 1 | 69 | Active | Auto |  | 299 | 0 | 0 | -299 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1039 | Silverton Pharmacy | 107 Barkly Highway, Bundoora | Office clean | Weekly | 1 | 187 | Active | Outside Jobber | T0029 | 810.33 | 1 | 748 | -62.33 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 1 North
J1040 | Silverton Pharmacy | 298 Main Road, Footscray | Office clean | Weekly | 2 | 97 | Active | Outside Jobber | T0030 | 840.67 | 1 | 840.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1041 | Silverton Pharmacy | 298 Main Road, Footscray | Carpet steam clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0031 | 135 | 1 | 135 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1042 | Brightside Podiatry | 142 Plenty Road, Camberwell | Kitchen and bathrooms | Weekly | 1 | 32 | Active | Outside Jobber | T0032 | 138.67 | 1 | 138.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1043 | Ashwood Optometrists | 195 Nicholson Road, Ringwood | Office clean | Weekly | 2 | 125 | Active | Auto |  | 1083.33 | 0 | 0 | -1083.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1044 | Ashwood Optometrists | 195 Nicholson Road, Ringwood | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0033 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1045 | Ashwood Optometrists | 245 Ballarat Avenue, Ringwood | Kitchen and bathrooms | Weekly | 1 | 40 | Active | Auto |  | 173.33 | 0 | 0 | -173.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1046 | Ashwood Optometrists | 245 Ballarat Avenue, Ringwood | Washroom service | Monthly | 0 | 125 | Active | Outside Jobber | T0034 | 125 | 1 | 125 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1047 | Parkside Accountants | 22 Hopkins Road, Bundoora | Kitchen and bathrooms | Weekly | 2 | 30 | Active | Outside Jobber | T0035 | 260 | 1 | 260 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1048 | Parkside Accountants | 356 Albert Avenue, Northcote | Office clean | Weekly | 1 | 193 | Active | Outside Jobber | T0036 | 836.33 | 1 | 836.33 | 0 | Matched | Matched | Move as is | Office | Pilot
J1049 | Parkside Accountants | 356 Albert Avenue, Northcote | Carpet steam clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0037 | 135 | 1 | 130 | -5 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 1 North
J1050 | Brightside Motors Pty Ltd | 364/12 High Road, Heidelberg | Office clean | Weekly | 1 | 101 | Active | Auto |  | 437.67 | 0 | 0 | -437.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1051 | Westend Motors Pty Ltd | 417 Main Road, Sunshine | Office clean | Weekly | 3 | 71 | Active | Outside Jobber | T0038 | 923 | 1 | 923 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1052 | Westend Motors Pty Ltd | 37 Nicholson Highway, Williamstown | Office clean | Weekly | 2 | 185 | Active | Outside Jobber | T0039 | 1603.33 | 1 | 1542.67 | -60.66 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1053 | Westend Motors Pty Ltd | 117 Railway Highway, Epping | Office clean | Weekly | 1 | 161 | Active | Outside Jobber | T0040 | 697.67 | 1 | 697.67 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1054 | Oakwood Lawyers Pty Ltd | 453 Plenty Parade, Moorabbin | Office clean | Weekly | 1 | 116 | Active | Auto |  | 502.67 | 0 | 0 | -502.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1055 | Oakwood Lawyers Pty Ltd | 188 Nicholson Road, Essendon | Office clean | Weekly | 2 | 204 | Active | Outside Jobber | T0041 | 1768 | 1 | 1768 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1056 | Riverside Medical Centre | 300 Sydney Highway, Camberwell | Office clean | Weekly | 1 | 90 | Active | Auto |  | 390 | 0 | 0 | -390 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1057 | Riverside Motors Pty Ltd | 205 Railway Street, Altona | Office clean | Weekly | 1 | 121 | Active | Outside Jobber | T0042 | 524.33 | 1 | 524.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1058 | Parkside Pathology Pty Ltd | 359 King Road, Yarraville | Office clean | Weekly | 3 | 75 | Active | Outside Jobber | T0043 | 975 | 1 | 975 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1059 | Sunbury Accountants Pty Ltd | 313A Queen Street, Camberwell | Office clean | Weekly | 2 | 135 | Active | Outside Jobber |  | 1170 | 0 | 0 | -1170 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 2 East
J1060 | Sunbury Early Learning | 386 Nepean Road, Glen Waverley | Office clean | Weekly | 2 | 185 | Active | Outside Jobber | T0044 | 1603.33 | 1 | 1542.67 | -60.66 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1061 | Silverton Lawyers Pty Ltd | 255 Glenferrie Parade, Thornbury | Office clean | Weekly | 2 | 127 | Active | Auto |  | 1100.67 | 0 | 0 | -1100.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1062 | Waverley Accountants Pty Ltd | 23A Ballarat Street, Brunswick | Office clean | Weekly | 5 | 116 | Active | Auto |  | 2513.33 | 0 | 0 | -2513.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1063 | Waverley Accountants Pty Ltd | 23A Ballarat Street, Brunswick | Window clean | Every 4 weeks | 0 | 218 | Active | Auto |  | 218 | 0 | 0 | -218 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1064 | Westend Podiatry | 310 Ballarat Avenue, Brunswick | Office clean | Weekly | 2 | 156 | Active | Outside Jobber | T0045 | 1352 | 1 | 1352 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1065 | Westend Podiatry | 310 Ballarat Avenue, Brunswick | Carpet steam clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0046 | 135 | 1 | 130 | -5 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 1 North
J1066 | Westend Podiatry | 269 Victoria Avenue, Thornbury | Office clean | Weekly | 3 | 161 | Active | Outside Jobber | T0047 | 2093 | 1 | 2093 | 0 | Matched | Matched | Move as is | Office | Pilot
J1067 | Westend Podiatry | 269 Victoria Avenue, Thornbury | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0048 | 116 | 1 | 116 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1068 | Westend Podiatry | 332A Glenferrie Parade, Essendon | Office clean | Weekly | 1 | 151 | Active | Outside Jobber | T0049 | 654.33 | 1 | 654.33 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1069 | Lakeside Engineering Pty Ltd | 157 Whitehorse Parade, Deer Park | Office clean | Weekly | 3 | 69 | Active | Outside Jobber | T0050 | 897 | 1 | 897 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1070 | Lakeside Engineering Pty Ltd | 439 Sydney Parade, Maribyrnong | Kitchen and bathrooms | Weekly | 2 | 69 | Active | Outside Jobber | T0051 | 598 | 1 | 598 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1071 | Kingsley Financial Planning | 204 Bridge Highway, Oakleigh | Office clean | Weekly | 1 | 181 | Active | Outside Jobber | T0052 T0053 | 784.33 | 2 | 1568.66 | 784.33 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 3 South
J1072 | Wattle Grove Physiotherapy | 48 Ballarat Parade, Cheltenham | Office clean | Weekly | 1 | 134 | Active | Outside Jobber | T0054 | 580.67 | 1 | 580.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1073 | Elm Street Fitness Pty Ltd | 479 Mason Parade, Hawthorn | Kitchen and bathrooms | Weekly | 1 | 63 | Active | Outside Jobber | T0055 | 273 | 1 | 273 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1074 | Elm Street Fitness Pty Ltd | 479 Mason Parade, Hawthorn | Window clean | Every 4 weeks | 0 | 218 | Active | Auto |  | 218 | 0 | 0 | -218 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1075 | Elm Street Fitness Pty Ltd | 450 King Road, Doncaster | Kitchen and bathrooms | Weekly | 2 | 37 | Active | Auto |  | 320.67 | 0 | 0 | -320.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1076 | Elm Street Fitness Pty Ltd | 450 King Road, Doncaster | Window clean | Every 4 weeks | 0 | 102 | Active | Outside Jobber | T0056 | 102 | 1 | 102 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1077 | Wattle Grove Dental | 259 Union Avenue, Hawthorn | Office clean | Weekly | 3 | 125 | Active | Outside Jobber |  | 1625 | 0 | 0 | -1625 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 2 East
J1078 | Lakeside Vet Clinic | 426 Ballarat Parade, Point Cook | Office clean | Weekly | 1 | 63 | Active | Outside Jobber | T0057 | 273 | 1 | 273 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1079 | Lakeside Vet Clinic | 164 Nicholson Street, Laverton | Office clean | Weekly | 1 | 66 | Active | Outside Jobber | T0058 | 286 | 1 | 286 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1080 | Lakeside Vet Clinic | 164 Nicholson Street, Laverton | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0059 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1081 | Clearwater Property Group Pty Ltd | 143/12 Nepean Street, Frankston | Office clean | Weekly | 3 | 130 | Active | Outside Jobber | T0060 T0061 | 1690 | 2 | 3380 | 1690 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 3 South
J1082 | Clearwater Property Group Pty Ltd | 143/12 Nepean Street, Frankston | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0062 | 151 | 1 | 151 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1083 | Clearwater Property Group Pty Ltd | 380 Nepean Parade, Laverton | Office clean | Weekly | 5 | 75 | Active | Outside Jobber | T0063 | 1625 | 1 | 1625 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1084 | Clearwater Property Group Pty Ltd | 380 Nepean Parade, Laverton | Window clean | Every 4 weeks | 0 | 234 | Active | Auto |  | 234 | 0 | 0 | -234 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1085 | Eastwood Real Estate Pty Ltd | 296 Barkly Highway, Hawthorn | Office clean | Weekly | 2 | 193 | Active | Outside Jobber | T0064 | 1672.67 | 1 | 1672.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1086 | Eastwood Real Estate Pty Ltd | 296 Barkly Highway, Hawthorn | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0065 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1087 | Eastwood Real Estate Pty Ltd | 296 Barkly Highway, Hawthorn | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0066 | 151 | 1 | 145 | -6 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1088 | Clearwater Physiotherapy | 46 Main Avenue, Bentleigh | Kitchen and bathrooms | Weekly | 1 | 69 | Active | Auto |  | 299 | 0 | 0 | -299 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1089 | Clearwater Physiotherapy | 46 Main Avenue, Bentleigh | Carpet steam clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0067 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1090 | Clearwater Physiotherapy | 46 Main Avenue, Bentleigh | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0068 | 151 | 1 | 151 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1091 | Clearwater Physiotherapy | 211 Union Road, Burwood | Kitchen and bathrooms | Weekly | 2 | 60 | Active | Outside Jobber | T0069 | 520 | 1 | 520 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1092 | Greenway Physiotherapy | 418 Nicholson Avenue, Burwood | Office clean | Weekly | 1 | 204 | Active | Outside Jobber | T0070 | 884 | 1 | 884 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1093 | Fairfield Engineering Pty Ltd | 43 Plenty Avenue, Bentleigh | Office clean | Weekly | 1 | 129 | Active | Outside Jobber | T0071 | 559 | 1 | 559 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1094 | Fairfield Engineering Pty Ltd | 27 Railway Avenue, Cheltenham | Office clean | Weekly | 2 | 93 | Active | Outside Jobber | T0072 | 806 | 1 | 806 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1095 | Fairfield Engineering Pty Ltd | 27 Railway Avenue, Cheltenham | Window clean | Every 4 weeks | 0 | 102 | Active | Outside Jobber | T0073 | 102 | 1 | 102 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1096 | Westend Optometrists Pty Ltd | 225/12 Glenferrie Parade, Mentone | Office clean | Weekly | 3 | 135 | Active | Outside Jobber | T0074 | 1755 | 1 | 1755 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1097 | Kingsley Insurance Brokers | 225 Park Avenue, Reservoir | Office clean | Weekly | 2 | 198 | Active | Auto | T0075 | 1716 | 1 | 1716 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 1 North
J1098 | Kingsley Insurance Brokers | 225 Park Avenue, Reservoir | Carpet steam clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0076 | 116 | 1 | 112 | -4 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 1 North
J1099 | Kingsley Insurance Brokers | 225 Park Avenue, Reservoir | Washroom service | Monthly | 0 | 125 | Active | Outside Jobber | T0077 | 125 | 1 | 125 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1100 | Kingsley Insurance Brokers | 410 Burke Highway, Point Cook | Office clean | Weekly | 2 | 116 | Active | Outside Jobber | T0078 | 1005.33 | 1 | 1005.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1101 | Kingsley Insurance Brokers | 410 Burke Highway, Point Cook | Window clean | Every 4 weeks | 0 | 218 | Active | Auto |  | 218 | 0 | 0 | -218 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1102 | Bluestone Learning Centre Pty Ltd | 205 Burke Highway, Glen Waverley | Office clean | Weekly | 2 | 101 | Active | Auto |  | 875.33 | 0 | 0 | -875.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1103 | Bluestone Learning Centre Pty Ltd | 205 Burke Highway, Glen Waverley | Washroom service | Monthly | 0 | 88 | Active | Outside Jobber | T0079 | 88 | 1 | 85 | -3 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1104 | Oakwood Logistics | 189 Union Highway, Hawthorn | Office clean | Weekly | 2 | 58 | Active | Outside Jobber | T0080 | 502.67 | 1 | 464 | -38.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 2 East
J1105 | Oakwood Logistics | 189 Union Highway, Hawthorn | Carpet steam clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0081 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1106 | Oakwood Logistics | 128 Victoria Road, Blackburn | Kitchen and bathrooms | Weekly | 3 | 42 | Active | Auto |  | 546 | 0 | 0 | -546 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1107 | Oakwood Logistics | 375 Station Highway, Cheltenham | Office clean | Weekly | 5 | 122 | Active | Outside Jobber | T0082 | 2643.33 | 1 | 2440 | -203.33 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1108 | Oakwood Logistics | 375 Station Highway, Cheltenham | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0083 | 116 | 1 | 116 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1109 | Oakwood Logistics | 378 Burke Highway, Box Hill | Office clean | Weekly | 2 | 70 | Active | Outside Jobber | T0084 | 606.67 | 1 | 606.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1110 | Banksia Insurance Brokers | 185 Church Parade, Burwood | Office clean | Weekly | 5 | 98 | Active | Outside Jobber | T0085 | 2123.33 | 1 | 2123.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1111 | Banksia Insurance Brokers | 185 Church Parade, Burwood | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0086 | 109 | 1 | 105 | -4 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1112 | Sunbury Lawyers Pty Ltd | 115 Nepean Parade, Reservoir | Kitchen and bathrooms | Weekly | 1 | 30 | Active | Outside Jobber | T0087 | 130 | 1 | 130 | 0 | Matched | Matched | Move as is | Office | Pilot
J1113 | Sunbury Lawyers Pty Ltd | 96A Glenferrie Parade, Essendon | Office clean | Weekly | 2 | 94 | Active | Auto |  | 814.67 | 0 | 0 | -814.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1114 | Sunbury Lawyers Pty Ltd | 96A Glenferrie Parade, Essendon | Washroom service | Monthly | 0 | 125 | Active | Outside Jobber | T0088 | 125 | 1 | 125 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1115 | Sunbury Lawyers Pty Ltd | 158 Station Street, Mentone | Kitchen and bathrooms | Weekly | 1 | 75 | Active | Outside Jobber | T0089 | 325 | 1 | 325 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1116 | Cobblestone Real Estate Pty Ltd | 476 Sydney Highway, Frankston | Office clean | Weekly | 1 | 185 | Active | Outside Jobber | T0090 | 801.67 | 1 | 801.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1117 | Bayview Engineering Pty Ltd | 436/12 Nepean Highway, Sunshine | Office clean | Weekly | 2 | 127 | Active | Outside Jobber | T0091 | 1100.67 | 1 | 1100.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1118 | Oakwood Financial Planning Pty Ltd | 394 Ballarat Avenue, Brighton | Office clean | Weekly | 1 | 187 | Active | Outside Jobber | T0092 | 810.33 | 1 | 748 | -62.33 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1119 | Oakwood Financial Planning Pty Ltd | 394 Ballarat Avenue, Brighton | Carpet steam clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0093 | 116 | 1 | 116 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1120 | Brightside Dental Pty Ltd | 135 Victoria Parade, Dandenong | Office clean | Weekly | 1 | 116 | Active | Outside Jobber | T0094 | 502.67 | 1 | 502.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1121 | Brightside Dental Pty Ltd | 472 Barkly Parade, Moorabbin | Kitchen and bathrooms | Weekly | 1 | 32 | Active | Outside Jobber | T0095 | 138.67 | 1 | 134.33 | -4.34 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1122 | Ashwood Physiotherapy | 151 Nicholson Street, Point Cook | Kitchen and bathrooms | Weekly | 3 | 43 | Active | Outside Jobber | T0096 | 559 | 1 | 559 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1123 | Ashwood Physiotherapy | 151 Nicholson Street, Point Cook | Window clean | Every 4 weeks | 0 | 135 | Active | Auto |  | 135 | 0 | 0 | -135 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1124 | Ashwood Physiotherapy | 4A Gilbert Road, Camberwell | Office clean | Weekly | 1 | 134 | Active | Outside Jobber | T0097 | 580.67 | 1 | 580.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1125 | Ashwood Physiotherapy | 144 Burke Avenue, Coburg | Office clean | Weekly | 2 | 156 | Active | Outside Jobber | T0098 | 1352 | 1 | 1300 | -52 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 1 North
J1126 | Ashwood Physiotherapy | 144 Burke Avenue, Coburg | Window clean | Every 4 weeks | 0 | 116 | Active | Auto |  | 116 | 0 | 0 | -116 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1127 | Ashwood Physiotherapy | 182 King Avenue, Footscray | Office clean | Weekly | 2 | 161 | Active | Outside Jobber | T0099 | 1395.33 | 1 | 1395.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1128 | Bluestone Dental | 79/12 Glenferrie Parade, Camberwell | Kitchen and bathrooms | Weekly | 5 | 30 | Active | Outside Jobber | T0100 | 650 | 1 | 650 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1129 | Bluestone Dental | 401 Park Highway, Burwood | Office clean | Weekly | 1 | 127 | Active | Outside Jobber | T0101 | 550.33 | 1 | 550.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1130 | Bluestone Dental | 401 Park Highway, Burwood | Carpet steam clean | Every 4 weeks | 0 | 203 | Active | Outside Jobber | T0102 | 203 | 1 | 203 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1131 | Bluestone Dental | 401 Burke Street, Burwood | Office clean | Weekly | 2 | 68 | Active | Outside Jobber | T0103 | 589.33 | 1 | 589.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1132 | Bluestone Dental | 11 Hopkins Avenue, Ringwood | Office clean | Weekly | 2 | 131 | Active | Auto |  | 1135.33 | 0 | 0 | -1135.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1133 | Bluestone Dental | 11 Hopkins Avenue, Ringwood | Carpet steam clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0104 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1134 | Kingsley Accountants | 263 Nepean Highway, Altona | Office clean | Weekly | 1 | 58 | Active | Outside Jobber | T0105 | 251.33 | 1 | 251.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1135 | Clearwater Early Learning Pty Ltd | 288 Main Highway, Northcote | Office clean | Weekly | 2 | 166 | Active | Outside Jobber | T0106 | 1438.67 | 1 | 1438.67 | 0 | Matched | Matched | Move as is | Office | Pilot
J1136 | Clearwater Early Learning Pty Ltd | 288 Main Highway, Northcote | Window clean | Every 4 weeks | 0 | 156 | Active | Outside Jobber | T0107 | 156 | 1 | 156 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1137 | Banksia Pathology Pty Ltd | 459 Park Avenue, Deer Park | Office clean | Weekly | 1 | 121 | Active | Outside Jobber | T0108 | 524.33 | 1 | 502.67 | -21.66 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1138 | Southgate Financial Planning Pty Ltd | 464 Barkly Road, Blackburn | Office clean | Weekly | 1 | 146 | Active | Outside Jobber | T0109 | 632.67 | 1 | 632.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1139 | Southgate Financial Planning Pty Ltd | 90A Albert Parade, Bentleigh | Office clean | Weekly | 2 | 135 | Active | Outside Jobber | T0110 | 1170 | 1 | 1170 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1140 | Bluestone Lawyers Pty Ltd | 29 Burke Parade, Burwood | Office clean | Weekly | 2 | 75 | Active | Auto | T0111 | 650 | 1 | 650 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1141 | Riverside Lawyers Pty Ltd | 23 Station Parade, Glen Waverley | Office clean | Weekly | 1 | 68 | Active | Outside Jobber | T0112 | 294.67 | 1 | 294.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1142 | Riverside Lawyers Pty Ltd | 23 Station Parade, Glen Waverley | Washroom service | Monthly | 0 | 99 | Active | Outside Jobber | T0113 | 99 | 1 | 99 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1143 | Banksia Accountants | 251 Union Avenue, Altona | Office clean | Weekly | 2 | 126 | Active | Auto | T0114 | 1092 | 1 | 1092 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 4 West
J1144 | Banksia Accountants | 270 Station Road, Doncaster | Office clean | Weekly | 1 | 156 | Active | Outside Jobber | T0115 | 676 | 1 | 676 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1145 | Banksia Accountants | 270 Station Road, Doncaster | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0116 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1146 | Banksia Accountants | 463 Gilbert Street, Glen Waverley | Kitchen and bathrooms | Weekly | 2 | 30 | Active | Outside Jobber | T0117 | 260 | 1 | 251.33 | -8.67 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1147 | Ironbark Physiotherapy Pty Ltd | 59 King Highway, Point Cook | Office clean | Weekly | 3 | 71 | Active | Outside Jobber | T0118 | 923 | 1 | 923 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1148 | Ironbark Physiotherapy Pty Ltd | 61 Church Street, Point Cook | Office clean | Weekly | 1 | 64 | Active | Outside Jobber | T0119 | 277.33 | 1 | 277.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1149 | Ironbark Physiotherapy Pty Ltd | 61 Church Street, Point Cook | Window clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0120 | 135 | 1 | 135 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1150 | Wattle Grove Lawyers Pty Ltd | 280 Railway Road, Point Cook | Kitchen and bathrooms | Weekly | 3 | 75 | Active | Outside Jobber | T0121 | 975 | 1 | 936 | -39 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1151 | Wattle Grove Lawyers Pty Ltd | 280 Railway Road, Point Cook | Window clean | Every 4 weeks | 0 | 203 | Active | Outside Jobber | T0122 | 203 | 1 | 203 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1152 | Kingsley Medical Centre Pty Ltd | 149 Main Road, Point Cook | Office clean | Weekly | 2 | 181 | Active | Outside Jobber | T0123 | 1568.67 | 1 | 1568.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1153 | Kingsley Medical Centre Pty Ltd | 149 Main Road, Point Cook | Washroom service | Monthly | 0 | 99 | Active | Outside Jobber | T0124 | 99 | 1 | 95 | -4 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1154 | Kingsley Medical Centre Pty Ltd | 313 King Road, Hawthorn | Office clean | Weekly | 1 | 101 | Active | Outside Jobber | T0125 | 437.67 | 1 | 437.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1155 | Ashwood Engineering | 155 Hopkins Road, Glen Waverley | Office clean | Weekly | 1 | 122 | Active | Outside Jobber | T0126 T0127 | 528.67 | 2 | 1057.34 | 528.67 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 2 East
J1156 | Sunbury Physiotherapy Pty Ltd | 284 Park Parade, Point Cook | Office clean | Weekly | 2 | 191 | Active | Outside Jobber | T0128 | 1655.33 | 1 | 1655.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1157 | Sunbury Physiotherapy Pty Ltd | 85 Nepean Road, Frankston | Office clean | Weekly | 3 | 146 | Active | Outside Jobber | T0129 | 1898 | 1 | 1752 | -146 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1158 | Sunbury Physiotherapy Pty Ltd | 231 Church Highway, Hawthorn | Office clean | Weekly | 5 | 58 | Active | Outside Jobber | T0130 | 1256.67 | 1 | 1213.33 | -43.34 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1159 | Eastwood Pathology | 223A Nicholson Parade, Werribee | Kitchen and bathrooms | Weekly | 2 | 32 | Active | Outside Jobber | T0131 | 277.33 | 1 | 277.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1160 | Eastwood Pathology | 223A Nicholson Parade, Werribee | Washroom service | Monthly | 0 | 88 | Active | Outside Jobber | T0132 | 88 | 1 | 85 | -3 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1161 | Waverley Fitness Pty Ltd | 382 Hopkins Street, Footscray | Office clean | Weekly | 1 | 62 | Active | Outside Jobber | T0133 | 268.67 | 1 | 268.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1162 | Waverley Fitness Pty Ltd | 443 Station Road, Footscray | Office clean | Weekly | 1 | 135 | Active | Outside Jobber | T0134 | 585 | 1 | 585 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1163 | Clearwater Logistics | 127 Main Highway, Reservoir | Office clean | Weekly | 1 | 62 | Active | Outside Jobber |  | 268.67 | 0 | 0 | -268.67 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 1 North
J1164 | Clearwater Logistics | 127 Main Highway, Reservoir | Carpet steam clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0135 | 146 | 1 | 146 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1165 | Wattle Grove Fitness | 68 Church Parade, Essendon | Kitchen and bathrooms | Weekly | 2 | 63 | Active | Outside Jobber |  | 546 | 0 | 0 | -546 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 1 North
J1166 | Wattle Grove Fitness | 102 Union Road, St Kilda | Office clean | Weekly | 2 | 166 | Active | Outside Jobber | T0136 | 1438.67 | 1 | 1438.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1167 | Ashwood Medical Centre | 61 Church Road, Bundoora | Kitchen and bathrooms | Weekly | 1 | 71 | Active | Outside Jobber | T0137 | 307.67 | 1 | 307.67 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1168 | Ashwood Medical Centre | 61 Church Road, Bundoora | Window clean | Every 4 weeks | 0 | 135 | Active | Auto |  | 135 | 0 | 0 | -135 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1169 | Parkside Vet Clinic | 287 Whitehorse Highway, Deer Park | Office clean | Weekly | 2 | 180 | Active | Outside Jobber | T0138 | 1560 | 1 | 1560 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1170 | Wattle Grove Architects | 289 Nepean Street, Bentleigh | Kitchen and bathrooms | Weekly | 1 | 58 | Active | Outside Jobber | T0139 | 251.33 | 1 | 251.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1171 | Bayview Pharmacy Pty Ltd | 221 Plenty Avenue, Footscray | Office clean | Weekly | 5 | 121 | Active | Outside Jobber | T0140 | 2621.67 | 1 | 2513.33 | -108.34 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1172 | Hillcrest Accountants | 77 Mason Highway, Mitcham | Kitchen and bathrooms | Weekly | 5 | 62 | Active | Auto | T0141 | 1343.33 | 1 | 1343.33 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1173 | Hillcrest Accountants | 77 Mason Highway, Mitcham | Carpet steam clean | Every 4 weeks | 0 | 116 | Active | Auto |  | 116 | 0 | 0 | -116 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1174 | Lakeside Architects | 170 Railway Highway, Reservoir | Office clean | Weekly | 2 | 93 | Active | Outside Jobber | T0142 | 806 | 1 | 806 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1175 | Lakeside Architects | 208 Glenferrie Road, Mitcham | Office clean | Weekly | 1 | 97 | Active | Outside Jobber | T0143 | 420.33 | 1 | 420.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1176 | Ashwood Accountants | 212 Sydney Avenue, Yarraville | Office clean | Weekly | 1 | 73 | Active | Outside Jobber | T0144 T0145 | 316.33 | 2 | 619.66 | 303.33 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 4 West
J1177 | Westend Property Group | 268 Sydney Road, Heidelberg | Kitchen and bathrooms | Weekly | 2 | 37 | Active | Outside Jobber | T0146 | 320.67 | 1 | 296 | -24.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 1 North
J1178 | Westend Property Group | 268 Sydney Road, Heidelberg | Carpet steam clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0147 | 135 | 1 | 135 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1179 | Eastwood Optometrists | 369 Station Road, Burwood | Office clean | Weekly | 1 | 122 | Active | Outside Jobber | T0148 | 528.67 | 1 | 488 | -40.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 2 East
J1180 | Eastwood Optometrists | 264 Queen Parade, Mitcham | Kitchen and bathrooms | Weekly | 5 | 70 | Active | Outside Jobber | T0149 | 1516.67 | 1 | 1516.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1181 | Westend Medical Centre | 130 Barkly Road, Sunshine | Office clean | Weekly | 2 | 102 | Active | Outside Jobber | T0150 | 884 | 1 | 884 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1182 | Riverside Learning Centre | 180 Union Avenue, Mentone | Office clean | Weekly | 1 | 151 | Active | Outside Jobber | T0151 | 654.33 | 1 | 654.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1183 | Riverside Learning Centre | 148 Plenty Street, Cheltenham | Office clean | Weekly | 2 | 125 | Active | Auto | T0152 | 1083.33 | 1 | 1083.33 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 3 South
J1184 | Riverside Learning Centre | 4A Main Highway, Moorabbin | Office clean | Weekly | 2 | 156 | Active | Outside Jobber | T0153 | 1352 | 1 | 1352 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1185 | Riverside Learning Centre | 4A Main Highway, Moorabbin | Window clean | Every 4 weeks | 0 | 146 | Active | Auto |  | 146 | 0 | 0 | -146 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1186 | Silverton Insurance Brokers Pty Ltd | 165 Hopkins Road, Cheltenham | Office clean | Weekly | 1 | 130 | Active | Outside Jobber | T0154 | 563.33 | 1 | 541.67 | -21.66 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1187 | Silverton Insurance Brokers Pty Ltd | 245 Victoria Road, Frankston | Office clean | Weekly | 2 | 63 | Active | Outside Jobber | T0155 | 546 | 1 | 546 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1188 | Silverton Insurance Brokers Pty Ltd | 274 Gilbert Avenue, Glen Waverley | Office clean | Weekly | 2 | 127 | Active | Outside Jobber | T0156 | 1100.67 | 1 | 1057.33 | -43.34 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1189 | Silverton Insurance Brokers Pty Ltd | 274 Gilbert Avenue, Glen Waverley | Washroom service | Monthly | 0 | 88 | Active | Outside Jobber | T0157 | 88 | 1 | 88 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1190 | Greenway Podiatry Pty Ltd | 198 Station Avenue, Burwood | Kitchen and bathrooms | Weekly | 1 | 40 | Active | Auto |  | 173.33 | 0 | 0 | -173.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1191 | Banksia Logistics | 387 Burke Parade, Northcote | Office clean | Weekly | 1 | 94 | Active | Outside Jobber | T0158 | 407.33 | 1 | 376 | -31.33 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 1 North
J1192 | Banksia Logistics | 467 High Avenue, Northcote | Office clean | Weekly | 1 | 199 | Active | Outside Jobber | T0159 | 862.33 | 1 | 862.33 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1193 | Banksia Logistics | 458 Glenferrie Parade, Thornbury | Office clean | Weekly | 1 | 107 | Active | Auto | T0160 | 463.67 | 1 | 463.67 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 1 North
J1194 | Sunbury Architects Pty Ltd | 111A Plenty Street, Epping | Kitchen and bathrooms | Weekly | 5 | 64 | Active | Outside Jobber | T0161 | 1386.67 | 1 | 1386.67 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1195 | Cobblestone Physiotherapy Pty Ltd | 12 Sydney Road, Bundoora | Kitchen and bathrooms | Weekly | 1 | 36 | Active | Outside Jobber | T0162 T0163 | 156 | 2 | 307.67 | 151.67 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 1 North
J1196 | Banksia Real Estate | 272 Gilbert Street, Maribyrnong | Office clean | Weekly | 2 | 139 | Active | Outside Jobber | T0164 | 1204.67 | 1 | 1204.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1197 | Banksia Real Estate | 272 Gilbert Street, Maribyrnong | Window clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0165 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1198 | Northside Pathology Pty Ltd | 416 Park Road, Ringwood | Office clean | Weekly | 1 | 139 | Active | Outside Jobber | T0166 | 602.33 | 1 | 580.67 | -21.66 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1199 | Harbourside Lawyers | 1 Mason Parade, Glen Waverley | Kitchen and bathrooms | Weekly | 2 | 37 | Active | Outside Jobber | T0167 | 320.67 | 1 | 320.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1200 | Kingsley Fitness Pty Ltd | 460 Sydney Highway, Werribee | Kitchen and bathrooms | Weekly | 1 | 60 | Active | Outside Jobber | T0168 | 260 | 1 | 251.33 | -8.67 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 4 West
J1201 | Lakeside Optometrists | 35 Nepean Avenue, Footscray | Office clean | Weekly | 1 | 130 | Active | Outside Jobber | T0169 | 563.33 | 1 | 563.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1202 | Lakeside Optometrists | 35 Nepean Avenue, Footscray | Carpet steam clean | Every 4 weeks | 0 | 234 | Active | Outside Jobber | T0170 | 234 | 1 | 234 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1203 | Southgate Dental | 271 Victoria Avenue, Hawthorn | Office clean | Weekly | 3 | 104 | Active | Outside Jobber | T0171 | 1352 | 1 | 1352 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1204 | Sunbury Optometrists | 375 Railway Road, Altona | Office clean | Weekly | 5 | 69 | Active | Auto |  | 1495 | 0 | 0 | -1495 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1205 | Bayview Vet Clinic | 186 Sydney Avenue, Coburg | Office clean | Weekly | 3 | 97 | Active | Outside Jobber | T0172 | 1261 | 1 | 1261 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1206 | Bayview Vet Clinic | 186 Sydney Avenue, Coburg | Window clean | Every 4 weeks | 0 | 135 | Active | Auto |  | 135 | 0 | 0 | -135 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1207 | Bayview Vet Clinic | 399 Whitehorse Road, Reservoir | Office clean | Weekly | 2 | 93 | Active | Outside Jobber |  | 806 | 0 | 0 | -806 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 1 North
J1208 | Bayview Vet Clinic | 399 Whitehorse Road, Reservoir | Window clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0173 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1209 | Redgum Pathology Pty Ltd | 453 Railway Parade, Camberwell | Office clean | Weekly | 1 | 198 | Active | Outside Jobber | T0174 | 858 | 1 | 858 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1210 | Greenway Medical Centre Pty Ltd | 326 Main Highway, Glen Waverley | Office clean | Weekly | 1 | 98 | Active | Outside Jobber | T0175 | 424.67 | 1 | 392 | -32.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 2 East
J1211 | Greenway Medical Centre Pty Ltd | 326 Main Highway, Glen Waverley | Carpet steam clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0176 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1212 | Westend Physiotherapy | 306 Bridge Road, Glen Waverley | Office clean | Weekly | 5 | 166 | Active | Outside Jobber | T0177 | 3596.67 | 1 | 3320 | -276.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 2 East
J1213 | Riverside Podiatry | 79 Ballarat Street, Point Cook | Office clean | Weekly | 3 | 135 | Active | Auto |  | 1755 | 0 | 0 | -1755 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1214 | Riverside Podiatry | 145 Church Avenue, Brighton | Office clean | Weekly | 1 | 107 | Active | Outside Jobber | T0178 | 463.67 | 1 | 463.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1215 | Northside Learning Centre | 190 Nicholson Avenue, Camberwell | Office clean | Weekly | 5 | 69 | Active | Auto | T0179 | 1495 | 1 | 1495 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1216 | Harbourside Logistics Pty Ltd | 387 Barkly Highway, Hawthorn | Office clean | Weekly | 3 | 97 | Active | Outside Jobber | T0180 | 1261 | 1 | 1261 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1217 | Harbourside Logistics Pty Ltd | 5 Park Highway, Kew | Office clean | Weekly | 2 | 66 | Active | Outside Jobber | T0181 | 572 | 1 | 572 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1218 | Redgum Podiatry | 204 Mason Parade, Williamstown | Office clean | Weekly | 2 | 94 | Active | Outside Jobber | T0182 | 814.67 | 1 | 814.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1219 | Redgum Podiatry | 445 Barkly Avenue, Cheltenham | Office clean | Weekly | 2 | 104 | Active | Outside Jobber | T0183 | 901.33 | 1 | 901.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1220 | Redgum Podiatry | 445 Barkly Avenue, Cheltenham | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber |  | 116 | 0 | 0 | -116 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 3 South
J1221 | Harbourside Chiropractic | 151 Glenferrie Highway, Oakleigh | Office clean | Weekly | 2 | 90 | Active | Outside Jobber | T0184 | 780 | 1 | 780 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1222 | Harbourside Chiropractic | 284 Mason Highway, Moorabbin | Office clean | Weekly | 2 | 116 | Active | Outside Jobber | T0185 | 1005.33 | 1 | 928 | -77.33 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1223 | Harbourside Chiropractic | 284 Mason Highway, Moorabbin | Carpet steam clean | Every 4 weeks | 0 | 135 | Active | Outside Jobber | T0186 | 135 | 1 | 135 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1224 | Harbourside Chiropractic | 218 Burke Street, St Kilda | Office clean | Weekly | 5 | 134 | Active | Auto |  | 2903.33 | 0 | 0 | -2903.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1225 | Hillcrest Lawyers | 362 Barkly Avenue, Mentone | Office clean | Weekly | 2 | 62 | Active | Outside Jobber | T0187 | 537.33 | 1 | 520 | -17.33 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1226 | Hillcrest Lawyers | 418 Main Avenue, Northcote | Office clean | Weekly | 5 | 102 | Active | Outside Jobber | T0188 | 2210 | 1 | 2210 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1227 | Silverton Logistics Pty Ltd | 176 High Highway, Brunswick | Kitchen and bathrooms | Weekly | 2 | 64 | Active | Outside Jobber | T0189 | 554.67 | 1 | 512 | -42.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 1 North
J1228 | Silverton Logistics Pty Ltd | 176 High Highway, Brunswick | Window clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0190 | 146 | 1 | 146 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1229 | Silverton Logistics Pty Ltd | 356 Glenferrie Parade, Frankston | Kitchen and bathrooms | Weekly | 1 | 29 | Active | Outside Jobber | T0191 | 125.67 | 1 | 116 | -9.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1230 | Hillcrest Motors Pty Ltd | 64 Glenferrie Parade, Bentleigh | Office clean | Weekly | 1 | 134 | Active | Outside Jobber | T0192 | 580.67 | 1 | 580.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1231 | Hillcrest Motors Pty Ltd | 64 Glenferrie Parade, Bentleigh | Carpet steam clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0193 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1232 | Southgate Pathology | 433 Mason Parade, Brunswick | Office clean | Weekly | 2 | 193 | Active | Auto | T0194 | 1672.67 | 1 | 1672.67 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 1 North
J1233 | Southgate Pathology | 291 Burke Highway, Hawthorn | Office clean | Weekly | 2 | 161 | Active | Outside Jobber | T0195 | 1395.33 | 1 | 1395.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1234 | Southgate Pathology | 186 Plenty Street, Altona | Kitchen and bathrooms | Weekly | 3 | 62 | Active | Outside Jobber | T0196 | 806 | 1 | 806 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1235 | Westend Engineering | 279 Nicholson Avenue, Deer Park | Office clean | Weekly | 2 | 126 | Active | Outside Jobber | T0197 | 1092 | 1 | 1092 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1236 | Westend Engineering | 313 Victoria Road, Reservoir | Kitchen and bathrooms | Weekly | 3 | 64 | Active | Outside Jobber | T0198 | 832 | 1 | 832 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1237 | Westend Engineering | 313 Victoria Road, Reservoir | Carpet steam clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber |  | 146 | 0 | 0 | -146 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 1 North
J1238 | Lakeside Real Estate Pty Ltd | 44 Nepean Parade, Brunswick | Office clean | Weekly | 3 | 70 | Active | Outside Jobber | T0199 | 910 | 1 | 910 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1239 | Lakeside Real Estate Pty Ltd | 67 Glenferrie Road, Preston | Office clean | Weekly | 3 | 96 | Active | Outside Jobber | T0200 | 1248 | 1 | 1248 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1240 | Lakeside Real Estate Pty Ltd | 6 Whitehorse Street, Mitcham | Office clean | Weekly | 2 | 63 | Active | Auto |  | 546 | 0 | 0 | -546 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1241 | Lakeside Real Estate Pty Ltd | 6 Whitehorse Street, Mitcham | Window clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0201 | 146 | 1 | 146 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1242 | Lakeside Real Estate Pty Ltd | 6 Whitehorse Street, Mitcham | Washroom service | Monthly | 0 | 99 | Active | Outside Jobber | T0202 | 99 | 1 | 99 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1243 | Harbourside Pharmacy Pty Ltd | 267 Nepean Street, Yarraville | Office clean | Weekly | 2 | 134 | Active | Outside Jobber | T0203 | 1161.33 | 1 | 1161.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1244 | Harbourside Pharmacy Pty Ltd | 266 Park Road, Williamstown | Office clean | Weekly | 2 | 104 | Active | Auto |  | 901.33 | 0 | 0 | -901.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1245 | Brightside Early Learning Pty Ltd | 158 Nepean Avenue, Footscray | Office clean | Weekly | 5 | 90 | Active | Outside Jobber | T0204 | 1950 | 1 | 1950 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1246 | Southgate Engineering | 135 Main Avenue, Frankston | Office clean | Weekly | 2 | 126 | Active | Auto |  | 1092 | 0 | 0 | -1092 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1247 | Riverside Dental Pty Ltd | 256 Albert Parade, Northcote | Kitchen and bathrooms | Weekly | 1 | 62 | Active | Auto |  | 268.67 | 0 | 0 | -268.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1248 | Bayview Early Learning | 215 Barkly Street, Laverton | Office clean | Weekly | 1 | 90 | Active | Outside Jobber | T0205 | 390 | 1 | 390 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1249 | Bayview Early Learning | 215 Barkly Street, Laverton | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0206 | 116 | 1 | 116 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1250 | Bayview Early Learning | 329 Station Avenue, Brighton | Office clean | Weekly | 1 | 75 | Active | Outside Jobber | T0207 | 325 | 1 | 312 | -13 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1251 | Elm Street Financial Planning Pty Ltd | 462A Victoria Road, Yarraville | Kitchen and bathrooms | Weekly | 2 | 71 | Active | Outside Jobber | T0208 | 615.33 | 1 | 615.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1252 | Ashwood Property Group | 248 Sydney Street, Cheltenham | Kitchen and bathrooms | Weekly | 1 | 35 | Active | Auto |  | 151.67 | 0 | 0 | -151.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1253 | Ashwood Property Group | 248 Sydney Street, Cheltenham | Carpet steam clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber |  | 116 | 0 | 0 | -116 | Not billed | Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | Wave 3 South
J1254 | Northside Early Learning Pty Ltd | 251 Plenty Highway, Bentleigh | Kitchen and bathrooms | Weekly | 2 | 64 | Active | Outside Jobber | T0209 | 554.67 | 1 | 554.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1255 | Brightside Logistics Pty Ltd | 148 Nepean Street, Bentleigh | Office clean | Weekly | 2 | 101 | Active | Outside Jobber | T0210 | 875.33 | 1 | 875.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1256 | Elm Street Early Learning | 431 Union Avenue, Hawthorn | Office clean | Weekly | 5 | 70 | Active | Outside Jobber | T0211 | 1516.67 | 1 | 1516.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1257 | Elm Street Early Learning | 356 Main Road, Camberwell | Office clean | Weekly | 1 | 73 | Active | Auto |  | 316.33 | 0 | 0 | -316.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1258 | Elm Street Early Learning | 422 Nicholson Parade, Glen Waverley | Office clean | Weekly | 2 | 98 | Active | Outside Jobber | T0212 | 849.33 | 1 | 849.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1259 | Elm Street Early Learning | 422 Nicholson Parade, Glen Waverley | Window clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0213 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1260 | Elm Street Early Learning | 422 Nicholson Parade, Glen Waverley | Washroom service | Monthly | 0 | 99 | Active | Auto |  | 99 | 0 | 0 | -99 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1261 | Redgum Financial Planning | 455 Railway Road, Williamstown | Office clean | Weekly | 2 | 96 | Active | Auto |  | 832 | 0 | 0 | -832 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1262 | Redgum Financial Planning | 217 King Street, Epping | Office clean | Weekly | 2 | 98 | Active | Outside Jobber | T0214 | 849.33 | 1 | 849.33 | 0 | Matched | Matched | Move as is | Office | Pilot
J1263 | Lakeside Fitness Pty Ltd | 58 Station Road, Mitcham | Office clean | Weekly | 2 | 104 | Active | Outside Jobber | T0215 | 901.33 | 1 | 901.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1264 | Elm Street Logistics Pty Ltd | 343 Sydney Street, Kew | Office clean | Weekly | 5 | 97 | Active | Auto | T0216 | 2101.67 | 1 | 2101.67 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1265 | Elm Street Logistics Pty Ltd | 399 Plenty Avenue, Ringwood | Office clean | Weekly | 2 | 62 | Active | Auto |  | 537.33 | 0 | 0 | -537.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1266 | Elm Street Logistics Pty Ltd | 256 Station Street, Blackburn | Office clean | Weekly | 5 | 64 | Active | Outside Jobber | T0217 | 1386.67 | 1 | 1280 | -106.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 2 East
J1267 | Elm Street Logistics Pty Ltd | 256 Station Street, Blackburn | Window clean | Every 4 weeks | 0 | 203 | Active | Outside Jobber | T0218 | 203 | 1 | 203 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1268 | Lakeside Insurance Brokers | 459 Whitehorse Parade, Sunshine | Kitchen and bathrooms | Weekly | 3 | 68 | Active | Auto |  | 884 | 0 | 0 | -884 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1269 | Lakeside Insurance Brokers | 459 Whitehorse Parade, Sunshine | Carpet steam clean | Every 4 weeks | 0 | 156 | Active | Outside Jobber | T0219 | 156 | 1 | 156 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1270 | Elm Street Pathology Pty Ltd | 87 Main Avenue, Maribyrnong | Kitchen and bathrooms | Weekly | 5 | 69 | Active | Outside Jobber | T0220 | 1495 | 1 | 1495 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1271 | Fairfield Accountants Pty Ltd | 313/12 Union Avenue, Dandenong | Office clean | Weekly | 5 | 151 | Active | Auto |  | 3271.67 | 0 | 0 | -3271.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1272 | Fairfield Accountants Pty Ltd | 354 King Avenue, Moorabbin | Office clean | Weekly | 2 | 87 | Active | Outside Jobber | T0221 | 754 | 1 | 754 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1273 | Fairfield Accountants Pty Ltd | 354 King Avenue, Moorabbin | Window clean | Every 4 weeks | 0 | 109 | Active | Outside Jobber | T0222 | 109 | 1 | 109 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1274 | Fairfield Dental | 122 Main Avenue, Box Hill | Office clean | Weekly | 2 | 146 | Active | Outside Jobber | T0223 | 1265.33 | 1 | 1265.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1275 | Oakwood Medical Centre Pty Ltd | 64 Bridge Street, Coburg | Office clean | Weekly | 3 | 93 | Active | Auto |  | 1209 | 0 | 0 | -1209 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1276 | Banksia Architects Pty Ltd | 213 Church Parade, Frankston | Office clean | Weekly | 3 | 186 | Active | Outside Jobber | T0224 | 2418 | 1 | 2327 | -91 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1277 | Ironbark Engineering Pty Ltd | 420 Railway Parade, Preston | Office clean | Weekly | 3 | 99 | Active | Outside Jobber | T0225 | 1287 | 1 | 1287 | 0 | Matched | Matched | Move as is | Office | Pilot
J1278 | Ironbark Engineering Pty Ltd | 301 Whitehorse Highway, Thornbury | Office clean | Weekly | 5 | 135 | Active | Auto |  | 2925 | 0 | 0 | -2925 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1279 | Wattle Grove Financial Planning | 294 Victoria Avenue, Northcote | Office clean | Weekly | 2 | 130 | Active | Auto |  | 1126.67 | 0 | 0 | -1126.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1280 | Parkside Fitness Pty Ltd | 81 Nepean Road, Burwood | Office clean | Weekly | 2 | 90 | Active | Outside Jobber | T0226 T0227 | 780 | 2 | 1534 | 754 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 2 East
J1281 | Parkside Fitness Pty Ltd | 440 Bridge Street, Maribyrnong | Office clean | Weekly | 1 | 75 | Active | Outside Jobber | T0228 | 325 | 1 | 325 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1282 | Parkside Fitness Pty Ltd | 440 Bridge Street, Maribyrnong | Window clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0229 | 146 | 1 | 146 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1283 | Greenway Chiropractic Pty Ltd | 347 High Highway, Ringwood | Office clean | Weekly | 5 | 93 | Active | Outside Jobber | T0230 | 2015 | 1 | 2015 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1284 | Greenway Chiropractic Pty Ltd | 347 High Highway, Ringwood | Window clean | Every 4 weeks | 0 | 218 | Active | Outside Jobber | T0231 | 218 | 1 | 218 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1285 | Greenway Chiropractic Pty Ltd | 250 Hopkins Highway, Kew | Office clean | Weekly | 5 | 175 | Active | Auto |  | 3791.67 | 0 | 0 | -3791.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1286 | Greenway Chiropractic Pty Ltd | 191 Albert Avenue, Burwood | Office clean | Weekly | 5 | 116 | Active | Outside Jobber | T0232 | 2513.33 | 1 | 2513.33 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1287 | Bayview Real Estate Pty Ltd | 414 Sydney Avenue, Brighton | Office clean | Weekly | 3 | 102 | Active | Outside Jobber | T0233 | 1326 | 1 | 1326 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1288 | Riverside Pharmacy | 472 Hopkins Highway, Box Hill | Kitchen and bathrooms | Weekly | 2 | 66 | Active | Outside Jobber | T0234 T0235 | 572 | 2 | 1144 | 572 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 2 East
J1289 | Riverside Pharmacy | 410 Queen Highway, Glen Waverley | Office clean | Weekly | 5 | 121 | Active | Auto |  | 2621.67 | 0 | 0 | -2621.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 2 East
J1290 | Riverside Pharmacy | 410 Queen Highway, Glen Waverley | Window clean | Every 4 weeks | 0 | 234 | Active | Outside Jobber | T0236 | 234 | 1 | 225 | -9 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 2 East
J1291 | Riverside Pharmacy | 410 Queen Highway, Glen Waverley | Washroom service | Monthly | 0 | 99 | Active | Outside Jobber | T0237 | 99 | 1 | 99 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1292 | Elm Street Chiropractic Pty Ltd | 348 Railway Street, Mentone | Office clean | Weekly | 2 | 121 | Active | Outside Jobber | T0238 | 1048.67 | 1 | 1005.33 | -43.34 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1293 | Elm Street Chiropractic Pty Ltd | 348 Railway Street, Mentone | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0239 | 116 | 1 | 116 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1294 | Elm Street Chiropractic Pty Ltd | 4 Sydney Highway, Cheltenham | Office clean | Weekly | 1 | 161 | Active | Outside Jobber | T0240 | 697.67 | 1 | 671.67 | -26 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1295 | Elm Street Chiropractic Pty Ltd | 4 Sydney Highway, Cheltenham | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0241 | 151 | 1 | 151 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1296 | Ironbark Real Estate Pty Ltd | 395 Plenty Avenue, Oakleigh | Office clean | Weekly | 1 | 70 | Active | Outside Jobber | T0242 | 303.33 | 1 | 303.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1297 | Ironbark Real Estate Pty Ltd | 32 Park Avenue, Oakleigh | Office clean | Weekly | 2 | 121 | Active | Auto |  | 1048.67 | 0 | 0 | -1048.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1298 | Elm Street Motors | 333 Albert Parade, Brighton | Office clean | Weekly | 1 | 187 | Active | Outside Jobber | T0243 | 810.33 | 1 | 810.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1299 | Elm Street Motors | 280 Station Street, Oakleigh | Kitchen and bathrooms | Weekly | 1 | 35 | Active | Auto |  | 151.67 | 0 | 0 | -151.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1300 | Sunbury Engineering | 87/12 Victoria Road, Point Cook | Office clean | Weekly | 3 | 71 | Active | Outside Jobber | T0244 | 923 | 1 | 923 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1301 | Ashwood Dental Pty Ltd | 241 Mason Road, Northcote | Office clean | Weekly | 2 | 75 | Active | Auto |  | 650 | 0 | 0 | -650 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1302 | Ashwood Dental Pty Ltd | 448 Barkly Avenue, Mentone | Kitchen and bathrooms | Weekly | 1 | 35 | Active | Auto |  | 151.67 | 0 | 0 | -151.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1303 | Bluestone Early Learning Pty Ltd | 351 High Street, Altona | Office clean | Weekly | 5 | 102 | Active | Auto |  | 2210 | 0 | 0 | -2210 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1304 | Bluestone Early Learning Pty Ltd | 351 High Street, Altona | Window clean | Every 4 weeks | 0 | 135 | Active | Auto | T0245 | 135 | 1 | 135 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 4 West
J1305 | Bluestone Early Learning Pty Ltd | 477 Hopkins Avenue, Hawthorn | Office clean | Weekly | 5 | 93 | Active | Outside Jobber | T0246 | 2015 | 1 | 2015 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1306 | Bluestone Early Learning Pty Ltd | 477 Hopkins Avenue, Hawthorn | Window clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0247 | 146 | 1 | 146 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1307 | Bluestone Early Learning Pty Ltd | 477 Hopkins Avenue, Hawthorn | Washroom service | Monthly | 0 | 88 | Active | Outside Jobber | T0248 | 88 | 1 | 88 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1308 | Harbourside Property Group | 428 Church Parade, Maribyrnong | Office clean | Weekly | 1 | 96 | Active | Auto |  | 416 | 0 | 0 | -416 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 4 West
J1309 | Harbourside Property Group | 428 Church Parade, Maribyrnong | Carpet steam clean | Every 4 weeks | 0 | 146 | Active | Outside Jobber | T0249 T0250 | 146 | 2 | 292 | 146 | Duplicate in QBO | Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | Wave 4 West
J1310 | Harbourside Property Group | 428 Church Parade, Maribyrnong | Washroom service | Monthly | 0 | 99 | Active | Outside Jobber | T0251 | 99 | 1 | 99 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1311 | Riverside Engineering Pty Ltd | 253A Glenferrie Street, Bundoora | Office clean | Weekly | 1 | 68 | Active | Outside Jobber | T0252 | 294.67 | 1 | 294.67 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1312 | Ashwood Lawyers | 466 Main Street, Werribee | Kitchen and bathrooms | Weekly | 2 | 68 | Active | Outside Jobber | T0253 | 589.33 | 1 | 589.33 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1313 | Bayview Fitness Pty Ltd | 367 Station Parade, Thornbury | Office clean | Weekly | 1 | 94 | Active | Auto |  | 407.33 | 0 | 0 | -407.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1314 | Ironbark Property Group Pty Ltd | 266/12 Albert Avenue, Mitcham | Kitchen and bathrooms | Weekly | 2 | 42 | Active | Outside Jobber | T0254 | 364 | 1 | 364 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1315 | Ironbark Property Group Pty Ltd | 479 Burke Road, Reservoir | Office clean | Weekly | 5 | 125 | Active | Auto |  | 2708.33 | 0 | 0 | -2708.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 1 North
J1316 | Ironbark Property Group Pty Ltd | 479 Burke Road, Reservoir | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0255 | 151 | 1 | 151 | 0 | Matched | Matched | Move as is | Office | Wave 1 North
J1317 | Oakwood Engineering | 216 Plenty Road, Burwood | Office clean | Weekly | 2 | 121 | Active | Outside Jobber | T0256 | 1048.67 | 1 | 1048.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1318 | Oakwood Engineering | 216 Plenty Road, Burwood | Window clean | Every 4 weeks | 0 | 218 | Active | Auto | T0257 | 218 | 1 | 218 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 2 East
J1319 | Waverley Physiotherapy Pty Ltd | 42 Queen Avenue, Bentleigh | Office clean | Weekly | 2 | 122 | Active | Auto |  | 1057.33 | 0 | 0 | -1057.33 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1320 | Waverley Physiotherapy Pty Ltd | 438 Church Highway, Bentleigh | Office clean | Weekly | 1 | 166 | Active | Outside Jobber | T0258 | 719.33 | 1 | 719.33 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1321 | Waverley Physiotherapy Pty Ltd | 438 Church Highway, Bentleigh | Carpet steam clean | Every 4 weeks | 0 | 203 | Active | Outside Jobber | T0259 | 203 | 1 | 203 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1322 | Waverley Physiotherapy Pty Ltd | 337 Plenty Parade, St Kilda | Office clean | Weekly | 1 | 161 | Active | Outside Jobber | T0260 | 697.67 | 1 | 671.67 | -26 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1323 | Harbourside Insurance Brokers Pty Ltd | 314 Plenty Street, Northcote | Office clean | Weekly | 1 | 181 | Active | Outside Jobber | T0261 | 784.33 | 1 | 754 | -30.33 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 1 North
J1324 | Harbourside Real Estate | 121 High Parade, Glen Waverley | Office clean | Weekly | 1 | 101 | Active | Outside Jobber | T0262 | 437.67 | 1 | 437.67 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1325 | Harbourside Real Estate | 317 Victoria Parade, Clayton | Office clean | Weekly | 2 | 193 | Active | Outside Jobber | T0263 | 1672.67 | 1 | 1672.67 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1326 | Eastwood Podiatry | 273/12 Plenty Parade, Coburg | Office clean | Weekly | 5 | 121 | Active | Outside Jobber | T0264 | 2621.67 | 1 | 2621.67 | 0 | Matched | Matched | Move as is | Office | Pilot
J1327 | Cityside Real Estate | 200 Nepean Avenue, Moorabbin | Office clean | Weekly | 1 | 134 | Active | Auto |  | 580.67 | 0 | 0 | -580.67 | Billed in Jobber | Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | Wave 3 South
J1328 | Cityside Real Estate | 455 Nicholson Highway, Moorabbin | Office clean | Weekly | 1 | 104 | Active | Outside Jobber | T0265 | 450.67 | 1 | 416 | -34.67 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1329 | Cityside Real Estate | 455 Nicholson Highway, Moorabbin | Window clean | Every 4 weeks | 0 | 116 | Active | Outside Jobber | T0266 | 116 | 1 | 112 | -4 | Rate mismatch | Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | Wave 3 South
J1330 | Parkside Dental | 400 Albert Street, Mentone | Office clean | Weekly | 3 | 101 | Active | Outside Jobber | T0267 | 1313 | 1 | 1212 | -101 | Basis mismatch | Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | Wave 3 South
J1331 | Parkside Dental | 400 Albert Street, Mentone | Washroom service | Monthly | 0 | 151 | Active | Outside Jobber | T0268 | 151 | 1 | 151 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1332 | Parkside Dental Group | 257 Hopkins Parade, Point Cook | Office clean | Weekly | 3 | 107 | Active | Outside Jobber | T0269 | 1391 | 1 | 1391 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1333 | Northside Physiotherapy | 139 Glenferrie Parade, Brighton | Kitchen and bathrooms | Weekly | 2 | 69 | Active | Outside Jobber | T0270 | 598 | 1 | 598 | 0 | Matched | Matched | Move as is | Office | Wave 3 South
J1334 | Northside Physiotherapy | 250 Bridge Highway, Werribee | Office clean | Weekly | 2 | 192 | Active | Outside Jobber | T0271 | 1664 | 1 | 1664 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1335 | North Side Physiotherapy | 284A Park Road, Point Cook | Office clean | Weekly | 1 | 131 | Active | Outside Jobber | T0272 | 567.67 | 1 | 567.67 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1336 | North Side Physiotherapy | 284A Park Road, Point Cook | Window clean | Every 4 weeks | 0 | 203 | Active | Auto | T0273 | 203 | 1 | 203 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 4 West
J1337 | North Side Physiotherapy | 163 Barkly Highway, Essendon | Office clean | Weekly | 1 | 185 | Active | Auto | T0274 | 801.67 | 1 | 801.67 | 0 | Double-billing risk | Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | Wave 1 North
J1338 | Bayview Accountants | 448 Nicholson Street, Kew | Office clean | Weekly | 1 | 99 | Active | Outside Jobber | T0275 | 429 | 1 | 429 | 0 | Matched | Matched | Move as is | Office | Wave 2 East
J1339 | Bay View Accountants | 360 Burke Street, Maribyrnong | Office clean | Weekly | 1 | 126 | Active | Outside Jobber | T0276 | 546 | 1 | 546 | 0 | Matched | Matched | Move as is | Office | Wave 4 West
J1340 | Oakwood Medical Centre Pty Ltd | 64 Bridge Street, Coburg | Office clean | Weekly | 1 | 87 | Archived | Outside Jobber | T0277 | 0 | 1 | 377 | 377 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 1 North
J1341 | Kingsley Fitness Pty Ltd | 460 Sydney Highway, Werribee | Office clean | Weekly | 1 | 61 | Archived | Outside Jobber | T0278 | 0 | 1 | 264.33 | 264.33 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 4 West
J1342 | Wattle Grove Fitness | 102 Union Road, St Kilda | Office clean | Weekly | 1 | 178 | Archived | Outside Jobber | T0279 | 0 | 1 | 771.33 | 771.33 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 3 South
J1343 | Southgate Pathology | 186 Plenty Street, Altona | Office clean | Weekly | 2 | 120 | Archived | Outside Jobber | T0280 | 0 | 1 | 1040 | 1040 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 4 West
J1344 | Oakwood Vet Clinic | 218 High Road, Bentleigh | Office clean | Weekly | 1 | 126 | Archived | Outside Jobber | T0281 | 0 | 1 | 546 | 546 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 3 South
J1345 | Hillcrest Lawyers | 418 Main Avenue, Northcote | Office clean | Weekly | 2 | 95 | Archived | Outside Jobber | T0282 | 0 | 1 | 823.33 | 823.33 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 1 North
J1346 | Sunbury Architects Pty Ltd | 111A Plenty Street, Epping | Office clean | Weekly | 3 | 98 | Archived | Outside Jobber | T0283 | 0 | 1 | 1274 | 1274 | Inactive in Jobber - confirm | Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | Wave 1 North
J1347 | Brightside Podiatry | 142 Plenty Road, Camberwell | Office clean | Weekly | 1 | 63 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 2 East
J1348 | Elm Street Early Learning | 431 Union Avenue, Hawthorn | Office clean | Weekly | 1 | 124 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 2 East
J1349 | Lakeside Real Estate Pty Ltd | 44 Nepean Parade, Brunswick | Office clean | Weekly | 2 | 90 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 1 North
J1350 | Lakeside Architects | 208 Glenferrie Road, Mitcham | Office clean | Weekly | 1 | 186 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 2 East
J1351 | Elm Street Chiropractic Pty Ltd | 4 Sydney Highway, Cheltenham | Office clean | Weekly | 1 | 145 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1352 | Oakwood Accountants Pty Ltd | 54 Mason Parade, Reservoir | Office clean | Weekly | 3 | 155 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Pilot
J1353 | Elm Street Pathology Pty Ltd | 87 Main Avenue, Maribyrnong | Office clean | Weekly | 2 | 58 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 4 West
J1354 | Oakwood Lawyers Pty Ltd | 453 Plenty Parade, Moorabbin | Office clean | Weekly | 3 | 94 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1355 | Ashwood Physiotherapy | 4A Gilbert Road, Camberwell | Office clean | Weekly | 1 | 100 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 2 East
J1356 | Riverside Dental Pty Ltd | 256 Albert Parade, Northcote | Office clean | Weekly | 3 | 100 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Pilot
J1357 | Ashwood Physiotherapy | 151 Nicholson Street, Point Cook | Office clean | Weekly | 1 | 126 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 4 West
J1358 | Waverley Physiotherapy Pty Ltd | 42 Queen Avenue, Bentleigh | Office clean | Weekly | 2 | 124 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1359 | Riverside Learning Centre | 148 Plenty Street, Cheltenham | Office clean | Weekly | 3 | 125 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1360 | Clearwater Property Group Pty Ltd | 143/12 Nepean Street, Frankston | Office clean | Weekly | 2 | 120 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1361 | Redgum Podiatry | 204 Mason Parade, Williamstown | Office clean | Weekly | 3 | 67 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 4 West
J1362 | Northside Engineering Pty Ltd | 430 Victoria Road, St Kilda | Office clean | Weekly | 3 | 103 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Wave 3 South
J1363 | Kingsley Insurance Brokers | 225 Park Avenue, Reservoir | Office clean | Weekly | 1 | 117 | Archived | Outside Jobber |  | 0 | 0 | 0 | 0 | Archived, no template | Archived, no template | Nothing to move; keep in the Jobber archive export | Office | Pilot
| Kingsley Real Estate | 208 Main Avenue, Mitcham | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0284 | 0 | 1 | 65 | 65 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 2 East
| Harbourside Real Estate | 317 Victoria Parade, Clayton | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0285 | 0 | 1 | 65 | 65 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 3 South
| Brightside Logistics Pty Ltd | 148 Nepean Street, Bentleigh | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0286 | 0 | 1 | 80 | 80 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 3 South
| Harbourside Logistics Pty Ltd | 387 Barkly Highway, Hawthorn | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0287 | 0 | 1 | 80 | 80 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 2 East
| Waverley Fitness Pty Ltd | 443 Station Road, Footscray | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0288 | 0 | 1 | 65 | 65 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 4 West
| Wattle Grove Dental | 259 Union Avenue, Hawthorn | Paper towel, soap and bin liners | Monthly |  |  | Not in Jobber |  | T0289 | 0 | 1 | 110 | 110 | Missing in Jobber | Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | Wave 2 East

## Actions
Actions by status
Work sample: realistic data, built to show how I approach this work.
Status | Action | Owner | Rows | Monthly difference
Matched | Move as is | Office | 195 | 0
Billed in Jobber | Create QBO template at the Jobber rate; switch off Jobber invoicing at cutover | Bookkeeper | 62 | -52180.34
Double-billing risk | Stop Jobber auto-invoicing now; credit the duplicate invoices | Bookkeeper | 15 | 0
Duplicate in QBO | Make the newer template inactive; credit the second invoice each month | Bookkeeper | 8 | 4930
Not billed | Create QBO template; raise catch-up invoices for Aug-Oct | Bookkeeper | 9 | -5703.67
Basis mismatch | Change template to the 52/12 monthly amount; bill the shortfall | Bookkeeper | 19 | -1483.02
Rate mismatch | Update template to the current agreed rate (1 Jul 2026 rise); bill the shortfall | Bookkeeper | 31 | -840
Inactive in Jobber - confirm | Confirm with the client whether the work ended; if so make the template inactive and credit | Owner | 7 | 5095.99
Archived, no template | Nothing to move; keep in the Jobber archive export | Office | 17 | 0
Missing in Jobber | Confirm what it is (supply-only charge); keep the template, add a note | Owner | 6 | 465

## Billing Check
Billing check Aug-Oct 2026: should have billed vs Jobber + QBO
Work sample: realistic data, built to show how I approach this work.
Job / template | Month | Frequency | 4-weekly runs | Should bill | Billed in Jobber | Billed in QBO | Gap | Finding | Status | Engine gap
J1001 | 2026-08 | Weekly |  | 550.33 | 550.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1001 | 2026-09 | Weekly |  | 550.33 | 550.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1001 | 2026-10 | Weekly |  | 550.33 | 550.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1002 | 2026-08 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1002 | 2026-09 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1002 | 2026-10 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1003 | 2026-08 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1003 | 2026-09 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1003 | 2026-10 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1004 | 2026-08 | Weekly |  | 307.67 | 0 | 284 | -23.67 | Under-billed | Basis mismatch | -23.67
J1004 | 2026-09 | Weekly |  | 307.67 | 0 | 284 | -23.67 | Under-billed | Basis mismatch | -23.67
J1004 | 2026-10 | Weekly |  | 307.67 | 0 | 284 | -23.67 | Under-billed | Basis mismatch | -23.67
J1005 | 2026-08 | Weekly |  | 606.67 | 606.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1005 | 2026-09 | Weekly |  | 606.67 | 606.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1005 | 2026-10 | Weekly |  | 606.67 | 606.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1006 | 2026-08 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1006 | 2026-09 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1006 | 2026-10 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1007 | 2026-08 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1007 | 2026-09 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1007 | 2026-10 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1008 | 2026-08 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1008 | 2026-09 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1008 | 2026-10 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1009 | 2026-08 | Weekly |  | 1135.33 | 0 | 1135.33 | 0 | Agrees | Matched | 0
J1009 | 2026-09 | Weekly |  | 1135.33 | 0 | 1135.33 | 0 | Agrees | Matched | 0
J1009 | 2026-10 | Weekly |  | 1135.33 | 0 | 1135.33 | 0 | Agrees | Matched | 0
J1010 | 2026-08 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1010 | 2026-09 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1010 | 2026-10 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1011 | 2026-08 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1011 | 2026-09 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1011 | 2026-10 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1012 | 2026-08 | Weekly |  | 632.67 | 632.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1012 | 2026-09 | Weekly |  | 632.67 | 632.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1012 | 2026-10 | Weekly |  | 632.67 | 632.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1013 | 2026-08 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1013 | 2026-09 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1013 | 2026-10 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1014 | 2026-08 | Weekly |  | 589.33 | 589.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1014 | 2026-09 | Weekly |  | 589.33 | 589.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1014 | 2026-10 | Weekly |  | 589.33 | 589.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1015 | 2026-08 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1015 | 2026-09 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1015 | 2026-10 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1016 | 2026-08 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1016 | 2026-09 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1016 | 2026-10 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1017 | 2026-08 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1017 | 2026-09 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1017 | 2026-10 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1018 | 2026-08 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1018 | 2026-09 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1018 | 2026-10 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1019 | 2026-08 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1019 | 2026-09 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1019 | 2026-10 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1020 | 2026-08 | Weekly |  | 806 | 806 | 0 | 0 | Agrees | Billed in Jobber | 0
J1020 | 2026-09 | Weekly |  | 806 | 806 | 0 | 0 | Agrees | Billed in Jobber | 0
J1020 | 2026-10 | Weekly |  | 806 | 806 | 0 | 0 | Agrees | Billed in Jobber | 0
J1021 | 2026-08 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1021 | 2026-09 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1021 | 2026-10 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1022 | 2026-08 | Weekly |  | 819 | 0 | 819 | 0 | Agrees | Matched | 0
J1022 | 2026-09 | Weekly |  | 819 | 0 | 819 | 0 | Agrees | Matched | 0
J1022 | 2026-10 | Weekly |  | 819 | 0 | 819 | 0 | Agrees | Matched | 0
J1023 | 2026-08 | Weekly |  | 1308.67 | 0 | 1256.67 | -52 | Under-billed | Rate mismatch | -52
J1023 | 2026-09 | Weekly |  | 1308.67 | 0 | 1256.67 | -52 | Under-billed | Rate mismatch | -52
J1023 | 2026-10 | Weekly |  | 1308.67 | 0 | 1256.67 | -52 | Under-billed | Rate mismatch | -52
J1024 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1024 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1024 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1025 | 2026-08 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1025 | 2026-09 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1025 | 2026-10 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1026 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1026 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1026 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1027 | 2026-08 | Weekly |  | 1586 | 0 | 1464 | -122 | Under-billed | Basis mismatch | -122
J1027 | 2026-09 | Weekly |  | 1586 | 0 | 1464 | -122 | Under-billed | Basis mismatch | -122
J1027 | 2026-10 | Weekly |  | 1586 | 0 | 1464 | -122 | Under-billed | Basis mismatch | -122
J1028 | 2026-08 | Weekly |  | 537.33 | 0 | 537.33 | 0 | Agrees | Matched | 0
J1028 | 2026-09 | Weekly |  | 537.33 | 0 | 537.33 | 0 | Agrees | Matched | 0
J1028 | 2026-10 | Weekly |  | 537.33 | 0 | 537.33 | 0 | Agrees | Matched | 0
J1029 | 2026-08 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1029 | 2026-09 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1029 | 2026-10 | Weekly |  | 442 | 0 | 442 | 0 | Agrees | Matched | 0
J1030 | 2026-08 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1030 | 2026-09 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1030 | 2026-10 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1031 | 2026-08 | Weekly |  | 806 | 806 | 806 | 806 | Over-billed | Double-billing risk | 806
J1031 | 2026-09 | Weekly |  | 806 | 806 | 806 | 806 | Over-billed | Double-billing risk | 806
J1031 | 2026-10 | Weekly |  | 806 | 806 | 806 | 806 | Over-billed | Double-billing risk | 806
J1032 | 2026-08 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1032 | 2026-09 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1032 | 2026-10 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1033 | 2026-08 | Weekly |  | 4051.67 | 0 | 4051.67 | 0 | Agrees | Matched | 0
J1033 | 2026-09 | Weekly |  | 4051.67 | 0 | 4051.67 | 0 | Agrees | Matched | 0
J1033 | 2026-10 | Weekly |  | 4051.67 | 0 | 4051.67 | 0 | Agrees | Matched | 0
J1034 | 2026-08 | Weekly |  | 606.67 | 0 | 560 | -46.67 | Under-billed | Basis mismatch | -46.67
J1034 | 2026-09 | Weekly |  | 606.67 | 0 | 560 | -46.67 | Under-billed | Basis mismatch | -46.67
J1034 | 2026-10 | Weekly |  | 606.67 | 0 | 560 | -46.67 | Under-billed | Basis mismatch | -46.67
J1035 | 2026-08 | Weekly |  | 910 | 0 | 0 | -910 | Under-billed | Not billed | -910
J1035 | 2026-09 | Weekly |  | 910 | 0 | 0 | -910 | Under-billed | Not billed | -910
J1035 | 2026-10 | Weekly |  | 910 | 0 | 0 | -910 | Under-billed | Not billed | -910
J1036 | 2026-08 | Every 4 weeks | 1 | 203 | 203 | 203 | 203 | Over-billed | Double-billing risk | 203
J1036 | 2026-09 | Every 4 weeks | 1 | 203 | 203 | 203 | 203 | Over-billed | Double-billing risk | 203
J1036 | 2026-10 | Every 4 weeks | 1 | 203 | 203 | 203 | 203 | Over-billed | Double-billing risk | 203
J1037 | 2026-08 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1037 | 2026-09 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1037 | 2026-10 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1038 | 2026-08 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1038 | 2026-09 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1038 | 2026-10 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1039 | 2026-08 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1039 | 2026-09 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1039 | 2026-10 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1040 | 2026-08 | Weekly |  | 840.67 | 0 | 840.67 | 0 | Agrees | Matched | 0
J1040 | 2026-09 | Weekly |  | 840.67 | 0 | 840.67 | 0 | Agrees | Matched | 0
J1040 | 2026-10 | Weekly |  | 840.67 | 0 | 840.67 | 0 | Agrees | Matched | 0
J1041 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1041 | 2026-09 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1041 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1042 | 2026-08 | Weekly |  | 138.67 | 0 | 138.67 | 0 | Agrees | Matched | 0
J1042 | 2026-09 | Weekly |  | 138.67 | 0 | 138.67 | 0 | Agrees | Matched | 0
J1042 | 2026-10 | Weekly |  | 138.67 | 0 | 138.67 | 0 | Agrees | Matched | 0
J1043 | 2026-08 | Weekly |  | 1083.33 | 1083.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1043 | 2026-09 | Weekly |  | 1083.33 | 1083.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1043 | 2026-10 | Weekly |  | 1083.33 | 1083.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1044 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1044 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1044 | 2026-10 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1045 | 2026-08 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1045 | 2026-09 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1045 | 2026-10 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1046 | 2026-08 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1046 | 2026-09 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1046 | 2026-10 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1047 | 2026-08 | Weekly |  | 260 | 0 | 260 | 0 | Agrees | Matched | 0
J1047 | 2026-09 | Weekly |  | 260 | 0 | 260 | 0 | Agrees | Matched | 0
J1047 | 2026-10 | Weekly |  | 260 | 0 | 260 | 0 | Agrees | Matched | 0
J1048 | 2026-08 | Weekly |  | 836.33 | 0 | 836.33 | 0 | Agrees | Matched | 0
J1048 | 2026-09 | Weekly |  | 836.33 | 0 | 836.33 | 0 | Agrees | Matched | 0
J1048 | 2026-10 | Weekly |  | 836.33 | 0 | 836.33 | 0 | Agrees | Matched | 0
J1049 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 130 | -5 | Under-billed | Rate mismatch | -5
J1049 | 2026-09 | Every 4 weeks | 2 | 270 | 0 | 260 | -10 | Under-billed | Rate mismatch | -10
J1049 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 130 | -5 | Under-billed | Rate mismatch | -5
J1050 | 2026-08 | Weekly |  | 437.67 | 437.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1050 | 2026-09 | Weekly |  | 437.67 | 437.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1050 | 2026-10 | Weekly |  | 437.67 | 437.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1051 | 2026-08 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1051 | 2026-09 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1051 | 2026-10 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1052 | 2026-08 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1052 | 2026-09 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1052 | 2026-10 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1053 | 2026-08 | Weekly |  | 697.67 | 0 | 697.67 | 0 | Agrees | Matched | 0
J1053 | 2026-09 | Weekly |  | 697.67 | 0 | 697.67 | 0 | Agrees | Matched | 0
J1053 | 2026-10 | Weekly |  | 697.67 | 0 | 697.67 | 0 | Agrees | Matched | 0
J1054 | 2026-08 | Weekly |  | 502.67 | 502.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1054 | 2026-09 | Weekly |  | 502.67 | 502.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1054 | 2026-10 | Weekly |  | 502.67 | 502.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1055 | 2026-08 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1055 | 2026-09 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1055 | 2026-10 | Weekly |  | 1768 | 0 | 1768 | 0 | Agrees | Matched | 0
J1056 | 2026-08 | Weekly |  | 390 | 390 | 0 | 0 | Agrees | Billed in Jobber | 0
J1056 | 2026-09 | Weekly |  | 390 | 390 | 0 | 0 | Agrees | Billed in Jobber | 0
J1056 | 2026-10 | Weekly |  | 390 | 390 | 0 | 0 | Agrees | Billed in Jobber | 0
J1057 | 2026-08 | Weekly |  | 524.33 | 0 | 524.33 | 0 | Agrees | Matched | 0
J1057 | 2026-09 | Weekly |  | 524.33 | 0 | 524.33 | 0 | Agrees | Matched | 0
J1057 | 2026-10 | Weekly |  | 524.33 | 0 | 524.33 | 0 | Agrees | Matched | 0
J1058 | 2026-08 | Weekly |  | 975 | 0 | 975 | 0 | Agrees | Matched | 0
J1058 | 2026-09 | Weekly |  | 975 | 0 | 975 | 0 | Agrees | Matched | 0
J1058 | 2026-10 | Weekly |  | 975 | 0 | 975 | 0 | Agrees | Matched | 0
J1059 | 2026-08 | Weekly |  | 1170 | 0 | 0 | -1170 | Under-billed | Not billed | -1170
J1059 | 2026-09 | Weekly |  | 1170 | 0 | 0 | -1170 | Under-billed | Not billed | -1170
J1059 | 2026-10 | Weekly |  | 1170 | 0 | 0 | -1170 | Under-billed | Not billed | -1170
J1060 | 2026-08 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1060 | 2026-09 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1060 | 2026-10 | Weekly |  | 1603.33 | 0 | 1542.67 | -60.66 | Under-billed | Rate mismatch | -60.66
J1061 | 2026-08 | Weekly |  | 1100.67 | 1100.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1061 | 2026-09 | Weekly |  | 1100.67 | 1100.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1061 | 2026-10 | Weekly |  | 1100.67 | 1100.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1062 | 2026-08 | Weekly |  | 2513.33 | 2513.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1062 | 2026-09 | Weekly |  | 2513.33 | 2513.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1062 | 2026-10 | Weekly |  | 2513.33 | 2513.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1063 | 2026-08 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1063 | 2026-09 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1063 | 2026-10 | Every 4 weeks | 2 | 436 | 436 | 0 | 0 | Agrees | Billed in Jobber | 0
J1064 | 2026-08 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1064 | 2026-09 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1064 | 2026-10 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1065 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 130 | -5 | Under-billed | Rate mismatch | -5
J1065 | 2026-09 | Every 4 weeks | 2 | 270 | 0 | 260 | -10 | Under-billed | Rate mismatch | -10
J1065 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 130 | -5 | Under-billed | Rate mismatch | -5
J1066 | 2026-08 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1066 | 2026-09 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1066 | 2026-10 | Weekly |  | 2093 | 0 | 2093 | 0 | Agrees | Matched | 0
J1067 | 2026-08 | Every 4 weeks | 2 | 232 | 0 | 232 | 0 | Agrees | Matched | 0
J1067 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1067 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1068 | 2026-08 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1068 | 2026-09 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1068 | 2026-10 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1069 | 2026-08 | Weekly |  | 897 | 0 | 897 | 0 | Agrees | Matched | 0
J1069 | 2026-09 | Weekly |  | 897 | 0 | 897 | 0 | Agrees | Matched | 0
J1069 | 2026-10 | Weekly |  | 897 | 0 | 897 | 0 | Agrees | Matched | 0
J1070 | 2026-08 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1070 | 2026-09 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1070 | 2026-10 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1071 | 2026-08 | Weekly |  | 784.33 | 0 | 1568.66 | 784.33 | Over-billed | Duplicate in QBO | 784.33
J1071 | 2026-09 | Weekly |  | 784.33 | 0 | 1568.66 | 784.33 | Over-billed | Duplicate in QBO | 784.33
J1071 | 2026-10 | Weekly |  | 784.33 | 0 | 1568.66 | 784.33 | Over-billed | Duplicate in QBO | 784.33
J1072 | 2026-08 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1072 | 2026-09 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1072 | 2026-10 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1073 | 2026-08 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1073 | 2026-09 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1073 | 2026-10 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1074 | 2026-08 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1074 | 2026-09 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1074 | 2026-10 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1075 | 2026-08 | Weekly |  | 320.67 | 320.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1075 | 2026-09 | Weekly |  | 320.67 | 320.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1075 | 2026-10 | Weekly |  | 320.67 | 320.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1076 | 2026-08 | Every 4 weeks | 1 | 102 | 0 | 102 | 0 | Agrees | Matched | 0
J1076 | 2026-09 | Every 4 weeks | 1 | 102 | 0 | 102 | 0 | Agrees | Matched | 0
J1076 | 2026-10 | Every 4 weeks | 1 | 102 | 0 | 102 | 0 | Agrees | Matched | 0
J1077 | 2026-08 | Weekly |  | 1625 | 0 | 0 | -1625 | Under-billed | Not billed | -1625
J1077 | 2026-09 | Weekly |  | 1625 | 0 | 0 | -1625 | Under-billed | Not billed | -1625
J1077 | 2026-10 | Weekly |  | 1625 | 0 | 0 | -1625 | Under-billed | Not billed | -1625
J1078 | 2026-08 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1078 | 2026-09 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1078 | 2026-10 | Weekly |  | 273 | 0 | 273 | 0 | Agrees | Matched | 0
J1079 | 2026-08 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1079 | 2026-09 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1079 | 2026-10 | Weekly |  | 286 | 0 | 286 | 0 | Agrees | Matched | 0
J1080 | 2026-08 | Every 4 weeks | 2 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1080 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1080 | 2026-10 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1081 | 2026-08 | Weekly |  | 1690 | 0 | 3380 | 1690 | Over-billed | Duplicate in QBO | 1690
J1081 | 2026-09 | Weekly |  | 1690 | 0 | 3380 | 1690 | Over-billed | Duplicate in QBO | 1690
J1081 | 2026-10 | Weekly |  | 1690 | 0 | 3380 | 1690 | Over-billed | Duplicate in QBO | 1690
J1082 | 2026-08 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1082 | 2026-09 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1082 | 2026-10 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1083 | 2026-08 | Weekly |  | 1625 | 0 | 1625 | 0 | Agrees | Matched | 0
J1083 | 2026-09 | Weekly |  | 1625 | 0 | 1625 | 0 | Agrees | Matched | 0
J1083 | 2026-10 | Weekly |  | 1625 | 0 | 1625 | 0 | Agrees | Matched | 0
J1084 | 2026-08 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1084 | 2026-09 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1084 | 2026-10 | Every 4 weeks | 1 | 234 | 234 | 0 | 0 | Agrees | Billed in Jobber | 0
J1085 | 2026-08 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1085 | 2026-09 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1085 | 2026-10 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1086 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1086 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1086 | 2026-10 | Every 4 weeks | 2 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1087 | 2026-08 | Monthly |  | 151 | 0 | 145 | -6 | Under-billed | Rate mismatch | -6
J1087 | 2026-09 | Monthly |  | 151 | 0 | 145 | -6 | Under-billed | Rate mismatch | -6
J1087 | 2026-10 | Monthly |  | 151 | 0 | 145 | -6 | Under-billed | Rate mismatch | -6
J1088 | 2026-08 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1088 | 2026-09 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1088 | 2026-10 | Weekly |  | 299 | 299 | 0 | 0 | Agrees | Billed in Jobber | 0
J1089 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1089 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1089 | 2026-10 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1090 | 2026-08 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1090 | 2026-09 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1090 | 2026-10 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1091 | 2026-08 | Weekly |  | 520 | 0 | 520 | 0 | Agrees | Matched | 0
J1091 | 2026-09 | Weekly |  | 520 | 0 | 520 | 0 | Agrees | Matched | 0
J1091 | 2026-10 | Weekly |  | 520 | 0 | 520 | 0 | Agrees | Matched | 0
J1092 | 2026-08 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1092 | 2026-09 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1092 | 2026-10 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1093 | 2026-08 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1093 | 2026-09 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1093 | 2026-10 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1094 | 2026-08 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1094 | 2026-09 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1094 | 2026-10 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1095 | 2026-08 | Every 4 weeks | 1 | 102 | 0 | 102 | 0 | Agrees | Matched | 0
J1095 | 2026-09 | Every 4 weeks | 2 | 204 | 0 | 204 | 0 | Agrees | Matched | 0
J1095 | 2026-10 | Every 4 weeks | 1 | 102 | 0 | 102 | 0 | Agrees | Matched | 0
J1096 | 2026-08 | Weekly |  | 1755 | 0 | 1755 | 0 | Agrees | Matched | 0
J1096 | 2026-09 | Weekly |  | 1755 | 0 | 1755 | 0 | Agrees | Matched | 0
J1096 | 2026-10 | Weekly |  | 1755 | 0 | 1755 | 0 | Agrees | Matched | 0
J1097 | 2026-08 | Weekly |  | 1716 | 1716 | 1716 | 1716 | Over-billed | Double-billing risk | 1716
J1097 | 2026-09 | Weekly |  | 1716 | 1716 | 1716 | 1716 | Over-billed | Double-billing risk | 1716
J1097 | 2026-10 | Weekly |  | 1716 | 1716 | 1716 | 1716 | Over-billed | Double-billing risk | 1716
J1098 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 112 | -4 | Under-billed | Rate mismatch | -4
J1098 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 112 | -4 | Under-billed | Rate mismatch | -4
J1098 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 112 | -4 | Under-billed | Rate mismatch | -4
J1099 | 2026-08 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1099 | 2026-09 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1099 | 2026-10 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1100 | 2026-08 | Weekly |  | 1005.33 | 0 | 1005.33 | 0 | Agrees | Matched | 0
J1100 | 2026-09 | Weekly |  | 1005.33 | 0 | 1005.33 | 0 | Agrees | Matched | 0
J1100 | 2026-10 | Weekly |  | 1005.33 | 0 | 1005.33 | 0 | Agrees | Matched | 0
J1101 | 2026-08 | Every 4 weeks | 2 | 436 | 436 | 0 | 0 | Agrees | Billed in Jobber | 0
J1101 | 2026-09 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1101 | 2026-10 | Every 4 weeks | 1 | 218 | 218 | 0 | 0 | Agrees | Billed in Jobber | 0
J1102 | 2026-08 | Weekly |  | 875.33 | 875.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1102 | 2026-09 | Weekly |  | 875.33 | 875.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1102 | 2026-10 | Weekly |  | 875.33 | 875.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1103 | 2026-08 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1103 | 2026-09 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1103 | 2026-10 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1104 | 2026-08 | Weekly |  | 502.67 | 0 | 464 | -38.67 | Under-billed | Basis mismatch | -38.67
J1104 | 2026-09 | Weekly |  | 502.67 | 0 | 464 | -38.67 | Under-billed | Basis mismatch | -38.67
J1104 | 2026-10 | Weekly |  | 502.67 | 0 | 464 | -38.67 | Under-billed | Basis mismatch | -38.67
J1105 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1105 | 2026-09 | Every 4 weeks | 2 | 436 | 0 | 436 | 0 | Agrees | Matched | 0
J1105 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1106 | 2026-08 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1106 | 2026-09 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1106 | 2026-10 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1107 | 2026-08 | Weekly |  | 2643.33 | 0 | 2440 | -203.33 | Under-billed | Basis mismatch | -203.33
J1107 | 2026-09 | Weekly |  | 2643.33 | 0 | 2440 | -203.33 | Under-billed | Basis mismatch | -203.33
J1107 | 2026-10 | Weekly |  | 2643.33 | 0 | 2440 | -203.33 | Under-billed | Basis mismatch | -203.33
J1108 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1108 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1108 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1109 | 2026-08 | Weekly |  | 606.67 | 0 | 606.67 | 0 | Agrees | Matched | 0
J1109 | 2026-09 | Weekly |  | 606.67 | 0 | 606.67 | 0 | Agrees | Matched | 0
J1109 | 2026-10 | Weekly |  | 606.67 | 0 | 606.67 | 0 | Agrees | Matched | 0
J1110 | 2026-08 | Weekly |  | 2123.33 | 0 | 2123.33 | 0 | Agrees | Matched | 0
J1110 | 2026-09 | Weekly |  | 2123.33 | 0 | 2123.33 | 0 | Agrees | Matched | 0
J1110 | 2026-10 | Weekly |  | 2123.33 | 0 | 2123.33 | 0 | Agrees | Matched | 0
J1111 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 105 | -4 | Under-billed | Rate mismatch | -4
J1111 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 105 | -4 | Under-billed | Rate mismatch | -4
J1111 | 2026-10 | Every 4 weeks | 1 | 109 | 0 | 105 | -4 | Under-billed | Rate mismatch | -4
J1112 | 2026-08 | Weekly |  | 130 | 0 | 130 | 0 | Agrees | Matched | 0
J1112 | 2026-09 | Weekly |  | 130 | 0 | 130 | 0 | Agrees | Matched | 0
J1112 | 2026-10 | Weekly |  | 130 | 0 | 130 | 0 | Agrees | Matched | 0
J1113 | 2026-08 | Weekly |  | 814.67 | 814.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1113 | 2026-09 | Weekly |  | 814.67 | 814.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1113 | 2026-10 | Weekly |  | 814.67 | 814.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1114 | 2026-08 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1114 | 2026-09 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1114 | 2026-10 | Monthly |  | 125 | 0 | 125 | 0 | Agrees | Matched | 0
J1115 | 2026-08 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1115 | 2026-09 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1115 | 2026-10 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1116 | 2026-08 | Weekly |  | 801.67 | 0 | 801.67 | 0 | Agrees | Matched | 0
J1116 | 2026-09 | Weekly |  | 801.67 | 0 | 801.67 | 0 | Agrees | Matched | 0
J1116 | 2026-10 | Weekly |  | 801.67 | 0 | 801.67 | 0 | Agrees | Matched | 0
J1117 | 2026-08 | Weekly |  | 1100.67 | 0 | 1100.67 | 0 | Agrees | Matched | 0
J1117 | 2026-09 | Weekly |  | 1100.67 | 0 | 1100.67 | 0 | Agrees | Matched | 0
J1117 | 2026-10 | Weekly |  | 1100.67 | 0 | 1100.67 | 0 | Agrees | Matched | 0
J1118 | 2026-08 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1118 | 2026-09 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1118 | 2026-10 | Weekly |  | 810.33 | 0 | 748 | -62.33 | Under-billed | Basis mismatch | -62.33
J1119 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1119 | 2026-09 | Every 4 weeks | 2 | 232 | 0 | 232 | 0 | Agrees | Matched | 0
J1119 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1120 | 2026-08 | Weekly |  | 502.67 | 0 | 502.67 | 0 | Agrees | Matched | 0
J1120 | 2026-09 | Weekly |  | 502.67 | 0 | 502.67 | 0 | Agrees | Matched | 0
J1120 | 2026-10 | Weekly |  | 502.67 | 0 | 502.67 | 0 | Agrees | Matched | 0
J1121 | 2026-08 | Weekly |  | 138.67 | 0 | 134.33 | -4.34 | Under-billed | Rate mismatch | -4.34
J1121 | 2026-09 | Weekly |  | 138.67 | 0 | 134.33 | -4.34 | Under-billed | Rate mismatch | -4.34
J1121 | 2026-10 | Weekly |  | 138.67 | 0 | 134.33 | -4.34 | Under-billed | Rate mismatch | -4.34
J1122 | 2026-08 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1122 | 2026-09 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1122 | 2026-10 | Weekly |  | 559 | 0 | 559 | 0 | Agrees | Matched | 0
J1123 | 2026-08 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1123 | 2026-09 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1123 | 2026-10 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1124 | 2026-08 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1124 | 2026-09 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1124 | 2026-10 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1125 | 2026-08 | Weekly |  | 1352 | 0 | 1300 | -52 | Under-billed | Rate mismatch | -52
J1125 | 2026-09 | Weekly |  | 1352 | 0 | 1300 | -52 | Under-billed | Rate mismatch | -52
J1125 | 2026-10 | Weekly |  | 1352 | 0 | 1300 | -52 | Under-billed | Rate mismatch | -52
J1126 | 2026-08 | Every 4 weeks | 2 | 232 | 232 | 0 | 0 | Agrees | Billed in Jobber | 0
J1126 | 2026-09 | Every 4 weeks | 1 | 116 | 116 | 0 | 0 | Agrees | Billed in Jobber | 0
J1126 | 2026-10 | Every 4 weeks | 1 | 116 | 116 | 0 | 0 | Agrees | Billed in Jobber | 0
J1127 | 2026-08 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1127 | 2026-09 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1127 | 2026-10 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1128 | 2026-08 | Weekly |  | 650 | 0 | 650 | 0 | Agrees | Matched | 0
J1128 | 2026-09 | Weekly |  | 650 | 0 | 650 | 0 | Agrees | Matched | 0
J1128 | 2026-10 | Weekly |  | 650 | 0 | 650 | 0 | Agrees | Matched | 0
J1129 | 2026-08 | Weekly |  | 550.33 | 0 | 550.33 | 0 | Agrees | Matched | 0
J1129 | 2026-09 | Weekly |  | 550.33 | 0 | 550.33 | 0 | Agrees | Matched | 0
J1129 | 2026-10 | Weekly |  | 550.33 | 0 | 550.33 | 0 | Agrees | Matched | 0
J1130 | 2026-08 | Every 4 weeks | 2 | 406 | 0 | 406 | 0 | Agrees | Matched | 0
J1130 | 2026-09 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1130 | 2026-10 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1131 | 2026-08 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1131 | 2026-09 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1131 | 2026-10 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1132 | 2026-08 | Weekly |  | 1135.33 | 1135.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1132 | 2026-09 | Weekly |  | 1135.33 | 1135.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1132 | 2026-10 | Weekly |  | 1135.33 | 1135.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1133 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1133 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1133 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1134 | 2026-08 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1134 | 2026-09 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1134 | 2026-10 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1135 | 2026-08 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1135 | 2026-09 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1135 | 2026-10 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1136 | 2026-08 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1136 | 2026-09 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1136 | 2026-10 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1137 | 2026-08 | Weekly |  | 524.33 | 0 | 502.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1137 | 2026-09 | Weekly |  | 524.33 | 0 | 502.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1137 | 2026-10 | Weekly |  | 524.33 | 0 | 502.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1138 | 2026-08 | Weekly |  | 632.67 | 0 | 632.67 | 0 | Agrees | Matched | 0
J1138 | 2026-09 | Weekly |  | 632.67 | 0 | 632.67 | 0 | Agrees | Matched | 0
J1138 | 2026-10 | Weekly |  | 632.67 | 0 | 632.67 | 0 | Agrees | Matched | 0
J1139 | 2026-08 | Weekly |  | 1170 | 0 | 1170 | 0 | Agrees | Matched | 0
J1139 | 2026-09 | Weekly |  | 1170 | 0 | 1170 | 0 | Agrees | Matched | 0
J1139 | 2026-10 | Weekly |  | 1170 | 0 | 1170 | 0 | Agrees | Matched | 0
J1140 | 2026-08 | Weekly |  | 650 | 650 | 650 | 650 | Over-billed | Double-billing risk | 650
J1140 | 2026-09 | Weekly |  | 650 | 650 | 650 | 650 | Over-billed | Double-billing risk | 650
J1140 | 2026-10 | Weekly |  | 650 | 650 | 650 | 650 | Over-billed | Double-billing risk | 650
J1141 | 2026-08 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1141 | 2026-09 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1141 | 2026-10 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1142 | 2026-08 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1142 | 2026-09 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1142 | 2026-10 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1143 | 2026-08 | Weekly |  | 1092 | 1092 | 1092 | 1092 | Over-billed | Double-billing risk | 1092
J1143 | 2026-09 | Weekly |  | 1092 | 1092 | 1092 | 1092 | Over-billed | Double-billing risk | 1092
J1143 | 2026-10 | Weekly |  | 1092 | 1092 | 1092 | 1092 | Over-billed | Double-billing risk | 1092
J1144 | 2026-08 | Weekly |  | 676 | 0 | 676 | 0 | Agrees | Matched | 0
J1144 | 2026-09 | Weekly |  | 676 | 0 | 676 | 0 | Agrees | Matched | 0
J1144 | 2026-10 | Weekly |  | 676 | 0 | 676 | 0 | Agrees | Matched | 0
J1145 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1145 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1145 | 2026-10 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1146 | 2026-08 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1146 | 2026-09 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1146 | 2026-10 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1147 | 2026-08 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1147 | 2026-09 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1147 | 2026-10 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1148 | 2026-08 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1148 | 2026-09 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1148 | 2026-10 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1149 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1149 | 2026-09 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1149 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1150 | 2026-08 | Weekly |  | 975 | 0 | 936 | -39 | Under-billed | Rate mismatch | -39
J1150 | 2026-09 | Weekly |  | 975 | 0 | 936 | -39 | Under-billed | Rate mismatch | -39
J1150 | 2026-10 | Weekly |  | 975 | 0 | 936 | -39 | Under-billed | Rate mismatch | -39
J1151 | 2026-08 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1151 | 2026-09 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1151 | 2026-10 | Every 4 weeks | 2 | 406 | 0 | 406 | 0 | Agrees | Matched | 0
J1152 | 2026-08 | Weekly |  | 1568.67 | 0 | 1568.67 | 0 | Agrees | Matched | 0
J1152 | 2026-09 | Weekly |  | 1568.67 | 0 | 1568.67 | 0 | Agrees | Matched | 0
J1152 | 2026-10 | Weekly |  | 1568.67 | 0 | 1568.67 | 0 | Agrees | Matched | 0
J1153 | 2026-08 | Monthly |  | 99 | 0 | 95 | -4 | Under-billed | Rate mismatch | -4
J1153 | 2026-09 | Monthly |  | 99 | 0 | 95 | -4 | Under-billed | Rate mismatch | -4
J1153 | 2026-10 | Monthly |  | 99 | 0 | 95 | -4 | Under-billed | Rate mismatch | -4
J1154 | 2026-08 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1154 | 2026-09 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1154 | 2026-10 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1155 | 2026-08 | Weekly |  | 528.67 | 0 | 1057.34 | 528.67 | Over-billed | Duplicate in QBO | 528.67
J1155 | 2026-09 | Weekly |  | 528.67 | 0 | 1057.34 | 528.67 | Over-billed | Duplicate in QBO | 528.67
J1155 | 2026-10 | Weekly |  | 528.67 | 0 | 1057.34 | 528.67 | Over-billed | Duplicate in QBO | 528.67
J1156 | 2026-08 | Weekly |  | 1655.33 | 0 | 1655.33 | 0 | Agrees | Matched | 0
J1156 | 2026-09 | Weekly |  | 1655.33 | 0 | 1655.33 | 0 | Agrees | Matched | 0
J1156 | 2026-10 | Weekly |  | 1655.33 | 0 | 1655.33 | 0 | Agrees | Matched | 0
J1157 | 2026-08 | Weekly |  | 1898 | 0 | 1752 | -146 | Under-billed | Basis mismatch | -146
J1157 | 2026-09 | Weekly |  | 1898 | 0 | 1752 | -146 | Under-billed | Basis mismatch | -146
J1157 | 2026-10 | Weekly |  | 1898 | 0 | 1752 | -146 | Under-billed | Basis mismatch | -146
J1158 | 2026-08 | Weekly |  | 1256.67 | 0 | 1213.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1158 | 2026-09 | Weekly |  | 1256.67 | 0 | 1213.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1158 | 2026-10 | Weekly |  | 1256.67 | 0 | 1213.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1159 | 2026-08 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1159 | 2026-09 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1159 | 2026-10 | Weekly |  | 277.33 | 0 | 277.33 | 0 | Agrees | Matched | 0
J1160 | 2026-08 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1160 | 2026-09 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1160 | 2026-10 | Monthly |  | 88 | 0 | 85 | -3 | Under-billed | Rate mismatch | -3
J1161 | 2026-08 | Weekly |  | 268.67 | 0 | 268.67 | 0 | Agrees | Matched | 0
J1161 | 2026-09 | Weekly |  | 268.67 | 0 | 268.67 | 0 | Agrees | Matched | 0
J1161 | 2026-10 | Weekly |  | 268.67 | 0 | 268.67 | 0 | Agrees | Matched | 0
J1162 | 2026-08 | Weekly |  | 585 | 0 | 585 | 0 | Agrees | Matched | 0
J1162 | 2026-09 | Weekly |  | 585 | 0 | 585 | 0 | Agrees | Matched | 0
J1162 | 2026-10 | Weekly |  | 585 | 0 | 585 | 0 | Agrees | Matched | 0
J1163 | 2026-08 | Weekly |  | 268.67 | 0 | 0 | -268.67 | Under-billed | Not billed | -268.67
J1163 | 2026-09 | Weekly |  | 268.67 | 0 | 0 | -268.67 | Under-billed | Not billed | -268.67
J1163 | 2026-10 | Weekly |  | 268.67 | 0 | 0 | -268.67 | Under-billed | Not billed | -268.67
J1164 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1164 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1164 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1165 | 2026-08 | Weekly |  | 546 | 0 | 0 | -546 | Under-billed | Not billed | -546
J1165 | 2026-09 | Weekly |  | 546 | 0 | 0 | -546 | Under-billed | Not billed | -546
J1165 | 2026-10 | Weekly |  | 546 | 0 | 0 | -546 | Under-billed | Not billed | -546
J1166 | 2026-08 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1166 | 2026-09 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1166 | 2026-10 | Weekly |  | 1438.67 | 0 | 1438.67 | 0 | Agrees | Matched | 0
J1167 | 2026-08 | Weekly |  | 307.67 | 0 | 307.67 | 0 | Agrees | Matched | 0
J1167 | 2026-09 | Weekly |  | 307.67 | 0 | 307.67 | 0 | Agrees | Matched | 0
J1167 | 2026-10 | Weekly |  | 307.67 | 0 | 307.67 | 0 | Agrees | Matched | 0
J1168 | 2026-08 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1168 | 2026-09 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1168 | 2026-10 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1169 | 2026-08 | Weekly |  | 1560 | 0 | 1560 | 0 | Agrees | Matched | 0
J1169 | 2026-09 | Weekly |  | 1560 | 0 | 1560 | 0 | Agrees | Matched | 0
J1169 | 2026-10 | Weekly |  | 1560 | 0 | 1560 | 0 | Agrees | Matched | 0
J1170 | 2026-08 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1170 | 2026-09 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1170 | 2026-10 | Weekly |  | 251.33 | 0 | 251.33 | 0 | Agrees | Matched | 0
J1171 | 2026-08 | Weekly |  | 2621.67 | 0 | 2513.33 | -108.34 | Under-billed | Rate mismatch | -108.34
J1171 | 2026-09 | Weekly |  | 2621.67 | 0 | 2513.33 | -108.34 | Under-billed | Rate mismatch | -108.34
J1171 | 2026-10 | Weekly |  | 2621.67 | 0 | 2513.33 | -108.34 | Under-billed | Rate mismatch | -108.34
J1172 | 2026-08 | Weekly |  | 1343.33 | 1343.33 | 1343.33 | 1343.33 | Over-billed | Double-billing risk | 1343.33
J1172 | 2026-09 | Weekly |  | 1343.33 | 1343.33 | 1343.33 | 1343.33 | Over-billed | Double-billing risk | 1343.33
J1172 | 2026-10 | Weekly |  | 1343.33 | 1343.33 | 1343.33 | 1343.33 | Over-billed | Double-billing risk | 1343.33
J1173 | 2026-08 | Every 4 weeks | 1 | 116 | 116 | 0 | 0 | Agrees | Billed in Jobber | 0
J1173 | 2026-09 | Every 4 weeks | 1 | 116 | 116 | 0 | 0 | Agrees | Billed in Jobber | 0
J1173 | 2026-10 | Every 4 weeks | 1 | 116 | 116 | 0 | 0 | Agrees | Billed in Jobber | 0
J1174 | 2026-08 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1174 | 2026-09 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1174 | 2026-10 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1175 | 2026-08 | Weekly |  | 420.33 | 0 | 420.33 | 0 | Agrees | Matched | 0
J1175 | 2026-09 | Weekly |  | 420.33 | 0 | 420.33 | 0 | Agrees | Matched | 0
J1175 | 2026-10 | Weekly |  | 420.33 | 0 | 420.33 | 0 | Agrees | Matched | 0
J1176 | 2026-08 | Weekly |  | 316.33 | 0 | 619.66 | 303.33 | Over-billed | Duplicate in QBO | 303.33
J1176 | 2026-09 | Weekly |  | 316.33 | 0 | 619.66 | 303.33 | Over-billed | Duplicate in QBO | 303.33
J1176 | 2026-10 | Weekly |  | 316.33 | 0 | 619.66 | 303.33 | Over-billed | Duplicate in QBO | 303.33
J1177 | 2026-08 | Weekly |  | 320.67 | 0 | 296 | -24.67 | Under-billed | Basis mismatch | -24.67
J1177 | 2026-09 | Weekly |  | 320.67 | 0 | 296 | -24.67 | Under-billed | Basis mismatch | -24.67
J1177 | 2026-10 | Weekly |  | 320.67 | 0 | 296 | -24.67 | Under-billed | Basis mismatch | -24.67
J1178 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1178 | 2026-09 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1178 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1179 | 2026-08 | Weekly |  | 528.67 | 0 | 488 | -40.67 | Under-billed | Basis mismatch | -40.67
J1179 | 2026-09 | Weekly |  | 528.67 | 0 | 488 | -40.67 | Under-billed | Basis mismatch | -40.67
J1179 | 2026-10 | Weekly |  | 528.67 | 0 | 488 | -40.67 | Under-billed | Basis mismatch | -40.67
J1180 | 2026-08 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1180 | 2026-09 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1180 | 2026-10 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1181 | 2026-08 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1181 | 2026-09 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1181 | 2026-10 | Weekly |  | 884 | 0 | 884 | 0 | Agrees | Matched | 0
J1182 | 2026-08 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1182 | 2026-09 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1182 | 2026-10 | Weekly |  | 654.33 | 0 | 654.33 | 0 | Agrees | Matched | 0
J1183 | 2026-08 | Weekly |  | 1083.33 | 1083.33 | 1083.33 | 1083.33 | Over-billed | Double-billing risk | 1083.33
J1183 | 2026-09 | Weekly |  | 1083.33 | 1083.33 | 1083.33 | 1083.33 | Over-billed | Double-billing risk | 1083.33
J1183 | 2026-10 | Weekly |  | 1083.33 | 1083.33 | 1083.33 | 1083.33 | Over-billed | Double-billing risk | 1083.33
J1184 | 2026-08 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1184 | 2026-09 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1184 | 2026-10 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1185 | 2026-08 | Every 4 weeks | 1 | 146 | 146 | 0 | 0 | Agrees | Billed in Jobber | 0
J1185 | 2026-09 | Every 4 weeks | 1 | 146 | 146 | 0 | 0 | Agrees | Billed in Jobber | 0
J1185 | 2026-10 | Every 4 weeks | 1 | 146 | 146 | 0 | 0 | Agrees | Billed in Jobber | 0
J1186 | 2026-08 | Weekly |  | 563.33 | 0 | 541.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1186 | 2026-09 | Weekly |  | 563.33 | 0 | 541.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1186 | 2026-10 | Weekly |  | 563.33 | 0 | 541.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1187 | 2026-08 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1187 | 2026-09 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1187 | 2026-10 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1188 | 2026-08 | Weekly |  | 1100.67 | 0 | 1057.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1188 | 2026-09 | Weekly |  | 1100.67 | 0 | 1057.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1188 | 2026-10 | Weekly |  | 1100.67 | 0 | 1057.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1189 | 2026-08 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1189 | 2026-09 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1189 | 2026-10 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1190 | 2026-08 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1190 | 2026-09 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1190 | 2026-10 | Weekly |  | 173.33 | 173.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1191 | 2026-08 | Weekly |  | 407.33 | 0 | 376 | -31.33 | Under-billed | Basis mismatch | -31.33
J1191 | 2026-09 | Weekly |  | 407.33 | 0 | 376 | -31.33 | Under-billed | Basis mismatch | -31.33
J1191 | 2026-10 | Weekly |  | 407.33 | 0 | 376 | -31.33 | Under-billed | Basis mismatch | -31.33
J1192 | 2026-08 | Weekly |  | 862.33 | 0 | 862.33 | 0 | Agrees | Matched | 0
J1192 | 2026-09 | Weekly |  | 862.33 | 0 | 862.33 | 0 | Agrees | Matched | 0
J1192 | 2026-10 | Weekly |  | 862.33 | 0 | 862.33 | 0 | Agrees | Matched | 0
J1193 | 2026-08 | Weekly |  | 463.67 | 463.67 | 463.67 | 463.67 | Over-billed | Double-billing risk | 463.67
J1193 | 2026-09 | Weekly |  | 463.67 | 463.67 | 463.67 | 463.67 | Over-billed | Double-billing risk | 463.67
J1193 | 2026-10 | Weekly |  | 463.67 | 463.67 | 463.67 | 463.67 | Over-billed | Double-billing risk | 463.67
J1194 | 2026-08 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1194 | 2026-09 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1194 | 2026-10 | Weekly |  | 1386.67 | 0 | 1386.67 | 0 | Agrees | Matched | 0
J1195 | 2026-08 | Weekly |  | 156 | 0 | 307.67 | 151.67 | Over-billed | Duplicate in QBO | 151.67
J1195 | 2026-09 | Weekly |  | 156 | 0 | 307.67 | 151.67 | Over-billed | Duplicate in QBO | 151.67
J1195 | 2026-10 | Weekly |  | 156 | 0 | 307.67 | 151.67 | Over-billed | Duplicate in QBO | 151.67
J1196 | 2026-08 | Weekly |  | 1204.67 | 0 | 1204.67 | 0 | Agrees | Matched | 0
J1196 | 2026-09 | Weekly |  | 1204.67 | 0 | 1204.67 | 0 | Agrees | Matched | 0
J1196 | 2026-10 | Weekly |  | 1204.67 | 0 | 1204.67 | 0 | Agrees | Matched | 0
J1197 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1197 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1197 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1198 | 2026-08 | Weekly |  | 602.33 | 0 | 580.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1198 | 2026-09 | Weekly |  | 602.33 | 0 | 580.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1198 | 2026-10 | Weekly |  | 602.33 | 0 | 580.67 | -21.66 | Under-billed | Rate mismatch | -21.66
J1199 | 2026-08 | Weekly |  | 320.67 | 0 | 320.67 | 0 | Agrees | Matched | 0
J1199 | 2026-09 | Weekly |  | 320.67 | 0 | 320.67 | 0 | Agrees | Matched | 0
J1199 | 2026-10 | Weekly |  | 320.67 | 0 | 320.67 | 0 | Agrees | Matched | 0
J1200 | 2026-08 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1200 | 2026-09 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1200 | 2026-10 | Weekly |  | 260 | 0 | 251.33 | -8.67 | Under-billed | Rate mismatch | -8.67
J1201 | 2026-08 | Weekly |  | 563.33 | 0 | 563.33 | 0 | Agrees | Matched | 0
J1201 | 2026-09 | Weekly |  | 563.33 | 0 | 563.33 | 0 | Agrees | Matched | 0
J1201 | 2026-10 | Weekly |  | 563.33 | 0 | 563.33 | 0 | Agrees | Matched | 0
J1202 | 2026-08 | Every 4 weeks | 1 | 234 | 0 | 234 | 0 | Agrees | Matched | 0
J1202 | 2026-09 | Every 4 weeks | 1 | 234 | 0 | 234 | 0 | Agrees | Matched | 0
J1202 | 2026-10 | Every 4 weeks | 1 | 234 | 0 | 234 | 0 | Agrees | Matched | 0
J1203 | 2026-08 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1203 | 2026-09 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1203 | 2026-10 | Weekly |  | 1352 | 0 | 1352 | 0 | Agrees | Matched | 0
J1204 | 2026-08 | Weekly |  | 1495 | 1495 | 0 | 0 | Agrees | Billed in Jobber | 0
J1204 | 2026-09 | Weekly |  | 1495 | 1495 | 0 | 0 | Agrees | Billed in Jobber | 0
J1204 | 2026-10 | Weekly |  | 1495 | 1495 | 0 | 0 | Agrees | Billed in Jobber | 0
J1205 | 2026-08 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1205 | 2026-09 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1205 | 2026-10 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1206 | 2026-08 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1206 | 2026-09 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1206 | 2026-10 | Every 4 weeks | 1 | 135 | 135 | 0 | 0 | Agrees | Billed in Jobber | 0
J1207 | 2026-08 | Weekly |  | 806 | 0 | 0 | -806 | Under-billed | Not billed | -806
J1207 | 2026-09 | Weekly |  | 806 | 0 | 0 | -806 | Under-billed | Not billed | -806
J1207 | 2026-10 | Weekly |  | 806 | 0 | 0 | -806 | Under-billed | Not billed | -806
J1208 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1208 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1208 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1209 | 2026-08 | Weekly |  | 858 | 0 | 858 | 0 | Agrees | Matched | 0
J1209 | 2026-09 | Weekly |  | 858 | 0 | 858 | 0 | Agrees | Matched | 0
J1209 | 2026-10 | Weekly |  | 858 | 0 | 858 | 0 | Agrees | Matched | 0
J1210 | 2026-08 | Weekly |  | 424.67 | 0 | 392 | -32.67 | Under-billed | Basis mismatch | -32.67
J1210 | 2026-09 | Weekly |  | 424.67 | 0 | 392 | -32.67 | Under-billed | Basis mismatch | -32.67
J1210 | 2026-10 | Weekly |  | 424.67 | 0 | 392 | -32.67 | Under-billed | Basis mismatch | -32.67
J1211 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1211 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1211 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1212 | 2026-08 | Weekly |  | 3596.67 | 0 | 3320 | -276.67 | Under-billed | Basis mismatch | -276.67
J1212 | 2026-09 | Weekly |  | 3596.67 | 0 | 3320 | -276.67 | Under-billed | Basis mismatch | -276.67
J1212 | 2026-10 | Weekly |  | 3596.67 | 0 | 3320 | -276.67 | Under-billed | Basis mismatch | -276.67
J1213 | 2026-08 | Weekly |  | 1755 | 1755 | 0 | 0 | Agrees | Billed in Jobber | 0
J1213 | 2026-09 | Weekly |  | 1755 | 1755 | 0 | 0 | Agrees | Billed in Jobber | 0
J1213 | 2026-10 | Weekly |  | 1755 | 1755 | 0 | 0 | Agrees | Billed in Jobber | 0
J1214 | 2026-08 | Weekly |  | 463.67 | 0 | 463.67 | 0 | Agrees | Matched | 0
J1214 | 2026-09 | Weekly |  | 463.67 | 0 | 463.67 | 0 | Agrees | Matched | 0
J1214 | 2026-10 | Weekly |  | 463.67 | 0 | 463.67 | 0 | Agrees | Matched | 0
J1215 | 2026-08 | Weekly |  | 1495 | 1495 | 1495 | 1495 | Over-billed | Double-billing risk | 1495
J1215 | 2026-09 | Weekly |  | 1495 | 1495 | 1495 | 1495 | Over-billed | Double-billing risk | 1495
J1215 | 2026-10 | Weekly |  | 1495 | 1495 | 1495 | 1495 | Over-billed | Double-billing risk | 1495
J1216 | 2026-08 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1216 | 2026-09 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1216 | 2026-10 | Weekly |  | 1261 | 0 | 1261 | 0 | Agrees | Matched | 0
J1217 | 2026-08 | Weekly |  | 572 | 0 | 572 | 0 | Agrees | Matched | 0
J1217 | 2026-09 | Weekly |  | 572 | 0 | 572 | 0 | Agrees | Matched | 0
J1217 | 2026-10 | Weekly |  | 572 | 0 | 572 | 0 | Agrees | Matched | 0
J1218 | 2026-08 | Weekly |  | 814.67 | 0 | 814.67 | 0 | Agrees | Matched | 0
J1218 | 2026-09 | Weekly |  | 814.67 | 0 | 814.67 | 0 | Agrees | Matched | 0
J1218 | 2026-10 | Weekly |  | 814.67 | 0 | 814.67 | 0 | Agrees | Matched | 0
J1219 | 2026-08 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1219 | 2026-09 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1219 | 2026-10 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1220 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1220 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1220 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1221 | 2026-08 | Weekly |  | 780 | 0 | 780 | 0 | Agrees | Matched | 0
J1221 | 2026-09 | Weekly |  | 780 | 0 | 780 | 0 | Agrees | Matched | 0
J1221 | 2026-10 | Weekly |  | 780 | 0 | 780 | 0 | Agrees | Matched | 0
J1222 | 2026-08 | Weekly |  | 1005.33 | 0 | 928 | -77.33 | Under-billed | Basis mismatch | -77.33
J1222 | 2026-09 | Weekly |  | 1005.33 | 0 | 928 | -77.33 | Under-billed | Basis mismatch | -77.33
J1222 | 2026-10 | Weekly |  | 1005.33 | 0 | 928 | -77.33 | Under-billed | Basis mismatch | -77.33
J1223 | 2026-08 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1223 | 2026-09 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1223 | 2026-10 | Every 4 weeks | 1 | 135 | 0 | 135 | 0 | Agrees | Matched | 0
J1224 | 2026-08 | Weekly |  | 2903.33 | 2903.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1224 | 2026-09 | Weekly |  | 2903.33 | 2903.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1224 | 2026-10 | Weekly |  | 2903.33 | 2903.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1225 | 2026-08 | Weekly |  | 537.33 | 0 | 520 | -17.33 | Under-billed | Rate mismatch | -17.33
J1225 | 2026-09 | Weekly |  | 537.33 | 0 | 520 | -17.33 | Under-billed | Rate mismatch | -17.33
J1225 | 2026-10 | Weekly |  | 537.33 | 0 | 520 | -17.33 | Under-billed | Rate mismatch | -17.33
J1226 | 2026-08 | Weekly |  | 2210 | 0 | 2210 | 0 | Agrees | Matched | 0
J1226 | 2026-09 | Weekly |  | 2210 | 0 | 2210 | 0 | Agrees | Matched | 0
J1226 | 2026-10 | Weekly |  | 2210 | 0 | 2210 | 0 | Agrees | Matched | 0
J1227 | 2026-08 | Weekly |  | 554.67 | 0 | 512 | -42.67 | Under-billed | Basis mismatch | -42.67
J1227 | 2026-09 | Weekly |  | 554.67 | 0 | 512 | -42.67 | Under-billed | Basis mismatch | -42.67
J1227 | 2026-10 | Weekly |  | 554.67 | 0 | 512 | -42.67 | Under-billed | Basis mismatch | -42.67
J1228 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1228 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1228 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1229 | 2026-08 | Weekly |  | 125.67 | 0 | 116 | -9.67 | Under-billed | Basis mismatch | -9.67
J1229 | 2026-09 | Weekly |  | 125.67 | 0 | 116 | -9.67 | Under-billed | Basis mismatch | -9.67
J1229 | 2026-10 | Weekly |  | 125.67 | 0 | 116 | -9.67 | Under-billed | Basis mismatch | -9.67
J1230 | 2026-08 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1230 | 2026-09 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1230 | 2026-10 | Weekly |  | 580.67 | 0 | 580.67 | 0 | Agrees | Matched | 0
J1231 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1231 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1231 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1232 | 2026-08 | Weekly |  | 1672.67 | 1672.67 | 1672.67 | 1672.67 | Over-billed | Double-billing risk | 1672.67
J1232 | 2026-09 | Weekly |  | 1672.67 | 1672.67 | 1672.67 | 1672.67 | Over-billed | Double-billing risk | 1672.67
J1232 | 2026-10 | Weekly |  | 1672.67 | 1672.67 | 1672.67 | 1672.67 | Over-billed | Double-billing risk | 1672.67
J1233 | 2026-08 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1233 | 2026-09 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1233 | 2026-10 | Weekly |  | 1395.33 | 0 | 1395.33 | 0 | Agrees | Matched | 0
J1234 | 2026-08 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1234 | 2026-09 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1234 | 2026-10 | Weekly |  | 806 | 0 | 806 | 0 | Agrees | Matched | 0
J1235 | 2026-08 | Weekly |  | 1092 | 0 | 1092 | 0 | Agrees | Matched | 0
J1235 | 2026-09 | Weekly |  | 1092 | 0 | 1092 | 0 | Agrees | Matched | 0
J1235 | 2026-10 | Weekly |  | 1092 | 0 | 1092 | 0 | Agrees | Matched | 0
J1236 | 2026-08 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1236 | 2026-09 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1236 | 2026-10 | Weekly |  | 832 | 0 | 832 | 0 | Agrees | Matched | 0
J1237 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 0 | -146 | Under-billed | Not billed | -146
J1237 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 0 | -146 | Under-billed | Not billed | -146
J1237 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 0 | -146 | Under-billed | Not billed | -146
J1238 | 2026-08 | Weekly |  | 910 | 0 | 910 | 0 | Agrees | Matched | 0
J1238 | 2026-09 | Weekly |  | 910 | 0 | 910 | 0 | Agrees | Matched | 0
J1238 | 2026-10 | Weekly |  | 910 | 0 | 910 | 0 | Agrees | Matched | 0
J1239 | 2026-08 | Weekly |  | 1248 | 0 | 1248 | 0 | Agrees | Matched | 0
J1239 | 2026-09 | Weekly |  | 1248 | 0 | 1248 | 0 | Agrees | Matched | 0
J1239 | 2026-10 | Weekly |  | 1248 | 0 | 1248 | 0 | Agrees | Matched | 0
J1240 | 2026-08 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1240 | 2026-09 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1240 | 2026-10 | Weekly |  | 546 | 546 | 0 | 0 | Agrees | Billed in Jobber | 0
J1241 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1241 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1241 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1242 | 2026-08 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1242 | 2026-09 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1242 | 2026-10 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1243 | 2026-08 | Weekly |  | 1161.33 | 0 | 1161.33 | 0 | Agrees | Matched | 0
J1243 | 2026-09 | Weekly |  | 1161.33 | 0 | 1161.33 | 0 | Agrees | Matched | 0
J1243 | 2026-10 | Weekly |  | 1161.33 | 0 | 1161.33 | 0 | Agrees | Matched | 0
J1244 | 2026-08 | Weekly |  | 901.33 | 901.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1244 | 2026-09 | Weekly |  | 901.33 | 901.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1244 | 2026-10 | Weekly |  | 901.33 | 901.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1245 | 2026-08 | Weekly |  | 1950 | 0 | 1950 | 0 | Agrees | Matched | 0
J1245 | 2026-09 | Weekly |  | 1950 | 0 | 1950 | 0 | Agrees | Matched | 0
J1245 | 2026-10 | Weekly |  | 1950 | 0 | 1950 | 0 | Agrees | Matched | 0
J1246 | 2026-08 | Weekly |  | 1092 | 1092 | 0 | 0 | Agrees | Billed in Jobber | 0
J1246 | 2026-09 | Weekly |  | 1092 | 1092 | 0 | 0 | Agrees | Billed in Jobber | 0
J1246 | 2026-10 | Weekly |  | 1092 | 1092 | 0 | 0 | Agrees | Billed in Jobber | 0
J1247 | 2026-08 | Weekly |  | 268.67 | 268.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1247 | 2026-09 | Weekly |  | 268.67 | 268.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1247 | 2026-10 | Weekly |  | 268.67 | 268.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1248 | 2026-08 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1248 | 2026-09 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1248 | 2026-10 | Weekly |  | 390 | 0 | 390 | 0 | Agrees | Matched | 0
J1249 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1249 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1249 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1250 | 2026-08 | Weekly |  | 325 | 0 | 312 | -13 | Under-billed | Rate mismatch | -13
J1250 | 2026-09 | Weekly |  | 325 | 0 | 312 | -13 | Under-billed | Rate mismatch | -13
J1250 | 2026-10 | Weekly |  | 325 | 0 | 312 | -13 | Under-billed | Rate mismatch | -13
J1251 | 2026-08 | Weekly |  | 615.33 | 0 | 615.33 | 0 | Agrees | Matched | 0
J1251 | 2026-09 | Weekly |  | 615.33 | 0 | 615.33 | 0 | Agrees | Matched | 0
J1251 | 2026-10 | Weekly |  | 615.33 | 0 | 615.33 | 0 | Agrees | Matched | 0
J1252 | 2026-08 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1252 | 2026-09 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1252 | 2026-10 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1253 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1253 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1253 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 0 | -116 | Under-billed | Not billed | -116
J1254 | 2026-08 | Weekly |  | 554.67 | 0 | 554.67 | 0 | Agrees | Matched | 0
J1254 | 2026-09 | Weekly |  | 554.67 | 0 | 554.67 | 0 | Agrees | Matched | 0
J1254 | 2026-10 | Weekly |  | 554.67 | 0 | 554.67 | 0 | Agrees | Matched | 0
J1255 | 2026-08 | Weekly |  | 875.33 | 0 | 875.33 | 0 | Agrees | Matched | 0
J1255 | 2026-09 | Weekly |  | 875.33 | 0 | 875.33 | 0 | Agrees | Matched | 0
J1255 | 2026-10 | Weekly |  | 875.33 | 0 | 875.33 | 0 | Agrees | Matched | 0
J1256 | 2026-08 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1256 | 2026-09 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1256 | 2026-10 | Weekly |  | 1516.67 | 0 | 1516.67 | 0 | Agrees | Matched | 0
J1257 | 2026-08 | Weekly |  | 316.33 | 316.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1257 | 2026-09 | Weekly |  | 316.33 | 316.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1257 | 2026-10 | Weekly |  | 316.33 | 316.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1258 | 2026-08 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1258 | 2026-09 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1258 | 2026-10 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1259 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1259 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1259 | 2026-10 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1260 | 2026-08 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1260 | 2026-09 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1260 | 2026-10 | Monthly |  | 99 | 99 | 0 | 0 | Agrees | Billed in Jobber | 0
J1261 | 2026-08 | Weekly |  | 832 | 832 | 0 | 0 | Agrees | Billed in Jobber | 0
J1261 | 2026-09 | Weekly |  | 832 | 832 | 0 | 0 | Agrees | Billed in Jobber | 0
J1261 | 2026-10 | Weekly |  | 832 | 832 | 0 | 0 | Agrees | Billed in Jobber | 0
J1262 | 2026-08 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1262 | 2026-09 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1262 | 2026-10 | Weekly |  | 849.33 | 0 | 849.33 | 0 | Agrees | Matched | 0
J1263 | 2026-08 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1263 | 2026-09 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1263 | 2026-10 | Weekly |  | 901.33 | 0 | 901.33 | 0 | Agrees | Matched | 0
J1264 | 2026-08 | Weekly |  | 2101.67 | 2101.67 | 2101.67 | 2101.67 | Over-billed | Double-billing risk | 2101.67
J1264 | 2026-09 | Weekly |  | 2101.67 | 2101.67 | 2101.67 | 2101.67 | Over-billed | Double-billing risk | 2101.67
J1264 | 2026-10 | Weekly |  | 2101.67 | 2101.67 | 2101.67 | 2101.67 | Over-billed | Double-billing risk | 2101.67
J1265 | 2026-08 | Weekly |  | 537.33 | 537.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1265 | 2026-09 | Weekly |  | 537.33 | 537.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1265 | 2026-10 | Weekly |  | 537.33 | 537.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1266 | 2026-08 | Weekly |  | 1386.67 | 0 | 1280 | -106.67 | Under-billed | Basis mismatch | -106.67
J1266 | 2026-09 | Weekly |  | 1386.67 | 0 | 1280 | -106.67 | Under-billed | Basis mismatch | -106.67
J1266 | 2026-10 | Weekly |  | 1386.67 | 0 | 1280 | -106.67 | Under-billed | Basis mismatch | -106.67
J1267 | 2026-08 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1267 | 2026-09 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1267 | 2026-10 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1268 | 2026-08 | Weekly |  | 884 | 884 | 0 | 0 | Agrees | Billed in Jobber | 0
J1268 | 2026-09 | Weekly |  | 884 | 884 | 0 | 0 | Agrees | Billed in Jobber | 0
J1268 | 2026-10 | Weekly |  | 884 | 884 | 0 | 0 | Agrees | Billed in Jobber | 0
J1269 | 2026-08 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1269 | 2026-09 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1269 | 2026-10 | Every 4 weeks | 1 | 156 | 0 | 156 | 0 | Agrees | Matched | 0
J1270 | 2026-08 | Weekly |  | 1495 | 0 | 1495 | 0 | Agrees | Matched | 0
J1270 | 2026-09 | Weekly |  | 1495 | 0 | 1495 | 0 | Agrees | Matched | 0
J1270 | 2026-10 | Weekly |  | 1495 | 0 | 1495 | 0 | Agrees | Matched | 0
J1271 | 2026-08 | Weekly |  | 3271.67 | 3271.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1271 | 2026-09 | Weekly |  | 3271.67 | 3271.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1271 | 2026-10 | Weekly |  | 3271.67 | 3271.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1272 | 2026-08 | Weekly |  | 754 | 0 | 754 | 0 | Agrees | Matched | 0
J1272 | 2026-09 | Weekly |  | 754 | 0 | 754 | 0 | Agrees | Matched | 0
J1272 | 2026-10 | Weekly |  | 754 | 0 | 754 | 0 | Agrees | Matched | 0
J1273 | 2026-08 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1273 | 2026-09 | Every 4 weeks | 1 | 109 | 0 | 109 | 0 | Agrees | Matched | 0
J1273 | 2026-10 | Every 4 weeks | 2 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1274 | 2026-08 | Weekly |  | 1265.33 | 0 | 1265.33 | 0 | Agrees | Matched | 0
J1274 | 2026-09 | Weekly |  | 1265.33 | 0 | 1265.33 | 0 | Agrees | Matched | 0
J1274 | 2026-10 | Weekly |  | 1265.33 | 0 | 1265.33 | 0 | Agrees | Matched | 0
J1275 | 2026-08 | Weekly |  | 1209 | 1209 | 0 | 0 | Agrees | Billed in Jobber | 0
J1275 | 2026-09 | Weekly |  | 1209 | 1209 | 0 | 0 | Agrees | Billed in Jobber | 0
J1275 | 2026-10 | Weekly |  | 1209 | 1209 | 0 | 0 | Agrees | Billed in Jobber | 0
J1276 | 2026-08 | Weekly |  | 2418 | 0 | 2327 | -91 | Under-billed | Rate mismatch | -91
J1276 | 2026-09 | Weekly |  | 2418 | 0 | 2327 | -91 | Under-billed | Rate mismatch | -91
J1276 | 2026-10 | Weekly |  | 2418 | 0 | 2327 | -91 | Under-billed | Rate mismatch | -91
J1277 | 2026-08 | Weekly |  | 1287 | 0 | 1287 | 0 | Agrees | Matched | 0
J1277 | 2026-09 | Weekly |  | 1287 | 0 | 1287 | 0 | Agrees | Matched | 0
J1277 | 2026-10 | Weekly |  | 1287 | 0 | 1287 | 0 | Agrees | Matched | 0
J1278 | 2026-08 | Weekly |  | 2925 | 2925 | 0 | 0 | Agrees | Billed in Jobber | 0
J1278 | 2026-09 | Weekly |  | 2925 | 2925 | 0 | 0 | Agrees | Billed in Jobber | 0
J1278 | 2026-10 | Weekly |  | 2925 | 2925 | 0 | 0 | Agrees | Billed in Jobber | 0
J1279 | 2026-08 | Weekly |  | 1126.67 | 1126.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1279 | 2026-09 | Weekly |  | 1126.67 | 1126.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1279 | 2026-10 | Weekly |  | 1126.67 | 1126.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1280 | 2026-08 | Weekly |  | 780 | 0 | 1534 | 754 | Over-billed | Duplicate in QBO | 754
J1280 | 2026-09 | Weekly |  | 780 | 0 | 1534 | 754 | Over-billed | Duplicate in QBO | 754
J1280 | 2026-10 | Weekly |  | 780 | 0 | 1534 | 754 | Over-billed | Duplicate in QBO | 754
J1281 | 2026-08 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1281 | 2026-09 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1281 | 2026-10 | Weekly |  | 325 | 0 | 325 | 0 | Agrees | Matched | 0
J1282 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1282 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1282 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1283 | 2026-08 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1283 | 2026-09 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1283 | 2026-10 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1284 | 2026-08 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1284 | 2026-09 | Every 4 weeks | 1 | 218 | 0 | 218 | 0 | Agrees | Matched | 0
J1284 | 2026-10 | Every 4 weeks | 2 | 436 | 0 | 436 | 0 | Agrees | Matched | 0
J1285 | 2026-08 | Weekly |  | 3791.67 | 3791.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1285 | 2026-09 | Weekly |  | 3791.67 | 3791.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1285 | 2026-10 | Weekly |  | 3791.67 | 3791.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1286 | 2026-08 | Weekly |  | 2513.33 | 0 | 2513.33 | 0 | Agrees | Matched | 0
J1286 | 2026-09 | Weekly |  | 2513.33 | 0 | 2513.33 | 0 | Agrees | Matched | 0
J1286 | 2026-10 | Weekly |  | 2513.33 | 0 | 2513.33 | 0 | Agrees | Matched | 0
J1287 | 2026-08 | Weekly |  | 1326 | 0 | 1326 | 0 | Agrees | Matched | 0
J1287 | 2026-09 | Weekly |  | 1326 | 0 | 1326 | 0 | Agrees | Matched | 0
J1287 | 2026-10 | Weekly |  | 1326 | 0 | 1326 | 0 | Agrees | Matched | 0
J1288 | 2026-08 | Weekly |  | 572 | 0 | 1144 | 572 | Over-billed | Duplicate in QBO | 572
J1288 | 2026-09 | Weekly |  | 572 | 0 | 1144 | 572 | Over-billed | Duplicate in QBO | 572
J1288 | 2026-10 | Weekly |  | 572 | 0 | 1144 | 572 | Over-billed | Duplicate in QBO | 572
J1289 | 2026-08 | Weekly |  | 2621.67 | 2621.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1289 | 2026-09 | Weekly |  | 2621.67 | 2621.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1289 | 2026-10 | Weekly |  | 2621.67 | 2621.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1290 | 2026-08 | Every 4 weeks | 1 | 234 | 0 | 225 | -9 | Under-billed | Rate mismatch | -9
J1290 | 2026-09 | Every 4 weeks | 1 | 234 | 0 | 225 | -9 | Under-billed | Rate mismatch | -9
J1290 | 2026-10 | Every 4 weeks | 1 | 234 | 0 | 225 | -9 | Under-billed | Rate mismatch | -9
J1291 | 2026-08 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1291 | 2026-09 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1291 | 2026-10 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1292 | 2026-08 | Weekly |  | 1048.67 | 0 | 1005.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1292 | 2026-09 | Weekly |  | 1048.67 | 0 | 1005.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1292 | 2026-10 | Weekly |  | 1048.67 | 0 | 1005.33 | -43.34 | Under-billed | Rate mismatch | -43.34
J1293 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1293 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1293 | 2026-10 | Every 4 weeks | 1 | 116 | 0 | 116 | 0 | Agrees | Matched | 0
J1294 | 2026-08 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1294 | 2026-09 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1294 | 2026-10 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1295 | 2026-08 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1295 | 2026-09 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1295 | 2026-10 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1296 | 2026-08 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1296 | 2026-09 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1296 | 2026-10 | Weekly |  | 303.33 | 0 | 303.33 | 0 | Agrees | Matched | 0
J1297 | 2026-08 | Weekly |  | 1048.67 | 1048.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1297 | 2026-09 | Weekly |  | 1048.67 | 1048.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1297 | 2026-10 | Weekly |  | 1048.67 | 1048.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1298 | 2026-08 | Weekly |  | 810.33 | 0 | 810.33 | 0 | Agrees | Matched | 0
J1298 | 2026-09 | Weekly |  | 810.33 | 0 | 810.33 | 0 | Agrees | Matched | 0
J1298 | 2026-10 | Weekly |  | 810.33 | 0 | 810.33 | 0 | Agrees | Matched | 0
J1299 | 2026-08 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1299 | 2026-09 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1299 | 2026-10 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1300 | 2026-08 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1300 | 2026-09 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1300 | 2026-10 | Weekly |  | 923 | 0 | 923 | 0 | Agrees | Matched | 0
J1301 | 2026-08 | Weekly |  | 650 | 650 | 0 | 0 | Agrees | Billed in Jobber | 0
J1301 | 2026-09 | Weekly |  | 650 | 650 | 0 | 0 | Agrees | Billed in Jobber | 0
J1301 | 2026-10 | Weekly |  | 650 | 650 | 0 | 0 | Agrees | Billed in Jobber | 0
J1302 | 2026-08 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1302 | 2026-09 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1302 | 2026-10 | Weekly |  | 151.67 | 151.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1303 | 2026-08 | Weekly |  | 2210 | 2210 | 0 | 0 | Agrees | Billed in Jobber | 0
J1303 | 2026-09 | Weekly |  | 2210 | 2210 | 0 | 0 | Agrees | Billed in Jobber | 0
J1303 | 2026-10 | Weekly |  | 2210 | 2210 | 0 | 0 | Agrees | Billed in Jobber | 0
J1304 | 2026-08 | Every 4 weeks | 1 | 135 | 135 | 135 | 135 | Over-billed | Double-billing risk | 135
J1304 | 2026-09 | Every 4 weeks | 1 | 135 | 135 | 135 | 135 | Over-billed | Double-billing risk | 135
J1304 | 2026-10 | Every 4 weeks | 1 | 135 | 135 | 135 | 135 | Over-billed | Double-billing risk | 135
J1305 | 2026-08 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1305 | 2026-09 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1305 | 2026-10 | Weekly |  | 2015 | 0 | 2015 | 0 | Agrees | Matched | 0
J1306 | 2026-08 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1306 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 146 | 0 | Agrees | Matched | 0
J1306 | 2026-10 | Every 4 weeks | 2 | 292 | 0 | 292 | 0 | Agrees | Matched | 0
J1307 | 2026-08 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1307 | 2026-09 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1307 | 2026-10 | Monthly |  | 88 | 0 | 88 | 0 | Agrees | Matched | 0
J1308 | 2026-08 | Weekly |  | 416 | 416 | 0 | 0 | Agrees | Billed in Jobber | 0
J1308 | 2026-09 | Weekly |  | 416 | 416 | 0 | 0 | Agrees | Billed in Jobber | 0
J1308 | 2026-10 | Weekly |  | 416 | 416 | 0 | 0 | Agrees | Billed in Jobber | 0
J1309 | 2026-08 | Every 4 weeks | 2 | 292 | 0 | 584 | 292 | Over-billed | Duplicate in QBO | 292
J1309 | 2026-09 | Every 4 weeks | 1 | 146 | 0 | 292 | 146 | Over-billed | Duplicate in QBO | 146
J1309 | 2026-10 | Every 4 weeks | 1 | 146 | 0 | 292 | 146 | Over-billed | Duplicate in QBO | 146
J1310 | 2026-08 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1310 | 2026-09 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1310 | 2026-10 | Monthly |  | 99 | 0 | 99 | 0 | Agrees | Matched | 0
J1311 | 2026-08 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1311 | 2026-09 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1311 | 2026-10 | Weekly |  | 294.67 | 0 | 294.67 | 0 | Agrees | Matched | 0
J1312 | 2026-08 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1312 | 2026-09 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1312 | 2026-10 | Weekly |  | 589.33 | 0 | 589.33 | 0 | Agrees | Matched | 0
J1313 | 2026-08 | Weekly |  | 407.33 | 407.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1313 | 2026-09 | Weekly |  | 407.33 | 407.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1313 | 2026-10 | Weekly |  | 407.33 | 407.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1314 | 2026-08 | Weekly |  | 364 | 0 | 364 | 0 | Agrees | Matched | 0
J1314 | 2026-09 | Weekly |  | 364 | 0 | 364 | 0 | Agrees | Matched | 0
J1314 | 2026-10 | Weekly |  | 364 | 0 | 364 | 0 | Agrees | Matched | 0
J1315 | 2026-08 | Weekly |  | 2708.33 | 2708.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1315 | 2026-09 | Weekly |  | 2708.33 | 2708.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1315 | 2026-10 | Weekly |  | 2708.33 | 2708.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1316 | 2026-08 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1316 | 2026-09 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1316 | 2026-10 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1317 | 2026-08 | Weekly |  | 1048.67 | 0 | 1048.67 | 0 | Agrees | Matched | 0
J1317 | 2026-09 | Weekly |  | 1048.67 | 0 | 1048.67 | 0 | Agrees | Matched | 0
J1317 | 2026-10 | Weekly |  | 1048.67 | 0 | 1048.67 | 0 | Agrees | Matched | 0
J1318 | 2026-08 | Every 4 weeks | 1 | 218 | 218 | 218 | 218 | Over-billed | Double-billing risk | 218
J1318 | 2026-09 | Every 4 weeks | 1 | 218 | 218 | 218 | 218 | Over-billed | Double-billing risk | 218
J1318 | 2026-10 | Every 4 weeks | 1 | 218 | 218 | 218 | 218 | Over-billed | Double-billing risk | 218
J1319 | 2026-08 | Weekly |  | 1057.33 | 1057.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1319 | 2026-09 | Weekly |  | 1057.33 | 1057.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1319 | 2026-10 | Weekly |  | 1057.33 | 1057.33 | 0 | 0 | Agrees | Billed in Jobber | 0
J1320 | 2026-08 | Weekly |  | 719.33 | 0 | 719.33 | 0 | Agrees | Matched | 0
J1320 | 2026-09 | Weekly |  | 719.33 | 0 | 719.33 | 0 | Agrees | Matched | 0
J1320 | 2026-10 | Weekly |  | 719.33 | 0 | 719.33 | 0 | Agrees | Matched | 0
J1321 | 2026-08 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1321 | 2026-09 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1321 | 2026-10 | Every 4 weeks | 1 | 203 | 0 | 203 | 0 | Agrees | Matched | 0
J1322 | 2026-08 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1322 | 2026-09 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1322 | 2026-10 | Weekly |  | 697.67 | 0 | 671.67 | -26 | Under-billed | Rate mismatch | -26
J1323 | 2026-08 | Weekly |  | 784.33 | 0 | 754 | -30.33 | Under-billed | Rate mismatch | -30.33
J1323 | 2026-09 | Weekly |  | 784.33 | 0 | 754 | -30.33 | Under-billed | Rate mismatch | -30.33
J1323 | 2026-10 | Weekly |  | 784.33 | 0 | 754 | -30.33 | Under-billed | Rate mismatch | -30.33
J1324 | 2026-08 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1324 | 2026-09 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1324 | 2026-10 | Weekly |  | 437.67 | 0 | 437.67 | 0 | Agrees | Matched | 0
J1325 | 2026-08 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1325 | 2026-09 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1325 | 2026-10 | Weekly |  | 1672.67 | 0 | 1672.67 | 0 | Agrees | Matched | 0
J1326 | 2026-08 | Weekly |  | 2621.67 | 0 | 2621.67 | 0 | Agrees | Matched | 0
J1326 | 2026-09 | Weekly |  | 2621.67 | 0 | 2621.67 | 0 | Agrees | Matched | 0
J1326 | 2026-10 | Weekly |  | 2621.67 | 0 | 2621.67 | 0 | Agrees | Matched | 0
J1327 | 2026-08 | Weekly |  | 580.67 | 580.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1327 | 2026-09 | Weekly |  | 580.67 | 580.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1327 | 2026-10 | Weekly |  | 580.67 | 580.67 | 0 | 0 | Agrees | Billed in Jobber | 0
J1328 | 2026-08 | Weekly |  | 450.67 | 0 | 416 | -34.67 | Under-billed | Basis mismatch | -34.67
J1328 | 2026-09 | Weekly |  | 450.67 | 0 | 416 | -34.67 | Under-billed | Basis mismatch | -34.67
J1328 | 2026-10 | Weekly |  | 450.67 | 0 | 416 | -34.67 | Under-billed | Basis mismatch | -34.67
J1329 | 2026-08 | Every 4 weeks | 1 | 116 | 0 | 112 | -4 | Under-billed | Rate mismatch | -4
J1329 | 2026-09 | Every 4 weeks | 1 | 116 | 0 | 112 | -4 | Under-billed | Rate mismatch | -4
J1329 | 2026-10 | Every 4 weeks | 2 | 232 | 0 | 224 | -8 | Under-billed | Rate mismatch | -8
J1330 | 2026-08 | Weekly |  | 1313 | 0 | 1212 | -101 | Under-billed | Basis mismatch | -101
J1330 | 2026-09 | Weekly |  | 1313 | 0 | 1212 | -101 | Under-billed | Basis mismatch | -101
J1330 | 2026-10 | Weekly |  | 1313 | 0 | 1212 | -101 | Under-billed | Basis mismatch | -101
J1331 | 2026-08 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1331 | 2026-09 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1331 | 2026-10 | Monthly |  | 151 | 0 | 151 | 0 | Agrees | Matched | 0
J1332 | 2026-08 | Weekly |  | 1391 | 0 | 1391 | 0 | Agrees | Matched | 0
J1332 | 2026-09 | Weekly |  | 1391 | 0 | 1391 | 0 | Agrees | Matched | 0
J1332 | 2026-10 | Weekly |  | 1391 | 0 | 1391 | 0 | Agrees | Matched | 0
J1333 | 2026-08 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1333 | 2026-09 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1333 | 2026-10 | Weekly |  | 598 | 0 | 598 | 0 | Agrees | Matched | 0
J1334 | 2026-08 | Weekly |  | 1664 | 0 | 1664 | 0 | Agrees | Matched | 0
J1334 | 2026-09 | Weekly |  | 1664 | 0 | 1664 | 0 | Agrees | Matched | 0
J1334 | 2026-10 | Weekly |  | 1664 | 0 | 1664 | 0 | Agrees | Matched | 0
J1335 | 2026-08 | Weekly |  | 567.67 | 0 | 567.67 | 0 | Agrees | Matched | 0
J1335 | 2026-09 | Weekly |  | 567.67 | 0 | 567.67 | 0 | Agrees | Matched | 0
J1335 | 2026-10 | Weekly |  | 567.67 | 0 | 567.67 | 0 | Agrees | Matched | 0
J1336 | 2026-08 | Every 4 weeks | 1 | 203 | 203 | 203 | 203 | Over-billed | Double-billing risk | 203
J1336 | 2026-09 | Every 4 weeks | 1 | 203 | 203 | 203 | 203 | Over-billed | Double-billing risk | 203
J1336 | 2026-10 | Every 4 weeks | 2 | 406 | 406 | 406 | 406 | Over-billed | Double-billing risk | 406
J1337 | 2026-08 | Weekly |  | 801.67 | 801.67 | 801.67 | 801.67 | Over-billed | Double-billing risk | 801.67
J1337 | 2026-09 | Weekly |  | 801.67 | 801.67 | 801.67 | 801.67 | Over-billed | Double-billing risk | 801.67
J1337 | 2026-10 | Weekly |  | 801.67 | 801.67 | 801.67 | 801.67 | Over-billed | Double-billing risk | 801.67
J1338 | 2026-08 | Weekly |  | 429 | 0 | 429 | 0 | Agrees | Matched | 0
J1338 | 2026-09 | Weekly |  | 429 | 0 | 429 | 0 | Agrees | Matched | 0
J1338 | 2026-10 | Weekly |  | 429 | 0 | 429 | 0 | Agrees | Matched | 0
J1339 | 2026-08 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1339 | 2026-09 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1339 | 2026-10 | Weekly |  | 546 | 0 | 546 | 0 | Agrees | Matched | 0
J1340 | 2026-08 | Weekly |  | 0 | 0 | 377 | 377 | Over-billed | Inactive in Jobber - confirm | 377
J1340 | 2026-09 | Weekly |  | 0 | 0 | 377 | 377 | Over-billed | Inactive in Jobber - confirm | 377
J1340 | 2026-10 | Weekly |  | 0 | 0 | 377 | 377 | Over-billed | Inactive in Jobber - confirm | 377
J1341 | 2026-08 | Weekly |  | 0 | 0 | 264.33 | 264.33 | Over-billed | Inactive in Jobber - confirm | 264.33
J1341 | 2026-09 | Weekly |  | 0 | 0 | 264.33 | 264.33 | Over-billed | Inactive in Jobber - confirm | 264.33
J1341 | 2026-10 | Weekly |  | 0 | 0 | 264.33 | 264.33 | Over-billed | Inactive in Jobber - confirm | 264.33
J1342 | 2026-08 | Weekly |  | 0 | 0 | 771.33 | 771.33 | Over-billed | Inactive in Jobber - confirm | 771.33
J1342 | 2026-09 | Weekly |  | 0 | 0 | 771.33 | 771.33 | Over-billed | Inactive in Jobber - confirm | 771.33
J1342 | 2026-10 | Weekly |  | 0 | 0 | 771.33 | 771.33 | Over-billed | Inactive in Jobber - confirm | 771.33
J1343 | 2026-08 | Weekly |  | 0 | 0 | 1040 | 1040 | Over-billed | Inactive in Jobber - confirm | 1040
J1343 | 2026-09 | Weekly |  | 0 | 0 | 1040 | 1040 | Over-billed | Inactive in Jobber - confirm | 1040
J1343 | 2026-10 | Weekly |  | 0 | 0 | 1040 | 1040 | Over-billed | Inactive in Jobber - confirm | 1040
J1344 | 2026-08 | Weekly |  | 0 | 0 | 546 | 546 | Over-billed | Inactive in Jobber - confirm | 546
J1344 | 2026-09 | Weekly |  | 0 | 0 | 546 | 546 | Over-billed | Inactive in Jobber - confirm | 546
J1344 | 2026-10 | Weekly |  | 0 | 0 | 546 | 546 | Over-billed | Inactive in Jobber - confirm | 546
J1345 | 2026-08 | Weekly |  | 0 | 0 | 823.33 | 823.33 | Over-billed | Inactive in Jobber - confirm | 823.33
J1345 | 2026-09 | Weekly |  | 0 | 0 | 823.33 | 823.33 | Over-billed | Inactive in Jobber - confirm | 823.33
J1345 | 2026-10 | Weekly |  | 0 | 0 | 823.33 | 823.33 | Over-billed | Inactive in Jobber - confirm | 823.33
J1346 | 2026-08 | Weekly |  | 0 | 0 | 1274 | 1274 | Over-billed | Inactive in Jobber - confirm | 1274
J1346 | 2026-09 | Weekly |  | 0 | 0 | 1274 | 1274 | Over-billed | Inactive in Jobber - confirm | 1274
J1346 | 2026-10 | Weekly |  | 0 | 0 | 1274 | 1274 | Over-billed | Inactive in Jobber - confirm | 1274
T0284 | 2026-08 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0284 | 2026-09 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0284 | 2026-10 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0285 | 2026-08 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0285 | 2026-09 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0285 | 2026-10 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0286 | 2026-08 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0286 | 2026-09 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0286 | 2026-10 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0287 | 2026-08 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0287 | 2026-09 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0287 | 2026-10 | QBO only |  | 0 | 0 | 80 | 80 | Over-billed | Missing in Jobber | 80
T0288 | 2026-08 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0288 | 2026-09 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0288 | 2026-10 | QBO only |  | 0 | 0 | 65 | 65 | Over-billed | Missing in Jobber | 65
T0289 | 2026-08 | QBO only |  | 0 | 0 | 110 | 110 | Over-billed | Missing in Jobber | 110
T0289 | 2026-09 | QBO only |  | 0 | 0 | 110 | 110 | Over-billed | Missing in Jobber | 110
T0289 | 2026-10 | QBO only |  | 0 | 0 | 110 | 110 | Over-billed | Missing in Jobber | 110

## Roster Clashes
Roster clashes: same cleaner, same day, overlapping
Work sample: realistic data, built to show how I approach this work.
Job A | Job B | Cleaner | Day | A window | B window | Overlap (min) | Wave A | Wave B | Same cleaner in Jobber | Fix
J1171 | J1245 | CL12 | MO | 21:30-23:30 | 21:00-22:30 | 60 | Wave 4 West | Wave 4 West | 1 | Move one job to a free cleaner in the region, or shift the start time
J1061 | J1301 | CL29 | TH | 08:00-10:00 | 07:30-08:30 | 30 | Wave 1 North | Wave 1 North | 1 | Move one job to a free cleaner in the region, or shift the start time
J1093 | J1186 | CL03 | TH | 17:30-19:30 | 18:00-20:00 | 90 | Wave 3 South | Wave 3 South | 1 | Move one job to a free cleaner in the region, or shift the start time
J1115 | J1328 | CL15 | WE | 20:30-21:30 | 20:00-21:30 | 60 | Wave 3 South | Wave 3 South | 1 | Move one job to a free cleaner in the region, or shift the start time
J1128 | J1158 | CL14 | MO | 07:00-07:30 | 07:00-08:00 | 30 | Wave 2 East | Wave 2 East | 1 | Move one job to a free cleaner in the region, or shift the start time
J1172 | J1212 | CL14 | MO | 20:30-21:30 | 20:00-22:30 | 60 | Wave 2 East | Wave 2 East | 1 | Move one job to a free cleaner in the region, or shift the start time
J1051 | J1069 | CL24 | MO | 05:30-06:30 | 06:00-07:00 | 30 | Wave 4 West | Wave 4 West | 1 | Move one job to a free cleaner in the region, or shift the start time
J1221 | J1254 | CL35 | TU | 20:00-21:30 | 19:30-20:30 | 30 | Wave 3 South | Wave 3 South | 1 | Move one job to a free cleaner in the region, or shift the start time
J1057 | J1162 | CL44 | WE | 06:00-08:00 | 05:30-07:30 | 90 | Wave 4 West | Wave 4 West | 1 | Move one job to a free cleaner in the region, or shift the start time
J1200 | J1281 | CL20 | FR | 07:30-08:30 | 07:00-08:00 | 30 | Wave 4 West | Wave 4 West | 1 | Move one job to a free cleaner in the region, or shift the start time
J1263 | J1317 | CL46 | TU | 06:00-07:30 | 05:30-07:30 | 90 | Wave 2 East | Wave 2 East | 1 | Move one job to a free cleaner in the region, or shift the start time

## Cleaner Load
Cleaner load: rostered vs contracted weekly hours
Work sample: realistic data, built to show how I approach this work.
Cleaner | Name | Region | Contracted | Rostered (avg/wk) | Active jobs | Use | Engine hours
CL01 | Ana A. | North | 20 | 14 | 3 | 70% | 14
CL02 | Bilal A. | East | 38 | 23 | 5 | 60.53% | 23
CL03 | Carmen A. | South | 25 | 17.5 | 5 | 70% | 17.5
CL04 | Dinh A. | West | 25 | 17.5 | 4 | 70% | 17.5
CL05 | Eleni A. | North | 30 | 13 | 4 | 43.33% | 13
CL06 | Farid A. | East | 30 | 19 | 6 | 63.33% | 19
CL07 | Grace A. | South | 25 | 19 | 4 | 76% | 19
CL08 | Hamid A. | West | 20 | 6 | 1 | 30% | 6
CL09 | Ines A. | North | 25 | 21.5 | 5 | 86% | 21.5
CL10 | Jun A. | East | 25 | 13.5 | 4 | 54% | 13.5
CL11 | Kavya A. | South | 30 | 14.5 | 5 | 48.33% | 14.5
CL12 | Luis A. | West | 38 | 27 | 5 | 71.05% | 27
CL13 | Maya A. | North | 38 | 13.5 | 5 | 35.53% | 13.5
CL14 | Nikos A. | East | 25 | 30 | 6 | 120% | 30
CL15 | Omar A. | South | 30 | 20 | 5 | 66.67% | 20
CL16 | Pita A. | West | 30 | 11 | 4 | 36.67% | 11
CL17 | Quynh A. | North | 20 | 19.5 | 4 | 97.5% | 19.5
CL18 | Rosa A. | East | 25 | 16.5 | 5 | 66% | 16.5
CL19 | Sione A. | South | 20 | 16.5 | 7 | 82.5% | 16.5
CL20 | Tara A. | West | 25 | 20 | 8 | 80% | 20
CL21 | Ana F. | North | 20 | 15 | 5 | 75% | 15
CL22 | Bilal F. | East | 25 | 16.5 | 5 | 66% | 16.5
CL23 | Carmen F. | South | 38 | 11.5 | 2 | 30.26% | 11.5
CL24 | Dinh F. | West | 20 | 19.5 | 6 | 97.5% | 19.5
CL25 | Eleni F. | North | 25 | 13.5 | 4 | 54% | 13.5
CL26 | Farid F. | East | 20 | 16 | 7 | 80% | 16
CL27 | Grace F. | South | 20 | 22 | 5 | 110% | 22
CL28 | Hamid F. | West | 25 | 10.5 | 4 | 42% | 10.5
CL29 | Ines F. | North | 20 | 16.5 | 5 | 82.5% | 16.5
CL30 | Jun F. | East | 38 | 20.5 | 4 | 53.95% | 20.5
CL31 | Kavya F. | South | 20 | 16.5 | 5 | 82.5% | 16.5
CL32 | Luis F. | West | 38 | 15 | 5 | 39.47% | 15
CL33 | Maya F. | North | 25 | 13.5 | 3 | 54% | 13.5
CL34 | Nikos F. | East | 30 | 10.5 | 5 | 35% | 10.5
CL35 | Omar F. | South | 25 | 18 | 8 | 72% | 18
CL36 | Pita F. | West | 25 | 15 | 5 | 60% | 15
CL37 | Quynh F. | North | 38 | 13 | 5 | 34.21% | 13
CL38 | Rosa F. | East | 20 | 27.5 | 4 | 137.5% | 27.5
CL39 | Sione F. | South | 30 | 14 | 7 | 46.67% | 14
CL40 | Tara F. | West | 20 | 15 | 5 | 75% | 15
CL41 | Ana L. | North | 38 | 12.5 | 3 | 32.89% | 12.5
CL42 | Bilal L. | East | 30 | 21.5 | 6 | 71.67% | 21.5
CL43 | Carmen L. | South | 20 | 16.5 | 5 | 82.5% | 16.5
CL44 | Dinh L. | West | 38 | 16 | 7 | 42.11% | 16
CL45 | Eleni L. | North | 25 | 14 | 4 | 56% | 14
CL46 | Farid L. | East | 20 | 20.5 | 8 | 102.5% | 20.5
CL47 | Grace L. | South | 38 | 14.5 | 5 | 38.16% | 14.5
CL48 | Hamid L. | West | 25 | 19.5 | 5 | 78% | 19.5
CL49 | Ines L. | North | 20 | 17 | 3 | 85% | 17
CL50 | Jun L. | East | 25 | 16 | 7 | 64% | 16
CL51 | Kavya L. | South | 38 | 17.5 | 4 | 46.05% | 17.5
CL52 | Luis L. | West | 30 | 15 | 1 | 50% | 15
CL53 | Maya L. | North | 30 | 3.25 | 8 | 10.83% | 3.25
CL54 | Nikos L. | East | 38 | 7.375 | 16 | 19.41% | 7.38
CL55 | Omar L. | South | 38 | 4.5 | 11 | 11.84% | 4.5
CL56 | Pita L. | West | 30 | 4.875 | 12 | 16.25% | 4.88
CL57 | Quynh L. | North | 38 | 4.625 | 10 | 12.17% | 4.62
CL58 | Rosa L. | East | 20 | 3.875 | 8 | 19.38% | 3.88
CL59 | Sione L. | South | 25 | 3.25 | 6 | 13% | 3.25
CL60 | Tara L. | West | 20 | 7.625 | 16 | 38.12% | 7.62

## Access Notes
Access codes pulled out of notes (codes go to 02 Site Access, office only)
Work sample: realistic data, built to show how I approach this work.
Property ID | Location | Code found | Calendar note (redacted) | Moved to
JP0001 | Main office - Bentleigh | 1 | Code for roller door: [in 02 Site Access]; Bins out on Tuesday night | 02 Site Access (office only)
JP0002 | Clinic - Oakleigh | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0003 | Main office - Deer Park | 0 | Level 3, lift to the left
JP0004 | Main office - Bundoora | 0
JP0005 | Main office - Footscray | 0 | Park in bay 12 under the building
JP0006 | Main office - Brighton | 0
JP0007 | Main office - Bundoora | 0 | Level 3, lift to the left
JP0008 | Clinic - Werribee | 0
JP0009 | Main office - Oakleigh | 0
JP0010 | Clinic - Point Cook | 0 | Do not use bleach on the timber floor
JP0011 | Main office - Hawthorn | 0 | Call 0400 000 000 if the door is locked
JP0012 | Main office - Epping | 0 | Store room on level 1, room 104
JP0013 | Clinic - Thornbury | 0 | Store room on level 1, room 104
JP0014 | Main office - Mitcham | 0
JP0015 | Clinic - Kew | 1 | Alarm code [in 02 Site Access]#, panel behind reception door | 02 Site Access (office only)
JP0016 | Main office - Clayton | 1 | Code for roller door: [in 02 Site Access] | 02 Site Access (office only)
JP0017 | Main office - Coburg | 1 | Key safe at side gate, code [in 02 Site Access] | 02 Site Access (office only)
JP0018 | Main office - Mentone | 0 | Kitchen: 2 fridges, empty on Fridays
JP0019 | Main office - Camberwell | 0 | Bins out on Tuesday night
JP0020 | Main office - Cheltenham | 0 | Sign in at security desk
JP0021 | Clinic - Oakleigh | 0 | Vacuum bags in cupboard 2
JP0022 | Warehouse - Clayton | 0 | Store room on level 1, room 104
JP0023 | Main office - Reservoir | 0 | Park in bay 12 under the building
JP0024 | Main office - St Kilda | 1 | Alarm [in 02 Site Access] then press OFF; Sign in at security desk | 02 Site Access (office only)
JP0025 | Clinic - Bentleigh | 0 | Kitchen: 2 fridges, empty on Fridays
JP0026 | Warehouse - Deer Park | 0 | Do not use bleach on the timber floor
JP0027 | Showroom - St Kilda | 1 | Alarm code [in 02 Site Access]#, panel behind reception door; Park in bay 12 under the building | 02 Site Access (office only)
JP0028 | Main office - Camberwell | 0 | Sign in at security desk
JP0029 | Main office - Point Cook | 0
JP0030 | Clinic - Kew | 0 | Call 0400 000 000 if the door is locked
JP0031 | Warehouse - Bundoora | 0 | Bins out on Tuesday night
JP0032 | Showroom - Footscray | 1 | Alarm code [in 02 Site Access]#, panel behind reception door | 02 Site Access (office only)
JP0033 | Main office - Camberwell | 0 | Reception closes 5:30 pm, use the side entry
JP0034 | Main office - Ringwood | 0 | Reception closes 5:30 pm, use the side entry
JP0035 | Clinic - Ringwood | 0
JP0036 | Main office - Bundoora | 0 | Bins out on Tuesday night
JP0037 | Clinic - Northcote | 0 | Bins out on Tuesday night
JP0038 | Main office - Heidelberg | 0 | Store room on level 1, room 104
JP0039 | Main office - Sunshine | 0 | Call 0400 000 000 if the door is locked
JP0040 | Clinic - Williamstown | 1 | Lockbox on meter box, [in 02 Site Access]; Reception closes 5:30 pm, use the side entry | 02 Site Access (office only)
JP0041 | Warehouse - Epping | 1 | Back door keypad [in 02 Site Access]* | 02 Site Access (office only)
JP0042 | Main office - Moorabbin | 0
JP0043 | Clinic - Essendon | 1 | Alarm [in 02 Site Access] then press OFF; Vacuum bags in cupboard 2 | 02 Site Access (office only)
JP0044 | Main office - Camberwell | 0
JP0045 | Main office - Altona | 0 | Call 0400 000 000 if the door is locked
JP0046 | Main office - Yarraville | 0 | Park in bay 12 under the building
JP0047 | Main office - Camberwell | 0 | Park in bay 12 under the building
JP0048 | Main office - Glen Waverley | 0 | Call 0400 000 000 if the door is locked
JP0049 | Main office - Thornbury | 1 | Alarm code [in 02 Site Access]#, panel behind reception door | 02 Site Access (office only)
JP0050 | Main office - Brunswick | 0 | Bins out on Tuesday night
JP0051 | Main office - Brunswick | 0 | Do not use bleach on the timber floor
JP0052 | Clinic - Thornbury | 0
JP0053 | Warehouse - Essendon | 0 | Vacuum bags in cupboard 2
JP0054 | Main office - Deer Park | 0
JP0055 | Clinic - Maribyrnong | 0 | Do not use bleach on the timber floor
JP0056 | Main office - Oakleigh | 0 | Store room on level 1, room 104
JP0057 | Main office - Cheltenham | 0 | Do not use bleach on the timber floor
JP0058 | Main office - Hawthorn | 1 | Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays | 02 Site Access (office only)
JP0059 | Clinic - Doncaster | 0 | Reception closes 5:30 pm, use the side entry
JP0060 | Main office - Hawthorn | 1 | Alarm [in 02 Site Access] then press OFF; Store room on level 1, room 104 | 02 Site Access (office only)
JP0061 | Main office - Point Cook | 0 | Park in bay 12 under the building
JP0062 | Clinic - Laverton | 0
JP0063 | Main office - Frankston | 0
JP0064 | Clinic - Laverton | 0 | Kitchen: 2 fridges, empty on Fridays
JP0065 | Main office - Hawthorn | 0 | Park in bay 12 under the building
JP0066 | Main office - Bentleigh | 0 | Bins out on Tuesday night
JP0067 | Clinic - Burwood | 1 | Code for roller door: [in 02 Site Access] | 02 Site Access (office only)
JP0068 | Main office - Burwood | 0 | Store room on level 1, room 104
JP0069 | Main office - Bentleigh | 0 | Bins out on Tuesday night
JP0070 | Clinic - Cheltenham | 1 | Lockbox on meter box, [in 02 Site Access] | 02 Site Access (office only)
JP0071 | Main office - Mentone | 0
JP0072 | Main office - Reservoir | 0
JP0073 | Clinic - Point Cook | 1 | Back door keypad [in 02 Site Access]*; Park in bay 12 under the building | 02 Site Access (office only)
JP0074 | Main office - Glen Waverley | 0 | Bins out on Tuesday night
JP0075 | Main office - Hawthorn | 1 | Key safe at side gate, code [in 02 Site Access]; Reception closes 5:30 pm, use the side entry | 02 Site Access (office only)
JP0076 | Clinic - Blackburn | 0 | Vacuum bags in cupboard 2
JP0077 | Warehouse - Cheltenham | 1 | Alarm code [in 02 Site Access]#, panel behind reception door | 02 Site Access (office only)
JP0078 | Showroom - Box Hill | 0 | Level 3, lift to the left
JP0079 | Main office - Burwood | 0 | Reception closes 5:30 pm, use the side entry
JP0080 | Main office - Reservoir | 0 | Park in bay 12 under the building
JP0081 | Clinic - Essendon | 1 | Back door keypad [in 02 Site Access]*; Sign in at security desk | 02 Site Access (office only)
JP0082 | Warehouse - Mentone | 0 | Store room on level 1, room 104
JP0083 | Main office - Frankston | 0 | Do not use bleach on the timber floor
JP0084 | Main office - Sunshine | 0 | Call 0400 000 000 if the door is locked
JP0085 | Main office - Brighton | 0 | Reception closes 5:30 pm, use the side entry
JP0086 | Main office - Dandenong | 0 | Level 3, lift to the left
JP0087 | Clinic - Moorabbin | 0 | Reception closes 5:30 pm, use the side entry
JP0088 | Main office - Point Cook | 0
JP0089 | Clinic - Camberwell | 0
JP0090 | Warehouse - Coburg | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0091 | Showroom - Footscray | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0092 | Main office - Camberwell | 0 | Store room on level 1, room 104
JP0093 | Clinic - Burwood | 0 | Store room on level 1, room 104
JP0094 | Warehouse - Burwood | 0 | Call 0400 000 000 if the door is locked
JP0095 | Showroom - Ringwood | 0 | Reception closes 5:30 pm, use the side entry
JP0096 | Main office - Altona | 0 | Kitchen: 2 fridges, empty on Fridays
JP0097 | Main office - Northcote | 0
JP0098 | Main office - Deer Park | 0 | Level 3, lift to the left
JP0099 | Main office - Blackburn | 1 | Alarm code [in 02 Site Access]#, panel behind reception door; Bins out on Tuesday night | 02 Site Access (office only)
JP0100 | Clinic - Bentleigh | 0 | Do not use bleach on the timber floor
JP0101 | Main office - Burwood | 0
JP0102 | Main office - Glen Waverley | 0 | Kitchen: 2 fridges, empty on Fridays
JP0103 | Main office - Altona | 0 | Kitchen: 2 fridges, empty on Fridays
JP0104 | Clinic - Doncaster | 0
JP0105 | Warehouse - Glen Waverley | 0
JP0106 | Main office - Point Cook | 0 | Level 3, lift to the left
JP0107 | Clinic - Point Cook | 0 | Sign in at security desk
JP0108 | Main office - Point Cook | 0 | Do not use bleach on the timber floor
JP0109 | Main office - Point Cook | 1 | Code for roller door: [in 02 Site Access]; Level 3, lift to the left | 02 Site Access (office only)
JP0110 | Clinic - Hawthorn | 1 | Lockbox on meter box, [in 02 Site Access]; Vacuum bags in cupboard 2 | 02 Site Access (office only)
JP0111 | Main office - Glen Waverley | 0
JP0112 | Main office - Point Cook | 1 | Code for roller door: [in 02 Site Access]; Reception closes 5:30 pm, use the side entry | 02 Site Access (office only)
JP0113 | Clinic - Frankston | 1 | Alarm code [in 02 Site Access]#, panel behind reception door; Store room on level 1, room 104 | 02 Site Access (office only)
JP0114 | Warehouse - Hawthorn | 1 | Key safe at side gate, code [in 02 Site Access]; Park in bay 12 under the building | 02 Site Access (office only)
JP0115 | Main office - Werribee | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0116 | Main office - Footscray | 0 | Level 3, lift to the left
JP0117 | Clinic - Footscray | 0
JP0118 | Main office - Reservoir | 1 | Code for roller door: [in 02 Site Access]; Level 3, lift to the left | 02 Site Access (office only)
JP0119 | Main office - Essendon | 1 | Lockbox on meter box, [in 02 Site Access]; Sign in at security desk | 02 Site Access (office only)
JP0120 | Clinic - St Kilda | 0
JP0121 | Main office - Bundoora | 0
JP0122 | Main office - Deer Park | 0 | Store room on level 1, room 104
JP0123 | Main office - Bentleigh | 0 | Vacuum bags in cupboard 2
JP0124 | Main office - Footscray | 0 | Sign in at security desk
JP0125 | Main office - Mitcham | 0
JP0126 | Main office - Reservoir | 0 | Do not use bleach on the timber floor
JP0127 | Clinic - Mitcham | 0 | Park in bay 12 under the building
JP0128 | Main office - Yarraville | 0 | Kitchen: 2 fridges, empty on Fridays
JP0129 | Main office - Heidelberg | 1 | Back door keypad [in 02 Site Access]* | 02 Site Access (office only)
JP0130 | Main office - Burwood | 0 | Kitchen: 2 fridges, empty on Fridays
JP0131 | Clinic - Mitcham | 0 | Level 3, lift to the left
JP0132 | Main office - Sunshine | 0 | Level 3, lift to the left
JP0133 | Main office - Mentone | 0 | Do not use bleach on the timber floor
JP0134 | Clinic - Cheltenham | 0 | Park in bay 12 under the building
JP0135 | Warehouse - Moorabbin | 0
JP0136 | Main office - Cheltenham | 1 | Key safe at side gate, code [in 02 Site Access]; Sign in at security desk | 02 Site Access (office only)
JP0137 | Clinic - Frankston | 0
JP0138 | Warehouse - Glen Waverley | 0 | Do not use bleach on the timber floor
JP0139 | Main office - Burwood | 1 | Code for roller door: [in 02 Site Access] | 02 Site Access (office only)
JP0140 | Main office - Northcote | 0 | Reception closes 5:30 pm, use the side entry
JP0141 | Clinic - Northcote | 0
JP0142 | Warehouse - Thornbury | 0
JP0143 | Main office - Epping | 1 | Lockbox on meter box, [in 02 Site Access] | 02 Site Access (office only)
JP0144 | Main office - Bundoora | 1 | Key safe at side gate, code [in 02 Site Access] | 02 Site Access (office only)
JP0145 | Main office - Maribyrnong | 0 | Park in bay 12 under the building
JP0146 | Main office - Ringwood | 0 | Kitchen: 2 fridges, empty on Fridays
JP0147 | Main office - Glen Waverley | 0 | Store room on level 1, room 104
JP0148 | Main office - Werribee | 1 | Lockbox on meter box, [in 02 Site Access] | 02 Site Access (office only)
JP0149 | Main office - Footscray | 0 | Store room on level 1, room 104
JP0150 | Main office - Hawthorn | 1 | Code for roller door: [in 02 Site Access] | 02 Site Access (office only)
JP0151 | Main office - Altona | 0
JP0152 | Main office - Coburg | 1 | Key safe at side gate, code [in 02 Site Access]; Vacuum bags in cupboard 2 | 02 Site Access (office only)
JP0153 | Clinic - Reservoir | 0 | Vacuum bags in cupboard 2
JP0154 | Main office - Camberwell | 1 | Back door keypad [in 02 Site Access]*; Level 3, lift to the left | 02 Site Access (office only)
JP0155 | Main office - Glen Waverley | 0
JP0156 | Main office - Glen Waverley | 0 | Bins out on Tuesday night
JP0157 | Main office - Point Cook | 0
JP0158 | Clinic - Brighton | 0 | Call 0400 000 000 if the door is locked
JP0159 | Main office - Camberwell | 0 | Kitchen: 2 fridges, empty on Fridays
JP0160 | Main office - Hawthorn | 1 | Alarm [in 02 Site Access] then press OFF; Vacuum bags in cupboard 2 | 02 Site Access (office only)
JP0161 | Clinic - Kew | 1 | Key safe at side gate, code [in 02 Site Access]; Park in bay 12 under the building | 02 Site Access (office only)
JP0162 | Main office - Williamstown | 0 | Level 3, lift to the left
JP0163 | Clinic - Cheltenham | 0 | Do not use bleach on the timber floor
JP0164 | Main office - Oakleigh | 0
JP0165 | Clinic - Moorabbin | 0 | Do not use bleach on the timber floor
JP0166 | Warehouse - St Kilda | 0 | Park in bay 12 under the building
JP0167 | Main office - Mentone | 0
JP0168 | Clinic - Northcote | 0 | Do not use bleach on the timber floor
JP0169 | Main office - Brunswick | 1 | Back door keypad [in 02 Site Access]* | 02 Site Access (office only)
JP0170 | Clinic - Frankston | 0 | Bins out on Tuesday night
JP0171 | Main office - Bentleigh | 0 | Bins out on Tuesday night
JP0172 | Main office - Brunswick | 1 | Alarm [in 02 Site Access] then press OFF; Park in bay 12 under the building | 02 Site Access (office only)
JP0173 | Clinic - Hawthorn | 1 | Alarm code [in 02 Site Access]#, panel behind reception door; Bins out on Tuesday night | 02 Site Access (office only)
JP0174 | Warehouse - Altona | 0 | Park in bay 12 under the building
JP0175 | Main office - Deer Park | 0 | Vacuum bags in cupboard 2
JP0176 | Clinic - Reservoir | 0 | Call 0400 000 000 if the door is locked
JP0177 | Main office - Brunswick | 0 | Sign in at security desk
JP0178 | Clinic - Preston | 0 | Level 3, lift to the left
JP0179 | Warehouse - Mitcham | 1 | Lockbox on meter box, [in 02 Site Access] | 02 Site Access (office only)
JP0180 | Main office - Yarraville | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0181 | Clinic - Williamstown | 0 | Store room on level 1, room 104
JP0182 | Main office - Footscray | 0 | Level 3, lift to the left
JP0183 | Main office - Frankston | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0184 | Main office - Northcote | 0 | Do not use bleach on the timber floor
JP0185 | Main office - Laverton | 1 | Key safe at side gate, code [in 02 Site Access] | 02 Site Access (office only)
JP0186 | Clinic - Brighton | 0 | Call 0400 000 000 if the door is locked
JP0187 | Main office - Yarraville | 0 | Reception closes 5:30 pm, use the side entry
JP0188 | Main office - Cheltenham | 0
JP0189 | Main office - Bentleigh | 0 | Do not use bleach on the timber floor
JP0190 | Main office - Bentleigh | 1 | Alarm [in 02 Site Access] then press OFF; Park in bay 12 under the building | 02 Site Access (office only)
JP0191 | Main office - Hawthorn | 0 | Vacuum bags in cupboard 2
JP0192 | Clinic - Camberwell | 0 | Do not use bleach on the timber floor
JP0193 | Warehouse - Glen Waverley | 1 | Alarm [in 02 Site Access] then press OFF; Reception closes 5:30 pm, use the side entry | 02 Site Access (office only)
JP0194 | Main office - Williamstown | 0 | Level 3, lift to the left
JP0195 | Clinic - Epping | 0 | Park in bay 12 under the building
JP0196 | Main office - Mitcham | 0
JP0197 | Main office - Kew | 0 | Kitchen: 2 fridges, empty on Fridays
JP0198 | Clinic - Ringwood | 0 | Bins out on Tuesday night
JP0199 | Warehouse - Blackburn | 0
JP0200 | Main office - Sunshine | 0 | Vacuum bags in cupboard 2
JP0201 | Main office - Maribyrnong | 0 | Store room on level 1, room 104
JP0202 | Main office - Dandenong | 0
JP0203 | Clinic - Moorabbin | 0
JP0204 | Main office - Box Hill | 0 | Sign in at security desk
JP0205 | Main office - Coburg | 1 | Code for roller door: [in 02 Site Access] | 02 Site Access (office only)
JP0206 | Main office - Frankston | 1 | Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor | 02 Site Access (office only)
JP0207 | Main office - Preston | 0 | Bins out on Tuesday night
JP0208 | Clinic - Thornbury | 0
JP0209 | Main office - Northcote | 1 | Back door keypad [in 02 Site Access]*; Store room on level 1, room 104 | 02 Site Access (office only)
JP0210 | Main office - Burwood | 0 | Park in bay 12 under the building
JP0211 | Clinic - Maribyrnong | 0 | Store room on level 1, room 104
JP0212 | Main office - Ringwood | 1 | Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays | 02 Site Access (office only)
JP0213 | Clinic - Kew | 0
JP0214 | Warehouse - Burwood | 0
JP0215 | Main office - Brighton | 0 | Reception closes 5:30 pm, use the side entry
JP0216 | Main office - Box Hill | 0 | Park in bay 12 under the building
JP0217 | Clinic - Glen Waverley | 0 | Level 3, lift to the left
JP0218 | Main office - Mentone | 0 | Park in bay 12 under the building
JP0219 | Clinic - Cheltenham | 0 | Park in bay 12 under the building
JP0220 | Main office - Oakleigh | 0
JP0221 | Clinic - Oakleigh | 1 | Code for roller door: [in 02 Site Access]; Level 3, lift to the left | 02 Site Access (office only)
JP0222 | Main office - Brighton | 0 | Call 0400 000 000 if the door is locked
JP0223 | Clinic - Oakleigh | 0 | Bins out on Tuesday night
JP0224 | Main office - Point Cook | 1 | Back door keypad [in 02 Site Access]* | 02 Site Access (office only)
JP0225 | Main office - Northcote | 0 | Reception closes 5:30 pm, use the side entry
JP0226 | Clinic - Mentone | 0
JP0227 | Main office - Altona | 1 | Alarm code [in 02 Site Access]#, panel behind reception door; Store room on level 1, room 104 | 02 Site Access (office only)
JP0228 | Clinic - Hawthorn | 1 | Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor | 02 Site Access (office only)
JP0229 | Main office - Maribyrnong | 0 | Sign in at security desk
JP0230 | Main office - Bundoora | 0
JP0231 | Main office - Werribee | 0 | Store room on level 1, room 104
JP0232 | Main office - Thornbury | 1 | Lockbox on meter box, [in 02 Site Access]; Kitchen: 2 fridges, empty on Fridays | 02 Site Access (office only)
JP0233 | Main office - Mitcham | 1 | Code for roller door: [in 02 Site Access]; Bins out on Tuesday night | 02 Site Access (office only)
JP0234 | Clinic - Reservoir | 0 | Do not use bleach on the timber floor
JP0235 | Main office - Burwood | 0 | Do not use bleach on the timber floor
JP0236 | Main office - Bentleigh | 0
JP0237 | Clinic - Bentleigh | 1 | Lockbox on meter box, [in 02 Site Access] | 02 Site Access (office only)
JP0238 | Warehouse - St Kilda | 0 | Do not use bleach on the timber floor
JP0239 | Main office - Northcote | 0 | Bins out on Tuesday night
JP0240 | Main office - Glen Waverley | 0
JP0241 | Clinic - Clayton | 0 | Sign in at security desk
JP0242 | Main office - Coburg | 1 | Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor | 02 Site Access (office only)
JP0243 | Main office - Moorabbin | 0 | Vacuum bags in cupboard 2
JP0244 | Clinic - Moorabbin | 0 | Level 3, lift to the left
JP0245 | Main office - Mentone | 0 | Reception closes 5:30 pm, use the side entry
JP0246 | Main office - Point Cook | 0 | Kitchen: 2 fridges, empty on Fridays
JP0247 | Main office - Brighton | 1 | Alarm [in 02 Site Access] then press OFF | 02 Site Access (office only)
JP0248 | Clinic - Werribee | 0 | Vacuum bags in cupboard 2
JP0249 | Main office - Point Cook | 1 | Key safe at side gate, code [in 02 Site Access]; Call 0400 000 000 if the door is locked | 02 Site Access (office only)
JP0250 | Clinic - Essendon | 0
JP0251 | Main office - Kew | 0 | Park in bay 12 under the building
JP0252 | Main office - Maribyrnong | 1 | Key safe at side gate, code [in 02 Site Access] | 02 Site Access (office only)

## Calendar Build
Google Calendar build: one recurring event per active job, one calendar per cleaner
Work sample: realistic data, built to show how I approach this work.
Job | Wave | Calendar | Title | First date | Start | End | RRULE | Location | Drive folder | Description | Clash | Code in text
J1001 | Wave 3 South | CL43 Carmen L. roster | Office clean - Oakwood Vet Clinic (Bentleigh) | 2027-01-26 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU | 218 High Road, Bentleigh VIC | Clients/Oakwood Vet Clinic/Main office - Bentleigh | Office clean. Checklist: Clients/Oakwood Vet Clinic/Main office - Bentleigh/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Bins out on Tuesday night. Access details: Clients/Oakwood Vet Clinic/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1002 | Wave 3 South | CL39 Sione F. roster | Kitchen and bathrooms - Oakwood Vet Clinic (Oakleigh) | 2027-01-26 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TU | 162 Station Parade, Oakleigh VIC | Clients/Oakwood Vet Clinic/Clinic - Oakleigh | Kitchen and bathrooms. Checklist: Clients/Oakwood Vet Clinic/Clinic - Oakleigh/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Oakwood Vet Clinic/Clinic - Oakleigh/02 Site Access (office will share). | No | 0
J1003 | Wave 3 South | CL59 Sione L. roster | Window clean - Oakwood Vet Clinic (Oakleigh) | 2027-01-25 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 162 Station Parade, Oakleigh VIC | Clients/Oakwood Vet Clinic/Clinic - Oakleigh | Window clean. Checklist: Clients/Oakwood Vet Clinic/Clinic - Oakleigh/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Oakwood Vet Clinic/Clinic - Oakleigh/02 Site Access (office will share). | No | 0
J1004 | Wave 4 West | CL48 Hamid L. roster | Kitchen and bathrooms - Clearwater Dental Pty Ltd (Deer Park) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 273 Albert Road, Deer Park VIC | Clients/Clearwater Dental Pty Ltd/Main office - Deer Park | Kitchen and bathrooms. Checklist: Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/02 Site Access (office will share). | No | 0
J1005 | Wave 1 North | CL37 Quynh F. roster | Kitchen and bathrooms - Riverside Insurance Brokers Pty Ltd (Bundoora) | 2027-01-12 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TU,WE | 59 Station Parade, Bundoora VIC | Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora | Kitchen and bathrooms. Checklist: Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1006 | Wave 1 North | CL60 Tara L. roster | Window clean - Riverside Insurance Brokers Pty Ltd (Bundoora) | 2027-01-28 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 59 Station Parade, Bundoora VIC | Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora | Window clean. Checklist: Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1007 | Wave 4 West | CL12 Luis A. roster | Kitchen and bathrooms - Ironbark Pathology Pty Ltd (Footscray) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,WE | 224 Ballarat Parade, Footscray VIC | Clients/Ironbark Pathology Pty Ltd/Main office - Footscray | Kitchen and bathrooms. Checklist: Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/02 Site Access (office will share). | No | 0
J1008 | Wave 3 South | CL23 Carmen F. roster | Office clean - Westend Fitness Pty Ltd (Brighton) | 2027-01-27 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=WE,TH,FR | 77 Ballarat Parade, Brighton VIC | Clients/Westend Fitness Pty Ltd/Main office - Brighton | Office clean. Checklist: Clients/Westend Fitness Pty Ltd/Main office - Brighton/01 Scope & Checklist. Notes: -. Access details: Clients/Westend Fitness Pty Ltd/Main office - Brighton/02 Site Access (office will share). | No | 0
J1009 | Wave 1 North | CL13 Maya A. roster | Office clean - Redgum Dental (Bundoora) | 2027-01-12 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU,WE | 290A Ballarat Highway, Bundoora VIC | Clients/Redgum Dental/Main office - Bundoora | Office clean. Checklist: Clients/Redgum Dental/Main office - Bundoora/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Redgum Dental/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1010 | Wave 4 West | CL32 Luis F. roster | Office clean - Redgum Dental (Werribee) | 2027-02-02 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU,WE | 359 Glenferrie Avenue, Werribee VIC | Clients/Redgum Dental/Clinic - Werribee | Office clean. Checklist: Clients/Redgum Dental/Clinic - Werribee/01 Scope & Checklist. Notes: -. Access details: Clients/Redgum Dental/Clinic - Werribee/02 Site Access (office will share). | No | 0
J1011 | Wave 3 South | CL27 Grace F. roster | Office clean - Elm Street Physiotherapy (Oakleigh) | 2027-01-27 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=WE | 315 Park Parade, Oakleigh VIC | Clients/Elm Street Physiotherapy/Main office - Oakleigh | Office clean. Checklist: Clients/Elm Street Physiotherapy/Main office - Oakleigh/01 Scope & Checklist. Notes: -. Access details: Clients/Elm Street Physiotherapy/Main office - Oakleigh/02 Site Access (office will share). | No | 0
J1012 | Wave 4 West | CL36 Pita F. roster | Office clean - Elm Street Physiotherapy (Point Cook) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,WE | 359 Albert Street, Point Cook VIC | Clients/Elm Street Physiotherapy/Clinic - Point Cook | Office clean. Checklist: Clients/Elm Street Physiotherapy/Clinic - Point Cook/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Elm Street Physiotherapy/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1013 | Wave 4 West | CL55 Omar L. roster | Washroom service - Elm Street Physiotherapy (Point Cook) | 2027-02-04 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TH | 359 Albert Street, Point Cook VIC | Clients/Elm Street Physiotherapy/Clinic - Point Cook | Washroom service. Checklist: Clients/Elm Street Physiotherapy/Clinic - Point Cook/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Elm Street Physiotherapy/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1014 | Wave 2 East | CL10 Jun A. roster | Office clean - Wattle Grove Property Group (Hawthorn) | 2027-01-18 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TU | 169 King Street, Hawthorn VIC | Clients/Wattle Grove Property Group/Main office - Hawthorn | Office clean. Checklist: Clients/Wattle Grove Property Group/Main office - Hawthorn/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Wattle Grove Property Group/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1015 | Wave 2 East | CL53 Maya L. roster | Washroom service - Wattle Grove Property Group (Hawthorn) | 2027-02-03 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1WE | 169 King Street, Hawthorn VIC | Clients/Wattle Grove Property Group/Main office - Hawthorn | Washroom service. Checklist: Clients/Wattle Grove Property Group/Main office - Hawthorn/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Wattle Grove Property Group/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1016 | Wave 1 North | CL45 Eleni L. roster | Kitchen and bathrooms - Hillcrest Physiotherapy Pty Ltd (Epping) | 2027-01-11 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 396 Park Highway, Epping VIC | Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping | Kitchen and bathrooms. Checklist: Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/02 Site Access (office will share). | No | 0
J1017 | Wave 1 North | CL29 Ines F. roster | Office clean - Hillcrest Physiotherapy Pty Ltd (Thornbury) | 2027-01-13 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=WE,TH | 214A Nepean Parade, Thornbury VIC | Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury | Office clean. Checklist: Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/02 Site Access (office will share). | No | 0
J1018 | Wave 2 East | CL34 Nikos F. roster | Office clean - Kingsley Real Estate (Mitcham) | 2027-01-21 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=TH | 208 Main Avenue, Mitcham VIC | Clients/Kingsley Real Estate/Main office - Mitcham | Office clean. Checklist: Clients/Kingsley Real Estate/Main office - Mitcham/01 Scope & Checklist. Notes: -. Access details: Clients/Kingsley Real Estate/Main office - Mitcham/02 Site Access (office will share). | No | 0
J1019 | Wave 2 East | CL50 Jun L. roster | Office clean - Kingsley Real Estate (Kew) | 2027-01-22 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=FR | 208 High Avenue, Kew VIC | Clients/Kingsley Real Estate/Clinic - Kew | Office clean. Checklist: Clients/Kingsley Real Estate/Clinic - Kew/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Kingsley Real Estate/Clinic - Kew/02 Site Access (office will share). | No | 0
J1020 | Wave 3 South | CL11 Kavya A. roster | Office clean - Wattle Grove Medical Centre Pty Ltd (Clayton) | 2027-01-28 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TH | 462 Mason Road, Clayton VIC | Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton | Office clean. Checklist: Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]. Access details: Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/02 Site Access (office will share). | No | 0
J1021 | Wave 1 North | CL25 Eleni F. roster | Office clean - Bluestone Engineering (Coburg) | 2027-01-11 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TU | 201 Plenty Avenue, Coburg VIC | Clients/Bluestone Engineering/Main office - Coburg | Office clean. Checklist: Clients/Bluestone Engineering/Main office - Coburg/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]. Access details: Clients/Bluestone Engineering/Main office - Coburg/02 Site Access (office will share). | No | 0
J1022 | Wave 3 South | CL51 Kavya L. roster | Office clean - Clearwater Insurance Brokers Pty Ltd (Mentone) | 2027-01-25 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE | 164 Whitehorse Street, Mentone VIC | Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone | Office clean. Checklist: Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/02 Site Access (office will share). | No | 0
J1023 | Wave 2 East | CL46 Farid L. roster | Office clean - Redgum Optometrists Pty Ltd (Camberwell) | 2027-01-20 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=WE,FR | 480 King Avenue, Camberwell VIC | Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell | Office clean. Checklist: Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1024 | Wave 2 East | CL58 Rosa L. roster | Carpet steam clean - Redgum Optometrists Pty Ltd (Camberwell) | 2027-02-05 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 480 King Avenue, Camberwell VIC | Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell | Carpet steam clean. Checklist: Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1025 | Wave 3 South | CL07 Grace A. roster | Kitchen and bathrooms - Northside Accountants Pty Ltd (Cheltenham) | 2027-01-27 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=WE,FR | 426 Mason Street, Cheltenham VIC | Clients/Northside Accountants Pty Ltd/Main office - Cheltenham | Kitchen and bathrooms. Checklist: Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/02 Site Access (office will share). | No | 0
J1026 | Wave 3 South | CL54 Nikos L. roster | Window clean - Northside Accountants Pty Ltd (Cheltenham) | 2027-02-09 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 426 Mason Street, Cheltenham VIC | Clients/Northside Accountants Pty Ltd/Main office - Cheltenham | Window clean. Checklist: Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/02 Site Access (office will share). | No | 0
J1027 | Wave 3 South | CL31 Kavya F. roster | Office clean - Northside Accountants Pty Ltd (Oakleigh) | 2027-01-25 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=MO,WE,TH | 351 Burke Road, Oakleigh VIC | Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh | Office clean. Checklist: Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/02 Site Access (office will share). | No | 0
J1028 | Wave 3 South | CL03 Carmen A. roster | Kitchen and bathrooms - Northside Accountants Pty Ltd (Clayton) | 2027-01-25 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TH | 354 High Street, Clayton VIC | Clients/Northside Accountants Pty Ltd/Warehouse - Clayton | Kitchen and bathrooms. Checklist: Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/02 Site Access (office will share). | No | 0
J1029 | Pilot | CL33 Maya F. roster | Office clean - Oakwood Accountants Pty Ltd (Reservoir) | 2026-12-07 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=MO | 54 Mason Parade, Reservoir VIC | Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir | Office clean. Checklist: Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1030 | Wave 3 South | CL47 Grace L. roster | Office clean - Northside Engineering Pty Ltd (St Kilda) | 2027-01-25 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=MO,WE | 430 Victoria Road, St Kilda VIC | Clients/Northside Engineering Pty Ltd/Main office - St Kilda | Office clean. Checklist: Clients/Northside Engineering Pty Ltd/Main office - St Kilda/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Sign in at security desk. Access details: Clients/Northside Engineering Pty Ltd/Main office - St Kilda/02 Site Access (office will share). | No | 0
J1031 | Wave 3 South | CL15 Omar A. roster | Office clean - Northside Engineering Pty Ltd (Bentleigh) | 2027-01-27 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=WE,FR | 195/12 Railway Highway, Bentleigh VIC | Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh | Office clean. Checklist: Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/02 Site Access (office will share). | No | 0
J1032 | Wave 3 South | CL56 Pita L. roster | Carpet steam clean - Northside Engineering Pty Ltd (Bentleigh) | 2027-01-28 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 195/12 Railway Highway, Bentleigh VIC | Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh | Carpet steam clean. Checklist: Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/02 Site Access (office will share). | No | 0
J1033 | Wave 4 West | CL52 Luis L. roster | Office clean - Northside Engineering Pty Ltd (Deer Park) | 2027-02-01 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 10 Queen Highway, Deer Park VIC | Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park | Office clean. Checklist: Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/02 Site Access (office will share). | No | 0
J1034 | Wave 3 South | CL19 Sione A. roster | Kitchen and bathrooms - Northside Engineering Pty Ltd (St Kilda) | 2027-01-25 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,WE | 17 Park Avenue, St Kilda VIC | Clients/Northside Engineering Pty Ltd/Showroom - St Kilda | Kitchen and bathrooms. Checklist: Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Park in bay 12 under the building. Access details: Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/02 Site Access (office will share). | No | 0
J1035 | Wave 2 East | CL14 Nikos A. roster | Office clean - Ashwood Early Learning (Camberwell) | 2027-01-18 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 378 Plenty Street, Camberwell VIC | Clients/Ashwood Early Learning/Main office - Camberwell | Office clean. Checklist: Clients/Ashwood Early Learning/Main office - Camberwell/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Ashwood Early Learning/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1036 | Wave 2 East | CL56 Pita L. roster | Window clean - Ashwood Early Learning (Camberwell) | 2027-02-02 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 378 Plenty Street, Camberwell VIC | Clients/Ashwood Early Learning/Main office - Camberwell | Window clean. Checklist: Clients/Ashwood Early Learning/Main office - Camberwell/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Ashwood Early Learning/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1037 | Wave 4 West | CL40 Tara F. roster | Office clean - Silverton Pharmacy (Point Cook) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 266 Union Avenue, Point Cook VIC | Clients/Silverton Pharmacy/Main office - Point Cook | Office clean. Checklist: Clients/Silverton Pharmacy/Main office - Point Cook/01 Scope & Checklist. Notes: -. Access details: Clients/Silverton Pharmacy/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1038 | Wave 2 East | CL22 Bilal F. roster | Office clean - Silverton Pharmacy (Kew) | 2027-01-21 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TH | 98 Park Road, Kew VIC | Clients/Silverton Pharmacy/Clinic - Kew | Office clean. Checklist: Clients/Silverton Pharmacy/Clinic - Kew/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Silverton Pharmacy/Clinic - Kew/02 Site Access (office will share). | No | 0
J1039 | Wave 1 North | CL21 Ana F. roster | Office clean - Silverton Pharmacy (Bundoora) | 2027-01-13 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=WE | 107 Barkly Highway, Bundoora VIC | Clients/Silverton Pharmacy/Warehouse - Bundoora | Office clean. Checklist: Clients/Silverton Pharmacy/Warehouse - Bundoora/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Silverton Pharmacy/Warehouse - Bundoora/02 Site Access (office will share). | No | 0
J1040 | Wave 4 West | CL20 Tara A. roster | Office clean - Silverton Pharmacy (Footscray) | 2027-02-02 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=TU,WE | 298 Main Road, Footscray VIC | Clients/Silverton Pharmacy/Showroom - Footscray | Office clean. Checklist: Clients/Silverton Pharmacy/Showroom - Footscray/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Silverton Pharmacy/Showroom - Footscray/02 Site Access (office will share). | No | 0
J1041 | Wave 4 West | CL58 Rosa L. roster | Carpet steam clean - Silverton Pharmacy (Footscray) | 2027-02-22 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 298 Main Road, Footscray VIC | Clients/Silverton Pharmacy/Showroom - Footscray | Carpet steam clean. Checklist: Clients/Silverton Pharmacy/Showroom - Footscray/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Silverton Pharmacy/Showroom - Footscray/02 Site Access (office will share). | No | 0
J1042 | Wave 2 East | CL06 Farid A. roster | Kitchen and bathrooms - Brightside Podiatry (Camberwell) | 2027-01-19 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=TU | 142 Plenty Road, Camberwell VIC | Clients/Brightside Podiatry/Main office - Camberwell | Kitchen and bathrooms. Checklist: Clients/Brightside Podiatry/Main office - Camberwell/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Brightside Podiatry/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1043 | Wave 2 East | CL30 Jun F. roster | Office clean - Ashwood Optometrists (Ringwood) | 2027-01-19 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU,WE | 195 Nicholson Road, Ringwood VIC | Clients/Ashwood Optometrists/Main office - Ringwood | Office clean. Checklist: Clients/Ashwood Optometrists/Main office - Ringwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Ashwood Optometrists/Main office - Ringwood/02 Site Access (office will share). | No | 0
J1044 | Wave 2 East | CL57 Quynh L. roster | Window clean - Ashwood Optometrists (Ringwood) | 2027-02-02 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 195 Nicholson Road, Ringwood VIC | Clients/Ashwood Optometrists/Main office - Ringwood | Window clean. Checklist: Clients/Ashwood Optometrists/Main office - Ringwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Ashwood Optometrists/Main office - Ringwood/02 Site Access (office will share). | No | 0
J1045 | Wave 2 East | CL42 Bilal L. roster | Kitchen and bathrooms - Ashwood Optometrists (Ringwood) | 2027-01-21 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=TH | 245 Ballarat Avenue, Ringwood VIC | Clients/Ashwood Optometrists/Clinic - Ringwood | Kitchen and bathrooms. Checklist: Clients/Ashwood Optometrists/Clinic - Ringwood/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Optometrists/Clinic - Ringwood/02 Site Access (office will share). | No | 0
J1046 | Wave 2 East | CL59 Sione L. roster | Washroom service - Ashwood Optometrists (Ringwood) | 2027-02-01 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1MO | 245 Ballarat Avenue, Ringwood VIC | Clients/Ashwood Optometrists/Clinic - Ringwood | Washroom service. Checklist: Clients/Ashwood Optometrists/Clinic - Ringwood/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Optometrists/Clinic - Ringwood/02 Site Access (office will share). | No | 0
J1047 | Wave 1 North | CL41 Ana L. roster | Kitchen and bathrooms - Parkside Accountants (Bundoora) | 2027-01-12 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=TU,WE | 22 Hopkins Road, Bundoora VIC | Clients/Parkside Accountants/Main office - Bundoora | Kitchen and bathrooms. Checklist: Clients/Parkside Accountants/Main office - Bundoora/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Parkside Accountants/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1048 | Pilot | CL09 Ines A. roster | Office clean - Parkside Accountants (Northcote) | 2026-12-11 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=FR | 356 Albert Avenue, Northcote VIC | Clients/Parkside Accountants/Clinic - Northcote | Office clean. Checklist: Clients/Parkside Accountants/Clinic - Northcote/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Parkside Accountants/Clinic - Northcote/02 Site Access (office will share). | No | 0
J1049 | Wave 1 North | CL57 Quynh L. roster | Carpet steam clean - Parkside Accountants (Northcote) | 2027-01-19 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 356 Albert Avenue, Northcote VIC | Clients/Parkside Accountants/Clinic - Northcote | Carpet steam clean. Checklist: Clients/Parkside Accountants/Clinic - Northcote/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Parkside Accountants/Clinic - Northcote/02 Site Access (office will share). | No | 0
J1050 | Wave 1 North | CL05 Eleni A. roster | Office clean - Brightside Motors Pty Ltd (Heidelberg) | 2027-01-13 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=WE | 364/12 High Road, Heidelberg VIC | Clients/Brightside Motors Pty Ltd/Main office - Heidelberg | Office clean. Checklist: Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/02 Site Access (office will share). | No | 0
J1051 | Wave 4 West | CL24 Dinh F. roster | Office clean - Westend Motors Pty Ltd (Sunshine) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 417 Main Road, Sunshine VIC | Clients/Westend Motors Pty Ltd/Main office - Sunshine | Office clean. Checklist: Clients/Westend Motors Pty Ltd/Main office - Sunshine/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Westend Motors Pty Ltd/Main office - Sunshine/02 Site Access (office will share). | Yes | 0
J1052 | Wave 4 West | CL08 Hamid A. roster | Office clean - Westend Motors Pty Ltd (Williamstown) | 2027-02-02 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU,WE | 37 Nicholson Highway, Williamstown VIC | Clients/Westend Motors Pty Ltd/Clinic - Williamstown | Office clean. Checklist: Clients/Westend Motors Pty Ltd/Clinic - Williamstown/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Reception closes 5:30 pm, use the side entry. Access details: Clients/Westend Motors Pty Ltd/Clinic - Williamstown/02 Site Access (office will share). | No | 0
J1053 | Wave 1 North | CL17 Quynh A. roster | Office clean - Westend Motors Pty Ltd (Epping) | 2027-01-13 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=WE | 117 Railway Highway, Epping VIC | Clients/Westend Motors Pty Ltd/Warehouse - Epping | Office clean. Checklist: Clients/Westend Motors Pty Ltd/Warehouse - Epping/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Westend Motors Pty Ltd/Warehouse - Epping/02 Site Access (office will share). | No | 0
J1054 | Wave 3 South | CL35 Omar F. roster | Office clean - Oakwood Lawyers Pty Ltd (Moorabbin) | 2027-01-26 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU | 453 Plenty Parade, Moorabbin VIC | Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin | Office clean. Checklist: Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/01 Scope & Checklist. Notes: -. Access details: Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/02 Site Access (office will share). | No | 0
J1055 | Wave 1 North | CL01 Ana A. roster | Office clean - Oakwood Lawyers Pty Ltd (Essendon) | 2027-01-11 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=MO,WE | 188 Nicholson Road, Essendon VIC | Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon | Office clean. Checklist: Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Vacuum bags in cupboard 2. Access details: Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/02 Site Access (office will share). | No | 0
J1056 | Wave 2 East | CL26 Farid F. roster | Office clean - Riverside Medical Centre (Camberwell) | 2027-01-18 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=MO | 300 Sydney Highway, Camberwell VIC | Clients/Riverside Medical Centre/Main office - Camberwell | Office clean. Checklist: Clients/Riverside Medical Centre/Main office - Camberwell/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Medical Centre/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1057 | Wave 4 West | CL44 Dinh L. roster | Office clean - Riverside Motors Pty Ltd (Altona) | 2027-02-03 | 06:00 | 08:00 | FREQ=WEEKLY;BYDAY=WE | 205 Railway Street, Altona VIC | Clients/Riverside Motors Pty Ltd/Main office - Altona | Office clean. Checklist: Clients/Riverside Motors Pty Ltd/Main office - Altona/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Riverside Motors Pty Ltd/Main office - Altona/02 Site Access (office will share). | Yes | 0
J1058 | Wave 4 West | CL04 Dinh A. roster | Office clean - Parkside Pathology Pty Ltd (Yarraville) | 2027-02-01 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE | 359 King Road, Yarraville VIC | Clients/Parkside Pathology Pty Ltd/Main office - Yarraville | Office clean. Checklist: Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/02 Site Access (office will share). | No | 0
J1059 | Wave 2 East | CL18 Rosa A. roster | Office clean - Sunbury Accountants Pty Ltd (Camberwell) | 2027-01-20 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=WE,FR | 313A Queen Street, Camberwell VIC | Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell | Office clean. Checklist: Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1060 | Wave 2 East | CL38 Rosa F. roster | Office clean - Sunbury Early Learning (Glen Waverley) | 2027-01-18 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TH | 386 Nepean Road, Glen Waverley VIC | Clients/Sunbury Early Learning/Main office - Glen Waverley | Office clean. Checklist: Clients/Sunbury Early Learning/Main office - Glen Waverley/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Sunbury Early Learning/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1061 | Wave 1 North | CL29 Ines F. roster | Office clean - Silverton Lawyers Pty Ltd (Thornbury) | 2027-01-12 | 08:00 | 10:00 | FREQ=WEEKLY;BYDAY=TU,TH | 255 Glenferrie Parade, Thornbury VIC | Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury | Office clean. Checklist: Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/02 Site Access (office will share). | Yes | 0
J1062 | Wave 1 North | CL41 Ana L. roster | Office clean - Waverley Accountants Pty Ltd (Brunswick) | 2027-01-11 | 06:30 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 23A Ballarat Street, Brunswick VIC | Clients/Waverley Accountants Pty Ltd/Main office - Brunswick | Office clean. Checklist: Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1063 | Wave 1 North | CL60 Tara L. roster | Window clean - Waverley Accountants Pty Ltd (Brunswick) | 2027-01-21 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 23A Ballarat Street, Brunswick VIC | Clients/Waverley Accountants Pty Ltd/Main office - Brunswick | Window clean. Checklist: Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1064 | Wave 1 North | CL05 Eleni A. roster | Office clean - Westend Podiatry (Brunswick) | 2027-01-11 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TH | 310 Ballarat Avenue, Brunswick VIC | Clients/Westend Podiatry/Main office - Brunswick | Office clean. Checklist: Clients/Westend Podiatry/Main office - Brunswick/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Westend Podiatry/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1065 | Wave 1 North | CL58 Rosa L. roster | Carpet steam clean - Westend Podiatry (Brunswick) | 2027-01-20 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 310 Ballarat Avenue, Brunswick VIC | Clients/Westend Podiatry/Main office - Brunswick | Carpet steam clean. Checklist: Clients/Westend Podiatry/Main office - Brunswick/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Westend Podiatry/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1066 | Pilot | CL33 Maya F. roster | Office clean - Westend Podiatry (Thornbury) | 2026-12-07 | 17:30 | 20:00 | FREQ=WEEKLY;BYDAY=MO,WE,FR | 269 Victoria Avenue, Thornbury VIC | Clients/Westend Podiatry/Clinic - Thornbury | Office clean. Checklist: Clients/Westend Podiatry/Clinic - Thornbury/01 Scope & Checklist. Notes: -. Access details: Clients/Westend Podiatry/Clinic - Thornbury/02 Site Access (office will share). | No | 0
J1067 | Wave 1 North | CL56 Pita L. roster | Window clean - Westend Podiatry (Thornbury) | 2027-01-18 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 269 Victoria Avenue, Thornbury VIC | Clients/Westend Podiatry/Clinic - Thornbury | Window clean. Checklist: Clients/Westend Podiatry/Clinic - Thornbury/01 Scope & Checklist. Notes: -. Access details: Clients/Westend Podiatry/Clinic - Thornbury/02 Site Access (office will share). | No | 0
J1068 | Wave 1 North | CL37 Quynh F. roster | Office clean - Westend Podiatry (Essendon) | 2027-01-14 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=TH | 332A Glenferrie Parade, Essendon VIC | Clients/Westend Podiatry/Warehouse - Essendon | Office clean. Checklist: Clients/Westend Podiatry/Warehouse - Essendon/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Westend Podiatry/Warehouse - Essendon/02 Site Access (office will share). | No | 0
J1069 | Wave 4 West | CL24 Dinh F. roster | Office clean - Lakeside Engineering Pty Ltd (Deer Park) | 2027-02-01 | 06:00 | 07:00 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 157 Whitehorse Parade, Deer Park VIC | Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park | Office clean. Checklist: Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/01 Scope & Checklist. Notes: -. Access details: Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/02 Site Access (office will share). | Yes | 0
J1070 | Wave 4 West | CL44 Dinh L. roster | Kitchen and bathrooms - Lakeside Engineering Pty Ltd (Maribyrnong) | 2027-02-02 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TU,FR | 439 Sydney Parade, Maribyrnong VIC | Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong | Kitchen and bathrooms. Checklist: Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/02 Site Access (office will share). | No | 0
J1071 | Wave 3 South | CL27 Grace F. roster | Office clean - Kingsley Financial Planning (Oakleigh) | 2027-01-28 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TH | 204 Bridge Highway, Oakleigh VIC | Clients/Kingsley Financial Planning/Main office - Oakleigh | Office clean. Checklist: Clients/Kingsley Financial Planning/Main office - Oakleigh/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Kingsley Financial Planning/Main office - Oakleigh/02 Site Access (office will share). | No | 0
J1072 | Wave 3 South | CL39 Sione F. roster | Office clean - Wattle Grove Physiotherapy (Cheltenham) | 2027-01-26 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TU | 48 Ballarat Parade, Cheltenham VIC | Clients/Wattle Grove Physiotherapy/Main office - Cheltenham | Office clean. Checklist: Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/02 Site Access (office will share). | No | 0
J1073 | Wave 2 East | CL02 Bilal A. roster | Kitchen and bathrooms - Elm Street Fitness Pty Ltd (Hawthorn) | 2027-01-18 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 479 Mason Parade, Hawthorn VIC | Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn | Kitchen and bathrooms. Checklist: Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1074 | Wave 2 East | CL60 Tara L. roster | Window clean - Elm Street Fitness Pty Ltd (Hawthorn) | 2027-02-05 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 479 Mason Parade, Hawthorn VIC | Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn | Window clean. Checklist: Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1075 | Wave 2 East | CL06 Farid A. roster | Kitchen and bathrooms - Elm Street Fitness Pty Ltd (Doncaster) | 2027-01-18 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=MO,TH | 450 King Road, Doncaster VIC | Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster | Kitchen and bathrooms. Checklist: Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/02 Site Access (office will share). | No | 0
J1076 | Wave 2 East | CL57 Quynh L. roster | Window clean - Elm Street Fitness Pty Ltd (Doncaster) | 2027-02-11 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 450 King Road, Doncaster VIC | Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster | Window clean. Checklist: Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/02 Site Access (office will share). | No | 0
J1077 | Wave 2 East | CL42 Bilal L. roster | Office clean - Wattle Grove Dental (Hawthorn) | 2027-01-20 | 06:30 | 08:30 | FREQ=WEEKLY;BYDAY=WE,TH,FR | 259 Union Avenue, Hawthorn VIC | Clients/Wattle Grove Dental/Main office - Hawthorn | Office clean. Checklist: Clients/Wattle Grove Dental/Main office - Hawthorn/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Store room on level 1, room 104. Access details: Clients/Wattle Grove Dental/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1078 | Wave 4 West | CL48 Hamid L. roster | Office clean - Lakeside Vet Clinic (Point Cook) | 2027-02-05 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=FR | 426 Ballarat Parade, Point Cook VIC | Clients/Lakeside Vet Clinic/Main office - Point Cook | Office clean. Checklist: Clients/Lakeside Vet Clinic/Main office - Point Cook/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Lakeside Vet Clinic/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1079 | Wave 4 West | CL40 Tara F. roster | Office clean - Lakeside Vet Clinic (Laverton) | 2027-02-02 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TU | 164 Nicholson Street, Laverton VIC | Clients/Lakeside Vet Clinic/Clinic - Laverton | Office clean. Checklist: Clients/Lakeside Vet Clinic/Clinic - Laverton/01 Scope & Checklist. Notes: -. Access details: Clients/Lakeside Vet Clinic/Clinic - Laverton/02 Site Access (office will share). | No | 0
J1080 | Wave 4 West | CL60 Tara L. roster | Window clean - Lakeside Vet Clinic (Laverton) | 2027-02-15 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 164 Nicholson Street, Laverton VIC | Clients/Lakeside Vet Clinic/Clinic - Laverton | Window clean. Checklist: Clients/Lakeside Vet Clinic/Clinic - Laverton/01 Scope & Checklist. Notes: -. Access details: Clients/Lakeside Vet Clinic/Clinic - Laverton/02 Site Access (office will share). | No | 0
J1081 | Wave 3 South | CL07 Grace A. roster | Office clean - Clearwater Property Group Pty Ltd (Frankston) | 2027-01-25 | 06:30 | 08:30 | FREQ=WEEKLY;BYDAY=MO,WE,FR | 143/12 Nepean Street, Frankston VIC | Clients/Clearwater Property Group Pty Ltd/Main office - Frankston | Office clean. Checklist: Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/01 Scope & Checklist. Notes: -. Access details: Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/02 Site Access (office will share). | No | 0
J1082 | Wave 3 South | CL56 Pita L. roster | Washroom service - Clearwater Property Group Pty Ltd (Frankston) | 2027-02-01 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1MO | 143/12 Nepean Street, Frankston VIC | Clients/Clearwater Property Group Pty Ltd/Main office - Frankston | Washroom service. Checklist: Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/01 Scope & Checklist. Notes: -. Access details: Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/02 Site Access (office will share). | No | 0
J1083 | Wave 4 West | CL48 Hamid L. roster | Office clean - Clearwater Property Group Pty Ltd (Laverton) | 2027-02-01 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 380 Nepean Parade, Laverton VIC | Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton | Office clean. Checklist: Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/02 Site Access (office will share). | No | 0
J1084 | Wave 4 West | CL53 Maya L. roster | Window clean - Clearwater Property Group Pty Ltd (Laverton) | 2027-02-05 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 380 Nepean Parade, Laverton VIC | Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton | Window clean. Checklist: Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/02 Site Access (office will share). | No | 0
J1085 | Wave 2 East | CL02 Bilal A. roster | Office clean - Eastwood Real Estate Pty Ltd (Hawthorn) | 2027-01-19 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU,WE | 296 Barkly Highway, Hawthorn VIC | Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn | Office clean. Checklist: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1086 | Wave 2 East | CL60 Tara L. roster | Window clean - Eastwood Real Estate Pty Ltd (Hawthorn) | 2027-01-21 | 12:30 | 14:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 296 Barkly Highway, Hawthorn VIC | Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn | Window clean. Checklist: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1087 | Wave 2 East | CL58 Rosa L. roster | Washroom service - Eastwood Real Estate Pty Ltd (Hawthorn) | 2027-02-04 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TH | 296 Barkly Highway, Hawthorn VIC | Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn | Washroom service. Checklist: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1088 | Wave 3 South | CL19 Sione A. roster | Kitchen and bathrooms - Clearwater Physiotherapy (Bentleigh) | 2027-01-27 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=WE | 46 Main Avenue, Bentleigh VIC | Clients/Clearwater Physiotherapy/Main office - Bentleigh | Kitchen and bathrooms. Checklist: Clients/Clearwater Physiotherapy/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Clearwater Physiotherapy/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1089 | Wave 3 South | CL60 Tara L. roster | Carpet steam clean - Clearwater Physiotherapy (Bentleigh) | 2027-01-27 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 46 Main Avenue, Bentleigh VIC | Clients/Clearwater Physiotherapy/Main office - Bentleigh | Carpet steam clean. Checklist: Clients/Clearwater Physiotherapy/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Clearwater Physiotherapy/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1090 | Wave 3 South | CL60 Tara L. roster | Washroom service - Clearwater Physiotherapy (Bentleigh) | 2027-02-01 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1MO | 46 Main Avenue, Bentleigh VIC | Clients/Clearwater Physiotherapy/Main office - Bentleigh | Washroom service. Checklist: Clients/Clearwater Physiotherapy/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Clearwater Physiotherapy/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1091 | Wave 2 East | CL22 Bilal F. roster | Kitchen and bathrooms - Clearwater Physiotherapy (Burwood) | 2027-01-18 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,TU | 211 Union Road, Burwood VIC | Clients/Clearwater Physiotherapy/Clinic - Burwood | Kitchen and bathrooms. Checklist: Clients/Clearwater Physiotherapy/Clinic - Burwood/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]. Access details: Clients/Clearwater Physiotherapy/Clinic - Burwood/02 Site Access (office will share). | No | 0
J1092 | Wave 2 East | CL06 Farid A. roster | Office clean - Greenway Physiotherapy (Burwood) | 2027-01-20 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=WE | 418 Nicholson Avenue, Burwood VIC | Clients/Greenway Physiotherapy/Main office - Burwood | Office clean. Checklist: Clients/Greenway Physiotherapy/Main office - Burwood/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Greenway Physiotherapy/Main office - Burwood/02 Site Access (office will share). | No | 0
J1093 | Wave 3 South | CL03 Carmen A. roster | Office clean - Fairfield Engineering Pty Ltd (Bentleigh) | 2027-01-28 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TH | 43 Plenty Avenue, Bentleigh VIC | Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh | Office clean. Checklist: Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | Yes | 0
J1094 | Wave 3 South | CL35 Omar F. roster | Office clean - Fairfield Engineering Pty Ltd (Cheltenham) | 2027-01-26 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=TU,TH | 27 Railway Avenue, Cheltenham VIC | Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham | Office clean. Checklist: Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1095 | Wave 3 South | CL60 Tara L. roster | Window clean - Fairfield Engineering Pty Ltd (Cheltenham) | 2027-02-16 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 27 Railway Avenue, Cheltenham VIC | Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham | Window clean. Checklist: Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1096 | Wave 3 South | CL43 Carmen L. roster | Office clean - Westend Optometrists Pty Ltd (Mentone) | 2027-01-27 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=WE,TH,FR | 225/12 Glenferrie Parade, Mentone VIC | Clients/Westend Optometrists Pty Ltd/Main office - Mentone | Office clean. Checklist: Clients/Westend Optometrists Pty Ltd/Main office - Mentone/01 Scope & Checklist. Notes: -. Access details: Clients/Westend Optometrists Pty Ltd/Main office - Mentone/02 Site Access (office will share). | No | 0
J1097 | Wave 1 North | CL17 Quynh A. roster | Office clean - Kingsley Insurance Brokers (Reservoir) | 2027-01-13 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=WE,FR | 225 Park Avenue, Reservoir VIC | Clients/Kingsley Insurance Brokers/Main office - Reservoir | Office clean. Checklist: Clients/Kingsley Insurance Brokers/Main office - Reservoir/01 Scope & Checklist. Notes: -. Access details: Clients/Kingsley Insurance Brokers/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1098 | Wave 1 North | CL60 Tara L. roster | Carpet steam clean - Kingsley Insurance Brokers (Reservoir) | 2027-01-14 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 225 Park Avenue, Reservoir VIC | Clients/Kingsley Insurance Brokers/Main office - Reservoir | Carpet steam clean. Checklist: Clients/Kingsley Insurance Brokers/Main office - Reservoir/01 Scope & Checklist. Notes: -. Access details: Clients/Kingsley Insurance Brokers/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1099 | Wave 1 North | CL53 Maya L. roster | Washroom service - Kingsley Insurance Brokers (Reservoir) | 2027-02-05 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1FR | 225 Park Avenue, Reservoir VIC | Clients/Kingsley Insurance Brokers/Main office - Reservoir | Washroom service. Checklist: Clients/Kingsley Insurance Brokers/Main office - Reservoir/01 Scope & Checklist. Notes: -. Access details: Clients/Kingsley Insurance Brokers/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1100 | Wave 4 West | CL16 Pita A. roster | Office clean - Kingsley Insurance Brokers (Point Cook) | 2027-02-01 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=MO,FR | 410 Burke Highway, Point Cook VIC | Clients/Kingsley Insurance Brokers/Clinic - Point Cook | Office clean. Checklist: Clients/Kingsley Insurance Brokers/Clinic - Point Cook/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Park in bay 12 under the building. Access details: Clients/Kingsley Insurance Brokers/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1101 | Wave 4 West | CL59 Sione L. roster | Window clean - Kingsley Insurance Brokers (Point Cook) | 2027-02-15 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 410 Burke Highway, Point Cook VIC | Clients/Kingsley Insurance Brokers/Clinic - Point Cook | Window clean. Checklist: Clients/Kingsley Insurance Brokers/Clinic - Point Cook/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Park in bay 12 under the building. Access details: Clients/Kingsley Insurance Brokers/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1102 | Wave 2 East | CL50 Jun L. roster | Office clean - Bluestone Learning Centre Pty Ltd (Glen Waverley) | 2027-01-18 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=MO,WE | 205 Burke Highway, Glen Waverley VIC | Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley | Office clean. Checklist: Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1103 | Wave 2 East | CL55 Omar L. roster | Washroom service - Bluestone Learning Centre Pty Ltd (Glen Waverley) | 2027-02-04 | 10:00 | 10:30 | FREQ=MONTHLY;BYDAY=1TH | 205 Burke Highway, Glen Waverley VIC | Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley | Washroom service. Checklist: Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1104 | Wave 2 East | CL34 Nikos F. roster | Office clean - Oakwood Logistics (Hawthorn) | 2027-01-18 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,FR | 189 Union Highway, Hawthorn VIC | Clients/Oakwood Logistics/Main office - Hawthorn | Office clean. Checklist: Clients/Oakwood Logistics/Main office - Hawthorn/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Reception closes 5:30 pm, use the side entry. Access details: Clients/Oakwood Logistics/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1105 | Wave 2 East | CL58 Rosa L. roster | Carpet steam clean - Oakwood Logistics (Hawthorn) | 2027-01-20 | 11:30 | 14:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 189 Union Highway, Hawthorn VIC | Clients/Oakwood Logistics/Main office - Hawthorn | Carpet steam clean. Checklist: Clients/Oakwood Logistics/Main office - Hawthorn/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Reception closes 5:30 pm, use the side entry. Access details: Clients/Oakwood Logistics/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1106 | Wave 2 East | CL26 Farid F. roster | Kitchen and bathrooms - Oakwood Logistics (Blackburn) | 2027-01-18 | 07:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 128 Victoria Road, Blackburn VIC | Clients/Oakwood Logistics/Clinic - Blackburn | Kitchen and bathrooms. Checklist: Clients/Oakwood Logistics/Clinic - Blackburn/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Oakwood Logistics/Clinic - Blackburn/02 Site Access (office will share). | No | 0
J1107 | Wave 3 South | CL15 Omar A. roster | Office clean - Oakwood Logistics (Cheltenham) | 2027-01-25 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 375 Station Highway, Cheltenham VIC | Clients/Oakwood Logistics/Warehouse - Cheltenham | Office clean. Checklist: Clients/Oakwood Logistics/Warehouse - Cheltenham/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Oakwood Logistics/Warehouse - Cheltenham/02 Site Access (office will share). | No | 0
J1108 | Wave 3 South | CL56 Pita L. roster | Window clean - Oakwood Logistics (Cheltenham) | 2027-02-01 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 375 Station Highway, Cheltenham VIC | Clients/Oakwood Logistics/Warehouse - Cheltenham | Window clean. Checklist: Clients/Oakwood Logistics/Warehouse - Cheltenham/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door. Access details: Clients/Oakwood Logistics/Warehouse - Cheltenham/02 Site Access (office will share). | No | 0
J1109 | Wave 2 East | CL10 Jun A. roster | Office clean - Oakwood Logistics (Box Hill) | 2027-01-19 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=TU,FR | 378 Burke Highway, Box Hill VIC | Clients/Oakwood Logistics/Showroom - Box Hill | Office clean. Checklist: Clients/Oakwood Logistics/Showroom - Box Hill/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Oakwood Logistics/Showroom - Box Hill/02 Site Access (office will share). | No | 0
J1110 | Wave 2 East | CL22 Bilal F. roster | Office clean - Banksia Insurance Brokers (Burwood) | 2027-01-18 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 185 Church Parade, Burwood VIC | Clients/Banksia Insurance Brokers/Main office - Burwood | Office clean. Checklist: Clients/Banksia Insurance Brokers/Main office - Burwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Banksia Insurance Brokers/Main office - Burwood/02 Site Access (office will share). | No | 0
J1111 | Wave 2 East | CL58 Rosa L. roster | Window clean - Banksia Insurance Brokers (Burwood) | 2027-02-11 | 10:00 | 11:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 185 Church Parade, Burwood VIC | Clients/Banksia Insurance Brokers/Main office - Burwood | Window clean. Checklist: Clients/Banksia Insurance Brokers/Main office - Burwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Banksia Insurance Brokers/Main office - Burwood/02 Site Access (office will share). | No | 0
J1112 | Pilot | CL09 Ines A. roster | Kitchen and bathrooms - Sunbury Lawyers Pty Ltd (Reservoir) | 2026-12-08 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=TU | 115 Nepean Parade, Reservoir VIC | Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir | Kitchen and bathrooms. Checklist: Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1113 | Wave 1 North | CL29 Ines F. roster | Office clean - Sunbury Lawyers Pty Ltd (Essendon) | 2027-01-11 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,WE | 96A Glenferrie Parade, Essendon VIC | Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon | Office clean. Checklist: Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Sign in at security desk. Access details: Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/02 Site Access (office will share). | No | 0
J1114 | Wave 1 North | CL56 Pita L. roster | Washroom service - Sunbury Lawyers Pty Ltd (Essendon) | 2027-02-04 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TH | 96A Glenferrie Parade, Essendon VIC | Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon | Washroom service. Checklist: Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Sign in at security desk. Access details: Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/02 Site Access (office will share). | No | 0
J1115 | Wave 3 South | CL15 Omar A. roster | Kitchen and bathrooms - Sunbury Lawyers Pty Ltd (Mentone) | 2027-01-27 | 20:30 | 21:30 | FREQ=WEEKLY;BYDAY=WE | 158 Station Street, Mentone VIC | Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone | Kitchen and bathrooms. Checklist: Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/02 Site Access (office will share). | Yes | 0
J1116 | Wave 3 South | CL11 Kavya A. roster | Office clean - Cobblestone Real Estate Pty Ltd (Frankston) | 2027-01-27 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=WE | 476 Sydney Highway, Frankston VIC | Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston | Office clean. Checklist: Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/02 Site Access (office will share). | No | 0
J1117 | Wave 4 West | CL40 Tara F. roster | Office clean - Bayview Engineering Pty Ltd (Sunshine) | 2027-02-04 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TH,FR | 436/12 Nepean Highway, Sunshine VIC | Clients/Bayview Engineering Pty Ltd/Main office - Sunshine | Office clean. Checklist: Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/02 Site Access (office will share). | No | 0
J1118 | Wave 3 South | CL19 Sione A. roster | Office clean - Oakwood Financial Planning Pty Ltd (Brighton) | 2027-01-29 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=FR | 394 Ballarat Avenue, Brighton VIC | Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton | Office clean. Checklist: Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/02 Site Access (office will share). | No | 0
J1119 | Wave 3 South | CL59 Sione L. roster | Carpet steam clean - Oakwood Financial Planning Pty Ltd (Brighton) | 2027-02-16 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 394 Ballarat Avenue, Brighton VIC | Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton | Carpet steam clean. Checklist: Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/02 Site Access (office will share). | No | 0
J1120 | Wave 3 South | CL47 Grace L. roster | Office clean - Brightside Dental Pty Ltd (Dandenong) | 2027-01-25 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO | 135 Victoria Parade, Dandenong VIC | Clients/Brightside Dental Pty Ltd/Main office - Dandenong | Office clean. Checklist: Clients/Brightside Dental Pty Ltd/Main office - Dandenong/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Brightside Dental Pty Ltd/Main office - Dandenong/02 Site Access (office will share). | No | 0
J1121 | Wave 3 South | CL51 Kavya L. roster | Kitchen and bathrooms - Brightside Dental Pty Ltd (Moorabbin) | 2027-01-27 | 07:00 | 07:30 | FREQ=WEEKLY;BYDAY=WE | 472 Barkly Parade, Moorabbin VIC | Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin | Kitchen and bathrooms. Checklist: Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1122 | Wave 4 West | CL12 Luis A. roster | Kitchen and bathrooms - Ashwood Physiotherapy (Point Cook) | 2027-02-01 | 07:00 | 07:30 | FREQ=WEEKLY;BYDAY=MO,WE,FR | 151 Nicholson Street, Point Cook VIC | Clients/Ashwood Physiotherapy/Main office - Point Cook | Kitchen and bathrooms. Checklist: Clients/Ashwood Physiotherapy/Main office - Point Cook/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Physiotherapy/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1123 | Wave 4 West | CL59 Sione L. roster | Window clean - Ashwood Physiotherapy (Point Cook) | 2027-02-09 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 151 Nicholson Street, Point Cook VIC | Clients/Ashwood Physiotherapy/Main office - Point Cook | Window clean. Checklist: Clients/Ashwood Physiotherapy/Main office - Point Cook/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Physiotherapy/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1124 | Wave 2 East | CL26 Farid F. roster | Office clean - Ashwood Physiotherapy (Camberwell) | 2027-01-21 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TH | 4A Gilbert Road, Camberwell VIC | Clients/Ashwood Physiotherapy/Clinic - Camberwell | Office clean. Checklist: Clients/Ashwood Physiotherapy/Clinic - Camberwell/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Physiotherapy/Clinic - Camberwell/02 Site Access (office will share). | No | 0
J1125 | Wave 1 North | CL21 Ana F. roster | Office clean - Ashwood Physiotherapy (Coburg) | 2027-01-12 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=TU,FR | 144 Burke Avenue, Coburg VIC | Clients/Ashwood Physiotherapy/Warehouse - Coburg | Office clean. Checklist: Clients/Ashwood Physiotherapy/Warehouse - Coburg/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Ashwood Physiotherapy/Warehouse - Coburg/02 Site Access (office will share). | No | 0
J1126 | Wave 1 North | CL55 Omar L. roster | Window clean - Ashwood Physiotherapy (Coburg) | 2027-01-18 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 144 Burke Avenue, Coburg VIC | Clients/Ashwood Physiotherapy/Warehouse - Coburg | Window clean. Checklist: Clients/Ashwood Physiotherapy/Warehouse - Coburg/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Ashwood Physiotherapy/Warehouse - Coburg/02 Site Access (office will share). | No | 0
J1127 | Wave 4 West | CL36 Pita F. roster | Office clean - Ashwood Physiotherapy (Footscray) | 2027-02-01 | 17:30 | 20:00 | FREQ=WEEKLY;BYDAY=MO,FR | 182 King Avenue, Footscray VIC | Clients/Ashwood Physiotherapy/Showroom - Footscray | Office clean. Checklist: Clients/Ashwood Physiotherapy/Showroom - Footscray/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Ashwood Physiotherapy/Showroom - Footscray/02 Site Access (office will share). | No | 0
J1128 | Wave 2 East | CL14 Nikos A. roster | Kitchen and bathrooms - Bluestone Dental (Camberwell) | 2027-01-18 | 07:00 | 07:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 79/12 Glenferrie Parade, Camberwell VIC | Clients/Bluestone Dental/Main office - Camberwell | Kitchen and bathrooms. Checklist: Clients/Bluestone Dental/Main office - Camberwell/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Bluestone Dental/Main office - Camberwell/02 Site Access (office will share). | Yes | 0
J1129 | Wave 2 East | CL34 Nikos F. roster | Office clean - Bluestone Dental (Burwood) | 2027-01-19 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU | 401 Park Highway, Burwood VIC | Clients/Bluestone Dental/Clinic - Burwood | Office clean. Checklist: Clients/Bluestone Dental/Clinic - Burwood/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Bluestone Dental/Clinic - Burwood/02 Site Access (office will share). | No | 0
J1130 | Wave 2 East | CL56 Pita L. roster | Carpet steam clean - Bluestone Dental (Burwood) | 2027-01-18 | 11:00 | 14:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 401 Park Highway, Burwood VIC | Clients/Bluestone Dental/Clinic - Burwood | Carpet steam clean. Checklist: Clients/Bluestone Dental/Clinic - Burwood/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Bluestone Dental/Clinic - Burwood/02 Site Access (office will share). | No | 0
J1131 | Wave 2 East | CL10 Jun A. roster | Office clean - Bluestone Dental (Burwood) | 2027-01-19 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=TU,WE | 401 Burke Street, Burwood VIC | Clients/Bluestone Dental/Warehouse - Burwood | Office clean. Checklist: Clients/Bluestone Dental/Warehouse - Burwood/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Bluestone Dental/Warehouse - Burwood/02 Site Access (office will share). | No | 0
J1132 | Wave 2 East | CL18 Rosa A. roster | Office clean - Bluestone Dental (Ringwood) | 2027-01-18 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,FR | 11 Hopkins Avenue, Ringwood VIC | Clients/Bluestone Dental/Showroom - Ringwood | Office clean. Checklist: Clients/Bluestone Dental/Showroom - Ringwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Bluestone Dental/Showroom - Ringwood/02 Site Access (office will share). | No | 0
J1133 | Wave 2 East | CL55 Omar L. roster | Carpet steam clean - Bluestone Dental (Ringwood) | 2027-02-12 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 11 Hopkins Avenue, Ringwood VIC | Clients/Bluestone Dental/Showroom - Ringwood | Carpet steam clean. Checklist: Clients/Bluestone Dental/Showroom - Ringwood/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Bluestone Dental/Showroom - Ringwood/02 Site Access (office will share). | No | 0
J1134 | Wave 4 West | CL44 Dinh L. roster | Office clean - Kingsley Accountants (Altona) | 2027-02-04 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TH | 263 Nepean Highway, Altona VIC | Clients/Kingsley Accountants/Main office - Altona | Office clean. Checklist: Clients/Kingsley Accountants/Main office - Altona/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Kingsley Accountants/Main office - Altona/02 Site Access (office will share). | No | 0
J1135 | Pilot | CL09 Ines A. roster | Office clean - Clearwater Early Learning Pty Ltd (Northcote) | 2026-12-07 | 17:30 | 20:00 | FREQ=WEEKLY;BYDAY=MO,TU | 288 Main Highway, Northcote VIC | Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote | Office clean. Checklist: Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/01 Scope & Checklist. Notes: -. Access details: Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/02 Site Access (office will share). | No | 0
J1136 | Wave 1 North | CL56 Pita L. roster | Window clean - Clearwater Early Learning Pty Ltd (Northcote) | 2027-02-01 | 11:00 | 13:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 288 Main Highway, Northcote VIC | Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote | Window clean. Checklist: Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/01 Scope & Checklist. Notes: -. Access details: Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/02 Site Access (office will share). | No | 0
J1137 | Wave 4 West | CL20 Tara A. roster | Office clean - Banksia Pathology Pty Ltd (Deer Park) | 2027-02-02 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TU | 459 Park Avenue, Deer Park VIC | Clients/Banksia Pathology Pty Ltd/Main office - Deer Park | Office clean. Checklist: Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/02 Site Access (office will share). | No | 0
J1138 | Wave 2 East | CL30 Jun F. roster | Office clean - Southgate Financial Planning Pty Ltd (Blackburn) | 2027-01-18 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO | 464 Barkly Road, Blackburn VIC | Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn | Office clean. Checklist: Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Bins out on Tuesday night. Access details: Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/02 Site Access (office will share). | No | 0
J1139 | Wave 3 South | CL51 Kavya L. roster | Office clean - Southgate Financial Planning Pty Ltd (Bentleigh) | 2027-01-26 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TU,TH | 90A Albert Parade, Bentleigh VIC | Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh | Office clean. Checklist: Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/02 Site Access (office will share). | No | 0
J1140 | Wave 2 East | CL06 Farid A. roster | Office clean - Bluestone Lawyers Pty Ltd (Burwood) | 2027-01-19 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=TU,WE | 29 Burke Parade, Burwood VIC | Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood | Office clean. Checklist: Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/01 Scope & Checklist. Notes: -. Access details: Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/02 Site Access (office will share). | No | 0
J1141 | Wave 2 East | CL50 Jun L. roster | Office clean - Riverside Lawyers Pty Ltd (Glen Waverley) | 2027-01-21 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TH | 23 Station Parade, Glen Waverley VIC | Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley | Office clean. Checklist: Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1142 | Wave 2 East | CL53 Maya L. roster | Washroom service - Riverside Lawyers Pty Ltd (Glen Waverley) | 2027-02-05 | 10:00 | 10:30 | FREQ=MONTHLY;BYDAY=1FR | 23 Station Parade, Glen Waverley VIC | Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley | Washroom service. Checklist: Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1143 | Wave 4 West | CL04 Dinh A. roster | Office clean - Banksia Accountants (Altona) | 2027-02-02 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TU,WE | 251 Union Avenue, Altona VIC | Clients/Banksia Accountants/Main office - Altona | Office clean. Checklist: Clients/Banksia Accountants/Main office - Altona/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Banksia Accountants/Main office - Altona/02 Site Access (office will share). | No | 0
J1144 | Wave 2 East | CL26 Farid F. roster | Office clean - Banksia Accountants (Doncaster) | 2027-01-20 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=WE | 270 Station Road, Doncaster VIC | Clients/Banksia Accountants/Clinic - Doncaster | Office clean. Checklist: Clients/Banksia Accountants/Clinic - Doncaster/01 Scope & Checklist. Notes: -. Access details: Clients/Banksia Accountants/Clinic - Doncaster/02 Site Access (office will share). | No | 0
J1145 | Wave 2 East | CL56 Pita L. roster | Window clean - Banksia Accountants (Doncaster) | 2027-02-08 | 10:00 | 11:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 270 Station Road, Doncaster VIC | Clients/Banksia Accountants/Clinic - Doncaster | Window clean. Checklist: Clients/Banksia Accountants/Clinic - Doncaster/01 Scope & Checklist. Notes: -. Access details: Clients/Banksia Accountants/Clinic - Doncaster/02 Site Access (office will share). | No | 0
J1146 | Wave 2 East | CL46 Farid L. roster | Kitchen and bathrooms - Banksia Accountants (Glen Waverley) | 2027-01-18 | 17:30 | 18:00 | FREQ=WEEKLY;BYDAY=MO,WE | 463 Gilbert Street, Glen Waverley VIC | Clients/Banksia Accountants/Warehouse - Glen Waverley | Kitchen and bathrooms. Checklist: Clients/Banksia Accountants/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: -. Access details: Clients/Banksia Accountants/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1147 | Wave 4 West | CL28 Hamid F. roster | Office clean - Ironbark Physiotherapy Pty Ltd (Point Cook) | 2027-02-02 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=TU,TH,FR | 59 King Highway, Point Cook VIC | Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook | Office clean. Checklist: Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1148 | Wave 4 West | CL24 Dinh F. roster | Office clean - Ironbark Physiotherapy Pty Ltd (Point Cook) | 2027-02-05 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=FR | 61 Church Street, Point Cook VIC | Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook | Office clean. Checklist: Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1149 | Wave 4 West | CL53 Maya L. roster | Window clean - Ironbark Physiotherapy Pty Ltd (Point Cook) | 2027-02-09 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 61 Church Street, Point Cook VIC | Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook | Window clean. Checklist: Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/02 Site Access (office will share). | No | 0
J1150 | Wave 4 West | CL44 Dinh L. roster | Kitchen and bathrooms - Wattle Grove Lawyers Pty Ltd (Point Cook) | 2027-02-01 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TU,TH | 280 Railway Road, Point Cook VIC | Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook | Kitchen and bathrooms. Checklist: Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1151 | Wave 4 West | CL57 Quynh L. roster | Window clean - Wattle Grove Lawyers Pty Ltd (Point Cook) | 2027-02-19 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 280 Railway Road, Point Cook VIC | Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook | Window clean. Checklist: Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1152 | Wave 4 West | CL12 Luis A. roster | Office clean - Kingsley Medical Centre Pty Ltd (Point Cook) | 2027-02-03 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=WE,TH | 149 Main Road, Point Cook VIC | Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook | Office clean. Checklist: Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Level 3, lift to the left. Access details: Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1153 | Wave 4 West | CL57 Quynh L. roster | Washroom service - Kingsley Medical Centre Pty Ltd (Point Cook) | 2027-02-01 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1MO | 149 Main Road, Point Cook VIC | Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook | Washroom service. Checklist: Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Level 3, lift to the left. Access details: Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1154 | Wave 2 East | CL50 Jun L. roster | Office clean - Kingsley Medical Centre Pty Ltd (Hawthorn) | 2027-01-19 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=TU | 313 King Road, Hawthorn VIC | Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn | Office clean. Checklist: Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Vacuum bags in cupboard 2. Access details: Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/02 Site Access (office will share). | No | 0
J1155 | Wave 2 East | CL14 Nikos A. roster | Office clean - Ashwood Engineering (Glen Waverley) | 2027-01-22 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=FR | 155 Hopkins Road, Glen Waverley VIC | Clients/Ashwood Engineering/Main office - Glen Waverley | Office clean. Checklist: Clients/Ashwood Engineering/Main office - Glen Waverley/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Engineering/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1156 | Wave 4 West | CL24 Dinh F. roster | Office clean - Sunbury Physiotherapy Pty Ltd (Point Cook) | 2027-02-01 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=MO,TH | 284 Park Parade, Point Cook VIC | Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook | Office clean. Checklist: Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Reception closes 5:30 pm, use the side entry. Access details: Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1157 | Wave 3 South | CL03 Carmen A. roster | Office clean - Sunbury Physiotherapy Pty Ltd (Frankston) | 2027-01-25 | 20:00 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,TH | 85 Nepean Road, Frankston VIC | Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston | Office clean. Checklist: Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Store room on level 1, room 104. Access details: Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/02 Site Access (office will share). | No | 0
J1158 | Wave 2 East | CL14 Nikos A. roster | Office clean - Sunbury Physiotherapy Pty Ltd (Hawthorn) | 2027-01-18 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 231 Church Highway, Hawthorn VIC | Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn | Office clean. Checklist: Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Park in bay 12 under the building. Access details: Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/02 Site Access (office will share). | Yes | 0
J1159 | Wave 4 West | CL20 Tara A. roster | Kitchen and bathrooms - Eastwood Pathology (Werribee) | 2027-02-03 | 07:30 | 08:00 | FREQ=WEEKLY;BYDAY=WE,TH | 223A Nicholson Parade, Werribee VIC | Clients/Eastwood Pathology/Main office - Werribee | Kitchen and bathrooms. Checklist: Clients/Eastwood Pathology/Main office - Werribee/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Eastwood Pathology/Main office - Werribee/02 Site Access (office will share). | No | 0
J1160 | Wave 4 West | CL58 Rosa L. roster | Washroom service - Eastwood Pathology (Werribee) | 2027-02-03 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1WE | 223A Nicholson Parade, Werribee VIC | Clients/Eastwood Pathology/Main office - Werribee | Washroom service. Checklist: Clients/Eastwood Pathology/Main office - Werribee/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Eastwood Pathology/Main office - Werribee/02 Site Access (office will share). | No | 0
J1161 | Wave 4 West | CL32 Luis F. roster | Office clean - Waverley Fitness Pty Ltd (Footscray) | 2027-02-02 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=TU | 382 Hopkins Street, Footscray VIC | Clients/Waverley Fitness Pty Ltd/Main office - Footscray | Office clean. Checklist: Clients/Waverley Fitness Pty Ltd/Main office - Footscray/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Waverley Fitness Pty Ltd/Main office - Footscray/02 Site Access (office will share). | No | 0
J1162 | Wave 4 West | CL44 Dinh L. roster | Office clean - Waverley Fitness Pty Ltd (Footscray) | 2027-02-03 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=WE | 443 Station Road, Footscray VIC | Clients/Waverley Fitness Pty Ltd/Clinic - Footscray | Office clean. Checklist: Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/01 Scope & Checklist. Notes: -. Access details: Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/02 Site Access (office will share). | Yes | 0
J1163 | Wave 1 North | CL13 Maya A. roster | Office clean - Clearwater Logistics (Reservoir) | 2027-01-11 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 127 Main Highway, Reservoir VIC | Clients/Clearwater Logistics/Main office - Reservoir | Office clean. Checklist: Clients/Clearwater Logistics/Main office - Reservoir/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Level 3, lift to the left. Access details: Clients/Clearwater Logistics/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1164 | Wave 1 North | CL60 Tara L. roster | Carpet steam clean - Clearwater Logistics (Reservoir) | 2027-02-03 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 127 Main Highway, Reservoir VIC | Clients/Clearwater Logistics/Main office - Reservoir | Carpet steam clean. Checklist: Clients/Clearwater Logistics/Main office - Reservoir/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Level 3, lift to the left. Access details: Clients/Clearwater Logistics/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1165 | Wave 1 North | CL49 Ines L. roster | Kitchen and bathrooms - Wattle Grove Fitness (Essendon) | 2027-01-11 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO,WE | 68 Church Parade, Essendon VIC | Clients/Wattle Grove Fitness/Main office - Essendon | Kitchen and bathrooms. Checklist: Clients/Wattle Grove Fitness/Main office - Essendon/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Sign in at security desk. Access details: Clients/Wattle Grove Fitness/Main office - Essendon/02 Site Access (office will share). | No | 0
J1166 | Wave 3 South | CL27 Grace F. roster | Office clean - Wattle Grove Fitness (St Kilda) | 2027-01-25 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO,FR | 102 Union Road, St Kilda VIC | Clients/Wattle Grove Fitness/Clinic - St Kilda | Office clean. Checklist: Clients/Wattle Grove Fitness/Clinic - St Kilda/01 Scope & Checklist. Notes: -. Access details: Clients/Wattle Grove Fitness/Clinic - St Kilda/02 Site Access (office will share). | No | 0
J1167 | Wave 1 North | CL37 Quynh F. roster | Kitchen and bathrooms - Ashwood Medical Centre (Bundoora) | 2027-01-11 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 61 Church Road, Bundoora VIC | Clients/Ashwood Medical Centre/Main office - Bundoora | Kitchen and bathrooms. Checklist: Clients/Ashwood Medical Centre/Main office - Bundoora/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Medical Centre/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1168 | Wave 1 North | CL60 Tara L. roster | Window clean - Ashwood Medical Centre (Bundoora) | 2027-01-26 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 61 Church Road, Bundoora VIC | Clients/Ashwood Medical Centre/Main office - Bundoora | Window clean. Checklist: Clients/Ashwood Medical Centre/Main office - Bundoora/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Medical Centre/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1169 | Wave 4 West | CL40 Tara F. roster | Office clean - Parkside Vet Clinic (Deer Park) | 2027-02-02 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=TU,WE | 287 Whitehorse Highway, Deer Park VIC | Clients/Parkside Vet Clinic/Main office - Deer Park | Office clean. Checklist: Clients/Parkside Vet Clinic/Main office - Deer Park/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Parkside Vet Clinic/Main office - Deer Park/02 Site Access (office will share). | No | 0
J1170 | Wave 3 South | CL39 Sione F. roster | Kitchen and bathrooms - Wattle Grove Architects (Bentleigh) | 2027-01-29 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=FR | 289 Nepean Street, Bentleigh VIC | Clients/Wattle Grove Architects/Main office - Bentleigh | Kitchen and bathrooms. Checklist: Clients/Wattle Grove Architects/Main office - Bentleigh/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Wattle Grove Architects/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1171 | Wave 4 West | CL12 Luis A. roster | Office clean - Bayview Pharmacy Pty Ltd (Footscray) | 2027-02-01 | 21:30 | 23:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 221 Plenty Avenue, Footscray VIC | Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray | Office clean. Checklist: Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/02 Site Access (office will share). | Yes | 0
J1172 | Wave 2 East | CL14 Nikos A. roster | Kitchen and bathrooms - Hillcrest Accountants (Mitcham) | 2027-01-18 | 20:30 | 21:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 77 Mason Highway, Mitcham VIC | Clients/Hillcrest Accountants/Main office - Mitcham | Kitchen and bathrooms. Checklist: Clients/Hillcrest Accountants/Main office - Mitcham/01 Scope & Checklist. Notes: -. Access details: Clients/Hillcrest Accountants/Main office - Mitcham/02 Site Access (office will share). | Yes | 0
J1173 | Wave 2 East | CL57 Quynh L. roster | Carpet steam clean - Hillcrest Accountants (Mitcham) | 2027-02-09 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 77 Mason Highway, Mitcham VIC | Clients/Hillcrest Accountants/Main office - Mitcham | Carpet steam clean. Checklist: Clients/Hillcrest Accountants/Main office - Mitcham/01 Scope & Checklist. Notes: -. Access details: Clients/Hillcrest Accountants/Main office - Mitcham/02 Site Access (office will share). | No | 0
J1174 | Wave 1 North | CL45 Eleni L. roster | Office clean - Lakeside Architects (Reservoir) | 2027-01-11 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TH | 170 Railway Highway, Reservoir VIC | Clients/Lakeside Architects/Main office - Reservoir | Office clean. Checklist: Clients/Lakeside Architects/Main office - Reservoir/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Lakeside Architects/Main office - Reservoir/02 Site Access (office will share). | No | 0
J1175 | Wave 2 East | CL46 Farid L. roster | Office clean - Lakeside Architects (Mitcham) | 2027-01-22 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=FR | 208 Glenferrie Road, Mitcham VIC | Clients/Lakeside Architects/Clinic - Mitcham | Office clean. Checklist: Clients/Lakeside Architects/Clinic - Mitcham/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Lakeside Architects/Clinic - Mitcham/02 Site Access (office will share). | No | 0
J1176 | Wave 4 West | CL16 Pita A. roster | Office clean - Ashwood Accountants (Yarraville) | 2027-02-05 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=FR | 212 Sydney Avenue, Yarraville VIC | Clients/Ashwood Accountants/Main office - Yarraville | Office clean. Checklist: Clients/Ashwood Accountants/Main office - Yarraville/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Ashwood Accountants/Main office - Yarraville/02 Site Access (office will share). | No | 0
J1177 | Wave 1 North | CL13 Maya A. roster | Kitchen and bathrooms - Westend Property Group (Heidelberg) | 2027-01-12 | 08:00 | 08:30 | FREQ=WEEKLY;BYDAY=TU,FR | 268 Sydney Road, Heidelberg VIC | Clients/Westend Property Group/Main office - Heidelberg | Kitchen and bathrooms. Checklist: Clients/Westend Property Group/Main office - Heidelberg/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Westend Property Group/Main office - Heidelberg/02 Site Access (office will share). | No | 0
J1178 | Wave 1 North | CL60 Tara L. roster | Carpet steam clean - Westend Property Group (Heidelberg) | 2027-02-05 | 12:30 | 14:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 268 Sydney Road, Heidelberg VIC | Clients/Westend Property Group/Main office - Heidelberg | Carpet steam clean. Checklist: Clients/Westend Property Group/Main office - Heidelberg/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Westend Property Group/Main office - Heidelberg/02 Site Access (office will share). | No | 0
J1179 | Wave 2 East | CL38 Rosa F. roster | Office clean - Eastwood Optometrists (Burwood) | 2027-01-20 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=WE | 369 Station Road, Burwood VIC | Clients/Eastwood Optometrists/Main office - Burwood | Office clean. Checklist: Clients/Eastwood Optometrists/Main office - Burwood/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Eastwood Optometrists/Main office - Burwood/02 Site Access (office will share). | No | 0
J1180 | Wave 2 East | CL06 Farid A. roster | Kitchen and bathrooms - Eastwood Optometrists (Mitcham) | 2027-01-18 | 19:00 | 20:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 264 Queen Parade, Mitcham VIC | Clients/Eastwood Optometrists/Clinic - Mitcham | Kitchen and bathrooms. Checklist: Clients/Eastwood Optometrists/Clinic - Mitcham/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Eastwood Optometrists/Clinic - Mitcham/02 Site Access (office will share). | No | 0
J1181 | Wave 4 West | CL28 Hamid F. roster | Office clean - Westend Medical Centre (Sunshine) | 2027-02-03 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=WE,FR | 130 Barkly Road, Sunshine VIC | Clients/Westend Medical Centre/Main office - Sunshine | Office clean. Checklist: Clients/Westend Medical Centre/Main office - Sunshine/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Westend Medical Centre/Main office - Sunshine/02 Site Access (office will share). | No | 0
J1182 | Wave 3 South | CL39 Sione F. roster | Office clean - Riverside Learning Centre (Mentone) | 2027-01-26 | 20:00 | 22:30 | FREQ=WEEKLY;BYDAY=TU | 180 Union Avenue, Mentone VIC | Clients/Riverside Learning Centre/Main office - Mentone | Office clean. Checklist: Clients/Riverside Learning Centre/Main office - Mentone/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Riverside Learning Centre/Main office - Mentone/02 Site Access (office will share). | No | 0
J1183 | Wave 3 South | CL35 Omar F. roster | Office clean - Riverside Learning Centre (Cheltenham) | 2027-01-27 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=WE,TH | 148 Plenty Street, Cheltenham VIC | Clients/Riverside Learning Centre/Clinic - Cheltenham | Office clean. Checklist: Clients/Riverside Learning Centre/Clinic - Cheltenham/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Riverside Learning Centre/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1184 | Wave 3 South | CL47 Grace L. roster | Office clean - Riverside Learning Centre (Moorabbin) | 2027-01-25 | 20:00 | 22:30 | FREQ=WEEKLY;BYDAY=MO,FR | 4A Main Highway, Moorabbin VIC | Clients/Riverside Learning Centre/Warehouse - Moorabbin | Office clean. Checklist: Clients/Riverside Learning Centre/Warehouse - Moorabbin/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Learning Centre/Warehouse - Moorabbin/02 Site Access (office will share). | No | 0
J1185 | Wave 3 South | CL60 Tara L. roster | Window clean - Riverside Learning Centre (Moorabbin) | 2027-01-29 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 4A Main Highway, Moorabbin VIC | Clients/Riverside Learning Centre/Warehouse - Moorabbin | Window clean. Checklist: Clients/Riverside Learning Centre/Warehouse - Moorabbin/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Learning Centre/Warehouse - Moorabbin/02 Site Access (office will share). | No | 0
J1186 | Wave 3 South | CL03 Carmen A. roster | Office clean - Silverton Insurance Brokers Pty Ltd (Cheltenham) | 2027-01-28 | 18:00 | 20:00 | FREQ=WEEKLY;BYDAY=TH | 165 Hopkins Road, Cheltenham VIC | Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham | Office clean. Checklist: Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Sign in at security desk. Access details: Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/02 Site Access (office will share). | Yes | 0
J1187 | Wave 3 South | CL11 Kavya A. roster | Office clean - Silverton Insurance Brokers Pty Ltd (Frankston) | 2027-01-27 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=WE,TH | 245 Victoria Road, Frankston VIC | Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston | Office clean. Checklist: Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/01 Scope & Checklist. Notes: -. Access details: Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/02 Site Access (office will share). | No | 0
J1188 | Wave 2 East | CL30 Jun F. roster | Office clean - Silverton Insurance Brokers Pty Ltd (Glen Waverley) | 2027-01-18 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,WE | 274 Gilbert Avenue, Glen Waverley VIC | Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley | Office clean. Checklist: Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1189 | Wave 2 East | CL60 Tara L. roster | Washroom service - Silverton Insurance Brokers Pty Ltd (Glen Waverley) | 2027-02-01 | 10:00 | 10:30 | FREQ=MONTHLY;BYDAY=1MO | 274 Gilbert Avenue, Glen Waverley VIC | Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley | Washroom service. Checklist: Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1190 | Wave 2 East | CL42 Bilal L. roster | Kitchen and bathrooms - Greenway Podiatry Pty Ltd (Burwood) | 2027-01-20 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=WE | 198 Station Avenue, Burwood VIC | Clients/Greenway Podiatry Pty Ltd/Main office - Burwood | Kitchen and bathrooms. Checklist: Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]. Access details: Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/02 Site Access (office will share). | No | 0
J1191 | Wave 1 North | CL25 Eleni F. roster | Office clean - Banksia Logistics (Northcote) | 2027-01-12 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=TU | 387 Burke Parade, Northcote VIC | Clients/Banksia Logistics/Main office - Northcote | Office clean. Checklist: Clients/Banksia Logistics/Main office - Northcote/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Banksia Logistics/Main office - Northcote/02 Site Access (office will share). | No | 0
J1192 | Wave 1 North | CL37 Quynh F. roster | Office clean - Banksia Logistics (Northcote) | 2027-01-13 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=WE | 467 High Avenue, Northcote VIC | Clients/Banksia Logistics/Clinic - Northcote | Office clean. Checklist: Clients/Banksia Logistics/Clinic - Northcote/01 Scope & Checklist. Notes: -. Access details: Clients/Banksia Logistics/Clinic - Northcote/02 Site Access (office will share). | No | 0
J1193 | Wave 1 North | CL13 Maya A. roster | Office clean - Banksia Logistics (Thornbury) | 2027-01-14 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=TH | 458 Glenferrie Parade, Thornbury VIC | Clients/Banksia Logistics/Warehouse - Thornbury | Office clean. Checklist: Clients/Banksia Logistics/Warehouse - Thornbury/01 Scope & Checklist. Notes: -. Access details: Clients/Banksia Logistics/Warehouse - Thornbury/02 Site Access (office will share). | No | 0
J1194 | Wave 1 North | CL49 Ines L. roster | Kitchen and bathrooms - Sunbury Architects Pty Ltd (Epping) | 2027-01-11 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 111A Plenty Street, Epping VIC | Clients/Sunbury Architects Pty Ltd/Main office - Epping | Kitchen and bathrooms. Checklist: Clients/Sunbury Architects Pty Ltd/Main office - Epping/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Sunbury Architects Pty Ltd/Main office - Epping/02 Site Access (office will share). | No | 0
J1195 | Wave 1 North | CL01 Ana A. roster | Kitchen and bathrooms - Cobblestone Physiotherapy Pty Ltd (Bundoora) | 2027-01-15 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=FR | 12 Sydney Road, Bundoora VIC | Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora | Kitchen and bathrooms. Checklist: Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]. Access details: Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1196 | Wave 4 West | CL20 Tara A. roster | Office clean - Banksia Real Estate (Maribyrnong) | 2027-02-01 | 20:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU | 272 Gilbert Street, Maribyrnong VIC | Clients/Banksia Real Estate/Main office - Maribyrnong | Office clean. Checklist: Clients/Banksia Real Estate/Main office - Maribyrnong/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Banksia Real Estate/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1197 | Wave 4 West | CL60 Tara L. roster | Window clean - Banksia Real Estate (Maribyrnong) | 2027-02-03 | 11:30 | 14:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 272 Gilbert Street, Maribyrnong VIC | Clients/Banksia Real Estate/Main office - Maribyrnong | Window clean. Checklist: Clients/Banksia Real Estate/Main office - Maribyrnong/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Banksia Real Estate/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1198 | Wave 2 East | CL42 Bilal L. roster | Office clean - Northside Pathology Pty Ltd (Ringwood) | 2027-01-18 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=MO | 416 Park Road, Ringwood VIC | Clients/Northside Pathology Pty Ltd/Main office - Ringwood | Office clean. Checklist: Clients/Northside Pathology Pty Ltd/Main office - Ringwood/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Northside Pathology Pty Ltd/Main office - Ringwood/02 Site Access (office will share). | No | 0
J1199 | Wave 2 East | CL02 Bilal A. roster | Kitchen and bathrooms - Harbourside Lawyers (Glen Waverley) | 2027-01-21 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=TH,FR | 1 Mason Parade, Glen Waverley VIC | Clients/Harbourside Lawyers/Main office - Glen Waverley | Kitchen and bathrooms. Checklist: Clients/Harbourside Lawyers/Main office - Glen Waverley/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Harbourside Lawyers/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1200 | Wave 4 West | CL20 Tara A. roster | Kitchen and bathrooms - Kingsley Fitness Pty Ltd (Werribee) | 2027-02-05 | 07:30 | 08:30 | FREQ=WEEKLY;BYDAY=FR | 460 Sydney Highway, Werribee VIC | Clients/Kingsley Fitness Pty Ltd/Main office - Werribee | Kitchen and bathrooms. Checklist: Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/02 Site Access (office will share). | Yes | 0
J1201 | Wave 4 West | CL32 Luis F. roster | Office clean - Lakeside Optometrists (Footscray) | 2027-02-04 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TH | 35 Nepean Avenue, Footscray VIC | Clients/Lakeside Optometrists/Main office - Footscray | Office clean. Checklist: Clients/Lakeside Optometrists/Main office - Footscray/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Lakeside Optometrists/Main office - Footscray/02 Site Access (office will share). | No | 0
J1202 | Wave 4 West | CL59 Sione L. roster | Carpet steam clean - Lakeside Optometrists (Footscray) | 2027-02-11 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 35 Nepean Avenue, Footscray VIC | Clients/Lakeside Optometrists/Main office - Footscray | Carpet steam clean. Checklist: Clients/Lakeside Optometrists/Main office - Footscray/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Lakeside Optometrists/Main office - Footscray/02 Site Access (office will share). | No | 0
J1203 | Wave 2 East | CL50 Jun L. roster | Office clean - Southgate Dental (Hawthorn) | 2027-01-18 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,WE,TH | 271 Victoria Avenue, Hawthorn VIC | Clients/Southgate Dental/Main office - Hawthorn | Office clean. Checklist: Clients/Southgate Dental/Main office - Hawthorn/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]. Access details: Clients/Southgate Dental/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1204 | Wave 4 West | CL48 Hamid L. roster | Office clean - Sunbury Optometrists (Altona) | 2027-02-01 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 375 Railway Road, Altona VIC | Clients/Sunbury Optometrists/Main office - Altona | Office clean. Checklist: Clients/Sunbury Optometrists/Main office - Altona/01 Scope & Checklist. Notes: -. Access details: Clients/Sunbury Optometrists/Main office - Altona/02 Site Access (office will share). | No | 0
J1205 | Wave 1 North | CL29 Ines F. roster | Office clean - Bayview Vet Clinic (Coburg) | 2027-01-13 | 19:30 | 21:00 | FREQ=WEEKLY;BYDAY=WE,TH,FR | 186 Sydney Avenue, Coburg VIC | Clients/Bayview Vet Clinic/Main office - Coburg | Office clean. Checklist: Clients/Bayview Vet Clinic/Main office - Coburg/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Vacuum bags in cupboard 2. Access details: Clients/Bayview Vet Clinic/Main office - Coburg/02 Site Access (office will share). | No | 0
J1206 | Wave 1 North | CL56 Pita L. roster | Window clean - Bayview Vet Clinic (Coburg) | 2027-01-11 | 12:00 | 14:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 186 Sydney Avenue, Coburg VIC | Clients/Bayview Vet Clinic/Main office - Coburg | Window clean. Checklist: Clients/Bayview Vet Clinic/Main office - Coburg/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Vacuum bags in cupboard 2. Access details: Clients/Bayview Vet Clinic/Main office - Coburg/02 Site Access (office will share). | No | 0
J1207 | Wave 1 North | CL25 Eleni F. roster | Office clean - Bayview Vet Clinic (Reservoir) | 2027-01-12 | 19:30 | 21:00 | FREQ=WEEKLY;BYDAY=TU,FR | 399 Whitehorse Road, Reservoir VIC | Clients/Bayview Vet Clinic/Clinic - Reservoir | Office clean. Checklist: Clients/Bayview Vet Clinic/Clinic - Reservoir/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Bayview Vet Clinic/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1208 | Wave 1 North | CL58 Rosa L. roster | Window clean - Bayview Vet Clinic (Reservoir) | 2027-01-11 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 399 Whitehorse Road, Reservoir VIC | Clients/Bayview Vet Clinic/Clinic - Reservoir | Window clean. Checklist: Clients/Bayview Vet Clinic/Clinic - Reservoir/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Bayview Vet Clinic/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1209 | Wave 2 East | CL46 Farid L. roster | Office clean - Redgum Pathology Pty Ltd (Camberwell) | 2027-01-20 | 18:30 | 21:30 | FREQ=WEEKLY;BYDAY=WE | 453 Railway Parade, Camberwell VIC | Clients/Redgum Pathology Pty Ltd/Main office - Camberwell | Office clean. Checklist: Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Level 3, lift to the left. Access details: Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1210 | Wave 2 East | CL26 Farid F. roster | Office clean - Greenway Medical Centre Pty Ltd (Glen Waverley) | 2027-01-18 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO | 326 Main Highway, Glen Waverley VIC | Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley | Office clean. Checklist: Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: -. Access details: Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1211 | Wave 2 East | CL60 Tara L. roster | Carpet steam clean - Greenway Medical Centre Pty Ltd (Glen Waverley) | 2027-02-12 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 326 Main Highway, Glen Waverley VIC | Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley | Carpet steam clean. Checklist: Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist. Notes: -. Access details: Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1212 | Wave 2 East | CL14 Nikos A. roster | Office clean - Westend Physiotherapy (Glen Waverley) | 2027-01-18 | 20:00 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 306 Bridge Road, Glen Waverley VIC | Clients/Westend Physiotherapy/Main office - Glen Waverley | Office clean. Checklist: Clients/Westend Physiotherapy/Main office - Glen Waverley/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Westend Physiotherapy/Main office - Glen Waverley/02 Site Access (office will share). | Yes | 0
J1213 | Wave 4 West | CL04 Dinh A. roster | Office clean - Riverside Podiatry (Point Cook) | 2027-02-01 | 20:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,FR | 79 Ballarat Street, Point Cook VIC | Clients/Riverside Podiatry/Main office - Point Cook | Office clean. Checklist: Clients/Riverside Podiatry/Main office - Point Cook/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Podiatry/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1214 | Wave 3 South | CL19 Sione A. roster | Office clean - Riverside Podiatry (Brighton) | 2027-01-27 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=WE | 145 Church Avenue, Brighton VIC | Clients/Riverside Podiatry/Clinic - Brighton | Office clean. Checklist: Clients/Riverside Podiatry/Clinic - Brighton/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Riverside Podiatry/Clinic - Brighton/02 Site Access (office will share). | No | 0
J1215 | Wave 2 East | CL02 Bilal A. roster | Office clean - Northside Learning Centre (Camberwell) | 2027-01-18 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 190 Nicholson Avenue, Camberwell VIC | Clients/Northside Learning Centre/Main office - Camberwell | Office clean. Checklist: Clients/Northside Learning Centre/Main office - Camberwell/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Northside Learning Centre/Main office - Camberwell/02 Site Access (office will share). | No | 0
J1216 | Wave 2 East | CL38 Rosa F. roster | Office clean - Harbourside Logistics Pty Ltd (Hawthorn) | 2027-01-18 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE | 387 Barkly Highway, Hawthorn VIC | Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn | Office clean. Checklist: Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Vacuum bags in cupboard 2. Access details: Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1217 | Wave 2 East | CL18 Rosa A. roster | Office clean - Harbourside Logistics Pty Ltd (Kew) | 2027-01-19 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=TU,WE | 5 Park Highway, Kew VIC | Clients/Harbourside Logistics Pty Ltd/Clinic - Kew | Office clean. Checklist: Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Park in bay 12 under the building. Access details: Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/02 Site Access (office will share). | No | 0
J1218 | Wave 4 West | CL36 Pita F. roster | Office clean - Redgum Podiatry (Williamstown) | 2027-02-01 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=MO,TH | 204 Mason Parade, Williamstown VIC | Clients/Redgum Podiatry/Main office - Williamstown | Office clean. Checklist: Clients/Redgum Podiatry/Main office - Williamstown/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Redgum Podiatry/Main office - Williamstown/02 Site Access (office will share). | No | 0
J1219 | Wave 3 South | CL07 Grace A. roster | Office clean - Redgum Podiatry (Cheltenham) | 2027-01-25 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,TH | 445 Barkly Avenue, Cheltenham VIC | Clients/Redgum Podiatry/Clinic - Cheltenham | Office clean. Checklist: Clients/Redgum Podiatry/Clinic - Cheltenham/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Redgum Podiatry/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1220 | Wave 3 South | CL54 Nikos L. roster | Window clean - Redgum Podiatry (Cheltenham) | 2027-02-01 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 445 Barkly Avenue, Cheltenham VIC | Clients/Redgum Podiatry/Clinic - Cheltenham | Window clean. Checklist: Clients/Redgum Podiatry/Clinic - Cheltenham/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Redgum Podiatry/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1221 | Wave 3 South | CL35 Omar F. roster | Office clean - Harbourside Chiropractic (Oakleigh) | 2027-01-25 | 20:00 | 21:30 | FREQ=WEEKLY;BYDAY=MO,TU | 151 Glenferrie Highway, Oakleigh VIC | Clients/Harbourside Chiropractic/Main office - Oakleigh | Office clean. Checklist: Clients/Harbourside Chiropractic/Main office - Oakleigh/01 Scope & Checklist. Notes: -. Access details: Clients/Harbourside Chiropractic/Main office - Oakleigh/02 Site Access (office will share). | Yes | 0
J1222 | Wave 3 South | CL19 Sione A. roster | Office clean - Harbourside Chiropractic (Moorabbin) | 2027-01-26 | 19:30 | 21:30 | FREQ=WEEKLY;BYDAY=TU,WE | 284 Mason Highway, Moorabbin VIC | Clients/Harbourside Chiropractic/Clinic - Moorabbin | Office clean. Checklist: Clients/Harbourside Chiropractic/Clinic - Moorabbin/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Harbourside Chiropractic/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1223 | Wave 3 South | CL54 Nikos L. roster | Carpet steam clean - Harbourside Chiropractic (Moorabbin) | 2027-02-05 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 284 Mason Highway, Moorabbin VIC | Clients/Harbourside Chiropractic/Clinic - Moorabbin | Carpet steam clean. Checklist: Clients/Harbourside Chiropractic/Clinic - Moorabbin/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Harbourside Chiropractic/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1224 | Wave 3 South | CL51 Kavya L. roster | Office clean - Harbourside Chiropractic (St Kilda) | 2027-01-25 | 20:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 218 Burke Street, St Kilda VIC | Clients/Harbourside Chiropractic/Warehouse - St Kilda | Office clean. Checklist: Clients/Harbourside Chiropractic/Warehouse - St Kilda/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Harbourside Chiropractic/Warehouse - St Kilda/02 Site Access (office will share). | No | 0
J1225 | Wave 3 South | CL39 Sione F. roster | Office clean - Hillcrest Lawyers (Mentone) | 2027-01-27 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=WE,FR | 362 Barkly Avenue, Mentone VIC | Clients/Hillcrest Lawyers/Main office - Mentone | Office clean. Checklist: Clients/Hillcrest Lawyers/Main office - Mentone/01 Scope & Checklist. Notes: -. Access details: Clients/Hillcrest Lawyers/Main office - Mentone/02 Site Access (office will share). | No | 0
J1226 | Wave 1 North | CL01 Ana A. roster | Office clean - Hillcrest Lawyers (Northcote) | 2027-01-11 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 418 Main Avenue, Northcote VIC | Clients/Hillcrest Lawyers/Clinic - Northcote | Office clean. Checklist: Clients/Hillcrest Lawyers/Clinic - Northcote/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Hillcrest Lawyers/Clinic - Northcote/02 Site Access (office will share). | No | 0
J1227 | Wave 1 North | CL05 Eleni A. roster | Kitchen and bathrooms - Silverton Logistics Pty Ltd (Brunswick) | 2027-01-11 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO,TU | 176 High Highway, Brunswick VIC | Clients/Silverton Logistics Pty Ltd/Main office - Brunswick | Kitchen and bathrooms. Checklist: Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1228 | Wave 1 North | CL54 Nikos L. roster | Window clean - Silverton Logistics Pty Ltd (Brunswick) | 2027-01-27 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 176 High Highway, Brunswick VIC | Clients/Silverton Logistics Pty Ltd/Main office - Brunswick | Window clean. Checklist: Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1229 | Wave 3 South | CL31 Kavya F. roster | Kitchen and bathrooms - Silverton Logistics Pty Ltd (Frankston) | 2027-01-27 | 08:00 | 08:30 | FREQ=WEEKLY;BYDAY=WE | 356 Glenferrie Parade, Frankston VIC | Clients/Silverton Logistics Pty Ltd/Clinic - Frankston | Kitchen and bathrooms. Checklist: Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/02 Site Access (office will share). | No | 0
J1230 | Wave 3 South | CL11 Kavya A. roster | Office clean - Hillcrest Motors Pty Ltd (Bentleigh) | 2027-01-29 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=FR | 64 Glenferrie Parade, Bentleigh VIC | Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh | Office clean. Checklist: Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1231 | Wave 3 South | CL54 Nikos L. roster | Carpet steam clean - Hillcrest Motors Pty Ltd (Bentleigh) | 2027-01-27 | 11:30 | 14:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 64 Glenferrie Parade, Bentleigh VIC | Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh | Carpet steam clean. Checklist: Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1232 | Wave 1 North | CL13 Maya A. roster | Office clean - Southgate Pathology (Brunswick) | 2027-01-12 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=TU,WE | 433 Mason Parade, Brunswick VIC | Clients/Southgate Pathology/Main office - Brunswick | Office clean. Checklist: Clients/Southgate Pathology/Main office - Brunswick/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Park in bay 12 under the building. Access details: Clients/Southgate Pathology/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1233 | Wave 2 East | CL42 Bilal L. roster | Office clean - Southgate Pathology (Hawthorn) | 2027-01-18 | 17:30 | 20:00 | FREQ=WEEKLY;BYDAY=MO,TH | 291 Burke Highway, Hawthorn VIC | Clients/Southgate Pathology/Clinic - Hawthorn | Office clean. Checklist: Clients/Southgate Pathology/Clinic - Hawthorn/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Bins out on Tuesday night. Access details: Clients/Southgate Pathology/Clinic - Hawthorn/02 Site Access (office will share). | No | 0
J1234 | Wave 4 West | CL16 Pita A. roster | Kitchen and bathrooms - Southgate Pathology (Altona) | 2027-02-03 | 20:30 | 21:30 | FREQ=WEEKLY;BYDAY=WE,TH,FR | 186 Plenty Street, Altona VIC | Clients/Southgate Pathology/Warehouse - Altona | Kitchen and bathrooms. Checklist: Clients/Southgate Pathology/Warehouse - Altona/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Southgate Pathology/Warehouse - Altona/02 Site Access (office will share). | No | 0
J1235 | Wave 4 West | CL44 Dinh L. roster | Office clean - Westend Engineering (Deer Park) | 2027-02-01 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,TH | 279 Nicholson Avenue, Deer Park VIC | Clients/Westend Engineering/Main office - Deer Park | Office clean. Checklist: Clients/Westend Engineering/Main office - Deer Park/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Westend Engineering/Main office - Deer Park/02 Site Access (office will share). | No | 0
J1236 | Wave 1 North | CL45 Eleni L. roster | Kitchen and bathrooms - Westend Engineering (Reservoir) | 2027-01-12 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=TU,WE,TH | 313 Victoria Road, Reservoir VIC | Clients/Westend Engineering/Clinic - Reservoir | Kitchen and bathrooms. Checklist: Clients/Westend Engineering/Clinic - Reservoir/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Westend Engineering/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1237 | Wave 1 North | CL53 Maya L. roster | Carpet steam clean - Westend Engineering (Reservoir) | 2027-01-27 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=WE | 313 Victoria Road, Reservoir VIC | Clients/Westend Engineering/Clinic - Reservoir | Carpet steam clean. Checklist: Clients/Westend Engineering/Clinic - Reservoir/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Westend Engineering/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1238 | Wave 1 North | CL21 Ana F. roster | Office clean - Lakeside Real Estate Pty Ltd (Brunswick) | 2027-01-11 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 44 Nepean Parade, Brunswick VIC | Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick | Office clean. Checklist: Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/02 Site Access (office will share). | No | 0
J1239 | Wave 1 North | CL05 Eleni A. roster | Office clean - Lakeside Real Estate Pty Ltd (Preston) | 2027-01-12 | 19:00 | 20:30 | FREQ=WEEKLY;BYDAY=TU,WE,TH | 67 Glenferrie Road, Preston VIC | Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston | Office clean. Checklist: Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/02 Site Access (office will share). | No | 0
J1240 | Wave 2 East | CL26 Farid F. roster | Office clean - Lakeside Real Estate Pty Ltd (Mitcham) | 2027-01-20 | 20:00 | 21:00 | FREQ=WEEKLY;BYDAY=WE,TH | 6 Whitehorse Street, Mitcham VIC | Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham | Office clean. Checklist: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/02 Site Access (office will share). | No | 0
J1241 | Wave 2 East | CL54 Nikos L. roster | Window clean - Lakeside Real Estate Pty Ltd (Mitcham) | 2027-02-01 | 11:00 | 13:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 6 Whitehorse Street, Mitcham VIC | Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham | Window clean. Checklist: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/02 Site Access (office will share). | No | 0
J1242 | Wave 2 East | CL54 Nikos L. roster | Washroom service - Lakeside Real Estate Pty Ltd (Mitcham) | 2027-02-02 | 12:30 | 13:00 | FREQ=MONTHLY;BYDAY=1TU | 6 Whitehorse Street, Mitcham VIC | Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham | Washroom service. Checklist: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/02 Site Access (office will share). | No | 0
J1243 | Wave 4 West | CL32 Luis F. roster | Office clean - Harbourside Pharmacy Pty Ltd (Yarraville) | 2027-02-01 | 19:00 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU | 267 Nepean Street, Yarraville VIC | Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville | Office clean. Checklist: Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/02 Site Access (office will share). | No | 0
J1244 | Wave 4 West | CL28 Hamid F. roster | Office clean - Harbourside Pharmacy Pty Ltd (Williamstown) | 2027-02-02 | 19:30 | 21:00 | FREQ=WEEKLY;BYDAY=TU,FR | 266 Park Road, Williamstown VIC | Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown | Office clean. Checklist: Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/02 Site Access (office will share). | No | 0
J1245 | Wave 4 West | CL12 Luis A. roster | Office clean - Brightside Early Learning Pty Ltd (Footscray) | 2027-02-01 | 21:00 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 158 Nepean Avenue, Footscray VIC | Clients/Brightside Early Learning Pty Ltd/Main office - Footscray | Office clean. Checklist: Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/02 Site Access (office will share). | Yes | 0
J1246 | Wave 3 South | CL43 Carmen L. roster | Office clean - Southgate Engineering (Frankston) | 2027-01-25 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,WE | 135 Main Avenue, Frankston VIC | Clients/Southgate Engineering/Main office - Frankston | Office clean. Checklist: Clients/Southgate Engineering/Main office - Frankston/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Southgate Engineering/Main office - Frankston/02 Site Access (office will share). | No | 0
J1247 | Wave 1 North | CL17 Quynh A. roster | Kitchen and bathrooms - Riverside Dental Pty Ltd (Northcote) | 2027-01-15 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=FR | 256 Albert Parade, Northcote VIC | Clients/Riverside Dental Pty Ltd/Main office - Northcote | Kitchen and bathrooms. Checklist: Clients/Riverside Dental Pty Ltd/Main office - Northcote/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Riverside Dental Pty Ltd/Main office - Northcote/02 Site Access (office will share). | No | 0
J1248 | Wave 4 West | CL24 Dinh F. roster | Office clean - Bayview Early Learning (Laverton) | 2027-02-04 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=TH | 215 Barkly Street, Laverton VIC | Clients/Bayview Early Learning/Main office - Laverton | Office clean. Checklist: Clients/Bayview Early Learning/Main office - Laverton/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]. Access details: Clients/Bayview Early Learning/Main office - Laverton/02 Site Access (office will share). | No | 0
J1249 | Wave 4 West | CL54 Nikos L. roster | Window clean - Bayview Early Learning (Laverton) | 2027-02-04 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 215 Barkly Street, Laverton VIC | Clients/Bayview Early Learning/Main office - Laverton | Window clean. Checklist: Clients/Bayview Early Learning/Main office - Laverton/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]. Access details: Clients/Bayview Early Learning/Main office - Laverton/02 Site Access (office will share). | No | 0
J1250 | Wave 3 South | CL31 Kavya F. roster | Office clean - Bayview Early Learning (Brighton) | 2027-01-25 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO | 329 Station Avenue, Brighton VIC | Clients/Bayview Early Learning/Clinic - Brighton | Office clean. Checklist: Clients/Bayview Early Learning/Clinic - Brighton/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Bayview Early Learning/Clinic - Brighton/02 Site Access (office will share). | No | 0
J1251 | Wave 4 West | CL20 Tara A. roster | Kitchen and bathrooms - Elm Street Financial Planning Pty Ltd (Yarraville) | 2027-02-04 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=TH,FR | 462A Victoria Road, Yarraville VIC | Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville | Kitchen and bathrooms. Checklist: Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/02 Site Access (office will share). | No | 0
J1252 | Wave 3 South | CL27 Grace F. roster | Kitchen and bathrooms - Ashwood Property Group (Cheltenham) | 2027-01-25 | 17:30 | 18:00 | FREQ=WEEKLY;BYDAY=MO | 248 Sydney Street, Cheltenham VIC | Clients/Ashwood Property Group/Main office - Cheltenham | Kitchen and bathrooms. Checklist: Clients/Ashwood Property Group/Main office - Cheltenham/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Property Group/Main office - Cheltenham/02 Site Access (office will share). | No | 0
J1253 | Wave 3 South | CL53 Maya L. roster | Carpet steam clean - Ashwood Property Group (Cheltenham) | 2027-01-26 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 248 Sydney Street, Cheltenham VIC | Clients/Ashwood Property Group/Main office - Cheltenham | Carpet steam clean. Checklist: Clients/Ashwood Property Group/Main office - Cheltenham/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Property Group/Main office - Cheltenham/02 Site Access (office will share). | No | 0
J1254 | Wave 3 South | CL35 Omar F. roster | Kitchen and bathrooms - Northside Early Learning Pty Ltd (Bentleigh) | 2027-01-25 | 19:30 | 20:30 | FREQ=WEEKLY;BYDAY=MO,TU | 251 Plenty Highway, Bentleigh VIC | Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh | Kitchen and bathrooms. Checklist: Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | Yes | 0
J1255 | Wave 3 South | CL31 Kavya F. roster | Office clean - Brightside Logistics Pty Ltd (Bentleigh) | 2027-01-26 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=TU,WE | 148 Nepean Street, Bentleigh VIC | Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh | Office clean. Checklist: Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Park in bay 12 under the building. Access details: Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1256 | Wave 2 East | CL18 Rosa A. roster | Office clean - Elm Street Early Learning (Hawthorn) | 2027-01-18 | 20:00 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 431 Union Avenue, Hawthorn VIC | Clients/Elm Street Early Learning/Main office - Hawthorn | Office clean. Checklist: Clients/Elm Street Early Learning/Main office - Hawthorn/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Elm Street Early Learning/Main office - Hawthorn/02 Site Access (office will share). | No | 0
J1257 | Wave 2 East | CL22 Bilal F. roster | Office clean - Elm Street Early Learning (Camberwell) | 2027-01-18 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=MO | 356 Main Road, Camberwell VIC | Clients/Elm Street Early Learning/Clinic - Camberwell | Office clean. Checklist: Clients/Elm Street Early Learning/Clinic - Camberwell/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Elm Street Early Learning/Clinic - Camberwell/02 Site Access (office will share). | No | 0
J1258 | Wave 2 East | CL34 Nikos F. roster | Office clean - Elm Street Early Learning (Glen Waverley) | 2027-01-18 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=MO,WE | 422 Nicholson Parade, Glen Waverley VIC | Clients/Elm Street Early Learning/Warehouse - Glen Waverley | Office clean. Checklist: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1259 | Wave 2 East | CL53 Maya L. roster | Window clean - Elm Street Early Learning (Glen Waverley) | 2027-02-08 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 422 Nicholson Parade, Glen Waverley VIC | Clients/Elm Street Early Learning/Warehouse - Glen Waverley | Window clean. Checklist: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1260 | Wave 2 East | CL54 Nikos L. roster | Washroom service - Elm Street Early Learning (Glen Waverley) | 2027-02-05 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1FR | 422 Nicholson Parade, Glen Waverley VIC | Clients/Elm Street Early Learning/Warehouse - Glen Waverley | Washroom service. Checklist: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF; Reception closes 5:30 pm, use the side entry. Access details: Clients/Elm Street Early Learning/Warehouse - Glen Waverley/02 Site Access (office will share). | No | 0
J1261 | Wave 4 West | CL36 Pita F. roster | Office clean - Redgum Financial Planning (Williamstown) | 2027-02-02 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=TU,FR | 455 Railway Road, Williamstown VIC | Clients/Redgum Financial Planning/Main office - Williamstown | Office clean. Checklist: Clients/Redgum Financial Planning/Main office - Williamstown/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Redgum Financial Planning/Main office - Williamstown/02 Site Access (office will share). | No | 0
J1262 | Pilot | CL09 Ines A. roster | Office clean - Redgum Financial Planning (Epping) | 2026-12-08 | 06:30 | 08:00 | FREQ=WEEKLY;BYDAY=TU,WE | 217 King Street, Epping VIC | Clients/Redgum Financial Planning/Clinic - Epping | Office clean. Checklist: Clients/Redgum Financial Planning/Clinic - Epping/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Redgum Financial Planning/Clinic - Epping/02 Site Access (office will share). | No | 0
J1263 | Wave 2 East | CL46 Farid L. roster | Office clean - Lakeside Fitness Pty Ltd (Mitcham) | 2027-01-19 | 06:00 | 07:30 | FREQ=WEEKLY;BYDAY=TU,TH | 58 Station Road, Mitcham VIC | Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham | Office clean. Checklist: Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/01 Scope & Checklist. Notes: -. Access details: Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/02 Site Access (office will share). | Yes | 0
J1264 | Wave 2 East | CL10 Jun A. roster | Office clean - Elm Street Logistics Pty Ltd (Kew) | 2027-01-18 | 20:30 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 343 Sydney Street, Kew VIC | Clients/Elm Street Logistics Pty Ltd/Main office - Kew | Office clean. Checklist: Clients/Elm Street Logistics Pty Ltd/Main office - Kew/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Elm Street Logistics Pty Ltd/Main office - Kew/02 Site Access (office will share). | No | 0
J1265 | Wave 2 East | CL46 Farid L. roster | Office clean - Elm Street Logistics Pty Ltd (Ringwood) | 2027-01-18 | 22:00 | 23:00 | FREQ=WEEKLY;BYDAY=MO,WE | 399 Plenty Avenue, Ringwood VIC | Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood | Office clean. Checklist: Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/02 Site Access (office will share). | No | 0
J1266 | Wave 2 East | CL26 Farid F. roster | Office clean - Elm Street Logistics Pty Ltd (Blackburn) | 2027-01-18 | 21:30 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 256 Station Street, Blackburn VIC | Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn | Office clean. Checklist: Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/01 Scope & Checklist. Notes: -. Access details: Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/02 Site Access (office will share). | No | 0
J1267 | Wave 2 East | CL57 Quynh L. roster | Window clean - Elm Street Logistics Pty Ltd (Blackburn) | 2027-02-05 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 256 Station Street, Blackburn VIC | Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn | Window clean. Checklist: Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/01 Scope & Checklist. Notes: -. Access details: Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/02 Site Access (office will share). | No | 0
J1268 | Wave 4 West | CL16 Pita A. roster | Kitchen and bathrooms - Lakeside Insurance Brokers (Sunshine) | 2027-02-01 | 22:00 | 23:00 | FREQ=WEEKLY;BYDAY=MO,WE,FR | 459 Whitehorse Parade, Sunshine VIC | Clients/Lakeside Insurance Brokers/Main office - Sunshine | Kitchen and bathrooms. Checklist: Clients/Lakeside Insurance Brokers/Main office - Sunshine/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Lakeside Insurance Brokers/Main office - Sunshine/02 Site Access (office will share). | No | 0
J1269 | Wave 4 West | CL57 Quynh L. roster | Carpet steam clean - Lakeside Insurance Brokers (Sunshine) | 2027-02-23 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 459 Whitehorse Parade, Sunshine VIC | Clients/Lakeside Insurance Brokers/Main office - Sunshine | Carpet steam clean. Checklist: Clients/Lakeside Insurance Brokers/Main office - Sunshine/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Lakeside Insurance Brokers/Main office - Sunshine/02 Site Access (office will share). | No | 0
J1270 | Wave 4 West | CL24 Dinh F. roster | Kitchen and bathrooms - Elm Street Pathology Pty Ltd (Maribyrnong) | 2027-02-01 | 21:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 87 Main Avenue, Maribyrnong VIC | Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong | Kitchen and bathrooms. Checklist: Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1271 | Wave 3 South | CL27 Grace F. roster | Office clean - Fairfield Accountants Pty Ltd (Dandenong) | 2027-01-25 | 18:30 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 313/12 Union Avenue, Dandenong VIC | Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong | Office clean. Checklist: Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/01 Scope & Checklist. Notes: -. Access details: Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/02 Site Access (office will share). | No | 0
J1272 | Wave 3 South | CL39 Sione F. roster | Office clean - Fairfield Accountants Pty Ltd (Moorabbin) | 2027-01-27 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=WE,FR | 354 King Avenue, Moorabbin VIC | Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin | Office clean. Checklist: Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/01 Scope & Checklist. Notes: -. Access details: Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1273 | Wave 3 South | CL57 Quynh L. roster | Window clean - Fairfield Accountants Pty Ltd (Moorabbin) | 2027-02-18 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 354 King Avenue, Moorabbin VIC | Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin | Window clean. Checklist: Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/01 Scope & Checklist. Notes: -. Access details: Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1274 | Wave 2 East | CL22 Bilal F. roster | Office clean - Fairfield Dental (Box Hill) | 2027-01-18 | 19:00 | 21:30 | FREQ=WEEKLY;BYDAY=MO,WE | 122 Main Avenue, Box Hill VIC | Clients/Fairfield Dental/Main office - Box Hill | Office clean. Checklist: Clients/Fairfield Dental/Main office - Box Hill/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Fairfield Dental/Main office - Box Hill/02 Site Access (office will share). | No | 0
J1275 | Wave 1 North | CL37 Quynh F. roster | Office clean - Oakwood Medical Centre Pty Ltd (Coburg) | 2027-01-11 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=MO,TU,TH | 64 Bridge Street, Coburg VIC | Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg | Office clean. Checklist: Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]. Access details: Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/02 Site Access (office will share). | No | 0
J1276 | Wave 3 South | CL07 Grace A. roster | Office clean - Banksia Architects Pty Ltd (Frankston) | 2027-01-25 | 19:30 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,TH | 213 Church Parade, Frankston VIC | Clients/Banksia Architects Pty Ltd/Main office - Frankston | Office clean. Checklist: Clients/Banksia Architects Pty Ltd/Main office - Frankston/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor. Access details: Clients/Banksia Architects Pty Ltd/Main office - Frankston/02 Site Access (office will share). | No | 0
J1277 | Pilot | CL33 Maya F. roster | Office clean - Ironbark Engineering Pty Ltd (Preston) | 2026-12-07 | 20:30 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE | 420 Railway Parade, Preston VIC | Clients/Ironbark Engineering Pty Ltd/Main office - Preston | Office clean. Checklist: Clients/Ironbark Engineering Pty Ltd/Main office - Preston/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Ironbark Engineering Pty Ltd/Main office - Preston/02 Site Access (office will share). | No | 0
J1278 | Wave 1 North | CL17 Quynh A. roster | Office clean - Ironbark Engineering Pty Ltd (Thornbury) | 2027-01-11 | 21:00 | 23:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 301 Whitehorse Highway, Thornbury VIC | Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury | Office clean. Checklist: Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/01 Scope & Checklist. Notes: -. Access details: Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/02 Site Access (office will share). | No | 0
J1279 | Wave 1 North | CL25 Eleni F. roster | Office clean - Wattle Grove Financial Planning (Northcote) | 2027-01-14 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TH,FR | 294 Victoria Avenue, Northcote VIC | Clients/Wattle Grove Financial Planning/Main office - Northcote | Office clean. Checklist: Clients/Wattle Grove Financial Planning/Main office - Northcote/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Store room on level 1, room 104. Access details: Clients/Wattle Grove Financial Planning/Main office - Northcote/02 Site Access (office will share). | No | 0
J1280 | Wave 2 East | CL50 Jun L. roster | Office clean - Parkside Fitness Pty Ltd (Burwood) | 2027-01-18 | 19:30 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU | 81 Nepean Road, Burwood VIC | Clients/Parkside Fitness Pty Ltd/Main office - Burwood | Office clean. Checklist: Clients/Parkside Fitness Pty Ltd/Main office - Burwood/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Parkside Fitness Pty Ltd/Main office - Burwood/02 Site Access (office will share). | No | 0
J1281 | Wave 4 West | CL20 Tara A. roster | Office clean - Parkside Fitness Pty Ltd (Maribyrnong) | 2027-02-05 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=FR | 440 Bridge Street, Maribyrnong VIC | Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong | Office clean. Checklist: Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/02 Site Access (office will share). | Yes | 0
J1282 | Wave 4 West | CL57 Quynh L. roster | Window clean - Parkside Fitness Pty Ltd (Maribyrnong) | 2027-02-09 | 11:00 | 13:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 440 Bridge Street, Maribyrnong VIC | Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong | Window clean. Checklist: Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/02 Site Access (office will share). | No | 0
J1283 | Wave 2 East | CL06 Farid A. roster | Office clean - Greenway Chiropractic Pty Ltd (Ringwood) | 2027-01-18 | 20:30 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 347 High Highway, Ringwood VIC | Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood | Office clean. Checklist: Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/02 Site Access (office will share). | No | 0
J1284 | Wave 2 East | CL54 Nikos L. roster | Window clean - Greenway Chiropractic Pty Ltd (Ringwood) | 2027-01-22 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=FR | 347 High Highway, Ringwood VIC | Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood | Window clean. Checklist: Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*; Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/02 Site Access (office will share). | No | 0
J1285 | Wave 2 East | CL38 Rosa F. roster | Office clean - Greenway Chiropractic Pty Ltd (Kew) | 2027-01-18 | 19:30 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 250 Hopkins Highway, Kew VIC | Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew | Office clean. Checklist: Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/01 Scope & Checklist. Notes: -. Access details: Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/02 Site Access (office will share). | No | 0
J1286 | Wave 2 East | CL02 Bilal A. roster | Office clean - Greenway Chiropractic Pty Ltd (Burwood) | 2027-01-18 | 19:00 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 191 Albert Avenue, Burwood VIC | Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood | Office clean. Checklist: Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/01 Scope & Checklist. Notes: -. Access details: Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/02 Site Access (office will share). | No | 0
J1287 | Wave 3 South | CL11 Kavya A. roster | Office clean - Bayview Real Estate Pty Ltd (Brighton) | 2027-01-25 | 19:00 | 20:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE | 414 Sydney Avenue, Brighton VIC | Clients/Bayview Real Estate Pty Ltd/Main office - Brighton | Office clean. Checklist: Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/02 Site Access (office will share). | No | 0
J1288 | Wave 2 East | CL34 Nikos F. roster | Kitchen and bathrooms - Riverside Pharmacy (Box Hill) | 2027-01-20 | 19:00 | 20:00 | FREQ=WEEKLY;BYDAY=WE,TH | 472 Hopkins Highway, Box Hill VIC | Clients/Riverside Pharmacy/Main office - Box Hill | Kitchen and bathrooms. Checklist: Clients/Riverside Pharmacy/Main office - Box Hill/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Riverside Pharmacy/Main office - Box Hill/02 Site Access (office will share). | No | 0
J1289 | Wave 2 East | CL30 Jun F. roster | Office clean - Riverside Pharmacy (Glen Waverley) | 2027-01-18 | 20:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 410 Queen Highway, Glen Waverley VIC | Clients/Riverside Pharmacy/Clinic - Glen Waverley | Office clean. Checklist: Clients/Riverside Pharmacy/Clinic - Glen Waverley/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Riverside Pharmacy/Clinic - Glen Waverley/02 Site Access (office will share). | No | 0
J1290 | Wave 2 East | CL54 Nikos L. roster | Window clean - Riverside Pharmacy (Glen Waverley) | 2027-01-25 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 410 Queen Highway, Glen Waverley VIC | Clients/Riverside Pharmacy/Clinic - Glen Waverley | Window clean. Checklist: Clients/Riverside Pharmacy/Clinic - Glen Waverley/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Riverside Pharmacy/Clinic - Glen Waverley/02 Site Access (office will share). | No | 0
J1291 | Wave 2 East | CL54 Nikos L. roster | Washroom service - Riverside Pharmacy (Glen Waverley) | 2027-02-05 | 10:00 | 10:30 | FREQ=MONTHLY;BYDAY=1FR | 410 Queen Highway, Glen Waverley VIC | Clients/Riverside Pharmacy/Clinic - Glen Waverley | Washroom service. Checklist: Clients/Riverside Pharmacy/Clinic - Glen Waverley/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Riverside Pharmacy/Clinic - Glen Waverley/02 Site Access (office will share). | No | 0
J1292 | Wave 3 South | CL23 Carmen F. roster | Office clean - Elm Street Chiropractic Pty Ltd (Mentone) | 2027-01-25 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=MO,TH | 348 Railway Street, Mentone VIC | Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone | Office clean. Checklist: Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/02 Site Access (office will share). | No | 0
J1293 | Wave 3 South | CL55 Omar L. roster | Window clean - Elm Street Chiropractic Pty Ltd (Mentone) | 2027-02-04 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 348 Railway Street, Mentone VIC | Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone | Window clean. Checklist: Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/02 Site Access (office will share). | No | 0
J1294 | Wave 3 South | CL47 Grace L. roster | Office clean - Elm Street Chiropractic Pty Ltd (Cheltenham) | 2027-01-29 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=FR | 4 Sydney Highway, Cheltenham VIC | Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham | Office clean. Checklist: Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1295 | Wave 3 South | CL55 Omar L. roster | Washroom service - Elm Street Chiropractic Pty Ltd (Cheltenham) | 2027-02-02 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TU | 4 Sydney Highway, Cheltenham VIC | Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham | Washroom service. Checklist: Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/02 Site Access (office will share). | No | 0
J1296 | Wave 3 South | CL35 Omar F. roster | Office clean - Ironbark Real Estate Pty Ltd (Oakleigh) | 2027-01-28 | 19:30 | 20:30 | FREQ=WEEKLY;BYDAY=TH | 395 Plenty Avenue, Oakleigh VIC | Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh | Office clean. Checklist: Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/01 Scope & Checklist. Notes: -. Access details: Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/02 Site Access (office will share). | No | 0
J1297 | Wave 3 South | CL03 Carmen A. roster | Office clean - Ironbark Real Estate Pty Ltd (Oakleigh) | 2027-01-26 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU,WE | 32 Park Avenue, Oakleigh VIC | Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh | Office clean. Checklist: Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Level 3, lift to the left. Access details: Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/02 Site Access (office will share). | No | 0
J1298 | Wave 3 South | CL19 Sione A. roster | Office clean - Elm Street Motors (Brighton) | 2027-01-26 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU | 333 Albert Parade, Brighton VIC | Clients/Elm Street Motors/Main office - Brighton | Office clean. Checklist: Clients/Elm Street Motors/Main office - Brighton/01 Scope & Checklist. Notes: Call 0400 000 000 if the door is locked. Access details: Clients/Elm Street Motors/Main office - Brighton/02 Site Access (office will share). | No | 0
J1299 | Wave 3 South | CL43 Carmen L. roster | Kitchen and bathrooms - Elm Street Motors (Oakleigh) | 2027-01-26 | 08:00 | 08:30 | FREQ=WEEKLY;BYDAY=TU | 280 Station Street, Oakleigh VIC | Clients/Elm Street Motors/Clinic - Oakleigh | Kitchen and bathrooms. Checklist: Clients/Elm Street Motors/Clinic - Oakleigh/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Elm Street Motors/Clinic - Oakleigh/02 Site Access (office will share). | No | 0
J1300 | Wave 4 West | CL40 Tara F. roster | Office clean - Sunbury Engineering (Point Cook) | 2027-02-01 | 21:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,WE,FR | 87/12 Victoria Road, Point Cook VIC | Clients/Sunbury Engineering/Main office - Point Cook | Office clean. Checklist: Clients/Sunbury Engineering/Main office - Point Cook/01 Scope & Checklist. Notes: Back door keypad [in 02 Site Access]*. Access details: Clients/Sunbury Engineering/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1301 | Wave 1 North | CL29 Ines F. roster | Office clean - Ashwood Dental Pty Ltd (Northcote) | 2027-01-12 | 07:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU,TH | 241 Mason Road, Northcote VIC | Clients/Ashwood Dental Pty Ltd/Main office - Northcote | Office clean. Checklist: Clients/Ashwood Dental Pty Ltd/Main office - Northcote/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Ashwood Dental Pty Ltd/Main office - Northcote/02 Site Access (office will share). | Yes | 0
J1302 | Wave 3 South | CL35 Omar F. roster | Kitchen and bathrooms - Ashwood Dental Pty Ltd (Mentone) | 2027-01-29 | 05:30 | 06:00 | FREQ=WEEKLY;BYDAY=FR | 448 Barkly Avenue, Mentone VIC | Clients/Ashwood Dental Pty Ltd/Clinic - Mentone | Kitchen and bathrooms. Checklist: Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/01 Scope & Checklist. Notes: -. Access details: Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/02 Site Access (office will share). | No | 0
J1303 | Wave 4 West | CL48 Hamid L. roster | Office clean - Bluestone Early Learning Pty Ltd (Altona) | 2027-02-01 | 19:00 | 20:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 351 High Street, Altona VIC | Clients/Bluestone Early Learning Pty Ltd/Main office - Altona | Office clean. Checklist: Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Store room on level 1, room 104. Access details: Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/02 Site Access (office will share). | No | 0
J1304 | Wave 4 West | CL55 Omar L. roster | Window clean - Bluestone Early Learning Pty Ltd (Altona) | 2027-02-23 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 351 High Street, Altona VIC | Clients/Bluestone Early Learning Pty Ltd/Main office - Altona | Window clean. Checklist: Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/01 Scope & Checklist. Notes: Alarm code [in 02 Site Access]#, panel behind reception door; Store room on level 1, room 104. Access details: Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/02 Site Access (office will share). | No | 0
J1305 | Wave 2 East | CL42 Bilal L. roster | Office clean - Bluestone Early Learning Pty Ltd (Hawthorn) | 2027-01-18 | 20:30 | 22:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 477 Hopkins Avenue, Hawthorn VIC | Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn | Office clean. Checklist: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor. Access details: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/02 Site Access (office will share). | No | 0
J1306 | Wave 2 East | CL55 Omar L. roster | Window clean - Bluestone Early Learning Pty Ltd (Hawthorn) | 2027-01-21 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 477 Hopkins Avenue, Hawthorn VIC | Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn | Window clean. Checklist: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor. Access details: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/02 Site Access (office will share). | No | 0
J1307 | Wave 2 East | CL56 Pita L. roster | Washroom service - Bluestone Early Learning Pty Ltd (Hawthorn) | 2027-02-04 | 10:00 | 10:30 | FREQ=MONTHLY;BYDAY=1TH | 477 Hopkins Avenue, Hawthorn VIC | Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn | Washroom service. Checklist: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor. Access details: Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/02 Site Access (office will share). | No | 0
J1308 | Wave 4 West | CL28 Hamid F. roster | Office clean - Harbourside Property Group (Maribyrnong) | 2027-02-01 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=MO | 428 Church Parade, Maribyrnong VIC | Clients/Harbourside Property Group/Main office - Maribyrnong | Office clean. Checklist: Clients/Harbourside Property Group/Main office - Maribyrnong/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Harbourside Property Group/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1309 | Wave 4 West | CL54 Nikos L. roster | Carpet steam clean - Harbourside Property Group (Maribyrnong) | 2027-02-15 | 09:00 | 11:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=MO | 428 Church Parade, Maribyrnong VIC | Clients/Harbourside Property Group/Main office - Maribyrnong | Carpet steam clean. Checklist: Clients/Harbourside Property Group/Main office - Maribyrnong/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Harbourside Property Group/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1310 | Wave 4 West | CL54 Nikos L. roster | Washroom service - Harbourside Property Group (Maribyrnong) | 2027-02-04 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TH | 428 Church Parade, Maribyrnong VIC | Clients/Harbourside Property Group/Main office - Maribyrnong | Washroom service. Checklist: Clients/Harbourside Property Group/Main office - Maribyrnong/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Harbourside Property Group/Main office - Maribyrnong/02 Site Access (office will share). | No | 0
J1311 | Wave 1 North | CL21 Ana F. roster | Office clean - Riverside Engineering Pty Ltd (Bundoora) | 2027-01-11 | 05:30 | 06:30 | FREQ=WEEKLY;BYDAY=MO | 253A Glenferrie Street, Bundoora VIC | Clients/Riverside Engineering Pty Ltd/Main office - Bundoora | Office clean. Checklist: Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/01 Scope & Checklist. Notes: -. Access details: Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/02 Site Access (office will share). | No | 0
J1312 | Wave 4 West | CL44 Dinh L. roster | Kitchen and bathrooms - Ashwood Lawyers (Werribee) | 2027-02-03 | 17:30 | 18:30 | FREQ=WEEKLY;BYDAY=WE,FR | 466 Main Street, Werribee VIC | Clients/Ashwood Lawyers/Main office - Werribee | Kitchen and bathrooms. Checklist: Clients/Ashwood Lawyers/Main office - Werribee/01 Scope & Checklist. Notes: Store room on level 1, room 104. Access details: Clients/Ashwood Lawyers/Main office - Werribee/02 Site Access (office will share). | No | 0
J1313 | Wave 1 North | CL41 Ana L. roster | Office clean - Bayview Fitness Pty Ltd (Thornbury) | 2027-01-13 | 17:30 | 19:00 | FREQ=WEEKLY;BYDAY=WE | 367 Station Parade, Thornbury VIC | Clients/Bayview Fitness Pty Ltd/Main office - Thornbury | Office clean. Checklist: Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/02 Site Access (office will share). | No | 0
J1314 | Wave 2 East | CL46 Farid L. roster | Kitchen and bathrooms - Ironbark Property Group Pty Ltd (Mitcham) | 2027-01-21 | 19:30 | 20:00 | FREQ=WEEKLY;BYDAY=TH,FR | 266/12 Albert Avenue, Mitcham VIC | Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham | Kitchen and bathrooms. Checklist: Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/01 Scope & Checklist. Notes: Code for roller door: [in 02 Site Access]; Bins out on Tuesday night. Access details: Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/02 Site Access (office will share). | No | 0
J1315 | Wave 1 North | CL49 Ines L. roster | Office clean - Ironbark Property Group Pty Ltd (Reservoir) | 2027-01-11 | 19:00 | 21:00 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 479 Burke Road, Reservoir VIC | Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir | Office clean. Checklist: Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1316 | Wave 1 North | CL55 Omar L. roster | Washroom service - Ironbark Property Group Pty Ltd (Reservoir) | 2027-02-04 | 11:00 | 11:30 | FREQ=MONTHLY;BYDAY=1TH | 479 Burke Road, Reservoir VIC | Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir | Washroom service. Checklist: Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/02 Site Access (office will share). | No | 0
J1317 | Wave 2 East | CL46 Farid L. roster | Office clean - Oakwood Engineering (Burwood) | 2027-01-19 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=TU,TH | 216 Plenty Road, Burwood VIC | Clients/Oakwood Engineering/Main office - Burwood | Office clean. Checklist: Clients/Oakwood Engineering/Main office - Burwood/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Oakwood Engineering/Main office - Burwood/02 Site Access (office will share). | Yes | 0
J1318 | Wave 2 East | CL54 Nikos L. roster | Window clean - Oakwood Engineering (Burwood) | 2027-02-02 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 216 Plenty Road, Burwood VIC | Clients/Oakwood Engineering/Main office - Burwood | Window clean. Checklist: Clients/Oakwood Engineering/Main office - Burwood/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Oakwood Engineering/Main office - Burwood/02 Site Access (office will share). | No | 0
J1319 | Wave 3 South | CL43 Carmen L. roster | Office clean - Waverley Physiotherapy Pty Ltd (Bentleigh) | 2027-01-25 | 20:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO,FR | 42 Queen Avenue, Bentleigh VIC | Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh | Office clean. Checklist: Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/01 Scope & Checklist. Notes: -. Access details: Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/02 Site Access (office will share). | No | 0
J1320 | Wave 3 South | CL39 Sione F. roster | Office clean - Waverley Physiotherapy Pty Ltd (Bentleigh) | 2027-01-28 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=TH | 438 Church Highway, Bentleigh VIC | Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh | Office clean. Checklist: Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/02 Site Access (office will share). | No | 0
J1321 | Wave 3 South | CL55 Omar L. roster | Carpet steam clean - Waverley Physiotherapy Pty Ltd (Bentleigh) | 2027-02-02 | 09:00 | 12:00 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TU | 438 Church Highway, Bentleigh VIC | Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh | Carpet steam clean. Checklist: Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]. Access details: Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/02 Site Access (office will share). | No | 0
J1322 | Wave 3 South | CL35 Omar F. roster | Office clean - Waverley Physiotherapy Pty Ltd (St Kilda) | 2027-01-25 | 05:30 | 08:00 | FREQ=WEEKLY;BYDAY=MO | 337 Plenty Parade, St Kilda VIC | Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda | Office clean. Checklist: Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/01 Scope & Checklist. Notes: Do not use bleach on the timber floor. Access details: Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/02 Site Access (office will share). | No | 0
J1323 | Wave 1 North | CL45 Eleni L. roster | Office clean - Harbourside Insurance Brokers Pty Ltd (Northcote) | 2027-01-12 | 19:00 | 22:00 | FREQ=WEEKLY;BYDAY=TU | 314 Plenty Street, Northcote VIC | Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote | Office clean. Checklist: Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/01 Scope & Checklist. Notes: Bins out on Tuesday night. Access details: Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/02 Site Access (office will share). | No | 0
J1324 | Wave 2 East | CL50 Jun L. roster | Office clean - Harbourside Real Estate (Glen Waverley) | 2027-01-20 | 19:30 | 21:00 | FREQ=WEEKLY;BYDAY=WE | 121 High Parade, Glen Waverley VIC | Clients/Harbourside Real Estate/Main office - Glen Waverley | Office clean. Checklist: Clients/Harbourside Real Estate/Main office - Glen Waverley/01 Scope & Checklist. Notes: -. Access details: Clients/Harbourside Real Estate/Main office - Glen Waverley/02 Site Access (office will share). | No | 0
J1325 | Wave 3 South | CL31 Kavya F. roster | Office clean - Harbourside Real Estate (Clayton) | 2027-01-26 | 05:30 | 08:30 | FREQ=WEEKLY;BYDAY=TU,FR | 317 Victoria Parade, Clayton VIC | Clients/Harbourside Real Estate/Clinic - Clayton | Office clean. Checklist: Clients/Harbourside Real Estate/Clinic - Clayton/01 Scope & Checklist. Notes: Sign in at security desk. Access details: Clients/Harbourside Real Estate/Clinic - Clayton/02 Site Access (office will share). | No | 0
J1326 | Pilot | CL09 Ines A. roster | Office clean - Eastwood Podiatry (Coburg) | 2026-12-07 | 20:30 | 22:30 | FREQ=WEEKLY;BYDAY=MO,TU,WE,TH,FR | 273/12 Plenty Parade, Coburg VIC | Clients/Eastwood Podiatry/Main office - Coburg | Office clean. Checklist: Clients/Eastwood Podiatry/Main office - Coburg/01 Scope & Checklist. Notes: Lockbox on meter box, [in 02 Site Access]; Do not use bleach on the timber floor. Access details: Clients/Eastwood Podiatry/Main office - Coburg/02 Site Access (office will share). | No | 0
J1327 | Wave 3 South | CL47 Grace L. roster | Office clean - Cityside Real Estate (Moorabbin) | 2027-01-29 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=FR | 200 Nepean Avenue, Moorabbin VIC | Clients/Cityside Real Estate/Main office - Moorabbin | Office clean. Checklist: Clients/Cityside Real Estate/Main office - Moorabbin/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Cityside Real Estate/Main office - Moorabbin/02 Site Access (office will share). | No | 0
J1328 | Wave 3 South | CL15 Omar A. roster | Office clean - Cityside Real Estate (Moorabbin) | 2027-01-27 | 20:00 | 21:30 | FREQ=WEEKLY;BYDAY=WE | 455 Nicholson Highway, Moorabbin VIC | Clients/Cityside Real Estate/Clinic - Moorabbin | Office clean. Checklist: Clients/Cityside Real Estate/Clinic - Moorabbin/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Cityside Real Estate/Clinic - Moorabbin/02 Site Access (office will share). | Yes | 0
J1329 | Wave 3 South | CL54 Nikos L. roster | Window clean - Cityside Real Estate (Moorabbin) | 2027-02-18 | 09:00 | 10:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 455 Nicholson Highway, Moorabbin VIC | Clients/Cityside Real Estate/Clinic - Moorabbin | Window clean. Checklist: Clients/Cityside Real Estate/Clinic - Moorabbin/01 Scope & Checklist. Notes: Level 3, lift to the left. Access details: Clients/Cityside Real Estate/Clinic - Moorabbin/02 Site Access (office will share). | No | 0
J1330 | Wave 3 South | CL15 Omar A. roster | Office clean - Parkside Dental (Mentone) | 2027-01-25 | 20:00 | 21:30 | FREQ=WEEKLY;BYDAY=MO,TH,FR | 400 Albert Street, Mentone VIC | Clients/Parkside Dental/Main office - Mentone | Office clean. Checklist: Clients/Parkside Dental/Main office - Mentone/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Parkside Dental/Main office - Mentone/02 Site Access (office will share). | No | 0
J1331 | Wave 3 South | CL56 Pita L. roster | Washroom service - Parkside Dental (Mentone) | 2027-02-02 | 09:00 | 09:30 | FREQ=MONTHLY;BYDAY=1TU | 400 Albert Street, Mentone VIC | Clients/Parkside Dental/Main office - Mentone | Washroom service. Checklist: Clients/Parkside Dental/Main office - Mentone/01 Scope & Checklist. Notes: Reception closes 5:30 pm, use the side entry. Access details: Clients/Parkside Dental/Main office - Mentone/02 Site Access (office will share). | No | 0
J1332 | Wave 4 West | CL04 Dinh A. roster | Office clean - Parkside Dental Group (Point Cook) | 2027-02-02 | 07:00 | 08:30 | FREQ=WEEKLY;BYDAY=TU,WE,TH | 257 Hopkins Parade, Point Cook VIC | Clients/Parkside Dental Group/Main office - Point Cook | Office clean. Checklist: Clients/Parkside Dental Group/Main office - Point Cook/01 Scope & Checklist. Notes: Kitchen: 2 fridges, empty on Fridays. Access details: Clients/Parkside Dental Group/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1333 | Wave 3 South | CL19 Sione A. roster | Kitchen and bathrooms - Northside Physiotherapy (Brighton) | 2027-01-25 | 07:00 | 08:00 | FREQ=WEEKLY;BYDAY=MO,TH | 139 Glenferrie Parade, Brighton VIC | Clients/Northside Physiotherapy/Main office - Brighton | Kitchen and bathrooms. Checklist: Clients/Northside Physiotherapy/Main office - Brighton/01 Scope & Checklist. Notes: Alarm [in 02 Site Access] then press OFF. Access details: Clients/Northside Physiotherapy/Main office - Brighton/02 Site Access (office will share). | No | 0
J1334 | Wave 4 West | CL20 Tara A. roster | Office clean - Northside Physiotherapy (Werribee) | 2027-02-03 | 17:30 | 20:30 | FREQ=WEEKLY;BYDAY=WE,TH | 250 Bridge Highway, Werribee VIC | Clients/Northside Physiotherapy/Clinic - Werribee | Office clean. Checklist: Clients/Northside Physiotherapy/Clinic - Werribee/01 Scope & Checklist. Notes: Vacuum bags in cupboard 2. Access details: Clients/Northside Physiotherapy/Clinic - Werribee/02 Site Access (office will share). | No | 0
J1335 | Wave 4 West | CL32 Luis F. roster | Office clean - North Side Physiotherapy (Point Cook) | 2027-02-05 | 05:30 | 07:30 | FREQ=WEEKLY;BYDAY=FR | 284A Park Road, Point Cook VIC | Clients/North Side Physiotherapy/Main office - Point Cook | Office clean. Checklist: Clients/North Side Physiotherapy/Main office - Point Cook/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Call 0400 000 000 if the door is locked. Access details: Clients/North Side Physiotherapy/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1336 | Wave 4 West | CL55 Omar L. roster | Window clean - North Side Physiotherapy (Point Cook) | 2027-02-18 | 11:30 | 14:30 | FREQ=WEEKLY;INTERVAL=4;BYDAY=TH | 284A Park Road, Point Cook VIC | Clients/North Side Physiotherapy/Main office - Point Cook | Window clean. Checklist: Clients/North Side Physiotherapy/Main office - Point Cook/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]; Call 0400 000 000 if the door is locked. Access details: Clients/North Side Physiotherapy/Main office - Point Cook/02 Site Access (office will share). | No | 0
J1337 | Wave 1 North | CL21 Ana F. roster | Office clean - North Side Physiotherapy (Essendon) | 2027-01-11 | 19:00 | 22:00 | FREQ=WEEKLY;BYDAY=MO | 163 Barkly Highway, Essendon VIC | Clients/North Side Physiotherapy/Clinic - Essendon | Office clean. Checklist: Clients/North Side Physiotherapy/Clinic - Essendon/01 Scope & Checklist. Notes: -. Access details: Clients/North Side Physiotherapy/Clinic - Essendon/02 Site Access (office will share). | No | 0
J1338 | Wave 2 East | CL18 Rosa A. roster | Office clean - Bayview Accountants (Kew) | 2027-01-18 | 05:30 | 07:00 | FREQ=WEEKLY;BYDAY=MO | 448 Nicholson Street, Kew VIC | Clients/Bayview Accountants/Main office - Kew | Office clean. Checklist: Clients/Bayview Accountants/Main office - Kew/01 Scope & Checklist. Notes: Park in bay 12 under the building. Access details: Clients/Bayview Accountants/Main office - Kew/02 Site Access (office will share). | No | 0
J1339 | Wave 4 West | CL36 Pita F. roster | Office clean - Bay View Accountants (Maribyrnong) | 2027-02-02 | 17:30 | 19:30 | FREQ=WEEKLY;BYDAY=TU | 360 Burke Street, Maribyrnong VIC | Clients/Bay View Accountants/Main office - Maribyrnong | Office clean. Checklist: Clients/Bay View Accountants/Main office - Maribyrnong/01 Scope & Checklist. Notes: Key safe at side gate, code [in 02 Site Access]. Access details: Clients/Bay View Accountants/Main office - Maribyrnong/02 Site Access (office will share). | No | 0

## Drive Folders
Google Drive folder plan (shared drive: Clients)
Work sample: realistic data, built to show how I approach this work.
Path | Level | Cleaners | Office | Bookkeeper
Clients/Oakwood Vet Clinic | Client | - | Editor | Viewer
Clients/Oakwood Vet Clinic/Main office - Bentleigh | Location | - | Editor | -
Clients/Oakwood Vet Clinic/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Vet Clinic/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Vet Clinic/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Vet Clinic/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Vet Clinic/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Vet Clinic/Clinic - Oakleigh | Location | - | Editor | -
Clients/Oakwood Vet Clinic/Clinic - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Vet Clinic/Clinic - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Vet Clinic/Clinic - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Vet Clinic/Clinic - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Vet Clinic/Clinic - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Dental Pty Ltd | Client | - | Editor | Viewer
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park | Location | - | Editor | -
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Dental Pty Ltd/Main office - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Insurance Brokers Pty Ltd | Client | - | Editor | Viewer
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora | Location | - | Editor | -
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Insurance Brokers Pty Ltd/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray | Location | - | Editor | -
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Pathology Pty Ltd/Main office - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Westend Fitness Pty Ltd/Main office - Brighton | Location | - | Editor | -
Clients/Westend Fitness Pty Ltd/Main office - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Fitness Pty Ltd/Main office - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Westend Fitness Pty Ltd/Main office - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Fitness Pty Ltd/Main office - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Westend Fitness Pty Ltd/Main office - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Dental | Client | - | Editor | Viewer
Clients/Redgum Dental/Main office - Bundoora | Location | - | Editor | -
Clients/Redgum Dental/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Dental/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Redgum Dental/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Dental/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Dental/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Dental/Clinic - Werribee | Location | - | Editor | -
Clients/Redgum Dental/Clinic - Werribee/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Dental/Clinic - Werribee/02 Site Access | Folder | - | Editor | -
Clients/Redgum Dental/Clinic - Werribee/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Dental/Clinic - Werribee/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Dental/Clinic - Werribee/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Physiotherapy | Client | - | Editor | Viewer
Clients/Elm Street Physiotherapy/Main office - Oakleigh | Location | - | Editor | -
Clients/Elm Street Physiotherapy/Main office - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Physiotherapy/Main office - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Physiotherapy/Main office - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Physiotherapy/Main office - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Physiotherapy/Main office - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Physiotherapy/Clinic - Point Cook | Location | - | Editor | -
Clients/Elm Street Physiotherapy/Clinic - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Physiotherapy/Clinic - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Physiotherapy/Clinic - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Physiotherapy/Clinic - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Physiotherapy/Clinic - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Property Group | Client | - | Editor | Viewer
Clients/Wattle Grove Property Group/Main office - Hawthorn | Location | - | Editor | -
Clients/Wattle Grove Property Group/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Property Group/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Property Group/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Property Group/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Property Group/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Physiotherapy Pty Ltd | Client | - | Editor | Viewer
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping | Location | - | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Physiotherapy Pty Ltd/Main office - Epping/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury | Location | - | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Physiotherapy Pty Ltd/Clinic - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Real Estate | Client | - | Editor | Viewer
Clients/Kingsley Real Estate/Main office - Mitcham | Location | - | Editor | -
Clients/Kingsley Real Estate/Main office - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Real Estate/Main office - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Real Estate/Main office - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Real Estate/Main office - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Real Estate/Main office - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Real Estate/Clinic - Kew | Location | - | Editor | -
Clients/Kingsley Real Estate/Clinic - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Real Estate/Clinic - Kew/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Real Estate/Clinic - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Real Estate/Clinic - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Real Estate/Clinic - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Medical Centre Pty Ltd | Client | - | Editor | Viewer
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton | Location | - | Editor | -
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Medical Centre Pty Ltd/Main office - Clayton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Engineering | Client | - | Editor | Viewer
Clients/Bluestone Engineering/Main office - Coburg | Location | - | Editor | -
Clients/Bluestone Engineering/Main office - Coburg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Engineering/Main office - Coburg/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Engineering/Main office - Coburg/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Engineering/Main office - Coburg/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Engineering/Main office - Coburg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Insurance Brokers Pty Ltd | Client | - | Editor | Viewer
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone | Location | - | Editor | -
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Insurance Brokers Pty Ltd/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Optometrists Pty Ltd | Client | - | Editor | Viewer
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell | Location | - | Editor | -
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Optometrists Pty Ltd/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Accountants Pty Ltd | Client | - | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham | Location | - | Editor | -
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Northside Accountants Pty Ltd/Main office - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh | Location | - | Editor | -
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Northside Accountants Pty Ltd/Clinic - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton | Location | - | Editor | -
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/02 Site Access | Folder | - | Editor | -
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/04 Billing | Folder | - | Editor | Editor
Clients/Northside Accountants Pty Ltd/Warehouse - Clayton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Accountants Pty Ltd | Client | - | Editor | Viewer
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir | Location | - | Editor | -
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Accountants Pty Ltd/Main office - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Main office - St Kilda | Location | - | Editor | -
Clients/Northside Engineering Pty Ltd/Main office - St Kilda/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Engineering Pty Ltd/Main office - St Kilda/02 Site Access | Folder | - | Editor | -
Clients/Northside Engineering Pty Ltd/Main office - St Kilda/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Main office - St Kilda/04 Billing | Folder | - | Editor | Editor
Clients/Northside Engineering Pty Ltd/Main office - St Kilda/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh | Location | - | Editor | -
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Northside Engineering Pty Ltd/Clinic - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park | Location | - | Editor | -
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Northside Engineering Pty Ltd/Warehouse - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda | Location | - | Editor | -
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/02 Site Access | Folder | - | Editor | -
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/04 Billing | Folder | - | Editor | Editor
Clients/Northside Engineering Pty Ltd/Showroom - St Kilda/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Early Learning | Client | - | Editor | Viewer
Clients/Ashwood Early Learning/Main office - Camberwell | Location | - | Editor | -
Clients/Ashwood Early Learning/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Early Learning/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Early Learning/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Early Learning/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Early Learning/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Pharmacy | Client | - | Editor | Viewer
Clients/Silverton Pharmacy/Main office - Point Cook | Location | - | Editor | -
Clients/Silverton Pharmacy/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Pharmacy/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Silverton Pharmacy/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Pharmacy/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Pharmacy/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Pharmacy/Clinic - Kew | Location | - | Editor | -
Clients/Silverton Pharmacy/Clinic - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Pharmacy/Clinic - Kew/02 Site Access | Folder | - | Editor | -
Clients/Silverton Pharmacy/Clinic - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Pharmacy/Clinic - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Pharmacy/Clinic - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Pharmacy/Warehouse - Bundoora | Location | - | Editor | -
Clients/Silverton Pharmacy/Warehouse - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Pharmacy/Warehouse - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Silverton Pharmacy/Warehouse - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Pharmacy/Warehouse - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Pharmacy/Warehouse - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Pharmacy/Showroom - Footscray | Location | - | Editor | -
Clients/Silverton Pharmacy/Showroom - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Pharmacy/Showroom - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Silverton Pharmacy/Showroom - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Pharmacy/Showroom - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Pharmacy/Showroom - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Podiatry | Client | - | Editor | Viewer
Clients/Brightside Podiatry/Main office - Camberwell | Location | - | Editor | -
Clients/Brightside Podiatry/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Podiatry/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Brightside Podiatry/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Podiatry/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Podiatry/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Optometrists | Client | - | Editor | Viewer
Clients/Ashwood Optometrists/Main office - Ringwood | Location | - | Editor | -
Clients/Ashwood Optometrists/Main office - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Optometrists/Main office - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Optometrists/Main office - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Optometrists/Main office - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Optometrists/Main office - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Optometrists/Clinic - Ringwood | Location | - | Editor | -
Clients/Ashwood Optometrists/Clinic - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Optometrists/Clinic - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Optometrists/Clinic - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Optometrists/Clinic - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Optometrists/Clinic - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Accountants | Client | - | Editor | Viewer
Clients/Parkside Accountants/Main office - Bundoora | Location | - | Editor | -
Clients/Parkside Accountants/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Accountants/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Parkside Accountants/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Accountants/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Accountants/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Accountants/Clinic - Northcote | Location | - | Editor | -
Clients/Parkside Accountants/Clinic - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Accountants/Clinic - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Parkside Accountants/Clinic - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Accountants/Clinic - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Accountants/Clinic - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Motors Pty Ltd | Client | - | Editor | Viewer
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg | Location | - | Editor | -
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/02 Site Access | Folder | - | Editor | -
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Motors Pty Ltd/Main office - Heidelberg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Motors Pty Ltd | Client | - | Editor | Viewer
Clients/Westend Motors Pty Ltd/Main office - Sunshine | Location | - | Editor | -
Clients/Westend Motors Pty Ltd/Main office - Sunshine/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Motors Pty Ltd/Main office - Sunshine/02 Site Access | Folder | - | Editor | -
Clients/Westend Motors Pty Ltd/Main office - Sunshine/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Motors Pty Ltd/Main office - Sunshine/04 Billing | Folder | - | Editor | Editor
Clients/Westend Motors Pty Ltd/Main office - Sunshine/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Motors Pty Ltd/Clinic - Williamstown | Location | - | Editor | -
Clients/Westend Motors Pty Ltd/Clinic - Williamstown/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Motors Pty Ltd/Clinic - Williamstown/02 Site Access | Folder | - | Editor | -
Clients/Westend Motors Pty Ltd/Clinic - Williamstown/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Motors Pty Ltd/Clinic - Williamstown/04 Billing | Folder | - | Editor | Editor
Clients/Westend Motors Pty Ltd/Clinic - Williamstown/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Motors Pty Ltd/Warehouse - Epping | Location | - | Editor | -
Clients/Westend Motors Pty Ltd/Warehouse - Epping/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Motors Pty Ltd/Warehouse - Epping/02 Site Access | Folder | - | Editor | -
Clients/Westend Motors Pty Ltd/Warehouse - Epping/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Motors Pty Ltd/Warehouse - Epping/04 Billing | Folder | - | Editor | Editor
Clients/Westend Motors Pty Ltd/Warehouse - Epping/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin | Location | - | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Lawyers Pty Ltd/Main office - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon | Location | - | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Lawyers Pty Ltd/Clinic - Essendon/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Medical Centre | Client | - | Editor | Viewer
Clients/Riverside Medical Centre/Main office - Camberwell | Location | - | Editor | -
Clients/Riverside Medical Centre/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Medical Centre/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Riverside Medical Centre/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Medical Centre/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Medical Centre/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Motors Pty Ltd | Client | - | Editor | Viewer
Clients/Riverside Motors Pty Ltd/Main office - Altona | Location | - | Editor | -
Clients/Riverside Motors Pty Ltd/Main office - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Motors Pty Ltd/Main office - Altona/02 Site Access | Folder | - | Editor | -
Clients/Riverside Motors Pty Ltd/Main office - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Motors Pty Ltd/Main office - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Motors Pty Ltd/Main office - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville | Location | - | Editor | -
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/02 Site Access | Folder | - | Editor | -
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Pathology Pty Ltd/Main office - Yarraville/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Accountants Pty Ltd | Client | - | Editor | Viewer
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell | Location | - | Editor | -
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Accountants Pty Ltd/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Early Learning | Client | - | Editor | Viewer
Clients/Sunbury Early Learning/Main office - Glen Waverley | Location | - | Editor | -
Clients/Sunbury Early Learning/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Early Learning/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Early Learning/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Early Learning/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Early Learning/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury | Location | - | Editor | -
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Lawyers Pty Ltd/Main office - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Accountants Pty Ltd | Client | - | Editor | Viewer
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick | Location | - | Editor | -
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/02 Site Access | Folder | - | Editor | -
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Accountants Pty Ltd/Main office - Brunswick/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Podiatry | Client | - | Editor | Viewer
Clients/Westend Podiatry/Main office - Brunswick | Location | - | Editor | -
Clients/Westend Podiatry/Main office - Brunswick/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Podiatry/Main office - Brunswick/02 Site Access | Folder | - | Editor | -
Clients/Westend Podiatry/Main office - Brunswick/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Podiatry/Main office - Brunswick/04 Billing | Folder | - | Editor | Editor
Clients/Westend Podiatry/Main office - Brunswick/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Podiatry/Clinic - Thornbury | Location | - | Editor | -
Clients/Westend Podiatry/Clinic - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Podiatry/Clinic - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Westend Podiatry/Clinic - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Podiatry/Clinic - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Westend Podiatry/Clinic - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Podiatry/Warehouse - Essendon | Location | - | Editor | -
Clients/Westend Podiatry/Warehouse - Essendon/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Podiatry/Warehouse - Essendon/02 Site Access | Folder | - | Editor | -
Clients/Westend Podiatry/Warehouse - Essendon/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Podiatry/Warehouse - Essendon/04 Billing | Folder | - | Editor | Editor
Clients/Westend Podiatry/Warehouse - Essendon/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park | Location | - | Editor | -
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Engineering Pty Ltd/Main office - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong | Location | - | Editor | -
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Engineering Pty Ltd/Clinic - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Financial Planning | Client | - | Editor | Viewer
Clients/Kingsley Financial Planning/Main office - Oakleigh | Location | - | Editor | -
Clients/Kingsley Financial Planning/Main office - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Financial Planning/Main office - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Financial Planning/Main office - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Financial Planning/Main office - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Financial Planning/Main office - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Physiotherapy | Client | - | Editor | Viewer
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham | Location | - | Editor | -
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Physiotherapy/Main office - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn | Location | - | Editor | -
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Fitness Pty Ltd/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster | Location | - | Editor | -
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Fitness Pty Ltd/Clinic - Doncaster/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Dental | Client | - | Editor | Viewer
Clients/Wattle Grove Dental/Main office - Hawthorn | Location | - | Editor | -
Clients/Wattle Grove Dental/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Dental/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Dental/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Dental/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Dental/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Vet Clinic | Client | - | Editor | Viewer
Clients/Lakeside Vet Clinic/Main office - Point Cook | Location | - | Editor | -
Clients/Lakeside Vet Clinic/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Vet Clinic/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Vet Clinic/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Vet Clinic/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Vet Clinic/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Vet Clinic/Clinic - Laverton | Location | - | Editor | -
Clients/Lakeside Vet Clinic/Clinic - Laverton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Vet Clinic/Clinic - Laverton/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Vet Clinic/Clinic - Laverton/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Vet Clinic/Clinic - Laverton/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Vet Clinic/Clinic - Laverton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Property Group Pty Ltd | Client | - | Editor | Viewer
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston | Location | - | Editor | -
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Property Group Pty Ltd/Main office - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton | Location | - | Editor | -
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Property Group Pty Ltd/Clinic - Laverton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Eastwood Real Estate Pty Ltd | Client | - | Editor | Viewer
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn | Location | - | Editor | -
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Eastwood Real Estate Pty Ltd/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Physiotherapy | Client | - | Editor | Viewer
Clients/Clearwater Physiotherapy/Main office - Bentleigh | Location | - | Editor | -
Clients/Clearwater Physiotherapy/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Physiotherapy/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Physiotherapy/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Physiotherapy/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Physiotherapy/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Physiotherapy/Clinic - Burwood | Location | - | Editor | -
Clients/Clearwater Physiotherapy/Clinic - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Physiotherapy/Clinic - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Physiotherapy/Clinic - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Physiotherapy/Clinic - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Physiotherapy/Clinic - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Physiotherapy | Client | - | Editor | Viewer
Clients/Greenway Physiotherapy/Main office - Burwood | Location | - | Editor | -
Clients/Greenway Physiotherapy/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Physiotherapy/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Greenway Physiotherapy/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Physiotherapy/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Physiotherapy/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Fairfield Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh | Location | - | Editor | -
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Fairfield Engineering Pty Ltd/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham | Location | - | Editor | -
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Fairfield Engineering Pty Ltd/Clinic - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Optometrists Pty Ltd | Client | - | Editor | Viewer
Clients/Westend Optometrists Pty Ltd/Main office - Mentone | Location | - | Editor | -
Clients/Westend Optometrists Pty Ltd/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Optometrists Pty Ltd/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Westend Optometrists Pty Ltd/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Optometrists Pty Ltd/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Westend Optometrists Pty Ltd/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Insurance Brokers | Client | - | Editor | Viewer
Clients/Kingsley Insurance Brokers/Main office - Reservoir | Location | - | Editor | -
Clients/Kingsley Insurance Brokers/Main office - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Insurance Brokers/Main office - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Insurance Brokers/Main office - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Insurance Brokers/Main office - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Insurance Brokers/Main office - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Insurance Brokers/Clinic - Point Cook | Location | - | Editor | -
Clients/Kingsley Insurance Brokers/Clinic - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Insurance Brokers/Clinic - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Insurance Brokers/Clinic - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Insurance Brokers/Clinic - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Insurance Brokers/Clinic - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Learning Centre Pty Ltd | Client | - | Editor | Viewer
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley | Location | - | Editor | -
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Learning Centre Pty Ltd/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Logistics | Client | - | Editor | Viewer
Clients/Oakwood Logistics/Main office - Hawthorn | Location | - | Editor | -
Clients/Oakwood Logistics/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Logistics/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Logistics/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Logistics/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Logistics/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Logistics/Clinic - Blackburn | Location | - | Editor | -
Clients/Oakwood Logistics/Clinic - Blackburn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Logistics/Clinic - Blackburn/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Logistics/Clinic - Blackburn/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Logistics/Clinic - Blackburn/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Logistics/Clinic - Blackburn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Logistics/Warehouse - Cheltenham | Location | - | Editor | -
Clients/Oakwood Logistics/Warehouse - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Logistics/Warehouse - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Logistics/Warehouse - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Logistics/Warehouse - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Logistics/Warehouse - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Logistics/Showroom - Box Hill | Location | - | Editor | -
Clients/Oakwood Logistics/Showroom - Box Hill/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Logistics/Showroom - Box Hill/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Logistics/Showroom - Box Hill/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Logistics/Showroom - Box Hill/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Logistics/Showroom - Box Hill/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Insurance Brokers | Client | - | Editor | Viewer
Clients/Banksia Insurance Brokers/Main office - Burwood | Location | - | Editor | -
Clients/Banksia Insurance Brokers/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Insurance Brokers/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Banksia Insurance Brokers/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Insurance Brokers/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Insurance Brokers/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir | Location | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Lawyers Pty Ltd/Main office - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon | Location | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Lawyers Pty Ltd/Clinic - Essendon/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone | Location | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Lawyers Pty Ltd/Warehouse - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Cobblestone Real Estate Pty Ltd | Client | - | Editor | Viewer
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston | Location | - | Editor | -
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Cobblestone Real Estate Pty Ltd/Main office - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine | Location | - | Editor | -
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/02 Site Access | Folder | - | Editor | -
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Engineering Pty Ltd/Main office - Sunshine/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Financial Planning Pty Ltd | Client | - | Editor | Viewer
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton | Location | - | Editor | -
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Financial Planning Pty Ltd/Main office - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Dental Pty Ltd | Client | - | Editor | Viewer
Clients/Brightside Dental Pty Ltd/Main office - Dandenong | Location | - | Editor | -
Clients/Brightside Dental Pty Ltd/Main office - Dandenong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Dental Pty Ltd/Main office - Dandenong/02 Site Access | Folder | - | Editor | -
Clients/Brightside Dental Pty Ltd/Main office - Dandenong/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Dental Pty Ltd/Main office - Dandenong/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Dental Pty Ltd/Main office - Dandenong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin | Location | - | Editor | -
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Dental Pty Ltd/Clinic - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Physiotherapy | Client | - | Editor | Viewer
Clients/Ashwood Physiotherapy/Main office - Point Cook | Location | - | Editor | -
Clients/Ashwood Physiotherapy/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Physiotherapy/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Physiotherapy/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Physiotherapy/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Physiotherapy/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Physiotherapy/Clinic - Camberwell | Location | - | Editor | -
Clients/Ashwood Physiotherapy/Clinic - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Physiotherapy/Clinic - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Physiotherapy/Clinic - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Physiotherapy/Clinic - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Physiotherapy/Clinic - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Physiotherapy/Warehouse - Coburg | Location | - | Editor | -
Clients/Ashwood Physiotherapy/Warehouse - Coburg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Physiotherapy/Warehouse - Coburg/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Physiotherapy/Warehouse - Coburg/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Physiotherapy/Warehouse - Coburg/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Physiotherapy/Warehouse - Coburg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Physiotherapy/Showroom - Footscray | Location | - | Editor | -
Clients/Ashwood Physiotherapy/Showroom - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Physiotherapy/Showroom - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Physiotherapy/Showroom - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Physiotherapy/Showroom - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Physiotherapy/Showroom - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Dental | Client | - | Editor | Viewer
Clients/Bluestone Dental/Main office - Camberwell | Location | - | Editor | -
Clients/Bluestone Dental/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Dental/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Dental/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Dental/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Dental/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Dental/Clinic - Burwood | Location | - | Editor | -
Clients/Bluestone Dental/Clinic - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Dental/Clinic - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Dental/Clinic - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Dental/Clinic - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Dental/Clinic - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Dental/Warehouse - Burwood | Location | - | Editor | -
Clients/Bluestone Dental/Warehouse - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Dental/Warehouse - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Dental/Warehouse - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Dental/Warehouse - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Dental/Warehouse - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Dental/Showroom - Ringwood | Location | - | Editor | -
Clients/Bluestone Dental/Showroom - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Dental/Showroom - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Dental/Showroom - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Dental/Showroom - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Dental/Showroom - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Accountants | Client | - | Editor | Viewer
Clients/Kingsley Accountants/Main office - Altona | Location | - | Editor | -
Clients/Kingsley Accountants/Main office - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Accountants/Main office - Altona/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Accountants/Main office - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Accountants/Main office - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Accountants/Main office - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Early Learning Pty Ltd | Client | - | Editor | Viewer
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote | Location | - | Editor | -
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Early Learning Pty Ltd/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park | Location | - | Editor | -
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Pathology Pty Ltd/Main office - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Financial Planning Pty Ltd | Client | - | Editor | Viewer
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn | Location | - | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/02 Site Access | Folder | - | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Financial Planning Pty Ltd/Main office - Blackburn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh | Location | - | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Financial Planning Pty Ltd/Clinic - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood | Location | - | Editor | -
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Lawyers Pty Ltd/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley | Location | - | Editor | -
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Lawyers Pty Ltd/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Accountants | Client | - | Editor | Viewer
Clients/Banksia Accountants/Main office - Altona | Location | - | Editor | -
Clients/Banksia Accountants/Main office - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Accountants/Main office - Altona/02 Site Access | Folder | - | Editor | -
Clients/Banksia Accountants/Main office - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Accountants/Main office - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Accountants/Main office - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Accountants/Clinic - Doncaster | Location | - | Editor | -
Clients/Banksia Accountants/Clinic - Doncaster/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Accountants/Clinic - Doncaster/02 Site Access | Folder | - | Editor | -
Clients/Banksia Accountants/Clinic - Doncaster/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Accountants/Clinic - Doncaster/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Accountants/Clinic - Doncaster/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Accountants/Warehouse - Glen Waverley | Location | - | Editor | -
Clients/Banksia Accountants/Warehouse - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Accountants/Warehouse - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Banksia Accountants/Warehouse - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Accountants/Warehouse - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Accountants/Warehouse - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Physiotherapy Pty Ltd | Client | - | Editor | Viewer
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook | Location | - | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Physiotherapy Pty Ltd/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook | Location | - | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Physiotherapy Pty Ltd/Clinic - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Lawyers Pty Ltd | Client | - | Editor | Viewer
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook | Location | - | Editor | -
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Lawyers Pty Ltd/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Medical Centre Pty Ltd | Client | - | Editor | Viewer
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook | Location | - | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Medical Centre Pty Ltd/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn | Location | - | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Medical Centre Pty Ltd/Clinic - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Engineering | Client | - | Editor | Viewer
Clients/Ashwood Engineering/Main office - Glen Waverley | Location | - | Editor | -
Clients/Ashwood Engineering/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Engineering/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Engineering/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Engineering/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Engineering/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd | Client | - | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook | Location | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Physiotherapy Pty Ltd/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston | Location | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Physiotherapy Pty Ltd/Clinic - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn | Location | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Physiotherapy Pty Ltd/Warehouse - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Eastwood Pathology | Client | - | Editor | Viewer
Clients/Eastwood Pathology/Main office - Werribee | Location | - | Editor | -
Clients/Eastwood Pathology/Main office - Werribee/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Eastwood Pathology/Main office - Werribee/02 Site Access | Folder | - | Editor | -
Clients/Eastwood Pathology/Main office - Werribee/03 Agreements | Folder | - | Editor | Viewer
Clients/Eastwood Pathology/Main office - Werribee/04 Billing | Folder | - | Editor | Editor
Clients/Eastwood Pathology/Main office - Werribee/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Waverley Fitness Pty Ltd/Main office - Footscray | Location | - | Editor | -
Clients/Waverley Fitness Pty Ltd/Main office - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Fitness Pty Ltd/Main office - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Waverley Fitness Pty Ltd/Main office - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Fitness Pty Ltd/Main office - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Fitness Pty Ltd/Main office - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray | Location | - | Editor | -
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Fitness Pty Ltd/Clinic - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Clearwater Logistics | Client | - | Editor | Viewer
Clients/Clearwater Logistics/Main office - Reservoir | Location | - | Editor | -
Clients/Clearwater Logistics/Main office - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Clearwater Logistics/Main office - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Clearwater Logistics/Main office - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Clearwater Logistics/Main office - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Clearwater Logistics/Main office - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Fitness | Client | - | Editor | Viewer
Clients/Wattle Grove Fitness/Main office - Essendon | Location | - | Editor | -
Clients/Wattle Grove Fitness/Main office - Essendon/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Fitness/Main office - Essendon/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Fitness/Main office - Essendon/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Fitness/Main office - Essendon/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Fitness/Main office - Essendon/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Fitness/Clinic - St Kilda | Location | - | Editor | -
Clients/Wattle Grove Fitness/Clinic - St Kilda/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Fitness/Clinic - St Kilda/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Fitness/Clinic - St Kilda/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Fitness/Clinic - St Kilda/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Fitness/Clinic - St Kilda/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Medical Centre | Client | - | Editor | Viewer
Clients/Ashwood Medical Centre/Main office - Bundoora | Location | - | Editor | -
Clients/Ashwood Medical Centre/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Medical Centre/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Medical Centre/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Medical Centre/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Medical Centre/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Vet Clinic | Client | - | Editor | Viewer
Clients/Parkside Vet Clinic/Main office - Deer Park | Location | - | Editor | -
Clients/Parkside Vet Clinic/Main office - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Vet Clinic/Main office - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Parkside Vet Clinic/Main office - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Vet Clinic/Main office - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Vet Clinic/Main office - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Architects | Client | - | Editor | Viewer
Clients/Wattle Grove Architects/Main office - Bentleigh | Location | - | Editor | -
Clients/Wattle Grove Architects/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Architects/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Architects/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Architects/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Architects/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Pharmacy Pty Ltd | Client | - | Editor | Viewer
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray | Location | - | Editor | -
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Pharmacy Pty Ltd/Main office - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Accountants | Client | - | Editor | Viewer
Clients/Hillcrest Accountants/Main office - Mitcham | Location | - | Editor | -
Clients/Hillcrest Accountants/Main office - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Accountants/Main office - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Accountants/Main office - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Accountants/Main office - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Accountants/Main office - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Architects | Client | - | Editor | Viewer
Clients/Lakeside Architects/Main office - Reservoir | Location | - | Editor | -
Clients/Lakeside Architects/Main office - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Architects/Main office - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Architects/Main office - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Architects/Main office - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Architects/Main office - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Architects/Clinic - Mitcham | Location | - | Editor | -
Clients/Lakeside Architects/Clinic - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Architects/Clinic - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Architects/Clinic - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Architects/Clinic - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Architects/Clinic - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Accountants | Client | - | Editor | Viewer
Clients/Ashwood Accountants/Main office - Yarraville | Location | - | Editor | -
Clients/Ashwood Accountants/Main office - Yarraville/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Accountants/Main office - Yarraville/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Accountants/Main office - Yarraville/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Accountants/Main office - Yarraville/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Accountants/Main office - Yarraville/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Property Group | Client | - | Editor | Viewer
Clients/Westend Property Group/Main office - Heidelberg | Location | - | Editor | -
Clients/Westend Property Group/Main office - Heidelberg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Property Group/Main office - Heidelberg/02 Site Access | Folder | - | Editor | -
Clients/Westend Property Group/Main office - Heidelberg/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Property Group/Main office - Heidelberg/04 Billing | Folder | - | Editor | Editor
Clients/Westend Property Group/Main office - Heidelberg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Eastwood Optometrists | Client | - | Editor | Viewer
Clients/Eastwood Optometrists/Main office - Burwood | Location | - | Editor | -
Clients/Eastwood Optometrists/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Eastwood Optometrists/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Eastwood Optometrists/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Eastwood Optometrists/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Eastwood Optometrists/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Eastwood Optometrists/Clinic - Mitcham | Location | - | Editor | -
Clients/Eastwood Optometrists/Clinic - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Eastwood Optometrists/Clinic - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Eastwood Optometrists/Clinic - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Eastwood Optometrists/Clinic - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Eastwood Optometrists/Clinic - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Medical Centre | Client | - | Editor | Viewer
Clients/Westend Medical Centre/Main office - Sunshine | Location | - | Editor | -
Clients/Westend Medical Centre/Main office - Sunshine/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Medical Centre/Main office - Sunshine/02 Site Access | Folder | - | Editor | -
Clients/Westend Medical Centre/Main office - Sunshine/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Medical Centre/Main office - Sunshine/04 Billing | Folder | - | Editor | Editor
Clients/Westend Medical Centre/Main office - Sunshine/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Learning Centre | Client | - | Editor | Viewer
Clients/Riverside Learning Centre/Main office - Mentone | Location | - | Editor | -
Clients/Riverside Learning Centre/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Learning Centre/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Riverside Learning Centre/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Learning Centre/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Learning Centre/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Learning Centre/Clinic - Cheltenham | Location | - | Editor | -
Clients/Riverside Learning Centre/Clinic - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Learning Centre/Clinic - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Riverside Learning Centre/Clinic - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Learning Centre/Clinic - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Learning Centre/Clinic - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Learning Centre/Warehouse - Moorabbin | Location | - | Editor | -
Clients/Riverside Learning Centre/Warehouse - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Learning Centre/Warehouse - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Riverside Learning Centre/Warehouse - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Learning Centre/Warehouse - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Learning Centre/Warehouse - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd | Client | - | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham | Location | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Insurance Brokers Pty Ltd/Main office - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston | Location | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Insurance Brokers Pty Ltd/Clinic - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley | Location | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Insurance Brokers Pty Ltd/Warehouse - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Podiatry Pty Ltd | Client | - | Editor | Viewer
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood | Location | - | Editor | -
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Podiatry Pty Ltd/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Logistics | Client | - | Editor | Viewer
Clients/Banksia Logistics/Main office - Northcote | Location | - | Editor | -
Clients/Banksia Logistics/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Logistics/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Banksia Logistics/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Logistics/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Logistics/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Logistics/Clinic - Northcote | Location | - | Editor | -
Clients/Banksia Logistics/Clinic - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Logistics/Clinic - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Banksia Logistics/Clinic - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Logistics/Clinic - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Logistics/Clinic - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Logistics/Warehouse - Thornbury | Location | - | Editor | -
Clients/Banksia Logistics/Warehouse - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Logistics/Warehouse - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Banksia Logistics/Warehouse - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Logistics/Warehouse - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Logistics/Warehouse - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Architects Pty Ltd | Client | - | Editor | Viewer
Clients/Sunbury Architects Pty Ltd/Main office - Epping | Location | - | Editor | -
Clients/Sunbury Architects Pty Ltd/Main office - Epping/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Architects Pty Ltd/Main office - Epping/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Architects Pty Ltd/Main office - Epping/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Architects Pty Ltd/Main office - Epping/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Architects Pty Ltd/Main office - Epping/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Cobblestone Physiotherapy Pty Ltd | Client | - | Editor | Viewer
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora | Location | - | Editor | -
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Cobblestone Physiotherapy Pty Ltd/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Real Estate | Client | - | Editor | Viewer
Clients/Banksia Real Estate/Main office - Maribyrnong | Location | - | Editor | -
Clients/Banksia Real Estate/Main office - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Real Estate/Main office - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Banksia Real Estate/Main office - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Real Estate/Main office - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Real Estate/Main office - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Northside Pathology Pty Ltd/Main office - Ringwood | Location | - | Editor | -
Clients/Northside Pathology Pty Ltd/Main office - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Pathology Pty Ltd/Main office - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Northside Pathology Pty Ltd/Main office - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Pathology Pty Ltd/Main office - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Northside Pathology Pty Ltd/Main office - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Lawyers | Client | - | Editor | Viewer
Clients/Harbourside Lawyers/Main office - Glen Waverley | Location | - | Editor | -
Clients/Harbourside Lawyers/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Lawyers/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Lawyers/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Lawyers/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Lawyers/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Kingsley Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee | Location | - | Editor | -
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/02 Site Access | Folder | - | Editor | -
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/03 Agreements | Folder | - | Editor | Viewer
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/04 Billing | Folder | - | Editor | Editor
Clients/Kingsley Fitness Pty Ltd/Main office - Werribee/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Optometrists | Client | - | Editor | Viewer
Clients/Lakeside Optometrists/Main office - Footscray | Location | - | Editor | -
Clients/Lakeside Optometrists/Main office - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Optometrists/Main office - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Optometrists/Main office - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Optometrists/Main office - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Optometrists/Main office - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Dental | Client | - | Editor | Viewer
Clients/Southgate Dental/Main office - Hawthorn | Location | - | Editor | -
Clients/Southgate Dental/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Dental/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Southgate Dental/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Dental/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Dental/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Optometrists | Client | - | Editor | Viewer
Clients/Sunbury Optometrists/Main office - Altona | Location | - | Editor | -
Clients/Sunbury Optometrists/Main office - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Optometrists/Main office - Altona/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Optometrists/Main office - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Optometrists/Main office - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Optometrists/Main office - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Vet Clinic | Client | - | Editor | Viewer
Clients/Bayview Vet Clinic/Main office - Coburg | Location | - | Editor | -
Clients/Bayview Vet Clinic/Main office - Coburg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Vet Clinic/Main office - Coburg/02 Site Access | Folder | - | Editor | -
Clients/Bayview Vet Clinic/Main office - Coburg/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Vet Clinic/Main office - Coburg/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Vet Clinic/Main office - Coburg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Vet Clinic/Clinic - Reservoir | Location | - | Editor | -
Clients/Bayview Vet Clinic/Clinic - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Vet Clinic/Clinic - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Bayview Vet Clinic/Clinic - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Vet Clinic/Clinic - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Vet Clinic/Clinic - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell | Location | - | Editor | -
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Pathology Pty Ltd/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Medical Centre Pty Ltd | Client | - | Editor | Viewer
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley | Location | - | Editor | -
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Medical Centre Pty Ltd/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Physiotherapy | Client | - | Editor | Viewer
Clients/Westend Physiotherapy/Main office - Glen Waverley | Location | - | Editor | -
Clients/Westend Physiotherapy/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Physiotherapy/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Westend Physiotherapy/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Physiotherapy/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Westend Physiotherapy/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Podiatry | Client | - | Editor | Viewer
Clients/Riverside Podiatry/Main office - Point Cook | Location | - | Editor | -
Clients/Riverside Podiatry/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Podiatry/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Riverside Podiatry/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Podiatry/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Podiatry/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Podiatry/Clinic - Brighton | Location | - | Editor | -
Clients/Riverside Podiatry/Clinic - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Podiatry/Clinic - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Riverside Podiatry/Clinic - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Podiatry/Clinic - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Podiatry/Clinic - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Learning Centre | Client | - | Editor | Viewer
Clients/Northside Learning Centre/Main office - Camberwell | Location | - | Editor | -
Clients/Northside Learning Centre/Main office - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Learning Centre/Main office - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Northside Learning Centre/Main office - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Learning Centre/Main office - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Northside Learning Centre/Main office - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Logistics Pty Ltd | Client | - | Editor | Viewer
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn | Location | - | Editor | -
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Logistics Pty Ltd/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew | Location | - | Editor | -
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Logistics Pty Ltd/Clinic - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Podiatry | Client | - | Editor | Viewer
Clients/Redgum Podiatry/Main office - Williamstown | Location | - | Editor | -
Clients/Redgum Podiatry/Main office - Williamstown/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Podiatry/Main office - Williamstown/02 Site Access | Folder | - | Editor | -
Clients/Redgum Podiatry/Main office - Williamstown/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Podiatry/Main office - Williamstown/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Podiatry/Main office - Williamstown/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Podiatry/Clinic - Cheltenham | Location | - | Editor | -
Clients/Redgum Podiatry/Clinic - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Podiatry/Clinic - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Redgum Podiatry/Clinic - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Podiatry/Clinic - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Podiatry/Clinic - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Chiropractic | Client | - | Editor | Viewer
Clients/Harbourside Chiropractic/Main office - Oakleigh | Location | - | Editor | -
Clients/Harbourside Chiropractic/Main office - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Chiropractic/Main office - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Chiropractic/Main office - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Chiropractic/Main office - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Chiropractic/Main office - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Chiropractic/Clinic - Moorabbin | Location | - | Editor | -
Clients/Harbourside Chiropractic/Clinic - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Chiropractic/Clinic - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Chiropractic/Clinic - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Chiropractic/Clinic - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Chiropractic/Clinic - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Chiropractic/Warehouse - St Kilda | Location | - | Editor | -
Clients/Harbourside Chiropractic/Warehouse - St Kilda/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Chiropractic/Warehouse - St Kilda/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Chiropractic/Warehouse - St Kilda/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Chiropractic/Warehouse - St Kilda/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Chiropractic/Warehouse - St Kilda/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Lawyers | Client | - | Editor | Viewer
Clients/Hillcrest Lawyers/Main office - Mentone | Location | - | Editor | -
Clients/Hillcrest Lawyers/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Lawyers/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Lawyers/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Lawyers/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Lawyers/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Lawyers/Clinic - Northcote | Location | - | Editor | -
Clients/Hillcrest Lawyers/Clinic - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Lawyers/Clinic - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Lawyers/Clinic - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Lawyers/Clinic - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Lawyers/Clinic - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Logistics Pty Ltd | Client | - | Editor | Viewer
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick | Location | - | Editor | -
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/02 Site Access | Folder | - | Editor | -
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Logistics Pty Ltd/Main office - Brunswick/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston | Location | - | Editor | -
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Silverton Logistics Pty Ltd/Clinic - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Hillcrest Motors Pty Ltd | Client | - | Editor | Viewer
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh | Location | - | Editor | -
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Hillcrest Motors Pty Ltd/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Pathology | Client | - | Editor | Viewer
Clients/Southgate Pathology/Main office - Brunswick | Location | - | Editor | -
Clients/Southgate Pathology/Main office - Brunswick/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Pathology/Main office - Brunswick/02 Site Access | Folder | - | Editor | -
Clients/Southgate Pathology/Main office - Brunswick/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Pathology/Main office - Brunswick/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Pathology/Main office - Brunswick/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Pathology/Clinic - Hawthorn | Location | - | Editor | -
Clients/Southgate Pathology/Clinic - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Pathology/Clinic - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Southgate Pathology/Clinic - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Pathology/Clinic - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Pathology/Clinic - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Pathology/Warehouse - Altona | Location | - | Editor | -
Clients/Southgate Pathology/Warehouse - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Pathology/Warehouse - Altona/02 Site Access | Folder | - | Editor | -
Clients/Southgate Pathology/Warehouse - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Pathology/Warehouse - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Pathology/Warehouse - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Engineering | Client | - | Editor | Viewer
Clients/Westend Engineering/Main office - Deer Park | Location | - | Editor | -
Clients/Westend Engineering/Main office - Deer Park/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Engineering/Main office - Deer Park/02 Site Access | Folder | - | Editor | -
Clients/Westend Engineering/Main office - Deer Park/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Engineering/Main office - Deer Park/04 Billing | Folder | - | Editor | Editor
Clients/Westend Engineering/Main office - Deer Park/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Westend Engineering/Clinic - Reservoir | Location | - | Editor | -
Clients/Westend Engineering/Clinic - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Westend Engineering/Clinic - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Westend Engineering/Clinic - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Westend Engineering/Clinic - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Westend Engineering/Clinic - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd | Client | - | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick | Location | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Real Estate Pty Ltd/Main office - Brunswick/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston | Location | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Real Estate Pty Ltd/Clinic - Preston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham | Location | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Real Estate Pty Ltd/Warehouse - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Pharmacy Pty Ltd | Client | - | Editor | Viewer
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville | Location | - | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Pharmacy Pty Ltd/Main office - Yarraville/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown | Location | - | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Pharmacy Pty Ltd/Clinic - Williamstown/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Early Learning Pty Ltd | Client | - | Editor | Viewer
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray | Location | - | Editor | -
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/02 Site Access | Folder | - | Editor | -
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Early Learning Pty Ltd/Main office - Footscray/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Southgate Engineering | Client | - | Editor | Viewer
Clients/Southgate Engineering/Main office - Frankston | Location | - | Editor | -
Clients/Southgate Engineering/Main office - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Southgate Engineering/Main office - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Southgate Engineering/Main office - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Southgate Engineering/Main office - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Southgate Engineering/Main office - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Dental Pty Ltd | Client | - | Editor | Viewer
Clients/Riverside Dental Pty Ltd/Main office - Northcote | Location | - | Editor | -
Clients/Riverside Dental Pty Ltd/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Dental Pty Ltd/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Riverside Dental Pty Ltd/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Dental Pty Ltd/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Dental Pty Ltd/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Early Learning | Client | - | Editor | Viewer
Clients/Bayview Early Learning/Main office - Laverton | Location | - | Editor | -
Clients/Bayview Early Learning/Main office - Laverton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Early Learning/Main office - Laverton/02 Site Access | Folder | - | Editor | -
Clients/Bayview Early Learning/Main office - Laverton/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Early Learning/Main office - Laverton/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Early Learning/Main office - Laverton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Early Learning/Clinic - Brighton | Location | - | Editor | -
Clients/Bayview Early Learning/Clinic - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Early Learning/Clinic - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Bayview Early Learning/Clinic - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Early Learning/Clinic - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Early Learning/Clinic - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Financial Planning Pty Ltd | Client | - | Editor | Viewer
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville | Location | - | Editor | -
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Financial Planning Pty Ltd/Main office - Yarraville/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Property Group | Client | - | Editor | Viewer
Clients/Ashwood Property Group/Main office - Cheltenham | Location | - | Editor | -
Clients/Ashwood Property Group/Main office - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Property Group/Main office - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Property Group/Main office - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Property Group/Main office - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Property Group/Main office - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Early Learning Pty Ltd | Client | - | Editor | Viewer
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh | Location | - | Editor | -
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Northside Early Learning Pty Ltd/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Brightside Logistics Pty Ltd | Client | - | Editor | Viewer
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh | Location | - | Editor | -
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Brightside Logistics Pty Ltd/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Early Learning | Client | - | Editor | Viewer
Clients/Elm Street Early Learning/Main office - Hawthorn | Location | - | Editor | -
Clients/Elm Street Early Learning/Main office - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Early Learning/Main office - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Early Learning/Main office - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Early Learning/Main office - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Early Learning/Main office - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Early Learning/Clinic - Camberwell | Location | - | Editor | -
Clients/Elm Street Early Learning/Clinic - Camberwell/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Early Learning/Clinic - Camberwell/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Early Learning/Clinic - Camberwell/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Early Learning/Clinic - Camberwell/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Early Learning/Clinic - Camberwell/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Early Learning/Warehouse - Glen Waverley | Location | - | Editor | -
Clients/Elm Street Early Learning/Warehouse - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Early Learning/Warehouse - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Early Learning/Warehouse - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Early Learning/Warehouse - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Early Learning/Warehouse - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Financial Planning | Client | - | Editor | Viewer
Clients/Redgum Financial Planning/Main office - Williamstown | Location | - | Editor | -
Clients/Redgum Financial Planning/Main office - Williamstown/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Financial Planning/Main office - Williamstown/02 Site Access | Folder | - | Editor | -
Clients/Redgum Financial Planning/Main office - Williamstown/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Financial Planning/Main office - Williamstown/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Financial Planning/Main office - Williamstown/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Redgum Financial Planning/Clinic - Epping | Location | - | Editor | -
Clients/Redgum Financial Planning/Clinic - Epping/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Redgum Financial Planning/Clinic - Epping/02 Site Access | Folder | - | Editor | -
Clients/Redgum Financial Planning/Clinic - Epping/03 Agreements | Folder | - | Editor | Viewer
Clients/Redgum Financial Planning/Clinic - Epping/04 Billing | Folder | - | Editor | Editor
Clients/Redgum Financial Planning/Clinic - Epping/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham | Location | - | Editor | -
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Fitness Pty Ltd/Main office - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd | Client | - | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Main office - Kew | Location | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Main office - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Logistics Pty Ltd/Main office - Kew/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Main office - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Main office - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Logistics Pty Ltd/Main office - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood | Location | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Logistics Pty Ltd/Clinic - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn | Location | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Logistics Pty Ltd/Warehouse - Blackburn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Lakeside Insurance Brokers | Client | - | Editor | Viewer
Clients/Lakeside Insurance Brokers/Main office - Sunshine | Location | - | Editor | -
Clients/Lakeside Insurance Brokers/Main office - Sunshine/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Lakeside Insurance Brokers/Main office - Sunshine/02 Site Access | Folder | - | Editor | -
Clients/Lakeside Insurance Brokers/Main office - Sunshine/03 Agreements | Folder | - | Editor | Viewer
Clients/Lakeside Insurance Brokers/Main office - Sunshine/04 Billing | Folder | - | Editor | Editor
Clients/Lakeside Insurance Brokers/Main office - Sunshine/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Pathology Pty Ltd | Client | - | Editor | Viewer
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong | Location | - | Editor | -
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Pathology Pty Ltd/Main office - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Fairfield Accountants Pty Ltd | Client | - | Editor | Viewer
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong | Location | - | Editor | -
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/02 Site Access | Folder | - | Editor | -
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/03 Agreements | Folder | - | Editor | Viewer
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/04 Billing | Folder | - | Editor | Editor
Clients/Fairfield Accountants Pty Ltd/Main office - Dandenong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin | Location | - | Editor | -
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Fairfield Accountants Pty Ltd/Clinic - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Fairfield Dental | Client | - | Editor | Viewer
Clients/Fairfield Dental/Main office - Box Hill | Location | - | Editor | -
Clients/Fairfield Dental/Main office - Box Hill/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Fairfield Dental/Main office - Box Hill/02 Site Access | Folder | - | Editor | -
Clients/Fairfield Dental/Main office - Box Hill/03 Agreements | Folder | - | Editor | Viewer
Clients/Fairfield Dental/Main office - Box Hill/04 Billing | Folder | - | Editor | Editor
Clients/Fairfield Dental/Main office - Box Hill/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Medical Centre Pty Ltd | Client | - | Editor | Viewer
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg | Location | - | Editor | -
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Medical Centre Pty Ltd/Main office - Coburg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Banksia Architects Pty Ltd | Client | - | Editor | Viewer
Clients/Banksia Architects Pty Ltd/Main office - Frankston | Location | - | Editor | -
Clients/Banksia Architects Pty Ltd/Main office - Frankston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Banksia Architects Pty Ltd/Main office - Frankston/02 Site Access | Folder | - | Editor | -
Clients/Banksia Architects Pty Ltd/Main office - Frankston/03 Agreements | Folder | - | Editor | Viewer
Clients/Banksia Architects Pty Ltd/Main office - Frankston/04 Billing | Folder | - | Editor | Editor
Clients/Banksia Architects Pty Ltd/Main office - Frankston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Ironbark Engineering Pty Ltd/Main office - Preston | Location | - | Editor | -
Clients/Ironbark Engineering Pty Ltd/Main office - Preston/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Engineering Pty Ltd/Main office - Preston/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Engineering Pty Ltd/Main office - Preston/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Engineering Pty Ltd/Main office - Preston/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Engineering Pty Ltd/Main office - Preston/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury | Location | - | Editor | -
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Engineering Pty Ltd/Clinic - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Wattle Grove Financial Planning | Client | - | Editor | Viewer
Clients/Wattle Grove Financial Planning/Main office - Northcote | Location | - | Editor | -
Clients/Wattle Grove Financial Planning/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Wattle Grove Financial Planning/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Wattle Grove Financial Planning/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Wattle Grove Financial Planning/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Wattle Grove Financial Planning/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Parkside Fitness Pty Ltd/Main office - Burwood | Location | - | Editor | -
Clients/Parkside Fitness Pty Ltd/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Fitness Pty Ltd/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Parkside Fitness Pty Ltd/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Fitness Pty Ltd/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Fitness Pty Ltd/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong | Location | - | Editor | -
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Fitness Pty Ltd/Clinic - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd | Client | - | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood | Location | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/02 Site Access | Folder | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Chiropractic Pty Ltd/Main office - Ringwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew | Location | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/02 Site Access | Folder | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Chiropractic Pty Ltd/Clinic - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood | Location | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Greenway Chiropractic Pty Ltd/Warehouse - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Real Estate Pty Ltd | Client | - | Editor | Viewer
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton | Location | - | Editor | -
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Real Estate Pty Ltd/Main office - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Pharmacy | Client | - | Editor | Viewer
Clients/Riverside Pharmacy/Main office - Box Hill | Location | - | Editor | -
Clients/Riverside Pharmacy/Main office - Box Hill/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Pharmacy/Main office - Box Hill/02 Site Access | Folder | - | Editor | -
Clients/Riverside Pharmacy/Main office - Box Hill/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Pharmacy/Main office - Box Hill/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Pharmacy/Main office - Box Hill/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Pharmacy/Clinic - Glen Waverley | Location | - | Editor | -
Clients/Riverside Pharmacy/Clinic - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Pharmacy/Clinic - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Riverside Pharmacy/Clinic - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Pharmacy/Clinic - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Pharmacy/Clinic - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Chiropractic Pty Ltd | Client | - | Editor | Viewer
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone | Location | - | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Chiropractic Pty Ltd/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham | Location | - | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Chiropractic Pty Ltd/Clinic - Cheltenham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Real Estate Pty Ltd | Client | - | Editor | Viewer
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh | Location | - | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Real Estate Pty Ltd/Main office - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh | Location | - | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Real Estate Pty Ltd/Clinic - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Motors | Client | - | Editor | Viewer
Clients/Elm Street Motors/Main office - Brighton | Location | - | Editor | -
Clients/Elm Street Motors/Main office - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Motors/Main office - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Motors/Main office - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Motors/Main office - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Motors/Main office - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Elm Street Motors/Clinic - Oakleigh | Location | - | Editor | -
Clients/Elm Street Motors/Clinic - Oakleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Elm Street Motors/Clinic - Oakleigh/02 Site Access | Folder | - | Editor | -
Clients/Elm Street Motors/Clinic - Oakleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Elm Street Motors/Clinic - Oakleigh/04 Billing | Folder | - | Editor | Editor
Clients/Elm Street Motors/Clinic - Oakleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Sunbury Engineering | Client | - | Editor | Viewer
Clients/Sunbury Engineering/Main office - Point Cook | Location | - | Editor | -
Clients/Sunbury Engineering/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Sunbury Engineering/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Sunbury Engineering/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Sunbury Engineering/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Sunbury Engineering/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Dental Pty Ltd | Client | - | Editor | Viewer
Clients/Ashwood Dental Pty Ltd/Main office - Northcote | Location | - | Editor | -
Clients/Ashwood Dental Pty Ltd/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Dental Pty Ltd/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Dental Pty Ltd/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Dental Pty Ltd/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Dental Pty Ltd/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone | Location | - | Editor | -
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Dental Pty Ltd/Clinic - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Early Learning Pty Ltd | Client | - | Editor | Viewer
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona | Location | - | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Early Learning Pty Ltd/Main office - Altona/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn | Location | - | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/02 Site Access | Folder | - | Editor | -
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/03 Agreements | Folder | - | Editor | Viewer
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/04 Billing | Folder | - | Editor | Editor
Clients/Bluestone Early Learning Pty Ltd/Clinic - Hawthorn/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Property Group | Client | - | Editor | Viewer
Clients/Harbourside Property Group/Main office - Maribyrnong | Location | - | Editor | -
Clients/Harbourside Property Group/Main office - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Property Group/Main office - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Property Group/Main office - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Property Group/Main office - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Property Group/Main office - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Riverside Engineering Pty Ltd | Client | - | Editor | Viewer
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora | Location | - | Editor | -
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/02 Site Access | Folder | - | Editor | -
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/03 Agreements | Folder | - | Editor | Viewer
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/04 Billing | Folder | - | Editor | Editor
Clients/Riverside Engineering Pty Ltd/Main office - Bundoora/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ashwood Lawyers | Client | - | Editor | Viewer
Clients/Ashwood Lawyers/Main office - Werribee | Location | - | Editor | -
Clients/Ashwood Lawyers/Main office - Werribee/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ashwood Lawyers/Main office - Werribee/02 Site Access | Folder | - | Editor | -
Clients/Ashwood Lawyers/Main office - Werribee/03 Agreements | Folder | - | Editor | Viewer
Clients/Ashwood Lawyers/Main office - Werribee/04 Billing | Folder | - | Editor | Editor
Clients/Ashwood Lawyers/Main office - Werribee/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Fitness Pty Ltd | Client | - | Editor | Viewer
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury | Location | - | Editor | -
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/02 Site Access | Folder | - | Editor | -
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Fitness Pty Ltd/Main office - Thornbury/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Property Group Pty Ltd | Client | - | Editor | Viewer
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham | Location | - | Editor | -
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Property Group Pty Ltd/Main office - Mitcham/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir | Location | - | Editor | -
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/02 Site Access | Folder | - | Editor | -
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/03 Agreements | Folder | - | Editor | Viewer
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/04 Billing | Folder | - | Editor | Editor
Clients/Ironbark Property Group Pty Ltd/Clinic - Reservoir/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Oakwood Engineering | Client | - | Editor | Viewer
Clients/Oakwood Engineering/Main office - Burwood | Location | - | Editor | -
Clients/Oakwood Engineering/Main office - Burwood/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Oakwood Engineering/Main office - Burwood/02 Site Access | Folder | - | Editor | -
Clients/Oakwood Engineering/Main office - Burwood/03 Agreements | Folder | - | Editor | Viewer
Clients/Oakwood Engineering/Main office - Burwood/04 Billing | Folder | - | Editor | Editor
Clients/Oakwood Engineering/Main office - Burwood/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd | Client | - | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh | Location | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Physiotherapy Pty Ltd/Main office - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh | Location | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/02 Site Access | Folder | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Physiotherapy Pty Ltd/Clinic - Bentleigh/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda | Location | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/02 Site Access | Folder | - | Editor | -
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/03 Agreements | Folder | - | Editor | Viewer
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/04 Billing | Folder | - | Editor | Editor
Clients/Waverley Physiotherapy Pty Ltd/Warehouse - St Kilda/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Insurance Brokers Pty Ltd | Client | - | Editor | Viewer
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote | Location | - | Editor | -
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Insurance Brokers Pty Ltd/Main office - Northcote/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Real Estate | Client | - | Editor | Viewer
Clients/Harbourside Real Estate/Main office - Glen Waverley | Location | - | Editor | -
Clients/Harbourside Real Estate/Main office - Glen Waverley/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Real Estate/Main office - Glen Waverley/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Real Estate/Main office - Glen Waverley/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Real Estate/Main office - Glen Waverley/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Real Estate/Main office - Glen Waverley/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Harbourside Real Estate/Clinic - Clayton | Location | - | Editor | -
Clients/Harbourside Real Estate/Clinic - Clayton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Harbourside Real Estate/Clinic - Clayton/02 Site Access | Folder | - | Editor | -
Clients/Harbourside Real Estate/Clinic - Clayton/03 Agreements | Folder | - | Editor | Viewer
Clients/Harbourside Real Estate/Clinic - Clayton/04 Billing | Folder | - | Editor | Editor
Clients/Harbourside Real Estate/Clinic - Clayton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Eastwood Podiatry | Client | - | Editor | Viewer
Clients/Eastwood Podiatry/Main office - Coburg | Location | - | Editor | -
Clients/Eastwood Podiatry/Main office - Coburg/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Eastwood Podiatry/Main office - Coburg/02 Site Access | Folder | - | Editor | -
Clients/Eastwood Podiatry/Main office - Coburg/03 Agreements | Folder | - | Editor | Viewer
Clients/Eastwood Podiatry/Main office - Coburg/04 Billing | Folder | - | Editor | Editor
Clients/Eastwood Podiatry/Main office - Coburg/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Cityside Real Estate | Client | - | Editor | Viewer
Clients/Cityside Real Estate/Main office - Moorabbin | Location | - | Editor | -
Clients/Cityside Real Estate/Main office - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Cityside Real Estate/Main office - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Cityside Real Estate/Main office - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Cityside Real Estate/Main office - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Cityside Real Estate/Main office - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Cityside Real Estate/Clinic - Moorabbin | Location | - | Editor | -
Clients/Cityside Real Estate/Clinic - Moorabbin/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Cityside Real Estate/Clinic - Moorabbin/02 Site Access | Folder | - | Editor | -
Clients/Cityside Real Estate/Clinic - Moorabbin/03 Agreements | Folder | - | Editor | Viewer
Clients/Cityside Real Estate/Clinic - Moorabbin/04 Billing | Folder | - | Editor | Editor
Clients/Cityside Real Estate/Clinic - Moorabbin/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Dental | Client | - | Editor | Viewer
Clients/Parkside Dental/Main office - Mentone | Location | - | Editor | -
Clients/Parkside Dental/Main office - Mentone/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Dental/Main office - Mentone/02 Site Access | Folder | - | Editor | -
Clients/Parkside Dental/Main office - Mentone/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Dental/Main office - Mentone/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Dental/Main office - Mentone/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Parkside Dental Group | Client | - | Editor | Viewer
Clients/Parkside Dental Group/Main office - Point Cook | Location | - | Editor | -
Clients/Parkside Dental Group/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Parkside Dental Group/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/Parkside Dental Group/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/Parkside Dental Group/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/Parkside Dental Group/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Physiotherapy | Client | - | Editor | Viewer
Clients/Northside Physiotherapy/Main office - Brighton | Location | - | Editor | -
Clients/Northside Physiotherapy/Main office - Brighton/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Physiotherapy/Main office - Brighton/02 Site Access | Folder | - | Editor | -
Clients/Northside Physiotherapy/Main office - Brighton/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Physiotherapy/Main office - Brighton/04 Billing | Folder | - | Editor | Editor
Clients/Northside Physiotherapy/Main office - Brighton/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Northside Physiotherapy/Clinic - Werribee | Location | - | Editor | -
Clients/Northside Physiotherapy/Clinic - Werribee/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Northside Physiotherapy/Clinic - Werribee/02 Site Access | Folder | - | Editor | -
Clients/Northside Physiotherapy/Clinic - Werribee/03 Agreements | Folder | - | Editor | Viewer
Clients/Northside Physiotherapy/Clinic - Werribee/04 Billing | Folder | - | Editor | Editor
Clients/Northside Physiotherapy/Clinic - Werribee/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/North Side Physiotherapy | Client | - | Editor | Viewer
Clients/North Side Physiotherapy/Main office - Point Cook | Location | - | Editor | -
Clients/North Side Physiotherapy/Main office - Point Cook/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/North Side Physiotherapy/Main office - Point Cook/02 Site Access | Folder | - | Editor | -
Clients/North Side Physiotherapy/Main office - Point Cook/03 Agreements | Folder | - | Editor | Viewer
Clients/North Side Physiotherapy/Main office - Point Cook/04 Billing | Folder | - | Editor | Editor
Clients/North Side Physiotherapy/Main office - Point Cook/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/North Side Physiotherapy/Clinic - Essendon | Location | - | Editor | -
Clients/North Side Physiotherapy/Clinic - Essendon/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/North Side Physiotherapy/Clinic - Essendon/02 Site Access | Folder | - | Editor | -
Clients/North Side Physiotherapy/Clinic - Essendon/03 Agreements | Folder | - | Editor | Viewer
Clients/North Side Physiotherapy/Clinic - Essendon/04 Billing | Folder | - | Editor | Editor
Clients/North Side Physiotherapy/Clinic - Essendon/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bayview Accountants | Client | - | Editor | Viewer
Clients/Bayview Accountants/Main office - Kew | Location | - | Editor | -
Clients/Bayview Accountants/Main office - Kew/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bayview Accountants/Main office - Kew/02 Site Access | Folder | - | Editor | -
Clients/Bayview Accountants/Main office - Kew/03 Agreements | Folder | - | Editor | Viewer
Clients/Bayview Accountants/Main office - Kew/04 Billing | Folder | - | Editor | Editor
Clients/Bayview Accountants/Main office - Kew/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer
Clients/Bay View Accountants | Client | - | Editor | Viewer
Clients/Bay View Accountants/Main office - Maribyrnong | Location | - | Editor | -
Clients/Bay View Accountants/Main office - Maribyrnong/01 Scope & Checklist | Folder | Viewer | Editor | -
Clients/Bay View Accountants/Main office - Maribyrnong/02 Site Access | Folder | - | Editor | -
Clients/Bay View Accountants/Main office - Maribyrnong/03 Agreements | Folder | - | Editor | Viewer
Clients/Bay View Accountants/Main office - Maribyrnong/04 Billing | Folder | - | Editor | Editor
Clients/Bay View Accountants/Main office - Maribyrnong/05 Visit Reports | Folder | Contributor (form uploads) | Editor | Viewer

## Drive Permissions
Who sees which subfolder
Work sample: realistic data, built to show how I approach this work.
Subfolder | Cleaners | Office | Bookkeeper | Why | Folders
01 Scope & Checklist | Viewer | Editor | - | Checklist the cleaner opens from the calendar event | 252
02 Site Access | - | Editor | - | Codes and keys; office reads them out or texts them, never in the calendar | 252
03 Agreements | - | Editor | Viewer | Signed agreement and current rate letter | 252
04 Billing | - | Editor | Editor | QBO template notes, credit notes, rate history | 252
05 Visit Reports | Contributor (form uploads) | Editor | Viewer | Photos and sign-off uploaded from the visit form | 252

## Cutover Waves
Cutover waves and go-live gates (a wave goes live only when all six gates PASS)
Work sample: realistic data, built to show how I approach this work.
Wave | Go-live | Gate | Rule | Open items | Result | Engine open items | Active jobs
Pilot | 2026-12-07 | G1 | No location billed by both Jobber and QBO | 0 | PASS | 0 | 8
Pilot | 2026-12-07 | G2 | No duplicate QBO templates | 0 | PASS | 0 | 8
Pilot | 2026-12-07 | G3 | Every location billed once, and nothing billed for ended work | 0 | PASS | 0 | 8
Pilot | 2026-12-07 | G4 | Rates agreed (Jobber = QBO) | 0 | PASS | 0 | 8
Pilot | 2026-12-07 | G5 | No roster clashes | 0 | PASS | 0 | 8
Pilot | 2026-12-07 | G6 | No access codes in calendar text | 0 | PASS | 0 | 8
Wave 1 North | 2027-01-11 | G1 | No location billed by both Jobber and QBO | 4 | BLOCKED | 4 | 63
Wave 1 North | 2027-01-11 | G2 | No duplicate QBO templates | 1 | BLOCKED | 1 | 63
Wave 1 North | 2027-01-11 | G3 | Every location billed once, and nothing billed for ended work | 7 | BLOCKED | 7 | 63
Wave 1 North | 2027-01-11 | G4 | Rates agreed (Jobber = QBO) | 9 | BLOCKED | 9 | 63
Wave 1 North | 2027-01-11 | G5 | No roster clashes | 1 | BLOCKED | 1 | 63
Wave 1 North | 2027-01-11 | G6 | No access codes in calendar text | 0 | PASS | 0 | 63
Wave 2 East | 2027-01-18 | G1 | No location billed by both Jobber and QBO | 6 | BLOCKED | 6 | 102
Wave 2 East | 2027-01-18 | G2 | No duplicate QBO templates | 3 | BLOCKED | 3 | 102
Wave 2 East | 2027-01-18 | G3 | Every location billed once, and nothing billed for ended work | 3 | BLOCKED | 3 | 102
Wave 2 East | 2027-01-18 | G4 | Rates agreed (Jobber = QBO) | 15 | BLOCKED | 15 | 102
Wave 2 East | 2027-01-18 | G5 | No roster clashes | 3 | BLOCKED | 3 | 102
Wave 2 East | 2027-01-18 | G6 | No access codes in calendar text | 0 | PASS | 0 | 102
Wave 3 South | 2027-01-25 | G1 | No location billed by both Jobber and QBO | 2 | BLOCKED | 2 | 87
Wave 3 South | 2027-01-25 | G2 | No duplicate QBO templates | 2 | BLOCKED | 2 | 87
Wave 3 South | 2027-01-25 | G3 | Every location billed once, and nothing billed for ended work | 4 | BLOCKED | 4 | 87
Wave 3 South | 2027-01-25 | G4 | Rates agreed (Jobber = QBO) | 18 | BLOCKED | 18 | 87
Wave 3 South | 2027-01-25 | G5 | No roster clashes | 3 | BLOCKED | 3 | 87
Wave 3 South | 2027-01-25 | G6 | No access codes in calendar text | 0 | PASS | 0 | 87
Wave 4 West | 2027-02-01 | G1 | No location billed by both Jobber and QBO | 3 | BLOCKED | 3 | 79
Wave 4 West | 2027-02-01 | G2 | No duplicate QBO templates | 2 | BLOCKED | 2 | 79
Wave 4 West | 2027-02-01 | G3 | Every location billed once, and nothing billed for ended work | 2 | BLOCKED | 2 | 79
Wave 4 West | 2027-02-01 | G4 | Rates agreed (Jobber = QBO) | 8 | BLOCKED | 8 | 79
Wave 4 West | 2027-02-01 | G5 | No roster clashes | 4 | BLOCKED | 4 | 79
Wave 4 West | 2027-02-01 | G6 | No access codes in calendar text | 0 | PASS | 0 | 79

## Exceptions
Exceptions register
Work sample: realistic data, built to show how I approach this work.
Area | Reference | Detail | Issue | Monthly difference | Owner | Status | Wave
Billing | J1001 | Oakwood Vet Clinic - 218 High Road, Bentleigh | Billed in Jobber | -550.33 | Bookkeeper | Open | Wave 3 South
Billing | J1003 | Oakwood Vet Clinic - 162 Station Parade, Oakleigh | Billed in Jobber | -218 | Bookkeeper | Open | Wave 3 South
Billing | J1004 | Clearwater Dental Pty Ltd - 273 Albert Road, Deer Park | Basis mismatch | -23.67 | Bookkeeper | Open | Wave 4 West
Billing | J1005 | Riverside Insurance Brokers Pty Ltd - 59 Station Parade, Bundoora | Billed in Jobber | -606.67 | Bookkeeper | Open | Wave 1 North
Billing | J1012 | Elm Street Physiotherapy - 359 Albert Street, Point Cook | Billed in Jobber | -632.67 | Bookkeeper | Open | Wave 4 West
Billing | J1013 | Elm Street Physiotherapy - 359 Albert Street, Point Cook | Billed in Jobber | -99 | Bookkeeper | Open | Wave 4 West
Billing | J1014 | Wattle Grove Property Group - 169 King Street, Hawthorn | Billed in Jobber | -589.33 | Bookkeeper | Open | Wave 2 East
Billing | J1020 | Wattle Grove Medical Centre Pty Ltd - 462 Mason Road, Clayton | Billed in Jobber | -806 | Bookkeeper | Open | Wave 3 South
Billing | J1023 | Redgum Optometrists Pty Ltd - 480 King Avenue, Camberwell | Rate mismatch | -52 | Bookkeeper | Open | Wave 2 East
Billing | J1027 | Northside Accountants Pty Ltd - 351 Burke Road, Oakleigh | Basis mismatch | -122 | Bookkeeper | Open | Wave 3 South
Billing | J1031 | Northside Engineering Pty Ltd - 195/12 Railway Highway, Bentleigh | Double-billing risk | 0 | Bookkeeper | Open | Wave 3 South
Billing | J1032 | Northside Engineering Pty Ltd - 195/12 Railway Highway, Bentleigh | Billed in Jobber | -234 | Bookkeeper | Open | Wave 3 South
Billing | J1034 | Northside Engineering Pty Ltd - 17 Park Avenue, St Kilda | Basis mismatch | -46.67 | Bookkeeper | Open | Wave 3 South
Billing | J1035 | Ashwood Early Learning - 378 Plenty Street, Camberwell | Not billed | -910 | Bookkeeper | Open | Wave 2 East
Billing | J1036 | Ashwood Early Learning - 378 Plenty Street, Camberwell | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1038 | Silverton Pharmacy - 98 Park Road, Kew | Billed in Jobber | -299 | Bookkeeper | Open | Wave 2 East
Billing | J1039 | Silverton Pharmacy - 107 Barkly Highway, Bundoora | Basis mismatch | -62.33 | Bookkeeper | Open | Wave 1 North
Billing | J1043 | Ashwood Optometrists - 195 Nicholson Road, Ringwood | Billed in Jobber | -1083.33 | Bookkeeper | Open | Wave 2 East
Billing | J1045 | Ashwood Optometrists - 245 Ballarat Avenue, Ringwood | Billed in Jobber | -173.33 | Bookkeeper | Open | Wave 2 East
Billing | J1049 | Parkside Accountants - 356 Albert Avenue, Northcote | Rate mismatch | -5 | Bookkeeper | Open | Wave 1 North
Billing | J1050 | Brightside Motors Pty Ltd - 364/12 High Road, Heidelberg | Billed in Jobber | -437.67 | Bookkeeper | Open | Wave 1 North
Billing | J1052 | Westend Motors Pty Ltd - 37 Nicholson Highway, Williamstown | Rate mismatch | -60.66 | Bookkeeper | Open | Wave 4 West
Billing | J1054 | Oakwood Lawyers Pty Ltd - 453 Plenty Parade, Moorabbin | Billed in Jobber | -502.67 | Bookkeeper | Open | Wave 3 South
Billing | J1056 | Riverside Medical Centre - 300 Sydney Highway, Camberwell | Billed in Jobber | -390 | Bookkeeper | Open | Wave 2 East
Billing | J1059 | Sunbury Accountants Pty Ltd - 313A Queen Street, Camberwell | Not billed | -1170 | Bookkeeper | Open | Wave 2 East
Billing | J1060 | Sunbury Early Learning - 386 Nepean Road, Glen Waverley | Rate mismatch | -60.66 | Bookkeeper | Open | Wave 2 East
Billing | J1061 | Silverton Lawyers Pty Ltd - 255 Glenferrie Parade, Thornbury | Billed in Jobber | -1100.67 | Bookkeeper | Open | Wave 1 North
Billing | J1062 | Waverley Accountants Pty Ltd - 23A Ballarat Street, Brunswick | Billed in Jobber | -2513.33 | Bookkeeper | Open | Wave 1 North
Billing | J1063 | Waverley Accountants Pty Ltd - 23A Ballarat Street, Brunswick | Billed in Jobber | -218 | Bookkeeper | Open | Wave 1 North
Billing | J1065 | Westend Podiatry - 310 Ballarat Avenue, Brunswick | Rate mismatch | -5 | Bookkeeper | Open | Wave 1 North
Billing | J1071 | Kingsley Financial Planning - 204 Bridge Highway, Oakleigh | Duplicate in QBO | 784.33 | Bookkeeper | Open | Wave 3 South
Billing | J1074 | Elm Street Fitness Pty Ltd - 479 Mason Parade, Hawthorn | Billed in Jobber | -218 | Bookkeeper | Open | Wave 2 East
Billing | J1075 | Elm Street Fitness Pty Ltd - 450 King Road, Doncaster | Billed in Jobber | -320.67 | Bookkeeper | Open | Wave 2 East
Billing | J1077 | Wattle Grove Dental - 259 Union Avenue, Hawthorn | Not billed | -1625 | Bookkeeper | Open | Wave 2 East
Billing | J1081 | Clearwater Property Group Pty Ltd - 143/12 Nepean Street, Frankston | Duplicate in QBO | 1690 | Bookkeeper | Open | Wave 3 South
Billing | J1084 | Clearwater Property Group Pty Ltd - 380 Nepean Parade, Laverton | Billed in Jobber | -234 | Bookkeeper | Open | Wave 4 West
Billing | J1087 | Eastwood Real Estate Pty Ltd - 296 Barkly Highway, Hawthorn | Rate mismatch | -6 | Bookkeeper | Open | Wave 2 East
Billing | J1088 | Clearwater Physiotherapy - 46 Main Avenue, Bentleigh | Billed in Jobber | -299 | Bookkeeper | Open | Wave 3 South
Billing | J1097 | Kingsley Insurance Brokers - 225 Park Avenue, Reservoir | Double-billing risk | 0 | Bookkeeper | Open | Wave 1 North
Billing | J1098 | Kingsley Insurance Brokers - 225 Park Avenue, Reservoir | Rate mismatch | -4 | Bookkeeper | Open | Wave 1 North
Billing | J1101 | Kingsley Insurance Brokers - 410 Burke Highway, Point Cook | Billed in Jobber | -218 | Bookkeeper | Open | Wave 4 West
Billing | J1102 | Bluestone Learning Centre Pty Ltd - 205 Burke Highway, Glen Waverley | Billed in Jobber | -875.33 | Bookkeeper | Open | Wave 2 East
Billing | J1103 | Bluestone Learning Centre Pty Ltd - 205 Burke Highway, Glen Waverley | Rate mismatch | -3 | Bookkeeper | Open | Wave 2 East
Billing | J1104 | Oakwood Logistics - 189 Union Highway, Hawthorn | Basis mismatch | -38.67 | Bookkeeper | Open | Wave 2 East
Billing | J1106 | Oakwood Logistics - 128 Victoria Road, Blackburn | Billed in Jobber | -546 | Bookkeeper | Open | Wave 2 East
Billing | J1107 | Oakwood Logistics - 375 Station Highway, Cheltenham | Basis mismatch | -203.33 | Bookkeeper | Open | Wave 3 South
Billing | J1111 | Banksia Insurance Brokers - 185 Church Parade, Burwood | Rate mismatch | -4 | Bookkeeper | Open | Wave 2 East
Billing | J1113 | Sunbury Lawyers Pty Ltd - 96A Glenferrie Parade, Essendon | Billed in Jobber | -814.67 | Bookkeeper | Open | Wave 1 North
Billing | J1118 | Oakwood Financial Planning Pty Ltd - 394 Ballarat Avenue, Brighton | Basis mismatch | -62.33 | Bookkeeper | Open | Wave 3 South
Billing | J1121 | Brightside Dental Pty Ltd - 472 Barkly Parade, Moorabbin | Rate mismatch | -4.34 | Bookkeeper | Open | Wave 3 South
Billing | J1123 | Ashwood Physiotherapy - 151 Nicholson Street, Point Cook | Billed in Jobber | -135 | Bookkeeper | Open | Wave 4 West
Billing | J1125 | Ashwood Physiotherapy - 144 Burke Avenue, Coburg | Rate mismatch | -52 | Bookkeeper | Open | Wave 1 North
Billing | J1126 | Ashwood Physiotherapy - 144 Burke Avenue, Coburg | Billed in Jobber | -116 | Bookkeeper | Open | Wave 1 North
Billing | J1132 | Bluestone Dental - 11 Hopkins Avenue, Ringwood | Billed in Jobber | -1135.33 | Bookkeeper | Open | Wave 2 East
Billing | J1137 | Banksia Pathology Pty Ltd - 459 Park Avenue, Deer Park | Rate mismatch | -21.66 | Bookkeeper | Open | Wave 4 West
Billing | J1140 | Bluestone Lawyers Pty Ltd - 29 Burke Parade, Burwood | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1143 | Banksia Accountants - 251 Union Avenue, Altona | Double-billing risk | 0 | Bookkeeper | Open | Wave 4 West
Billing | J1146 | Banksia Accountants - 463 Gilbert Street, Glen Waverley | Rate mismatch | -8.67 | Bookkeeper | Open | Wave 2 East
Billing | J1150 | Wattle Grove Lawyers Pty Ltd - 280 Railway Road, Point Cook | Rate mismatch | -39 | Bookkeeper | Open | Wave 4 West
Billing | J1153 | Kingsley Medical Centre Pty Ltd - 149 Main Road, Point Cook | Rate mismatch | -4 | Bookkeeper | Open | Wave 4 West
Billing | J1155 | Ashwood Engineering - 155 Hopkins Road, Glen Waverley | Duplicate in QBO | 528.67 | Bookkeeper | Open | Wave 2 East
Billing | J1157 | Sunbury Physiotherapy Pty Ltd - 85 Nepean Road, Frankston | Basis mismatch | -146 | Bookkeeper | Open | Wave 3 South
Billing | J1158 | Sunbury Physiotherapy Pty Ltd - 231 Church Highway, Hawthorn | Rate mismatch | -43.34 | Bookkeeper | Open | Wave 2 East
Billing | J1160 | Eastwood Pathology - 223A Nicholson Parade, Werribee | Rate mismatch | -3 | Bookkeeper | Open | Wave 4 West
Billing | J1163 | Clearwater Logistics - 127 Main Highway, Reservoir | Not billed | -268.67 | Bookkeeper | Open | Wave 1 North
Billing | J1165 | Wattle Grove Fitness - 68 Church Parade, Essendon | Not billed | -546 | Bookkeeper | Open | Wave 1 North
Billing | J1168 | Ashwood Medical Centre - 61 Church Road, Bundoora | Billed in Jobber | -135 | Bookkeeper | Open | Wave 1 North
Billing | J1171 | Bayview Pharmacy Pty Ltd - 221 Plenty Avenue, Footscray | Rate mismatch | -108.34 | Bookkeeper | Open | Wave 4 West
Billing | J1172 | Hillcrest Accountants - 77 Mason Highway, Mitcham | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1173 | Hillcrest Accountants - 77 Mason Highway, Mitcham | Billed in Jobber | -116 | Bookkeeper | Open | Wave 2 East
Billing | J1176 | Ashwood Accountants - 212 Sydney Avenue, Yarraville | Duplicate in QBO | 303.33 | Bookkeeper | Open | Wave 4 West
Billing | J1177 | Westend Property Group - 268 Sydney Road, Heidelberg | Basis mismatch | -24.67 | Bookkeeper | Open | Wave 1 North
Billing | J1179 | Eastwood Optometrists - 369 Station Road, Burwood | Basis mismatch | -40.67 | Bookkeeper | Open | Wave 2 East
Billing | J1183 | Riverside Learning Centre - 148 Plenty Street, Cheltenham | Double-billing risk | 0 | Bookkeeper | Open | Wave 3 South
Billing | J1185 | Riverside Learning Centre - 4A Main Highway, Moorabbin | Billed in Jobber | -146 | Bookkeeper | Open | Wave 3 South
Billing | J1186 | Silverton Insurance Brokers Pty Ltd - 165 Hopkins Road, Cheltenham | Rate mismatch | -21.66 | Bookkeeper | Open | Wave 3 South
Billing | J1188 | Silverton Insurance Brokers Pty Ltd - 274 Gilbert Avenue, Glen Waverley | Rate mismatch | -43.34 | Bookkeeper | Open | Wave 2 East
Billing | J1190 | Greenway Podiatry Pty Ltd - 198 Station Avenue, Burwood | Billed in Jobber | -173.33 | Bookkeeper | Open | Wave 2 East
Billing | J1191 | Banksia Logistics - 387 Burke Parade, Northcote | Basis mismatch | -31.33 | Bookkeeper | Open | Wave 1 North
Billing | J1193 | Banksia Logistics - 458 Glenferrie Parade, Thornbury | Double-billing risk | 0 | Bookkeeper | Open | Wave 1 North
Billing | J1195 | Cobblestone Physiotherapy Pty Ltd - 12 Sydney Road, Bundoora | Duplicate in QBO | 151.67 | Bookkeeper | Open | Wave 1 North
Billing | J1198 | Northside Pathology Pty Ltd - 416 Park Road, Ringwood | Rate mismatch | -21.66 | Bookkeeper | Open | Wave 2 East
Billing | J1200 | Kingsley Fitness Pty Ltd - 460 Sydney Highway, Werribee | Rate mismatch | -8.67 | Bookkeeper | Open | Wave 4 West
Billing | J1204 | Sunbury Optometrists - 375 Railway Road, Altona | Billed in Jobber | -1495 | Bookkeeper | Open | Wave 4 West
Billing | J1206 | Bayview Vet Clinic - 186 Sydney Avenue, Coburg | Billed in Jobber | -135 | Bookkeeper | Open | Wave 1 North
Billing | J1207 | Bayview Vet Clinic - 399 Whitehorse Road, Reservoir | Not billed | -806 | Bookkeeper | Open | Wave 1 North
Billing | J1210 | Greenway Medical Centre Pty Ltd - 326 Main Highway, Glen Waverley | Basis mismatch | -32.67 | Bookkeeper | Open | Wave 2 East
Billing | J1212 | Westend Physiotherapy - 306 Bridge Road, Glen Waverley | Basis mismatch | -276.67 | Bookkeeper | Open | Wave 2 East
Billing | J1213 | Riverside Podiatry - 79 Ballarat Street, Point Cook | Billed in Jobber | -1755 | Bookkeeper | Open | Wave 4 West
Billing | J1215 | Northside Learning Centre - 190 Nicholson Avenue, Camberwell | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1220 | Redgum Podiatry - 445 Barkly Avenue, Cheltenham | Not billed | -116 | Bookkeeper | Open | Wave 3 South
Billing | J1222 | Harbourside Chiropractic - 284 Mason Highway, Moorabbin | Basis mismatch | -77.33 | Bookkeeper | Open | Wave 3 South
Billing | J1224 | Harbourside Chiropractic - 218 Burke Street, St Kilda | Billed in Jobber | -2903.33 | Bookkeeper | Open | Wave 3 South
Billing | J1225 | Hillcrest Lawyers - 362 Barkly Avenue, Mentone | Rate mismatch | -17.33 | Bookkeeper | Open | Wave 3 South
Billing | J1227 | Silverton Logistics Pty Ltd - 176 High Highway, Brunswick | Basis mismatch | -42.67 | Bookkeeper | Open | Wave 1 North
Billing | J1229 | Silverton Logistics Pty Ltd - 356 Glenferrie Parade, Frankston | Basis mismatch | -9.67 | Bookkeeper | Open | Wave 3 South
Billing | J1232 | Southgate Pathology - 433 Mason Parade, Brunswick | Double-billing risk | 0 | Bookkeeper | Open | Wave 1 North
Billing | J1237 | Westend Engineering - 313 Victoria Road, Reservoir | Not billed | -146 | Bookkeeper | Open | Wave 1 North
Billing | J1240 | Lakeside Real Estate Pty Ltd - 6 Whitehorse Street, Mitcham | Billed in Jobber | -546 | Bookkeeper | Open | Wave 2 East
Billing | J1244 | Harbourside Pharmacy Pty Ltd - 266 Park Road, Williamstown | Billed in Jobber | -901.33 | Bookkeeper | Open | Wave 4 West
Billing | J1246 | Southgate Engineering - 135 Main Avenue, Frankston | Billed in Jobber | -1092 | Bookkeeper | Open | Wave 3 South
Billing | J1247 | Riverside Dental Pty Ltd - 256 Albert Parade, Northcote | Billed in Jobber | -268.67 | Bookkeeper | Open | Wave 1 North
Billing | J1250 | Bayview Early Learning - 329 Station Avenue, Brighton | Rate mismatch | -13 | Bookkeeper | Open | Wave 3 South
Billing | J1252 | Ashwood Property Group - 248 Sydney Street, Cheltenham | Billed in Jobber | -151.67 | Bookkeeper | Open | Wave 3 South
Billing | J1253 | Ashwood Property Group - 248 Sydney Street, Cheltenham | Not billed | -116 | Bookkeeper | Open | Wave 3 South
Billing | J1257 | Elm Street Early Learning - 356 Main Road, Camberwell | Billed in Jobber | -316.33 | Bookkeeper | Open | Wave 2 East
Billing | J1260 | Elm Street Early Learning - 422 Nicholson Parade, Glen Waverley | Billed in Jobber | -99 | Bookkeeper | Open | Wave 2 East
Billing | J1261 | Redgum Financial Planning - 455 Railway Road, Williamstown | Billed in Jobber | -832 | Bookkeeper | Open | Wave 4 West
Billing | J1264 | Elm Street Logistics Pty Ltd - 343 Sydney Street, Kew | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1265 | Elm Street Logistics Pty Ltd - 399 Plenty Avenue, Ringwood | Billed in Jobber | -537.33 | Bookkeeper | Open | Wave 2 East
Billing | J1266 | Elm Street Logistics Pty Ltd - 256 Station Street, Blackburn | Basis mismatch | -106.67 | Bookkeeper | Open | Wave 2 East
Billing | J1268 | Lakeside Insurance Brokers - 459 Whitehorse Parade, Sunshine | Billed in Jobber | -884 | Bookkeeper | Open | Wave 4 West
Billing | J1271 | Fairfield Accountants Pty Ltd - 313/12 Union Avenue, Dandenong | Billed in Jobber | -3271.67 | Bookkeeper | Open | Wave 3 South
Billing | J1275 | Oakwood Medical Centre Pty Ltd - 64 Bridge Street, Coburg | Billed in Jobber | -1209 | Bookkeeper | Open | Wave 1 North
Billing | J1276 | Banksia Architects Pty Ltd - 213 Church Parade, Frankston | Rate mismatch | -91 | Bookkeeper | Open | Wave 3 South
Billing | J1278 | Ironbark Engineering Pty Ltd - 301 Whitehorse Highway, Thornbury | Billed in Jobber | -2925 | Bookkeeper | Open | Wave 1 North
Billing | J1279 | Wattle Grove Financial Planning - 294 Victoria Avenue, Northcote | Billed in Jobber | -1126.67 | Bookkeeper | Open | Wave 1 North
Billing | J1280 | Parkside Fitness Pty Ltd - 81 Nepean Road, Burwood | Duplicate in QBO | 754 | Bookkeeper | Open | Wave 2 East
Billing | J1285 | Greenway Chiropractic Pty Ltd - 250 Hopkins Highway, Kew | Billed in Jobber | -3791.67 | Bookkeeper | Open | Wave 2 East
Billing | J1288 | Riverside Pharmacy - 472 Hopkins Highway, Box Hill | Duplicate in QBO | 572 | Bookkeeper | Open | Wave 2 East
Billing | J1289 | Riverside Pharmacy - 410 Queen Highway, Glen Waverley | Billed in Jobber | -2621.67 | Bookkeeper | Open | Wave 2 East
Billing | J1290 | Riverside Pharmacy - 410 Queen Highway, Glen Waverley | Rate mismatch | -9 | Bookkeeper | Open | Wave 2 East
Billing | J1292 | Elm Street Chiropractic Pty Ltd - 348 Railway Street, Mentone | Rate mismatch | -43.34 | Bookkeeper | Open | Wave 3 South
Billing | J1294 | Elm Street Chiropractic Pty Ltd - 4 Sydney Highway, Cheltenham | Rate mismatch | -26 | Bookkeeper | Open | Wave 3 South
Billing | J1297 | Ironbark Real Estate Pty Ltd - 32 Park Avenue, Oakleigh | Billed in Jobber | -1048.67 | Bookkeeper | Open | Wave 3 South
Billing | J1299 | Elm Street Motors - 280 Station Street, Oakleigh | Billed in Jobber | -151.67 | Bookkeeper | Open | Wave 3 South
Billing | J1301 | Ashwood Dental Pty Ltd - 241 Mason Road, Northcote | Billed in Jobber | -650 | Bookkeeper | Open | Wave 1 North
Billing | J1302 | Ashwood Dental Pty Ltd - 448 Barkly Avenue, Mentone | Billed in Jobber | -151.67 | Bookkeeper | Open | Wave 3 South
Billing | J1303 | Bluestone Early Learning Pty Ltd - 351 High Street, Altona | Billed in Jobber | -2210 | Bookkeeper | Open | Wave 4 West
Billing | J1304 | Bluestone Early Learning Pty Ltd - 351 High Street, Altona | Double-billing risk | 0 | Bookkeeper | Open | Wave 4 West
Billing | J1308 | Harbourside Property Group - 428 Church Parade, Maribyrnong | Billed in Jobber | -416 | Bookkeeper | Open | Wave 4 West
Billing | J1309 | Harbourside Property Group - 428 Church Parade, Maribyrnong | Duplicate in QBO | 146 | Bookkeeper | Open | Wave 4 West
Billing | J1313 | Bayview Fitness Pty Ltd - 367 Station Parade, Thornbury | Billed in Jobber | -407.33 | Bookkeeper | Open | Wave 1 North
Billing | J1315 | Ironbark Property Group Pty Ltd - 479 Burke Road, Reservoir | Billed in Jobber | -2708.33 | Bookkeeper | Open | Wave 1 North
Billing | J1318 | Oakwood Engineering - 216 Plenty Road, Burwood | Double-billing risk | 0 | Bookkeeper | Open | Wave 2 East
Billing | J1319 | Waverley Physiotherapy Pty Ltd - 42 Queen Avenue, Bentleigh | Billed in Jobber | -1057.33 | Bookkeeper | Open | Wave 3 South
Billing | J1322 | Waverley Physiotherapy Pty Ltd - 337 Plenty Parade, St Kilda | Rate mismatch | -26 | Bookkeeper | Open | Wave 3 South
Billing | J1323 | Harbourside Insurance Brokers Pty Ltd - 314 Plenty Street, Northcote | Rate mismatch | -30.33 | Bookkeeper | Open | Wave 1 North
Billing | J1327 | Cityside Real Estate - 200 Nepean Avenue, Moorabbin | Billed in Jobber | -580.67 | Bookkeeper | Open | Wave 3 South
Billing | J1328 | Cityside Real Estate - 455 Nicholson Highway, Moorabbin | Basis mismatch | -34.67 | Bookkeeper | Open | Wave 3 South
Billing | J1329 | Cityside Real Estate - 455 Nicholson Highway, Moorabbin | Rate mismatch | -4 | Bookkeeper | Open | Wave 3 South
Billing | J1330 | Parkside Dental - 400 Albert Street, Mentone | Basis mismatch | -101 | Bookkeeper | Open | Wave 3 South
Billing | J1336 | North Side Physiotherapy - 284A Park Road, Point Cook | Double-billing risk | 0 | Bookkeeper | Open | Wave 4 West
Billing | J1337 | North Side Physiotherapy - 163 Barkly Highway, Essendon | Double-billing risk | 0 | Bookkeeper | Open | Wave 1 North
Billing | J1340 | Oakwood Medical Centre Pty Ltd - 64 Bridge Street, Coburg | Inactive in Jobber - confirm | 377 | Owner | Open | Wave 1 North
Billing | J1341 | Kingsley Fitness Pty Ltd - 460 Sydney Highway, Werribee | Inactive in Jobber - confirm | 264.33 | Owner | Open | Wave 4 West
Billing | J1342 | Wattle Grove Fitness - 102 Union Road, St Kilda | Inactive in Jobber - confirm | 771.33 | Owner | Open | Wave 3 South
Billing | J1343 | Southgate Pathology - 186 Plenty Street, Altona | Inactive in Jobber - confirm | 1040 | Owner | Open | Wave 4 West
Billing | J1344 | Oakwood Vet Clinic - 218 High Road, Bentleigh | Inactive in Jobber - confirm | 546 | Owner | Open | Wave 3 South
Billing | J1345 | Hillcrest Lawyers - 418 Main Avenue, Northcote | Inactive in Jobber - confirm | 823.33 | Owner | Open | Wave 1 North
Billing | J1346 | Sunbury Architects Pty Ltd - 111A Plenty Street, Epping | Inactive in Jobber - confirm | 1274 | Owner | Open | Wave 1 North
Billing | T0284 | Kingsley Real Estate - 208 Main Avenue, Mitcham | Missing in Jobber | 65 | Owner | Open | Wave 2 East
Billing | T0285 | Harbourside Real Estate - 317 Victoria Parade, Clayton | Missing in Jobber | 65 | Owner | Open | Wave 3 South
Billing | T0286 | Brightside Logistics Pty Ltd - 148 Nepean Street, Bentleigh | Missing in Jobber | 80 | Owner | Open | Wave 3 South
Billing | T0287 | Harbourside Logistics Pty Ltd - 387 Barkly Highway, Hawthorn | Missing in Jobber | 80 | Owner | Open | Wave 2 East
Billing | T0288 | Waverley Fitness Pty Ltd - 443 Station Road, Footscray | Missing in Jobber | 65 | Owner | Open | Wave 4 West
Billing | T0289 | Wattle Grove Dental - 259 Union Avenue, Hawthorn | Missing in Jobber | 110 | Owner | Open | Wave 2 East
Roster | J1171 / J1245 | CL12 MO 21:30-23:30 and 21:00-22:30 | Roster clash | 0 | Office | Open | Wave 4 West
Roster | J1061 / J1301 | CL29 TH 08:00-10:00 and 07:30-08:30 | Roster clash | 0 | Office | Open | Wave 1 North
Roster | J1093 / J1186 | CL03 TH 17:30-19:30 and 18:00-20:00 | Roster clash | 0 | Office | Open | Wave 3 South
Roster | J1115 / J1328 | CL15 WE 20:30-21:30 and 20:00-21:30 | Roster clash | 0 | Office | Open | Wave 3 South
Roster | J1128 / J1158 | CL14 MO 07:00-07:30 and 07:00-08:00 | Roster clash | 0 | Office | Open | Wave 2 East
Roster | J1172 / J1212 | CL14 MO 20:30-21:30 and 20:00-22:30 | Roster clash | 0 | Office | Open | Wave 2 East
Roster | J1051 / J1069 | CL24 MO 05:30-06:30 and 06:00-07:00 | Roster clash | 0 | Office | Open | Wave 4 West
Roster | J1221 / J1254 | CL35 TU 20:00-21:30 and 19:30-20:30 | Roster clash | 0 | Office | Open | Wave 3 South
Roster | J1057 / J1162 | CL44 WE 06:00-08:00 and 05:30-07:30 | Roster clash | 0 | Office | Open | Wave 4 West
Roster | J1200 / J1281 | CL20 FR 07:30-08:30 and 07:00-08:00 | Roster clash | 0 | Office | Open | Wave 4 West
Roster | J1263 / J1317 | CL46 TU 06:00-07:30 and 05:30-07:30 | Roster clash | 0 | Office | Open | Wave 2 East
Customers | Q0159 | Northside Enginering - Accounts | Merge into Q0017 | 0 | Bookkeeper | Open
Customers | Q0160 | Hillcrest Accontants - Accounts | Merge into Q0077 | 0 | Bookkeeper | Open
Customers | Q0161 | Kngsley Fitness | Merge into Q0092 | 0 | Bookkeeper | Open
Customers | Q0162 | Fairfield Engineerng | Merge into Q0044 | 0 | Bookkeeper | Open
Customers | Q0163 | Westend Poiatry - Accounts | Merge into Q0033 | 0 | Bookkeeper | Open
Customers | Q0164 | Banksia Logistics - Accounts | Merge into Q0086 | 0 | Bookkeeper | Open
Customers | Q0165 | Elm Street Lgistics - Accounts | Merge into Q0123 | 0 | Bookkeeper | Open
Customers | Q0166 | Lakeside Inusrance Brokers - Accounts | Merge into Q0124 | 0 | Bookkeeper | Open
Customers | Q0167 | Ashwod Medical Centre - Accounts | Merge into Q0073 | 0 | Bookkeeper | Open
Customers | Q0168 | Harbourside Chiorpractic - Accounts | Merge into Q0104 | 0 | Bookkeeper | Open

## Controls
Control checks (formula-driven)
Work sample: realistic data, built to show how I approach this work.
Check | Expected | Actual | Result | Why it matters
Rate Reconciliation job rows = Jobber jobs | 363 | 363 | PASS | Every job is reconciled once
Active templates on Rate Reconciliation = active QBO templates | 289 | 289 | PASS | Every live template is accounted for, including QBO-only ones
Formula status = engine status (rows that differ) | 0 | 0 | PASS | The workbook logic and the engine agree on every row
Rows with no next action | 0 | 0 | PASS | Every status has an action and an owner
Actions tab rows = Rate Reconciliation rows | 369 | 369 | PASS | Nothing falls outside the action list
QBO parents with no Jobber client | 0 | 0 | PASS | Every customer has a home
QBO parents in Customer Match = parents in QBO | 168 | 168 | PASS | No customer skipped
QBO sub-customers with no Jobber property | 0 | 0 | PASS | Every location has a home
Templates pointing at a job that does not exist | 0 | 0 | PASS | No broken template links
Jobber invoices total = Billing Check Jobber column | 199249.04 | 199249.04 | PASS | Every Jobber invoice is in the check
QBO invoices total = Billing Check QBO column | 622362.98 | 622362.98 | PASS | Every QBO invoice is in the check
Should-bill (weekly + monthly active jobs) = 3 x monthly basis | 737036.1 | 737036.1 | PASS | Billing policy applied the same way everywhere
Gap total = billed (both systems) - should bill | 49680.92 | 49680.92 | PASS | Gaps add up
Billing Check gap = engine gap (rows that differ) | 0 | 0 | PASS | Workbook and engine agree on every job-month
Double-billed jobs: over-billing = their QBO billing | 42156.02 | 42156.02 | PASS | The QBO invoices are the duplicate
Not-billed jobs: anything billed | 0 | 0 | PASS | They really were missed
Archived jobs: should bill | 0 | 0 | PASS | Ended work is never expected
Roster clashes where Jobber shows a different cleaner | 0 | 0 | PASS | Clashes are real
Calendar events marked as clashing = 2 x clashes | 22 | 22 | PASS | Every clash is visible on the roster
Calendar events = active jobs | 339 | 339 | PASS | Every live job is on a calendar, nothing ended is
Codes found = codes moved to 02 Site Access | 66 | 66 | PASS | Every code is kept, just not in the calendar
Calendar events with an access code in the text | 0 | 0 | PASS | Codes never reach a phone calendar
Drive folders = clients + 6 x locations | 1670 | 1670 | PASS | Folder plan is complete
Active jobs with no wave | 0 | 0 | PASS | Every job has a cutover date
Active jobs across waves = active jobs | 339 | 339 | PASS | Waves cover everything once
Gate open items: formula = engine (cells that differ) | 0 | 0 | PASS | Gate logic agrees with the engine
Pilot gates passed | 6 | 6 | PASS | The pilot can go live
Rostered hours = active jobs' weekly hours | 911.875 | 911.875 | PASS | Load covers every job
Rostered hours: workbook = engine (cleaners that differ) | 0 | 0 | PASS | Same load either way
Exceptions: billing rows = rows needing a fix | 157 | 157 | PASS | Every billing fix is on the register
Exceptions: roster rows = clashes | 11 | 11 | PASS | Every clash is on the register
Engine regression: job status disagreements | 0 | 0 | PASS | Engine matches the answer key on every job
Controls passed | 32 | 32 | PASS

## Test Log
Test log: engine and scenario tests
Work sample: realistic data, built to show how I approach this work.
Test | Method | Tested | Expected | Actual | Result
Job status vs answer key | engine.py reconciles every job; compared with truth_jobs | 363 | 363 | 363 | PASS
QBO customers matched to the right client | Parents and sub-customers vs truth_customers (look-alike names included) | 168 | 168 | 168 | PASS
Wrong-client matches | A customer linked to a different business | 168 | 0 | 0 | PASS
Templates matched to the right job | Property + service, amount where two jobs share an address | 289 | 289 | 289 | PASS
Access codes found | Seeded codes in property notes | 66 | 66 | 66 | PASS
Access code false flags | Notes flagged that hold no code (phone numbers, bin days) | 252 | 0 | 0 | PASS
Roster clashes found | Seeded overlapping visits | 11 | 11 | 11 | PASS
Extra clashes reported | Clashes that are not real | 11 | 0 | 0 | PASS
Billing check vs answer key | Should-bill and Jobber billing per job-month vs truth_billing | 1017 | 1017 | 1017 | PASS
Codes leaked into calendar text | Search every event description for a code | 339 | 0 | 0 | PASS
Archived jobs not on any calendar | Archived jobs found in Calendar Build | 24 | 0 | 0 | PASS
Pilot cleaners have no open item | Open items on Pilot gates | 6 | 0 | 0 | PASS