## Read me
WIP and claims workbook: simPRO progress claims, retention and WIP, tied to Xero
Work sample: realistic data, not a past client job. Amounts are in AUD and GST is 10%.
Illustrative sample data for a Melbourne commercial electrical contractor: 46 projects over the 12 months to 30 September 2026. It shows how contract value, variations, retention and WIP are held and checked.
Formulas are live. Change a claimed percentage, a variation or a claim line and the claim totals, GST, retention, tie-out and WIP figures recalculate.
Sheet | What it shows
Summary | Key totals and checks as live formulas, next to the figure printed in the walkthrough.
Projects | One row per project. Approved variations, claimable total, claimed to date and remaining are formulas.
Cost centres | 310 cost centres, including variation cost centres. Claimed and remaining are calculated from the claimed percentage.
Claims | 520 progress and final claims. Claimed amount is summed from the claim lines; net, GST (10%) and invoice total are formulas.
Claim lines | The cost-centre lines behind each claim.
Variations | The variation register with status and whether each was on the old claim spreadsheet.
Retention | Retention register. Still held is deducted less released.
Xero tie-out | Monthly comparison of approved simPRO claims with the invoices in Xero that came from simPRO. Difference is a formula.
WIP 30 Sep 2026 | Live projects: percent complete, earned revenue, over or under billing and forecast margin as formulas.
WIP by month | Twelve month-end WIP positions.
Cost centre list | The standard cost centres and the Xero revenue account for each.
The totals row under each table follows the filters. All amounts are in AUD ex GST unless a column says inc GST.
Prepared by Manaz Afzal

## Summary
Summary and tie-out checks
Green cells are live formulas. 'Printed in walkthrough' is the figure shown in index.md, so the workbook can be compared with it.
Sample size | Value | Printed in walkthrough | Match | Note
Projects | 46 | 46 | OK
Live projects at 30 Sep 2026 | 17 | 17 | OK
Cost centres | 310 | 310 | OK
Progress claims | 520 | 520 | OK
Variations (all statuses) | 140 | 140 | OK
Contract and variations | Value | Printed in walkthrough | Match | Note
Contract value (ex GST) | 13477900 | 13477900 | OK
Approved variations (ex GST) | 1777600 | 1777600 | OK | From the variation register, status Approved
Variations awaiting approval (ex GST) | 438700 | 438700 | OK | The 'chase approval' list
Projects where claimed + remaining = contract + approved variations | 46 | 46 | OK | Exhibit C check, 46 of 46
Projects where cost centres add up to the claimable total | 46 | 46 | OK
Claims, GST and the Xero tie-out (12 months) | Value | Printed in walkthrough | Match | Note
Claims net (ex GST) | 11467005.17 | 11467005.17 | OK
GST | 1146701.15 | 1146701.15 | OK | 10% of each claim's net, rounded to the cent
simPRO total (inc GST) | 12613706.32 | 12613706.32 | OK
Xero total (inc GST) | 12613706.32 | 12613706.32 | OK | Typed in from the Xero export
Difference, simPRO less Xero | 0 | 0 | OK | Printed as $0.00 in the walkthrough
Months with a zero difference | 12 | 12 | OK | 12 of 12 months
Approved claims counted in the tie-out | 520 | 520 | OK
Retention | Value | Printed in walkthrough | Match | Note
Retention still held | 268094.22 | 268094.22 | OK | Deducted less released
Retention projects | 22 | 22 | OK
Held at September month end (tie-out sheet) | 268094.22 | 268094.22 | OK | Should equal the retention register
Retention deducted = released + still held (projects) | 22 | 22 | OK | 22 of 22
WIP at 30 September 2026 (live projects, cost to cost) | Value | Printed in walkthrough | Match | Note
Contract + approved variations | 5529250 | 5529250 | OK
Billed to date | 5039377 | 5039377 | OK
Earned revenue | 5083985.34 | 5083985 | OK
Net over / (under) billed | -44608.34 | -44608 | OK | Negative = work done but not yet claimed
Billed ahead of the work (projects over-billed) | 40984.05 | 40984 | OK
Work not yet claimed (projects under-billed) | 85592.39 | 85592 | OK

## Projects
Project | Project name | Customer | Started | Status at 30 Sep 2026 | Contract (ex GST) | Approved variations (ex GST) | Total claimable (ex GST) | Claimed to date (ex GST) | Remaining (ex GST) | Retention | Cost centres total (ex GST) | Check: cost centres = claimable
P2511 | Office fit-out, Heidelberg | Head contractor 1 | Before Oct 2025 | Complete | 351500 | 49700 | 401200 | 401200 | 0 | 5% | 401200 | OK
P2512 | Warehouse lighting upgrade, Northcote | Head contractor 1 | Before Oct 2025 | Complete | 220500 | 6250 | 226750 | 226750 | 0 | 5% | 226750 | OK
P2513 | Aged care wing, St Kilda | Direct to owner | Before Oct 2025 | Complete | 145600 | 21950 | 167550 | 167550 | 0 | 0% | 167550 | OK
P2514 | School science block, Richmond | Head contractor 2 | Before Oct 2025 | Complete | 321800 | 67900 | 389700 | 389700 | 0 | 5% | 389700 | OK
P2515 | Showroom refurbishment, Preston West | Head contractor 1 | Before Oct 2025 | Complete | 542600 | 32550 | 575150 | 575150 | 0 | 5% | 575150 | OK
P2516 | Showroom refurbishment, Werribee | Direct to owner | Before Oct 2025 | Complete | 980000 | 296050 | 1276050 | 1276050 | 0 | 5% | 1276050 | OK
P2517 | Aged care wing, Essendon | Head contractor 1 | Before Oct 2025 | Complete | 434800 | 82600 | 517400 | 517400 | 0 | 5% | 517400 | OK
P2518 | Car park lighting and EV, Heidelberg | Direct to owner | Before Oct 2025 | Complete | 316100 | 30750 | 346850 | 346850 | 0 | 5% | 346850 | OK
P2519 | Car park lighting and EV, Williamstown | Direct to owner | Before Oct 2025 | Complete | 212900 | 26150 | 239050 | 239050 | 0 | 5% | 239050 | OK
P2520 | Industrial unit power upgrade, Hawthorn | Head contractor 4 | Before Oct 2025 | Complete | 326300 | 47950 | 374250 | 374250 | 0 | 0% | 374250 | OK
P2521 | Aged care wing, Coburg | Direct to owner | Before Oct 2025 | Complete | 379300 | 49500 | 428800 | 428800 | 0 | 0% | 428800 | OK
P2522 | Car park lighting and EV, Oakleigh | Direct to owner | Before Oct 2025 | Complete | 201700 | 9600 | 211300 | 211300 | 0 | 5% | 211300 | OK
P2523 | Aged care wing, Bayswater | Head contractor 3 | Before Oct 2025 | Complete | 147300 | 27400 | 174700 | 174700 | 0 | 0% | 174700 | OK
P2524 | Childcare centre, Preston | Head contractor 3 | Before Oct 2025 | Complete | 469600 | 98050 | 567650 | 567650 | 0 | 5% | 567650 | OK
P2525 | Medical centre electrical, Mentone | Head contractor 4 | Before Oct 2025 | Complete | 350500 | 71350 | 421850 | 421850 | 0 | 5% | 421850 | OK
P2526 | School science block, Clayton | Head contractor 2 | Before Oct 2025 | Live | 388300 | 39700 | 428000 | 408585 | 19415 | 5% | 428000 | OK
P2527 | Showroom refurbishment, Williamstown | Head contractor 2 | Before Oct 2025 | Complete | 307300 | 5500 | 312800 | 312800 | 0 | 5% | 312800 | OK
P2528 | Apartment common areas, Bayswater | Direct to owner | Before Oct 2025 | Complete | 364200 | 46050 | 410250 | 410250 | 0 | 0% | 410250 | OK
P2529 | Apartment common areas, Preston | Head contractor 5 | Before Oct 2025 | Complete | 75000 | 3200 | 78200 | 78200 | 0 | 0% | 78200 | OK
P2530 | Gym fit-out, Preston | Direct to owner | Before Oct 2025 | Complete | 367500 | 7600 | 375100 | 375100 | 0 | 5% | 375100 | OK
P2531 | Industrial unit power upgrade, Abbotsford | Head contractor 2 | Before Oct 2025 | Complete | 291100 | 5900 | 297000 | 297000 | 0 | 5% | 297000 | OK
P2532 | Industrial unit power upgrade, Ascot Vale | Head contractor 3 | Before Oct 2025 | Complete | 347300 | 19550 | 366850 | 366850 | 0 | 5% | 366850 | OK
P2533 | Office fit-out, Oakleigh | Head contractor 5 | Before Oct 2025 | Complete | 388900 | 89350 | 478250 | 478250 | 0 | 5% | 478250 | OK
P2534 | Retail tenancy fit-out, Bayswater | Head contractor 1 | Before Oct 2025 | Complete | 222400 | 0 | 222400 | 222400 | 0 | 5% | 222400 | OK
P2535 | Office fit-out, Preston | Head contractor 3 | Oct 2025 | Complete | 83300 | 0 | 83300 | 83300 | 0 | 0% | 83300 | OK
P2536 | Warehouse lighting upgrade, Preston | Head contractor 5 | Oct 2025 | Live | 251300 | 24650 | 275950 | 256222.95 | 19727.05 | 0% | 275950 | OK
P2537 | Car park lighting and EV, Ascot Vale | Direct to owner | Nov 2025 | Complete | 176600 | 10850 | 187450 | 187450 | 0 | 0% | 187450 | OK
P2538 | Medical centre electrical, Kew | Direct to owner | Nov 2025 | Complete | 77000 | 8550 | 85550 | 85550 | 0 | 0% | 85550 | OK
P2539 | Retail tenancy fit-out, Carlton | Direct to owner | Nov 2025 | Live | 256000 | 0 | 256000 | 232256 | 23744 | 0% | 256000 | OK
P2540 | Aged care wing, Burwood | Direct to owner | Dec 2025 | Complete | 106300 | 0 | 106300 | 106300 | 0 | 0% | 106300 | OK
P2541 | Apartment common areas, Clayton | Head contractor 3 | Dec 2025 | Live | 293900 | 34000 | 327900 | 311000.75 | 16899.25 | 5% | 327900 | OK
P2542 | Apartment common areas, Moonee Ponds | Head contractor 5 | Dec 2025 | Live | 95900 | 4950 | 100850 | 93705.8 | 7144.2 | 0% | 100850 | OK
P2543 | Retail tenancy fit-out, Yarraville | Head contractor 1 | Dec 2025 | Complete | 253700 | 12300 | 266000 | 266000 | 0 | 0% | 266000 | OK
P2544 | School science block, St Kilda | Head contractor 5 | Dec 2025 | Complete | 122100 | 16450 | 138550 | 138550 | 0 | 0% | 138550 | OK
P2545 | Showroom refurbishment, Hawthorn | Head contractor 5 | Dec 2025 | Live | 435400 | 36450 | 471850 | 429398.5 | 42451.5 | 0% | 471850 | OK
P2546 | Showroom refurbishment, Malvern | Direct to owner | Dec 2025 | Live | 980000 | 266800 | 1246800 | 1148458.2 | 98341.8 | 0% | 1246800 | OK
P2547 | School science block, Dandenong | Head contractor 1 | Jan 2026 | Live | 360200 | 39750 | 399950 | 372484.75 | 27465.25 | 0% | 399950 | OK
P2548 | School science block, Essendon | Head contractor 3 | Jan 2026 | Live | 240100 | 31000 | 271100 | 251411.8 | 19688.2 | 5% | 271100 | OK
P2549 | Warehouse lighting upgrade, Box Hill | Head contractor 3 | Jan 2026 | Live | 360200 | 35500 | 395700 | 304816.95 | 90883.05 | 0% | 395700 | OK
P2550 | Warehouse lighting upgrade, Fitzroy | Direct to owner | Jan 2026 | Live | 65500 | 0 | 65500 | 59113.75 | 6386.25 | 0% | 65500 | OK
P2551 | Warehouse lighting upgrade, Reservoir | Head contractor 1 | Jan 2026 | Live | 87300 | 3350 | 90650 | 80633.45 | 10016.55 | 0% | 90650 | OK
P2552 | Aged care wing, Hawthorn | Head contractor 2 | Feb 2026 | Live | 113800 | 0 | 113800 | 104326.15 | 9473.85 | 0% | 113800 | OK
P2553 | School science block, Bayswater | Head contractor 1 | Feb 2026 | Live | 506700 | 90900 | 597600 | 553010.4 | 44589.6 | 5% | 597600 | OK
P2554 | Showroom refurbishment, Reservoir | Head contractor 3 | Feb 2026 | Live | 137600 | 2500 | 140100 | 127337.6 | 12762.4 | 0% | 140100 | OK
P2555 | Gym fit-out, Camberwell | Direct to owner | Mar 2026 | Live | 101800 | 0 | 101800 | 81414.9 | 20385.1 | 0% | 101800 | OK
P2556 | Office fit-out, Preston West | Head contractor 3 | Apr 2026 | Live | 220700 | 25000 | 245700 | 225200.05 | 20499.95 | 5% | 245700 | OK
Total (follows filters) |  |  |  |  | 13477900 | 1777600 | 15255500 | 14765627 | 489873 |  | 15255500

## Cost centres
Project | Cost centre | Type | Variation | Value (ex GST) | Claimed to date % | Claimed to date (ex GST) | Remaining (ex GST)
P2511 | Site establishment and temporary power | Contract |  | 52319 | 100% | 52319 | 0
P2511 | Switchboards and metering | Contract |  | 45977 | 100% | 45977 | 0
P2511 | Containment and cabling | Contract |  | 68383 | 100% | 68383 | 0
P2511 | Mechanical services wiring | Contract |  | 96811 | 100% | 96811 | 0
P2511 | Fire detection interface | Contract |  | 77465 | 100% | 77465 | 0
P2511 | Testing and commissioning | Contract |  | 10545 | 100% | 10545 | 0
P2511 | Variation V033 | Approved variation | V033 | 24250 | 100% | 24250 | 0
P2511 | Variation V043 | Approved variation | V043 | 11650 | 100% | 11650 | 0
P2511 | Variation V047 | Approved variation | V047 | 6600 | 100% | 6600 | 0
P2511 | Variation V102 | Approved variation | V102 | 7200 | 100% | 7200 | 0
P2512 | Switchboards and metering | Contract |  | 36630 | 100% | 36630 | 0
P2512 | Lighting and emergency lighting | Contract |  | 48450 | 100% | 48450 | 0
P2512 | Power and data outlets | Contract |  | 73191 | 100% | 73191 | 0
P2512 | Fire detection interface | Contract |  | 54512 | 100% | 54512 | 0
P2512 | Testing and commissioning | Contract |  | 7717 | 100% | 7717 | 0
P2512 | Variation V048 | Approved variation | V048 | 6250 | 100% | 6250 | 0
P2513 | Switchboards and metering | Contract |  | 41650 | 100% | 41650 | 0
P2513 | Containment and cabling | Contract |  | 61883 | 100% | 61883 | 0
P2513 | Mechanical services wiring | Contract |  | 36243 | 100% | 36243 | 0
P2513 | Testing and commissioning | Contract |  | 5824 | 100% | 5824 | 0
P2513 | Variation V030 | Approved variation | V030 | 7400 | 100% | 7400 | 0
P2513 | Variation V049 | Approved variation | V049 | 6350 | 100% | 6350 | 0
P2513 | Variation V084 | Approved variation | V084 | 8200 | 100% | 8200 | 0
P2514 | Switchboards and metering | Contract |  | 64299 | 100% | 64299 | 0
P2514 | Containment and cabling | Contract |  | 85842 | 100% | 85842 | 0
P2514 | Lighting and emergency lighting | Contract |  | 71111 | 100% | 71111 | 0
P2514 | Power and data outlets | Contract |  | 86067 | 100% | 86067 | 0
P2514 | Testing and commissioning | Contract |  | 14481 | 100% | 14481 | 0
P2514 | Variation V009 | Approved variation | V009 | 21150 | 100% | 21150 | 0
P2514 | Variation V069 | Approved variation | V069 | 8450 | 100% | 8450 | 0
P2514 | Variation V073 | Approved variation | V073 | 7850 | 100% | 7850 | 0
P2514 | Variation V083 | Approved variation | V083 | 10000 | 100% | 10000 | 0
P2514 | Variation V107 | Approved variation | V107 | 6850 | 100% | 6850 | 0
P2514 | Variation V115 | Approved variation | V115 | 13600 | 100% | 13600 | 0
P2515 | Site establishment and temporary power | Contract |  | 128681 | 100% | 128681 | 0
P2515 | Switchboards and metering | Contract |  | 82041 | 100% | 82041 | 0
P2515 | Lighting and emergency lighting | Contract |  | 130001 | 100% | 130001 | 0
P2515 | Power and data outlets | Contract |  | 104299 | 100% | 104299 | 0
P2515 | Mechanical services wiring | Contract |  | 70448 | 100% | 70448 | 0
P2515 | Testing and commissioning | Contract |  | 27130 | 100% | 27130 | 0
P2515 | Variation V027 | Approved variation | V027 | 17100 | 100% | 17100 | 0
P2515 | Variation V036 | Approved variation | V036 | 15450 | 100% | 15450 | 0
P2516 | Switchboards and metering | Contract |  | 215278 | 100% | 215278 | 0
P2516 | Containment and cabling | Contract |  | 250856 | 100% | 250856 | 0
P2516 | Power and data outlets | Contract |  | 209774 | 100% | 209774 | 0
P2516 | Fire detection interface | Contract |  | 274692 | 100% | 274692 | 0
P2516 | Testing and commissioning | Contract |  | 29400 | 100% | 29400 | 0
P2516 | Variation V003 | Approved variation | V003 | 44450 | 100% | 44450 | 0
P2516 | Variation V021 | Approved variation | V021 | 16900 | 100% | 16900 | 0
P2516 | Variation V024 | Approved variation | V024 | 20800 | 100% | 20800 | 0
P2516 | Variation V032 | Approved variation | V032 | 65800 | 100% | 65800 | 0
P2516 | Variation V037 | Approved variation | V037 | 65450 | 100% | 65450 | 0
P2516 | Variation V041 | Approved variation | V041 | 54200 | 100% | 54200 | 0
P2516 | Variation V092 | Approved variation | V092 | 28450 | 100% | 28450 | 0
P2517 | Site establishment and temporary power | Contract |  | 52988 | 100% | 52988 | 0
P2517 | Containment and cabling | Contract |  | 60364 | 100% | 60364 | 0
P2517 | Lighting and emergency lighting | Contract |  | 57120 | 100% | 57120 | 0
P2517 | Power and data outlets | Contract |  | 93725 | 100% | 93725 | 0
P2517 | Mechanical services wiring | Contract |  | 67365 | 100% | 67365 | 0
P2517 | Fire detection interface | Contract |  | 88020 | 100% | 88020 | 0
P2517 | Testing and commissioning | Contract |  | 15218 | 100% | 15218 | 0
P2517 | Variation V001 | Approved variation | V001 | 22650 | 100% | 22650 | 0
P2517 | Variation V006 | Approved variation | V006 | 28250 | 100% | 28250 | 0
P2517 | Variation V022 | Approved variation | V022 | 20650 | 100% | 20650 | 0
P2517 | Variation V055 | Approved variation | V055 | 11050 | 100% | 11050 | 0
P2518 | Switchboards and metering | Contract |  | 147236 | 100% | 147236 | 0
P2518 | Lighting and emergency lighting | Contract |  | 156220 | 100% | 156220 | 0
P2518 | Testing and commissioning | Contract |  | 12644 | 100% | 12644 | 0
P2518 | Variation V011 | Approved variation | V011 | 15050 | 100% | 15050 | 0
P2518 | Variation V019 | Approved variation | V019 | 15700 | 100% | 15700 | 0
P2519 | Switchboards and metering | Contract |  | 130115 | 100% | 130115 | 0
P2519 | Lighting and emergency lighting | Contract |  | 73205 | 100% | 73205 | 0
P2519 | Testing and commissioning | Contract |  | 9580 | 100% | 9580 | 0
P2519 | Variation V012 | Approved variation | V012 | 8500 | 100% | 8500 | 0
P2519 | Variation V060 | Approved variation | V060 | 12300 | 100% | 12300 | 0
P2519 | Variation V072 | Approved variation | V072 | 5350 | 100% | 5350 | 0
P2520 | Switchboards and metering | Contract |  | 149425 | 100% | 149425 | 0
P2520 | Fire detection interface | Contract |  | 160560 | 100% | 160560 | 0
P2520 | Testing and commissioning | Contract |  | 16315 | 100% | 16315 | 0
P2520 | Variation V052 | Approved variation | V052 | 22400 | 100% | 22400 | 0
P2520 | Variation V061 | Approved variation | V061 | 10050 | 100% | 10050 | 0
P2520 | Variation V088 | Approved variation | V088 | 15500 | 100% | 15500 | 0
P2521 | Site establishment and temporary power | Contract |  | 35611 | 100% | 35611 | 0
P2521 | Switchboards and metering | Contract |  | 68718 | 100% | 68718 | 0
P2521 | Containment and cabling | Contract |  | 65820 | 100% | 65820 | 0
P2521 | Lighting and emergency lighting | Contract |  | 56454 | 100% | 56454 | 0
P2521 | Power and data outlets | Contract |  | 70509 | 100% | 70509 | 0
P2521 | Mechanical services wiring | Contract |  | 70809 | 100% | 70809 | 0
P2521 | Testing and commissioning | Contract |  | 11379 | 100% | 11379 | 0
P2521 | Variation V031 | Approved variation | V031 | 20350 | 100% | 20350 | 0
P2521 | Variation V058 | Approved variation | V058 | 17000 | 100% | 17000 | 0
P2521 | Variation V133 | Approved variation | V133 | 12150 | 100% | 12150 | 0
P2522 | Switchboards and metering | Contract |  | 86803 | 100% | 86803 | 0
P2522 | Containment and cabling | Contract |  | 61294 | 100% | 61294 | 0
P2522 | Mechanical services wiring | Contract |  | 46544 | 100% | 46544 | 0
P2522 | Testing and commissioning | Contract |  | 7059 | 100% | 7059 | 0
P2522 | Variation V013 | Approved variation | V013 | 9600 | 100% | 9600 | 0
P2523 | Switchboards and metering | Contract |  | 71290 | 100% | 71290 | 0
P2523 | Power and data outlets | Contract |  | 70118 | 100% | 70118 | 0
P2523 | Testing and commissioning | Contract |  | 5892 | 100% | 5892 | 0
P2523 | Variation V002 | Approved variation | V002 | 9850 | 100% | 9850 | 0
P2523 | Variation V111 | Approved variation | V111 | 7700 | 100% | 7700 | 0
P2523 | Variation V125 | Approved variation | V125 | 9850 | 100% | 9850 | 0
P2524 | Switchboards and metering | Contract |  | 76466 | 100% | 76466 | 0
P2524 | Containment and cabling | Contract |  | 161713 | 100% | 161713 | 0
P2524 | Power and data outlets | Contract |  | 82588 | 100% | 82588 | 0
P2524 | Mechanical services wiring | Contract |  | 127701 | 100% | 127701 | 0
P2524 | Testing and commissioning | Contract |  | 21132 | 100% | 21132 | 0
P2524 | Variation V046 | Approved variation | V046 | 32450 | 100% | 32450 | 0
P2524 | Variation V070 | Approved variation | V070 | 15300 | 100% | 15300 | 0
P2524 | Variation V101 | Approved variation | V101 | 30150 | 100% | 30150 | 0
P2524 | Variation V105 | Approved variation | V105 | 20150 | 100% | 20150 | 0
P2525 | Site establishment and temporary power | Contract |  | 82329 | 100% | 82329 | 0
P2525 | Switchboards and metering | Contract |  | 58862 | 100% | 58862 | 0
P2525 | Containment and cabling | Contract |  | 36548 | 100% | 36548 | 0
P2525 | Lighting and emergency lighting | Contract |  | 64673 | 100% | 64673 | 0
P2525 | Mechanical services wiring | Contract |  | 38963 | 100% | 38963 | 0
P2525 | Fire detection interface | Contract |  | 51600 | 100% | 51600 | 0
P2525 | Testing and commissioning | Contract |  | 17525 | 100% | 17525 | 0
P2525 | Variation V007 | Approved variation | V007 | 20350 | 100% | 20350 | 0
P2525 | Variation V014 | Approved variation | V014 | 16100 | 100% | 16100 | 0
P2525 | Variation V020 | Approved variation | V020 | 20150 | 100% | 20150 | 0
P2525 | Variation V050 | Approved variation | V050 | 14750 | 100% | 14750 | 0
P2526 | Site establishment and temporary power | Contract |  | 113189 | 95% | 107529.55 | 5659.45
P2526 | Switchboards and metering | Contract |  | 117059 | 95% | 111206.05 | 5852.95
P2526 | Lighting and emergency lighting | Contract |  | 88538 | 95% | 84111.1 | 4426.9
P2526 | Mechanical services wiring | Contract |  | 57865 | 95% | 54971.75 | 2893.25
P2526 | Testing and commissioning | Contract |  | 11649 | 95% | 11066.55 | 582.45
P2526 | Variation V025 | Approved variation | V025 | 18850 | 100% | 18850 | 0
P2526 | Variation V134 | Approved variation | V134 | 20850 | 100% | 20850 | 0
P2527 | Switchboards and metering | Contract |  | 102217 | 100% | 102217 | 0
P2527 | Containment and cabling | Contract |  | 71314 | 100% | 71314 | 0
P2527 | Lighting and emergency lighting | Contract |  | 123013 | 100% | 123013 | 0
P2527 | Testing and commissioning | Contract |  | 10756 | 100% | 10756 | 0
P2527 | Variation V038 | Approved variation | V038 | 5500 | 100% | 5500 | 0
P2528 | Switchboards and metering | Contract |  | 128247 | 100% | 128247 | 0
P2528 | Mechanical services wiring | Contract |  | 64638 | 100% | 64638 | 0
P2528 | Fire detection interface | Contract |  | 156747 | 100% | 156747 | 0
P2528 | Testing and commissioning | Contract |  | 14568 | 100% | 14568 | 0
P2528 | Variation V062 | Approved variation | V062 | 20100 | 100% | 20100 | 0
P2528 | Variation V075 | Approved variation | V075 | 9300 | 100% | 9300 | 0
P2528 | Variation V079 | Approved variation | V079 | 16650 | 100% | 16650 | 0
P2529 | Switchboards and metering | Contract |  | 30532 | 100% | 30532 | 0
P2529 | Mechanical services wiring | Contract |  | 41093 | 100% | 41093 | 0
P2529 | Testing and commissioning | Contract |  | 3375 | 100% | 3375 | 0
P2529 | Variation V086 | Approved variation | V086 | 3200 | 100% | 3200 | 0
P2530 | Site establishment and temporary power | Contract |  | 93920 | 100% | 93920 | 0
P2530 | Switchboards and metering | Contract |  | 49233 | 100% | 49233 | 0
P2530 | Containment and cabling | Contract |  | 55177 | 100% | 55177 | 0
P2530 | Lighting and emergency lighting | Contract |  | 87014 | 100% | 87014 | 0
P2530 | Mechanical services wiring | Contract |  | 63781 | 100% | 63781 | 0
P2530 | Testing and commissioning | Contract |  | 18375 | 100% | 18375 | 0
P2530 | Variation V117 | Approved variation | V117 | 7600 | 100% | 7600 | 0
P2531 | Site establishment and temporary power | Contract |  | 62744 | 100% | 62744 | 0
P2531 | Containment and cabling | Contract |  | 60889 | 100% | 60889 | 0
P2531 | Lighting and emergency lighting | Contract |  | 75891 | 100% | 75891 | 0
P2531 | Power and data outlets | Contract |  | 39422 | 100% | 39422 | 0
P2531 | Fire detection interface | Contract |  | 43421 | 100% | 43421 | 0
P2531 | Testing and commissioning | Contract |  | 8733 | 100% | 8733 | 0
P2531 | Variation V035 | Approved variation | V035 | 5900 | 100% | 5900 | 0
P2532 | Switchboards and metering | Contract |  | 102426 | 100% | 102426 | 0
P2532 | Containment and cabling | Contract |  | 114338 | 100% | 114338 | 0
P2532 | Lighting and emergency lighting | Contract |  | 56498 | 100% | 56498 | 0
P2532 | Power and data outlets | Contract |  | 61883 | 100% | 61883 | 0
P2532 | Testing and commissioning | Contract |  | 12155 | 100% | 12155 | 0
P2532 | Variation V040 | Approved variation | V040 | 8100 | 100% | 8100 | 0
P2532 | Variation V094 | Approved variation | V094 | 6050 | 100% | 6050 | 0
P2532 | Variation V098 | Approved variation | V098 | 5400 | 100% | 5400 | 0
P2533 | Switchboards and metering | Contract |  | 112049 | 100% | 112049 | 0
P2533 | Containment and cabling | Contract |  | 117441 | 100% | 117441 | 0
P2533 | Lighting and emergency lighting | Contract |  | 69841 | 100% | 69841 | 0
P2533 | Power and data outlets | Contract |  | 74013 | 100% | 74013 | 0
P2533 | Testing and commissioning | Contract |  | 15556 | 100% | 15556 | 0
P2533 | Variation V023 | Approved variation | V023 | 25450 | 100% | 25450 | 0
P2533 | Variation V054 | Approved variation | V054 | 26050 | 100% | 26050 | 0
P2533 | Variation V066 | Approved variation | V066 | 15300 | 100% | 15300 | 0
P2533 | Variation V103 | Approved variation | V103 | 9500 | 100% | 9500 | 0
P2533 | Variation V114 | Approved variation | V114 | 13050 | 100% | 13050 | 0
P2534 | Switchboards and metering | Contract |  | 87293 | 100% | 87293 | 0
P2534 | Lighting and emergency lighting | Contract |  | 67372 | 100% | 67372 | 0
P2534 | Mechanical services wiring | Contract |  | 57727 | 100% | 57727 | 0
P2534 | Testing and commissioning | Contract |  | 10008 | 100% | 10008 | 0
P2535 | Switchboards and metering | Contract |  | 39359 | 100% | 39359 | 0
P2535 | Lighting and emergency lighting | Contract |  | 39776 | 100% | 39776 | 0
P2535 | Testing and commissioning | Contract |  | 4165 | 100% | 4165 | 0
P2536 | Site establishment and temporary power | Contract |  | 55065 | 95% | 52311.75 | 2753.25
P2536 | Switchboards and metering | Contract |  | 60141 | 95% | 57133.95 | 3007.05
P2536 | Power and data outlets | Contract |  | 50415 | 95% | 47894.25 | 2520.75
P2536 | Mechanical services wiring | Contract |  | 78140 | 95% | 74233 | 3907
P2536 | Testing and commissioning | Contract |  | 7539 | 0% | 0 | 7539
P2536 | Variation V015 | Approved variation | V015 | 13650 | 100% | 13650 | 0
P2536 | Variation V097 | Approved variation | V097 | 7100 | 100% | 7100 | 0
P2536 | Variation V127 | Approved variation | V127 | 3900 | 100% | 3900 | 0
P2537 | Switchboards and metering | Contract |  | 51858 | 100% | 51858 | 0
P2537 | Power and data outlets | Contract |  | 63669 | 100% | 63669 | 0
P2537 | Mechanical services wiring | Contract |  | 54892 | 100% | 54892 | 0
P2537 | Testing and commissioning | Contract |  | 6181 | 100% | 6181 | 0
P2537 | Variation V076 | Approved variation | V076 | 10850 | 100% | 10850 | 0
P2538 | Switchboards and metering | Contract |  | 13621 | 100% | 13621 | 0
P2538 | Containment and cabling | Contract |  | 27857 | 100% | 27857 | 0
P2538 | Mechanical services wiring | Contract |  | 32442 | 100% | 32442 | 0
P2538 | Testing and commissioning | Contract |  | 3080 | 100% | 3080 | 0
P2538 | Variation V026 | Approved variation | V026 | 3600 | 100% | 3600 | 0
P2538 | Variation V139 | Approved variation | V139 | 4950 | 100% | 4950 | 0
P2539 | Switchboards and metering | Contract |  | 78199 | 95% | 74289.05 | 3909.95
P2539 | Containment and cabling | Contract |  | 53912 | 95% | 51216.4 | 2695.6
P2539 | Lighting and emergency lighting | Contract |  | 52446 | 95% | 49823.7 | 2622.3
P2539 | Mechanical services wiring | Contract |  | 59923 | 95% | 56926.85 | 2996.15
P2539 | Testing and commissioning | Contract |  | 11520 | 0% | 0 | 11520
P2540 | Switchboards and metering | Contract |  | 36891 | 100% | 36891 | 0
P2540 | Lighting and emergency lighting | Contract |  | 34168 | 100% | 34168 | 0
P2540 | Fire detection interface | Contract |  | 29926 | 100% | 29926 | 0
P2540 | Testing and commissioning | Contract |  | 5315 | 100% | 5315 | 0
P2541 | Switchboards and metering | Contract |  | 65960 | 95% | 62662 | 3298
P2541 | Lighting and emergency lighting | Contract |  | 97780 | 95% | 92891 | 4889
P2541 | Power and data outlets | Contract |  | 121343 | 95% | 115275.85 | 6067.15
P2541 | Testing and commissioning | Contract |  | 8817 | 70% | 6171.9 | 2645.1
P2541 | Variation V042 | Approved variation | V042 | 15000 | 100% | 15000 | 0
P2541 | Variation V044 | Approved variation | V044 | 10800 | 100% | 10800 | 0
P2541 | Variation V109 | Approved variation | V109 | 8200 | 100% | 8200 | 0
P2542 | Switchboards and metering | Contract |  | 46711 | 95% | 44375.45 | 2335.55
P2542 | Containment and cabling | Contract |  | 45833 | 95% | 43541.35 | 2291.65
P2542 | Testing and commissioning | Contract |  | 3356 | 25% | 839 | 2517
P2542 | Variation V082 | Approved variation | V082 | 4950 | 100% | 4950 | 0
P2543 | Switchboards and metering | Contract |  | 131163 | 100% | 131163 | 0
P2543 | Containment and cabling | Contract |  | 112389 | 100% | 112389 | 0
P2543 | Testing and commissioning | Contract |  | 10148 | 100% | 10148 | 0
P2543 | Variation V064 | Approved variation | V064 | 5700 | 100% | 5700 | 0
P2543 | Variation V100 | Approved variation | V100 | 6600 | 100% | 6600 | 0
P2544 | Switchboards and metering | Contract |  | 70302 | 100% | 70302 | 0
P2544 | Mechanical services wiring | Contract |  | 46304 | 100% | 46304 | 0
P2544 | Testing and commissioning | Contract |  | 5494 | 100% | 5494 | 0
P2544 | Variation V099 | Approved variation | V099 | 8250 | 100% | 8250 | 0
P2544 | Variation V119 | Approved variation | V119 | 5650 | 100% | 5650 | 0
P2544 | Variation V122 | Approved variation | V122 | 2550 | 100% | 2550 | 0
P2545 | Site establishment and temporary power | Contract |  | 66674 | 95% | 63340.3 | 3333.7
P2545 | Containment and cabling | Contract |  | 65213 | 95% | 61952.35 | 3260.65
P2545 | Lighting and emergency lighting | Contract |  | 74772 | 95% | 71033.4 | 3738.6
P2545 | Power and data outlets | Contract |  | 75250 | 95% | 71487.5 | 3762.5
P2545 | Mechanical services wiring | Contract |  | 66549 | 95% | 63221.55 | 3327.45
P2545 | Fire detection interface | Contract |  | 65172 | 95% | 61913.4 | 3258.6
P2545 | Testing and commissioning | Contract |  | 21770 | 0% | 0 | 21770
P2545 | Variation V081 | Approved variation | V081 | 25200 | 100% | 25200 | 0
P2545 | Variation V130 | Approved variation | V130 | 11250 | 100% | 11250 | 0
P2546 | Site establishment and temporary power | Contract |  | 111692 | 95% | 106107.4 | 5584.6
P2546 | Switchboards and metering | Contract |  | 199143 | 95% | 189185.85 | 9957.15
P2546 | Lighting and emergency lighting | Contract |  | 149254 | 95% | 141791.3 | 7462.7
P2546 | Power and data outlets | Contract |  | 145202 | 95% | 137941.9 | 7260.1
P2546 | Mechanical services wiring | Contract |  | 131191 | 95% | 124631.45 | 6559.55
P2546 | Fire detection interface | Contract |  | 214118 | 85% | 182000.3 | 32117.7
P2546 | Testing and commissioning | Contract |  | 29400 | 0% | 0 | 29400
P2546 | Variation V071 | Approved variation | V071 | 63150 | 100% | 63150 | 0
P2546 | Variation V110 | Approved variation | V110 | 58250 | 100% | 58250 | 0
P2546 | Variation V112 | Approved variation | V112 | 62850 | 100% | 62850 | 0
P2546 | Variation V128 | Approved variation | V128 | 59300 | 100% | 59300 | 0
P2546 | Variation V138 | Approved variation | V138 | 23250 | 100% | 23250 | 0
P2547 | Site establishment and temporary power | Contract |  | 87945 | 95% | 83547.75 | 4397.25
P2547 | Switchboards and metering | Contract |  | 76199 | 95% | 72389.05 | 3809.95
P2547 | Containment and cabling | Contract |  | 85753 | 95% | 81465.35 | 4287.65
P2547 | Lighting and emergency lighting | Contract |  | 38357 | 95% | 36439.15 | 1917.85
P2547 | Mechanical services wiring | Contract |  | 59339 | 95% | 56372.05 | 2966.95
P2547 | Testing and commissioning | Contract |  | 12607 | 20% | 2521.4 | 10085.6
P2547 | Variation V124 | Approved variation | V124 | 6150 | 100% | 6150 | 0
P2547 | Variation V135 | Approved variation | V135 | 20450 | 100% | 20450 | 0
P2547 | Variation V136 | Approved variation | V136 | 13150 | 100% | 13150 | 0
P2548 | Switchboards and metering | Contract |  | 111932 | 95% | 106335.4 | 5596.6
P2548 | Lighting and emergency lighting | Contract |  | 118564 | 95% | 112635.8 | 5928.2
P2548 | Testing and commissioning | Contract |  | 9604 | 15% | 1440.6 | 8163.4
P2548 | Variation V053 | Approved variation | V053 | 9950 | 100% | 9950 | 0
P2548 | Variation V067 | Approved variation | V067 | 13500 | 100% | 13500 | 0
P2548 | Variation V074 | Approved variation | V074 | 7550 | 100% | 7550 | 0
P2549 | Switchboards and metering | Contract |  | 110292 | 95% | 104777.4 | 5514.6
P2549 | Containment and cabling | Contract |  | 120017 | 85% | 102014.45 | 18002.55
P2549 | Lighting and emergency lighting | Contract |  | 113682 | 55% | 62525.1 | 51156.9
P2549 | Testing and commissioning | Contract |  | 16209 | 0% | 0 | 16209
P2549 | Variation V059 | Approved variation | V059 | 18300 | 100% | 18300 | 0
P2549 | Variation V078 | Approved variation | V078 | 17200 | 100% | 17200 | 0
P2550 | Switchboards and metering | Contract |  | 27539 | 95% | 26162.05 | 1376.95
P2550 | Mechanical services wiring | Contract |  | 34686 | 95% | 32951.7 | 1734.3
P2550 | Testing and commissioning | Contract |  | 3275 | 0% | 0 | 3275
P2551 | Site establishment and temporary power | Contract |  | 18927 | 95% | 17980.65 | 946.35
P2551 | Switchboards and metering | Contract |  | 44664 | 95% | 42430.8 | 2233.2
P2551 | Containment and cabling | Contract |  | 21090 | 80% | 16872 | 4218
P2551 | Testing and commissioning | Contract |  | 2619 | 0% | 0 | 2619
P2551 | Variation V056 | Approved variation | V056 | 3350 | 100% | 3350 | 0
P2552 | Switchboards and metering | Contract |  | 49674 | 95% | 47190.3 | 2483.7
P2552 | Mechanical services wiring | Contract |  | 60143 | 95% | 57135.85 | 3007.15
P2552 | Testing and commissioning | Contract |  | 3983 | 0% | 0 | 3983
P2553 | Switchboards and metering | Contract |  | 114922 | 95% | 109175.9 | 5746.1
P2553 | Containment and cabling | Contract |  | 121249 | 95% | 115186.55 | 6062.45
P2553 | Mechanical services wiring | Contract |  | 117163 | 95% | 111304.85 | 5858.15
P2553 | Fire detection interface | Contract |  | 133098 | 95% | 126443.1 | 6654.9
P2553 | Testing and commissioning | Contract |  | 20268 | 0% | 0 | 20268
P2553 | Variation V091 | Approved variation | V091 | 30150 | 100% | 30150 | 0
P2553 | Variation V108 | Approved variation | V108 | 33300 | 100% | 33300 | 0
P2553 | Variation V129 | Approved variation | V129 | 27450 | 100% | 27450 | 0
P2554 | Switchboards and metering | Contract |  | 66953 | 95% | 63605.35 | 3347.65
P2554 | Mechanical services wiring | Contract |  | 64455 | 95% | 61232.25 | 3222.75
P2554 | Testing and commissioning | Contract |  | 6192 | 0% | 0 | 6192
P2554 | Variation V126 | Approved variation | V126 | 2500 | 100% | 2500 | 0
P2555 | Switchboards and metering | Contract |  | 44412 | 95% | 42191.4 | 2220.6
P2555 | Containment and cabling | Contract |  | 52298 | 75% | 39223.5 | 13074.5
P2555 | Testing and commissioning | Contract |  | 5090 | 0% | 0 | 5090
P2556 | Switchboards and metering | Contract |  | 73962 | 95% | 70263.9 | 3698.1
P2556 | Lighting and emergency lighting | Contract |  | 77160 | 95% | 73302 | 3858
P2556 | Power and data outlets | Contract |  | 62957 | 95% | 59809.15 | 3147.85
P2556 | Testing and commissioning | Contract |  | 6621 | 0% | 0 | 6621
P2556 | Variation V113 | Approved variation | V113 | 14750 | 100% | 14750 | 0
P2556 | Variation V132 | Approved variation | V132 | 3900 | 100% | 3900 | 0
P2556 | Variation V140 | Approved variation | V140 | 6350 | 50% | 3175 | 3175
Total (follows filters) |  |  |  | 15255500 |  | 14765627 | 489873

## Claims
Claim | Project | Project name | Claim date | Type | Claimed (ex GST) | Retention held back | Retention released | Net (ex GST) | GST 10% | Invoice total (inc GST) | Status | Month
INV-30401 | P2511 | Office fit-out, Heidelberg | 2025-10-25 | Progress claim | 34859.25 | 1742.96 | 0 | 33116.29 | 3311.63 | 36427.92 | Approved - sent to Xero | 2025-10-01
INV-30402 | P2512 | Warehouse lighting upgrade, Northcote | 2025-10-25 | Progress claim | 38562.4 | 1928.12 | 0 | 36634.28 | 3663.43 | 40297.71 | Approved - sent to Xero | 2025-10-01
INV-30403 | P2513 | Aged care wing, St Kilda | 2025-10-25 | Progress claim | 7248.6 | 0 | 0 | 7248.6 | 724.86 | 7973.46 | Approved - sent to Xero | 2025-10-01
INV-30404 | P2514 | School science block, Richmond | 2025-10-25 | Progress claim | 80272.05 | 4013.6 | 0 | 76258.45 | 7625.85 | 83884.3 | Approved - sent to Xero | 2025-10-01
INV-30405 | P2515 | Showroom refurbishment, Preston West | 2025-10-25 | Progress claim | 14374.4 | 718.72 | 0 | 13655.68 | 1365.57 | 15021.25 | Approved - sent to Xero | 2025-10-01
INV-30406 | P2516 | Showroom refurbishment, Werribee | 2025-10-25 | Progress claim | 153079.2 | 7653.96 | 0 | 145425.24 | 14542.52 | 159967.76 | Approved - sent to Xero | 2025-10-01
INV-30407 | P2517 | Aged care wing, Essendon | 2025-10-25 | Progress claim | 25450 | 1272.5 | 0 | 24177.5 | 2417.75 | 26595.25 | Approved - sent to Xero | 2025-10-01
INV-30408 | P2518 | Car park lighting and EV, Heidelberg | 2025-10-25 | Progress claim | 17640.2 | 882.01 | 0 | 16758.19 | 1675.82 | 18434.01 | Approved - sent to Xero | 2025-10-01
INV-30409 | P2519 | Car park lighting and EV, Williamstown | 2025-10-25 | Progress claim | 55080 | 2754 | 0 | 52326 | 5232.6 | 57558.6 | Approved - sent to Xero | 2025-10-01
INV-30410 | P2520 | Industrial unit power upgrade, Hawthorn | 2025-10-25 | Progress claim | 93552.25 | 0 | 0 | 93552.25 | 9355.23 | 102907.48 | Approved - sent to Xero | 2025-10-01
INV-30411 | P2521 | Aged care wing, Coburg | 2025-10-25 | Progress claim | 24282 | 0 | 0 | 24282 | 2428.2 | 26710.2 | Approved - sent to Xero | 2025-10-01
INV-30412 | P2522 | Car park lighting and EV, Oakleigh | 2025-10-25 | Progress claim | 53351.25 | 2667.56 | 0 | 50683.69 | 5068.37 | 55752.06 | Approved - sent to Xero | 2025-10-01
INV-30413 | P2523 | Aged care wing, Bayswater | 2025-10-25 | Progress claim | 15618.5 | 0 | 0 | 15618.5 | 1561.85 | 17180.35 | Approved - sent to Xero | 2025-10-01
INV-30414 | P2524 | Childcare centre, Preston | 2025-10-25 | Progress claim | 63102.15 | 3155.11 | 0 | 59947.04 | 5994.7 | 65941.74 | Approved - sent to Xero | 2025-10-01
INV-30415 | P2525 | Medical centre electrical, Mentone | 2025-10-25 | Progress claim | 123080.65 | 6154.03 | 0 | 116926.62 | 11692.66 | 128619.28 | Approved - sent to Xero | 2025-10-01
INV-30416 | P2526 | School science block, Clayton | 2025-10-25 | Progress claim | 23024.8 | 1151.24 | 0 | 21873.56 | 2187.36 | 24060.92 | Approved - sent to Xero | 2025-10-01
INV-30417 | P2527 | Showroom refurbishment, Williamstown | 2025-10-25 | Progress claim | 20443.4 | 1022.17 | 0 | 19421.23 | 1942.12 | 21363.35 | Approved - sent to Xero | 2025-10-01
INV-30418 | P2528 | Apartment common areas, Bayswater | 2025-10-25 | Progress claim | 102649.05 | 0 | 0 | 102649.05 | 10264.91 | 112913.96 | Approved - sent to Xero | 2025-10-01
INV-30419 | P2529 | Apartment common areas, Preston | 2025-10-25 | Progress claim | 16792.6 | 0 | 0 | 16792.6 | 1679.26 | 18471.86 | Approved - sent to Xero | 2025-10-01
INV-30420 | P2530 | Gym fit-out, Preston | 2025-10-25 | Progress claim | 14088 | 704.4 | 0 | 13383.6 | 1338.36 | 14721.96 | Approved - sent to Xero | 2025-10-01
INV-30421 | P2531 | Industrial unit power upgrade, Abbotsford | 2025-10-25 | Progress claim | 63780.45 | 3189.02 | 0 | 60591.43 | 6059.14 | 66650.57 | Approved - sent to Xero | 2025-10-01
INV-30422 | P2532 | Industrial unit power upgrade, Ascot Vale | 2025-10-25 | Progress claim | 25606.5 | 1280.33 | 0 | 24326.17 | 2432.62 | 26758.79 | Approved - sent to Xero | 2025-10-01
INV-30423 | P2533 | Office fit-out, Oakleigh | 2025-10-25 | Progress claim | 28281.85 | 1414.09 | 0 | 26867.76 | 2686.78 | 29554.54 | Approved - sent to Xero | 2025-10-01
INV-30424 | P2536 | Warehouse lighting upgrade, Preston | 2025-10-25 | Progress claim | 6825 | 0 | 0 | 6825 | 682.5 | 7507.5 | Approved - sent to Xero | 2025-10-01
INV-30425 | P2512 | Warehouse lighting upgrade, Northcote | 2025-11-10 | Progress claim | 8176.8 | 408.84 | 0 | 7767.96 | 776.8 | 8544.76 | Approved - sent to Xero | 2025-11-01
INV-30426 | P2514 | School science block, Richmond | 2025-11-10 | Progress claim | 38455.05 | 1922.75 | 0 | 36532.3 | 3653.23 | 40185.53 | Approved - sent to Xero | 2025-11-01
INV-30427 | P2515 | Showroom refurbishment, Preston West | 2025-11-10 | Progress claim | 9495.5 | 474.78 | 0 | 9020.72 | 902.07 | 9922.79 | Approved - sent to Xero | 2025-11-01
INV-30428 | P2516 | Showroom refurbishment, Werribee | 2025-11-10 | Progress claim | 82278.8 | 4113.94 | 0 | 78164.86 | 7816.49 | 85981.35 | Approved - sent to Xero | 2025-11-01
INV-30429 | P2517 | Aged care wing, Essendon | 2025-11-10 | Progress claim | 37296.8 | 1864.84 | 0 | 35431.96 | 3543.2 | 38975.16 | Approved - sent to Xero | 2025-11-01
INV-30430 | P2519 | Car park lighting and EV, Williamstown | 2025-11-10 | Progress claim | 25396.75 | 1269.84 | 0 | 24126.91 | 2412.69 | 26539.6 | Approved - sent to Xero | 2025-11-01
INV-30431 | P2520 | Industrial unit power upgrade, Hawthorn | 2025-11-10 | Progress claim | 62553.75 | 0 | 0 | 62553.75 | 6255.38 | 68809.13 | Approved - sent to Xero | 2025-11-01
INV-30432 | P2521 | Aged care wing, Coburg | 2025-11-10 | Progress claim | 24585.75 | 0 | 0 | 24585.75 | 2458.58 | 27044.33 | Approved - sent to Xero | 2025-11-01
INV-30433 | P2522 | Car park lighting and EV, Oakleigh | 2025-11-10 | Progress claim | 14108.8 | 705.44 | 0 | 13403.36 | 1340.34 | 14743.7 | Approved - sent to Xero | 2025-11-01
INV-30434 | P2523 | Aged care wing, Bayswater | 2025-11-10 | Progress claim | 19124.4 | 0 | 0 | 19124.4 | 1912.44 | 21036.84 | Approved - sent to Xero | 2025-11-01
INV-30435 | P2526 | School science block, Clayton | 2025-11-10 | Progress claim | 23024.8 | 1151.24 | 0 | 21873.56 | 2187.36 | 24060.92 | Approved - sent to Xero | 2025-11-01
INV-30436 | P2527 | Showroom refurbishment, Williamstown | 2025-11-10 | Progress claim | 28614.6 | 1430.73 | 0 | 27183.87 | 2718.39 | 29902.26 | Approved - sent to Xero | 2025-11-01
INV-30437 | P2528 | Apartment common areas, Bayswater | 2025-11-10 | Progress claim | 49315.8 | 0 | 0 | 49315.8 | 4931.58 | 54247.38 | Approved - sent to Xero | 2025-11-01
INV-30438 | P2529 | Apartment common areas, Preston | 2025-11-10 | Progress claim | 9159.6 | 0 | 0 | 9159.6 | 915.96 | 10075.56 | Approved - sent to Xero | 2025-11-01
INV-30439 | P2530 | Gym fit-out, Preston | 2025-11-10 | Progress claim | 9392 | 469.6 | 0 | 8922.4 | 892.24 | 9814.64 | Approved - sent to Xero | 2025-11-01
INV-30440 | P2531 | Industrial unit power upgrade, Abbotsford | 2025-11-10 | Progress claim | 59070.2 | 2953.51 | 0 | 56116.69 | 5611.67 | 61728.36 | Approved - sent to Xero | 2025-11-01
INV-30441 | P2532 | Industrial unit power upgrade, Ascot Vale | 2025-11-10 | Progress claim | 31919 | 1595.95 | 0 | 30323.05 | 3032.31 | 33355.36 | Approved - sent to Xero | 2025-11-01
INV-30442 | P2535 | Office fit-out, Preston | 2025-11-10 | Progress claim | 1967.95 | 0 | 0 | 1967.95 | 196.8 | 2164.75 | Approved - sent to Xero | 2025-11-01
INV-30443 | P2511 | Office fit-out, Heidelberg | 2025-11-25 | Progress claim | 7746.5 | 387.33 | 0 | 7359.17 | 735.92 | 8095.09 | Approved - sent to Xero | 2025-11-01
INV-30444 | P2512 | Warehouse lighting upgrade, Northcote | 2025-11-25 | Progress claim | 5451.2 | 272.56 | 0 | 5178.64 | 517.86 | 5696.5 | Approved - sent to Xero | 2025-11-01
INV-30445 | P2513 | Aged care wing, St Kilda | 2025-11-25 | Progress claim | 3700 | 0 | 0 | 3700 | 370 | 4070 | Approved - sent to Xero | 2025-11-01
INV-30446 | P2514 | School science block, Richmond | 2025-11-25 | Progress claim | 27880.05 | 1394 | 0 | 26486.05 | 2648.61 | 29134.66 | Approved - sent to Xero | 2025-11-01
INV-30447 | P2515 | Showroom refurbishment, Preston West | 2025-11-25 | Progress claim | 13976 | 698.8 | 0 | 13277.2 | 1327.72 | 14604.92 | Approved - sent to Xero | 2025-11-01
INV-30448 | P2516 | Showroom refurbishment, Werribee | 2025-11-25 | Progress claim | 79219.2 | 3960.96 | 0 | 75258.24 | 7525.82 | 82784.06 | Approved - sent to Xero | 2025-11-01
INV-30449 | P2517 | Aged care wing, Essendon | 2025-11-25 | Progress claim | 15651.3 | 782.57 | 0 | 14868.73 | 1486.87 | 16355.6 | Approved - sent to Xero | 2025-11-01
INV-30450 | P2518 | Car park lighting and EV, Heidelberg | 2025-11-25 | Final claim | 40294.4 | 2014.72 | 8671.25 | 46950.93 | 4695.09 | 51646.02 | Approved - sent to Xero | 2025-11-01
INV-30451 | P2519 | Car park lighting and EV, Williamstown | 2025-11-25 | Progress claim | 14641 | 732.05 | 0 | 13908.95 | 1390.9 | 15299.85 | Approved - sent to Xero | 2025-11-01
INV-30452 | P2520 | Industrial unit power upgrade, Hawthorn | 2025-11-25 | Progress claim | 47054.5 | 0 | 0 | 47054.5 | 4705.45 | 51759.95 | Approved - sent to Xero | 2025-11-01
INV-30453 | P2521 | Aged care wing, Coburg | 2025-11-25 | Progress claim | 41342.75 | 0 | 0 | 41342.75 | 4134.28 | 45477.03 | Approved - sent to Xero | 2025-11-01
INV-30454 | P2522 | Car park lighting and EV, Oakleigh | 2025-11-25 | Progress claim | 2327.2 | 116.36 | 0 | 2210.84 | 221.08 | 2431.92 | Approved - sent to Xero | 2025-11-01
INV-30455 | P2523 | Aged care wing, Bayswater | 2025-11-25 | Progress claim | 17705.3 | 0 | 0 | 17705.3 | 1770.53 | 19475.83 | Approved - sent to Xero | 2025-11-01
INV-30456 | P2524 | Childcare centre, Preston | 2025-11-25 | Progress claim | 88277.4 | 4413.87 | 0 | 83863.53 | 8386.35 | 92249.88 | Approved - sent to Xero | 2025-11-01
INV-30457 | P2525 | Medical centre electrical, Mentone | 2025-11-25 | Progress claim | 45095.65 | 2254.78 | 0 | 42840.87 | 4284.09 | 47124.96 | Approved - sent to Xero | 2025-11-01
INV-30458 | P2526 | School science block, Clayton | 2025-11-25 | Progress claim | 36876.7 | 1843.84 | 0 | 35032.86 | 3503.29 | 38536.15 | Approved - sent to Xero | 2025-11-01
INV-30459 | P2527 | Showroom refurbishment, Williamstown | 2025-11-25 | Progress claim | 40915.9 | 2045.8 | 0 | 38870.1 | 3887.01 | 42757.11 | Approved - sent to Xero | 2025-11-01
INV-30460 | P2528 | Apartment common areas, Bayswater | 2025-11-25 | Progress claim | 72879.3 | 0 | 0 | 72879.3 | 7287.93 | 80167.23 | Approved - sent to Xero | 2025-11-01
INV-30461 | P2529 | Apartment common areas, Preston | 2025-11-25 | Progress claim | 9745.2 | 0 | 0 | 9745.2 | 974.52 | 10719.72 | Approved - sent to Xero | 2025-11-01
INV-30462 | P2530 | Gym fit-out, Preston | 2025-11-25 | Progress claim | 23707.3 | 1185.37 | 0 | 22521.93 | 2252.19 | 24774.12 | Approved - sent to Xero | 2025-11-01
INV-30463 | P2531 | Industrial unit power upgrade, Abbotsford | 2025-11-25 | Progress claim | 71630.8 | 3581.54 | 0 | 68049.26 | 6804.93 | 74854.19 | Approved - sent to Xero | 2025-11-01
INV-30464 | P2532 | Industrial unit power upgrade, Ascot Vale | 2025-11-25 | Progress claim | 47878.5 | 2393.93 | 0 | 45484.57 | 4548.46 | 50033.03 | Approved - sent to Xero | 2025-11-01
INV-30465 | P2533 | Office fit-out, Oakleigh | 2025-11-25 | Progress claim | 114457.95 | 5722.9 | 0 | 108735.05 | 10873.51 | 119608.56 | Approved - sent to Xero | 2025-11-01
INV-30466 | P2534 | Retail tenancy fit-out, Bayswater | 2025-11-25 | Progress claim | 17458.6 | 872.93 | 0 | 16585.67 | 1658.57 | 18244.24 | Approved - sent to Xero | 2025-11-01
INV-30467 | P2535 | Office fit-out, Preston | 2025-11-25 | Progress claim | 1967.95 | 0 | 0 | 1967.95 | 196.8 | 2164.75 | Approved - sent to Xero | 2025-11-01
INV-30468 | P2536 | Warehouse lighting upgrade, Preston | 2025-11-25 | Progress claim | 6825 | 0 | 0 | 6825 | 682.5 | 7507.5 | Approved - sent to Xero | 2025-11-01
INV-30469 | P2538 | Medical centre electrical, Kew | 2025-11-25 | Progress claim | 1800 | 0 | 0 | 1800 | 180 | 1980 | Approved - sent to Xero | 2025-11-01
INV-30470 | P2511 | Office fit-out, Heidelberg | 2025-12-10 | Progress claim | 12125 | 606.25 | 0 | 11518.75 | 1151.88 | 12670.63 | Approved - sent to Xero | 2025-12-01
INV-30471 | P2514 | School science block, Richmond | 2025-12-10 | Progress claim | 15717.8 | 785.89 | 0 | 14931.91 | 1493.19 | 16425.1 | Approved - sent to Xero | 2025-12-01
INV-30472 | P2515 | Showroom refurbishment, Preston West | 2025-12-10 | Progress claim | 16275 | 813.75 | 0 | 15461.25 | 1546.13 | 17007.38 | Approved - sent to Xero | 2025-12-01
INV-30473 | P2516 | Showroom refurbishment, Werribee | 2025-12-10 | Progress claim | 65625 | 3281.25 | 0 | 62343.75 | 6234.38 | 68578.13 | Approved - sent to Xero | 2025-12-01
INV-30474 | P2517 | Aged care wing, Essendon | 2025-12-10 | Progress claim | 4565.4 | 228.27 | 0 | 4337.13 | 433.71 | 4770.84 | Approved - sent to Xero | 2025-12-01
INV-30475 | P2519 | Car park lighting and EV, Williamstown | 2025-12-10 | Progress claim | 14641 | 732.05 | 0 | 13908.95 | 1390.9 | 15299.85 | Approved - sent to Xero | 2025-12-01
INV-30476 | P2521 | Aged care wing, Coburg | 2025-12-10 | Progress claim | 48268.45 | 0 | 0 | 48268.45 | 4826.85 | 53095.3 | Approved - sent to Xero | 2025-12-01
INV-30477 | P2523 | Aged care wing, Bayswater | 2025-12-10 | Progress claim | 17646.7 | 0 | 0 | 17646.7 | 1764.67 | 19411.37 | Approved - sent to Xero | 2025-12-01
INV-30478 | P2525 | Medical centre electrical, Mentone | 2025-12-10 | Progress claim | 14456.25 | 722.81 | 0 | 13733.44 | 1373.34 | 15106.78 | Approved - sent to Xero | 2025-12-01
INV-30479 | P2526 | School science block, Clayton | 2025-12-10 | Progress claim | 52816 | 2640.8 | 0 | 50175.2 | 5017.52 | 55192.72 | Approved - sent to Xero | 2025-12-01
INV-30480 | P2532 | Industrial unit power upgrade, Ascot Vale | 2025-12-10 | Progress claim | 53119.7 | 2655.99 | 0 | 50463.71 | 5046.37 | 55510.08 | Approved - sent to Xero | 2025-12-01
INV-30481 | P2533 | Office fit-out, Oakleigh | 2025-12-10 | Progress claim | 81955.3 | 4097.77 | 0 | 77857.53 | 7785.75 | 85643.28 | Approved - sent to Xero | 2025-12-01
INV-30482 | P2534 | Retail tenancy fit-out, Bayswater | 2025-12-10 | Progress claim | 20827.2 | 1041.36 | 0 | 19785.84 | 1978.58 | 21764.42 | Approved - sent to Xero | 2025-12-01
INV-30483 | P2535 | Office fit-out, Preston | 2025-12-10 | Progress claim | 5903.85 | 0 | 0 | 5903.85 | 590.39 | 6494.24 | Approved - sent to Xero | 2025-12-01
INV-30484 | P2511 | Office fit-out, Heidelberg | 2025-12-25 | Progress claim | 21250 | 1062.5 | 0 | 20187.5 | 2018.75 | 22206.25 | Approved - sent to Xero | 2025-12-01
INV-30485 | P2512 | Warehouse lighting upgrade, Northcote | 2025-12-25 | Progress claim | 3125 | 156.25 | 0 | 2968.75 | 296.88 | 3265.63 | Approved - sent to Xero | 2025-12-01
INV-30486 | P2513 | Aged care wing, St Kilda | 2025-12-25 | Progress claim | 6875 | 0 | 0 | 6875 | 687.5 | 7562.5 | Approved - sent to Xero | 2025-12-01
INV-30487 | P2514 | School science block, Richmond | 2025-12-25 | Progress claim | 3555.55 | 177.78 | 0 | 3377.77 | 337.78 | 3715.55 | Approved - sent to Xero | 2025-12-01
INV-30488 | P2515 | Showroom refurbishment, Preston West | 2025-12-25 | Final claim | 34855 | 1742.75 | 14378.76 | 47491.01 | 4749.1 | 52240.11 | Approved - sent to Xero | 2025-12-01
INV-30489 | P2516 | Showroom refurbishment, Werribee | 2025-12-25 | Progress claim | 61295 | 3064.75 | 0 | 58230.25 | 5823.03 | 64053.28 | Approved - sent to Xero | 2025-12-01
INV-30490 | P2517 | Aged care wing, Essendon | 2025-12-25 | Progress claim | 3043.6 | 152.18 | 0 | 2891.42 | 289.14 | 3180.56 | Approved - sent to Xero | 2025-12-01
INV-30491 | P2519 | Car park lighting and EV, Williamstown | 2025-12-25 | Progress claim | 7320.5 | 366.03 | 0 | 6954.47 | 695.45 | 7649.92 | Approved - sent to Xero | 2025-12-01
INV-30492 | P2520 | Industrial unit power upgrade, Hawthorn | 2025-12-25 | Progress claim | 19228 | 0 | 0 | 19228 | 1922.8 | 21150.8 | Approved - sent to Xero | 2025-12-01
INV-30493 | P2521 | Aged care wing, Coburg | 2025-12-25 | Progress claim | 42531.15 | 0 | 0 | 42531.15 | 4253.12 | 46784.27 | Approved - sent to Xero | 2025-12-01
INV-30494 | P2522 | Car park lighting and EV, Oakleigh | 2025-12-25 | Progress claim | 705.9 | 35.3 | 0 | 670.6 | 67.06 | 737.66 | Approved - sent to Xero | 2025-12-01
INV-30495 | P2523 | Aged care wing, Bayswater | 2025-12-25 | Progress claim | 21211.2 | 0 | 0 | 21211.2 | 2121.12 | 23332.32 | Approved - sent to Xero | 2025-12-01
INV-30496 | P2524 | Childcare centre, Preston | 2025-12-25 | Progress claim | 133655.6 | 6682.78 | 0 | 126972.82 | 12697.28 | 139670.1 | Approved - sent to Xero | 2025-12-01
INV-30497 | P2525 | Medical centre electrical, Mentone | 2025-12-25 | Final claim | 32275 | 1613.75 | 10546.25 | 41207.5 | 4120.75 | 45328.25 | Approved - sent to Xero | 2025-12-01
INV-30498 | P2526 | School science block, Clayton | 2025-12-25 | Progress claim | 48011.4 | 2400.57 | 0 | 45610.83 | 4561.08 | 50171.91 | Approved - sent to Xero | 2025-12-01
INV-30499 | P2527 | Showroom refurbishment, Williamstown | 2025-12-25 | Progress claim | 110165.15 | 5508.26 | 0 | 104656.89 | 10465.69 | 115122.58 | Approved - sent to Xero | 2025-12-01
INV-30500 | P2528 | Apartment common areas, Bayswater | 2025-12-25 | Progress claim | 88069.2 | 0 | 0 | 88069.2 | 8806.92 | 96876.12 | Approved - sent to Xero | 2025-12-01
INV-30501 | P2529 | Apartment common areas, Preston | 2025-12-25 | Progress claim | 22601.15 | 0 | 0 | 22601.15 | 2260.12 | 24861.27 | Approved - sent to Xero | 2025-12-01
INV-30502 | P2530 | Gym fit-out, Preston | 2025-12-25 | Progress claim | 73814.3 | 3690.72 | 0 | 70123.58 | 7012.36 | 77135.94 | Approved - sent to Xero | 2025-12-01
INV-30503 | P2531 | Industrial unit power upgrade, Abbotsford | 2025-12-25 | Progress claim | 60792.45 | 3039.62 | 0 | 57752.83 | 5775.28 | 63528.11 | Approved - sent to Xero | 2025-12-01
INV-30504 | P2532 | Industrial unit power upgrade, Ascot Vale | 2025-12-25 | Progress claim | 47364.6 | 2368.23 | 0 | 44996.37 | 4499.64 | 49496.01 | Approved - sent to Xero | 2025-12-01
INV-30505 | P2533 | Office fit-out, Oakleigh | 2025-12-25 | Progress claim | 59407.05 | 2970.35 | 0 | 56436.7 | 5643.67 | 62080.37 | Approved - sent to Xero | 2025-12-01
INV-30506 | P2534 | Retail tenancy fit-out, Bayswater | 2025-12-25 | Progress claim | 24195.8 | 1209.79 | 0 | 22986.01 | 2298.6 | 25284.61 | Approved - sent to Xero | 2025-12-01
INV-30507 | P2535 | Office fit-out, Preston | 2025-12-25 | Progress claim | 9881.45 | 0 | 0 | 9881.45 | 988.15 | 10869.6 | Approved - sent to Xero | 2025-12-01
INV-30508 | P2536 | Warehouse lighting upgrade, Preston | 2025-12-25 | Progress claim | 2753.25 | 0 | 0 | 2753.25 | 275.33 | 3028.58 | Approved - sent to Xero | 2025-12-01
INV-30509 | P2537 | Car park lighting and EV, Ascot Vale | 2025-12-25 | Progress claim | 2592.9 | 0 | 0 | 2592.9 | 259.29 | 2852.19 | Approved - sent to Xero | 2025-12-01
INV-30510 | P2538 | Medical centre electrical, Kew | 2025-12-25 | Progress claim | 2481.05 | 0 | 0 | 2481.05 | 248.11 | 2729.16 | Approved - sent to Xero | 2025-12-01
INV-30511 | P2541 | Apartment common areas, Clayton | 2025-12-25 | Progress claim | 12900 | 645 | 0 | 12255 | 1225.5 | 13480.5 | Approved - sent to Xero | 2025-12-01
INV-30512 | P2544 | School science block, St Kilda | 2025-12-25 | Progress claim | 3515.1 | 0 | 0 | 3515.1 | 351.51 | 3866.61 | Approved - sent to Xero | 2025-12-01
INV-30513 | P2511 | Office fit-out, Heidelberg | 2026-01-10 | Progress claim | 9652.25 | 482.61 | 0 | 9169.64 | 916.96 | 10086.6 | Approved - sent to Xero | 2026-01-01
INV-30514 | P2516 | Showroom refurbishment, Werribee | 2026-01-10 | Progress claim | 34450 | 1722.5 | 0 | 32727.5 | 3272.75 | 36000.25 | Approved - sent to Xero | 2026-01-01
INV-30515 | P2519 | Car park lighting and EV, Williamstown | 2026-01-10 | Progress claim | 6150 | 307.5 | 0 | 5842.5 | 584.25 | 6426.75 | Approved - sent to Xero | 2026-01-01
INV-30516 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-01-10 | Progress claim | 11200 | 0 | 0 | 11200 | 1120 | 12320 | Approved - sent to Xero | 2026-01-01
INV-30517 | P2522 | Car park lighting and EV, Oakleigh | 2026-01-10 | Progress claim | 3176.55 | 158.83 | 0 | 3017.72 | 301.77 | 3319.49 | Approved - sent to Xero | 2026-01-01
INV-30518 | P2526 | School science block, Clayton | 2026-01-10 | Progress claim | 52244.8 | 2612.24 | 0 | 49632.56 | 4963.26 | 54595.82 | Approved - sent to Xero | 2026-01-01
INV-30519 | P2530 | Gym fit-out, Preston | 2026-01-10 | Progress claim | 46954.75 | 2347.74 | 0 | 44607.01 | 4460.7 | 49067.71 | Approved - sent to Xero | 2026-01-01
INV-30520 | P2531 | Industrial unit power upgrade, Abbotsford | 2026-01-10 | Progress claim | 9463.15 | 473.16 | 0 | 8989.99 | 899 | 9888.99 | Approved - sent to Xero | 2026-01-01
INV-30521 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-01-10 | Progress claim | 35177.1 | 1758.86 | 0 | 33418.24 | 3341.82 | 36760.06 | Approved - sent to Xero | 2026-01-01
INV-30522 | P2534 | Retail tenancy fit-out, Bayswater | 2026-01-10 | Progress claim | 27564.4 | 1378.22 | 0 | 26186.18 | 2618.62 | 28804.8 | Approved - sent to Xero | 2026-01-01
INV-30523 | P2535 | Office fit-out, Preston | 2026-01-10 | Progress claim | 17815.8 | 0 | 0 | 17815.8 | 1781.58 | 19597.38 | Approved - sent to Xero | 2026-01-01
INV-30524 | P2537 | Car park lighting and EV, Ascot Vale | 2026-01-10 | Progress claim | 5185.8 | 0 | 0 | 5185.8 | 518.58 | 5704.38 | Approved - sent to Xero | 2026-01-01
INV-30525 | P2540 | Aged care wing, Burwood | 2026-01-10 | Progress claim | 1844.55 | 0 | 0 | 1844.55 | 184.46 | 2029.01 | Approved - sent to Xero | 2026-01-01
INV-30526 | P2541 | Apartment common areas, Clayton | 2026-01-10 | Progress claim | 16198 | 809.9 | 0 | 15388.1 | 1538.81 | 16926.91 | Approved - sent to Xero | 2026-01-01
INV-30527 | P2542 | Apartment common areas, Moonee Ponds | 2026-01-10 | Progress claim | 2335.55 | 0 | 0 | 2335.55 | 233.56 | 2569.11 | Approved - sent to Xero | 2026-01-01
INV-30528 | P2544 | School science block, St Kilda | 2026-01-10 | Progress claim | 14060.4 | 0 | 0 | 14060.4 | 1406.04 | 15466.44 | Approved - sent to Xero | 2026-01-01
INV-30529 | P2511 | Office fit-out, Heidelberg | 2026-01-25 | Progress claim | 2109 | 105.45 | 0 | 2003.55 | 200.36 | 2203.91 | Approved - sent to Xero | 2026-01-01
INV-30530 | P2512 | Warehouse lighting upgrade, Northcote | 2026-01-25 | Progress claim | 4668.4 | 233.42 | 0 | 4434.98 | 443.5 | 4878.48 | Approved - sent to Xero | 2026-01-01
INV-30531 | P2513 | Aged care wing, St Kilda | 2026-01-25 | Progress claim | 6378.2 | 0 | 0 | 6378.2 | 637.82 | 7016.02 | Approved - sent to Xero | 2026-01-01
INV-30532 | P2516 | Showroom refurbishment, Werribee | 2026-01-25 | Progress claim | 10290 | 514.5 | 0 | 9775.5 | 977.55 | 10753.05 | Approved - sent to Xero | 2026-01-01
INV-30533 | P2517 | Aged care wing, Essendon | 2026-01-25 | Final claim | 32790 | 1639.5 | 12935.01 | 44085.51 | 4408.55 | 48494.06 | Approved - sent to Xero | 2026-01-01
INV-30534 | P2519 | Car park lighting and EV, Williamstown | 2026-01-25 | Progress claim | 6150 | 307.5 | 0 | 5842.5 | 584.25 | 6426.75 | Approved - sent to Xero | 2026-01-01
INV-30535 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-01-25 | Progress claim | 5025 | 0 | 0 | 5025 | 502.5 | 5527.5 | Approved - sent to Xero | 2026-01-01
INV-30536 | P2521 | Aged care wing, Coburg | 2026-01-25 | Progress claim | 90789.4 | 0 | 0 | 90789.4 | 9078.94 | 99868.34 | Approved - sent to Xero | 2026-01-01
INV-30537 | P2522 | Car park lighting and EV, Oakleigh | 2026-01-25 | Progress claim | 2470.65 | 123.53 | 0 | 2347.12 | 234.71 | 2581.83 | Approved - sent to Xero | 2026-01-01
INV-30538 | P2523 | Aged care wing, Bayswater | 2026-01-25 | Progress claim | 31670.3 | 0 | 0 | 31670.3 | 3167.03 | 34837.33 | Approved - sent to Xero | 2026-01-01
INV-30539 | P2524 | Childcare centre, Preston | 2026-01-25 | Progress claim | 118594.4 | 5929.72 | 0 | 112664.68 | 11266.47 | 123931.15 | Approved - sent to Xero | 2026-01-01
INV-30540 | P2526 | School science block, Clayton | 2026-01-25 | Progress claim | 36305.5 | 1815.28 | 0 | 34490.22 | 3449.02 | 37939.24 | Approved - sent to Xero | 2026-01-01
INV-30541 | P2527 | Showroom refurbishment, Williamstown | 2026-01-25 | Progress claim | 66158.95 | 3307.95 | 0 | 62851 | 6285.1 | 69136.1 | Approved - sent to Xero | 2026-01-01
INV-30542 | P2528 | Apartment common areas, Bayswater | 2026-01-25 | Progress claim | 20247.6 | 0 | 0 | 20247.6 | 2024.76 | 22272.36 | Approved - sent to Xero | 2026-01-01
INV-30543 | P2529 | Apartment common areas, Preston | 2026-01-25 | Progress claim | 8218.6 | 0 | 0 | 8218.6 | 821.86 | 9040.46 | Approved - sent to Xero | 2026-01-01
INV-30544 | P2530 | Gym fit-out, Preston | 2026-01-25 | Progress claim | 37420.35 | 1871.02 | 0 | 35549.33 | 3554.93 | 39104.26 | Approved - sent to Xero | 2026-01-01
INV-30545 | P2531 | Industrial unit power upgrade, Abbotsford | 2026-01-25 | Progress claim | 4803.15 | 240.16 | 0 | 4562.99 | 456.3 | 5019.29 | Approved - sent to Xero | 2026-01-01
INV-30546 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-01-25 | Progress claim | 26770.35 | 1338.52 | 0 | 25431.83 | 2543.18 | 27975.01 | Approved - sent to Xero | 2026-01-01
INV-30547 | P2533 | Office fit-out, Oakleigh | 2026-01-25 | Progress claim | 83393.8 | 4169.69 | 0 | 79224.11 | 7922.41 | 87146.52 | Approved - sent to Xero | 2026-01-01
INV-30548 | P2534 | Retail tenancy fit-out, Bayswater | 2026-01-25 | Progress claim | 26568.35 | 1328.42 | 0 | 25239.93 | 2523.99 | 27763.92 | Approved - sent to Xero | 2026-01-01
INV-30549 | P2535 | Office fit-out, Preston | 2026-01-25 | Progress claim | 19804.6 | 0 | 0 | 19804.6 | 1980.46 | 21785.06 | Approved - sent to Xero | 2026-01-01
INV-30550 | P2536 | Warehouse lighting upgrade, Preston | 2026-01-25 | Progress claim | 11013 | 0 | 0 | 11013 | 1101.3 | 12114.3 | Approved - sent to Xero | 2026-01-01
INV-30551 | P2537 | Car park lighting and EV, Ascot Vale | 2026-01-25 | Progress claim | 16147.95 | 0 | 0 | 16147.95 | 1614.8 | 17762.75 | Approved - sent to Xero | 2026-01-01
INV-30552 | P2538 | Medical centre electrical, Kew | 2026-01-25 | Progress claim | 3405.25 | 0 | 0 | 3405.25 | 340.53 | 3745.78 | Approved - sent to Xero | 2026-01-01
INV-30553 | P2539 | Retail tenancy fit-out, Carlton | 2026-01-25 | Progress claim | 3909.95 | 0 | 0 | 3909.95 | 391 | 4300.95 | Approved - sent to Xero | 2026-01-01
INV-30554 | P2540 | Aged care wing, Burwood | 2026-01-25 | Progress claim | 5533.65 | 0 | 0 | 5533.65 | 553.37 | 6087.02 | Approved - sent to Xero | 2026-01-01
INV-30555 | P2541 | Apartment common areas, Clayton | 2026-01-25 | Progress claim | 3298 | 164.9 | 0 | 3133.1 | 313.31 | 3446.41 | Approved - sent to Xero | 2026-01-01
INV-30556 | P2542 | Apartment common areas, Moonee Ponds | 2026-01-25 | Progress claim | 2335.55 | 0 | 0 | 2335.55 | 233.56 | 2569.11 | Approved - sent to Xero | 2026-01-01
INV-30557 | P2543 | Retail tenancy fit-out, Yarraville | 2026-01-25 | Progress claim | 15966.3 | 0 | 0 | 15966.3 | 1596.63 | 17562.93 | Approved - sent to Xero | 2026-01-01
INV-30558 | P2544 | School science block, St Kilda | 2026-01-25 | Progress claim | 24605.7 | 0 | 0 | 24605.7 | 2460.57 | 27066.27 | Approved - sent to Xero | 2026-01-01
INV-30559 | P2546 | Showroom refurbishment, Malvern | 2026-01-25 | Progress claim | 5584.6 | 0 | 0 | 5584.6 | 558.46 | 6143.06 | Approved - sent to Xero | 2026-01-01
INV-30560 | P2548 | School science block, Essendon | 2026-01-25 | Progress claim | 4975 | 248.75 | 0 | 4726.25 | 472.63 | 5198.88 | Approved - sent to Xero | 2026-01-01
INV-30561 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-01-25 | Progress claim | 9150 | 0 | 0 | 9150 | 915 | 10065 | Approved - sent to Xero | 2026-01-01
INV-30562 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-01-25 | Progress claim | 1675 | 0 | 0 | 1675 | 167.5 | 1842.5 | Approved - sent to Xero | 2026-01-01
INV-30563 | P2512 | Warehouse lighting upgrade, Northcote | 2026-02-10 | Progress claim | 1543.4 | 77.17 | 0 | 1466.23 | 146.62 | 1612.85 | Approved - sent to Xero | 2026-02-01
INV-30564 | P2514 | School science block, Richmond | 2026-02-10 | Progress claim | 8150 | 407.5 | 0 | 7742.5 | 774.25 | 8516.75 | Approved - sent to Xero | 2026-02-01
INV-30565 | P2516 | Showroom refurbishment, Werribee | 2026-02-10 | Progress claim | 5880 | 294 | 0 | 5586 | 558.6 | 6144.6 | Approved - sent to Xero | 2026-02-01
INV-30566 | P2523 | Aged care wing, Bayswater | 2026-02-10 | Progress claim | 7011.8 | 0 | 0 | 7011.8 | 701.18 | 7712.98 | Approved - sent to Xero | 2026-02-01
INV-30567 | P2526 | School science block, Clayton | 2026-02-10 | Progress claim | 32113.25 | 1605.66 | 0 | 30507.59 | 3050.76 | 33558.35 | Approved - sent to Xero | 2026-02-01
INV-30568 | P2527 | Showroom refurbishment, Williamstown | 2026-02-10 | Progress claim | 7131.4 | 356.57 | 0 | 6774.83 | 677.48 | 7452.31 | Approved - sent to Xero | 2026-02-01
INV-30569 | P2530 | Gym fit-out, Preston | 2026-02-10 | Progress claim | 31760.25 | 1588.01 | 0 | 30172.24 | 3017.22 | 33189.46 | Approved - sent to Xero | 2026-02-01
INV-30570 | P2531 | Industrial unit power upgrade, Abbotsford | 2026-02-10 | Progress claim | 3493.2 | 174.66 | 0 | 3318.54 | 331.85 | 3650.39 | Approved - sent to Xero | 2026-02-01
INV-30571 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-02-10 | Progress claim | 26770.35 | 1338.52 | 0 | 25431.83 | 2543.18 | 27975.01 | Approved - sent to Xero | 2026-02-01
INV-30572 | P2533 | Office fit-out, Oakleigh | 2026-02-10 | Progress claim | 42878.9 | 2143.95 | 0 | 40734.95 | 4073.5 | 44808.45 | Approved - sent to Xero | 2026-02-01
INV-30573 | P2535 | Office fit-out, Preston | 2026-02-10 | Progress claim | 15847.85 | 0 | 0 | 15847.85 | 1584.79 | 17432.64 | Approved - sent to Xero | 2026-02-01
INV-30574 | P2536 | Warehouse lighting upgrade, Preston | 2026-02-10 | Progress claim | 5506.5 | 0 | 0 | 5506.5 | 550.65 | 6057.15 | Approved - sent to Xero | 2026-02-01
INV-30575 | P2537 | Car park lighting and EV, Ascot Vale | 2026-02-10 | Progress claim | 25698.3 | 0 | 0 | 25698.3 | 2569.83 | 28268.13 | Approved - sent to Xero | 2026-02-01
INV-30576 | P2538 | Medical centre electrical, Kew | 2026-02-10 | Progress claim | 3436 | 0 | 0 | 3436 | 343.6 | 3779.6 | Approved - sent to Xero | 2026-02-01
INV-30577 | P2539 | Retail tenancy fit-out, Carlton | 2026-02-10 | Progress claim | 7819.9 | 0 | 0 | 7819.9 | 781.99 | 8601.89 | Approved - sent to Xero | 2026-02-01
INV-30578 | P2541 | Apartment common areas, Clayton | 2026-02-10 | Progress claim | 3298 | 164.9 | 0 | 3133.1 | 313.31 | 3446.41 | Approved - sent to Xero | 2026-02-01
INV-30579 | P2542 | Apartment common areas, Moonee Ponds | 2026-02-10 | Progress claim | 4671.1 | 0 | 0 | 4671.1 | 467.11 | 5138.21 | Approved - sent to Xero | 2026-02-01
INV-30580 | P2543 | Retail tenancy fit-out, Yarraville | 2026-02-10 | Progress claim | 22524.45 | 0 | 0 | 22524.45 | 2252.45 | 24776.9 | Approved - sent to Xero | 2026-02-01
INV-30581 | P2544 | School science block, St Kilda | 2026-02-10 | Progress claim | 24605.7 | 0 | 0 | 24605.7 | 2460.57 | 27066.27 | Approved - sent to Xero | 2026-02-01
INV-30582 | P2546 | Showroom refurbishment, Malvern | 2026-02-10 | Progress claim | 47116.75 | 0 | 0 | 47116.75 | 4711.68 | 51828.43 | Approved - sent to Xero | 2026-02-01
INV-30583 | P2547 | School science block, Dandenong | 2026-02-10 | Progress claim | 4397.25 | 0 | 0 | 4397.25 | 439.73 | 4836.98 | Approved - sent to Xero | 2026-02-01
INV-30584 | P2548 | School science block, Essendon | 2026-02-10 | Progress claim | 15500 | 775 | 0 | 14725 | 1472.5 | 16197.5 | Approved - sent to Xero | 2026-02-01
INV-30585 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-02-10 | Progress claim | 9150 | 0 | 0 | 9150 | 915 | 10065 | Approved - sent to Xero | 2026-02-01
INV-30586 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-02-10 | Progress claim | 1675 | 0 | 0 | 1675 | 167.5 | 1842.5 | Approved - sent to Xero | 2026-02-01
INV-30587 | P2511 | Office fit-out, Heidelberg | 2026-02-25 | Progress claim | 5272.5 | 263.63 | 0 | 5008.87 | 500.89 | 5509.76 | Approved - sent to Xero | 2026-02-01
INV-30588 | P2512 | Warehouse lighting upgrade, Northcote | 2026-02-25 | Progress claim | 1543.4 | 77.17 | 0 | 1466.23 | 146.62 | 1612.85 | Approved - sent to Xero | 2026-02-01
INV-30589 | P2513 | Aged care wing, St Kilda | 2026-02-25 | Progress claim | 2329.6 | 0 | 0 | 2329.6 | 232.96 | 2562.56 | Approved - sent to Xero | 2026-02-01
INV-30590 | P2514 | School science block, Richmond | 2026-02-25 | Progress claim | 8150 | 407.5 | 0 | 7742.5 | 774.25 | 8516.75 | Approved - sent to Xero | 2026-02-01
INV-30591 | P2516 | Showroom refurbishment, Werribee | 2026-02-25 | Progress claim | 2940 | 147 | 0 | 2793 | 279.3 | 3072.3 | Approved - sent to Xero | 2026-02-01
INV-30592 | P2519 | Car park lighting and EV, Williamstown | 2026-02-25 | Progress claim | 2675 | 133.75 | 0 | 2541.25 | 254.13 | 2795.38 | Approved - sent to Xero | 2026-02-01
INV-30593 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-02-25 | Progress claim | 5025 | 0 | 0 | 5025 | 502.5 | 5527.5 | Approved - sent to Xero | 2026-02-01
INV-30594 | P2521 | Aged care wing, Coburg | 2026-02-25 | Progress claim | 65477.2 | 0 | 0 | 65477.2 | 6547.72 | 72024.92 | Approved - sent to Xero | 2026-02-01
INV-30595 | P2522 | Car park lighting and EV, Oakleigh | 2026-02-25 | Final claim | 10437.95 | 521.9 | 5282.51 | 15198.56 | 1519.86 | 16718.42 | Approved - sent to Xero | 2026-02-01
INV-30596 | P2523 | Aged care wing, Bayswater | 2026-02-25 | Progress claim | 3505.9 | 0 | 0 | 3505.9 | 350.59 | 3856.49 | Approved - sent to Xero | 2026-02-01
INV-30597 | P2524 | Childcare centre, Preston | 2026-02-25 | Progress claim | 39575.25 | 1978.76 | 0 | 37596.49 | 3759.65 | 41356.14 | Approved - sent to Xero | 2026-02-01
INV-30598 | P2526 | School science block, Clayton | 2026-02-25 | Progress claim | 11747.05 | 587.35 | 0 | 11159.7 | 1115.97 | 12275.67 | Approved - sent to Xero | 2026-02-01
INV-30599 | P2527 | Showroom refurbishment, Williamstown | 2026-02-25 | Progress claim | 3565.7 | 178.29 | 0 | 3387.41 | 338.74 | 3726.15 | Approved - sent to Xero | 2026-02-01
INV-30600 | P2528 | Apartment common areas, Bayswater | 2026-02-25 | Final claim | 57852 | 0 | 0 | 57852 | 5785.2 | 63637.2 | Approved - sent to Xero | 2026-02-01
INV-30601 | P2529 | Apartment common areas, Preston | 2026-02-25 | Progress claim | 2700 | 0 | 0 | 2700 | 270 | 2970 | Approved - sent to Xero | 2026-02-01
INV-30602 | P2530 | Gym fit-out, Preston | 2026-02-25 | Progress claim | 30159 | 1507.95 | 0 | 28651.05 | 2865.11 | 31516.16 | Approved - sent to Xero | 2026-02-01
INV-30603 | P2531 | Industrial unit power upgrade, Abbotsford | 2026-02-25 | Final claim | 14555 | 727.75 | 7425 | 21252.25 | 2125.23 | 23377.48 | Approved - sent to Xero | 2026-02-01
INV-30604 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-02-25 | Progress claim | 20582.05 | 1029.1 | 0 | 19552.95 | 1955.3 | 21508.25 | Approved - sent to Xero | 2026-02-01
INV-30605 | P2533 | Office fit-out, Oakleigh | 2026-02-25 | Progress claim | 11101.95 | 555.1 | 0 | 10546.85 | 1054.69 | 11601.54 | Approved - sent to Xero | 2026-02-01
INV-30606 | P2534 | Retail tenancy fit-out, Bayswater | 2026-02-25 | Progress claim | 32239.25 | 1611.96 | 0 | 30627.29 | 3062.73 | 33690.02 | Approved - sent to Xero | 2026-02-01
INV-30607 | P2535 | Office fit-out, Preston | 2026-02-25 | Progress claim | 1988.8 | 0 | 0 | 1988.8 | 198.88 | 2187.68 | Approved - sent to Xero | 2026-02-01
INV-30608 | P2536 | Warehouse lighting upgrade, Preston | 2026-02-25 | Progress claim | 11266.8 | 0 | 0 | 11266.8 | 1126.68 | 12393.48 | Approved - sent to Xero | 2026-02-01
INV-30609 | P2537 | Car park lighting and EV, Ascot Vale | 2026-02-25 | Progress claim | 45724 | 0 | 0 | 45724 | 4572.4 | 50296.4 | Approved - sent to Xero | 2026-02-01
INV-30610 | P2538 | Medical centre electrical, Kew | 2026-02-25 | Progress claim | 4828.85 | 0 | 0 | 4828.85 | 482.89 | 5311.74 | Approved - sent to Xero | 2026-02-01
INV-30611 | P2539 | Retail tenancy fit-out, Carlton | 2026-02-25 | Progress claim | 7819.9 | 0 | 0 | 7819.9 | 781.99 | 8601.89 | Approved - sent to Xero | 2026-02-01
INV-30612 | P2540 | Aged care wing, Burwood | 2026-02-25 | Progress claim | 43283.3 | 0 | 0 | 43283.3 | 4328.33 | 47611.63 | Approved - sent to Xero | 2026-02-01
INV-30613 | P2541 | Apartment common areas, Clayton | 2026-02-25 | Progress claim | 9894 | 494.7 | 0 | 9399.3 | 939.93 | 10339.23 | Approved - sent to Xero | 2026-02-01
INV-30614 | P2542 | Apartment common areas, Moonee Ponds | 2026-02-25 | Progress claim | 7006.65 | 0 | 0 | 7006.65 | 700.67 | 7707.32 | Approved - sent to Xero | 2026-02-01
INV-30615 | P2543 | Retail tenancy fit-out, Yarraville | 2026-02-25 | Progress claim | 37471.5 | 0 | 0 | 37471.5 | 3747.15 | 41218.65 | Approved - sent to Xero | 2026-02-01
INV-30616 | P2544 | School science block, St Kilda | 2026-02-25 | Progress claim | 9260.8 | 0 | 0 | 9260.8 | 926.08 | 10186.88 | Approved - sent to Xero | 2026-02-01
INV-30617 | P2545 | Showroom refurbishment, Hawthorn | 2026-02-25 | Progress claim | 15860.65 | 0 | 0 | 15860.65 | 1586.07 | 17446.72 | Approved - sent to Xero | 2026-02-01
INV-30618 | P2546 | Showroom refurbishment, Malvern | 2026-02-25 | Progress claim | 52701.35 | 0 | 0 | 52701.35 | 5270.14 | 57971.49 | Approved - sent to Xero | 2026-02-01
INV-30619 | P2547 | School science block, Dandenong | 2026-02-25 | Progress claim | 4397.25 | 0 | 0 | 4397.25 | 439.73 | 4836.98 | Approved - sent to Xero | 2026-02-01
INV-30620 | P2548 | School science block, Essendon | 2026-02-25 | Progress claim | 10525 | 526.25 | 0 | 9998.75 | 999.88 | 10998.63 | Approved - sent to Xero | 2026-02-01
INV-30621 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-02-25 | Progress claim | 8600 | 0 | 0 | 8600 | 860 | 9460 | Approved - sent to Xero | 2026-02-01
INV-30622 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-02-25 | Progress claim | 946.35 | 0 | 0 | 946.35 | 94.64 | 1040.99 | Approved - sent to Xero | 2026-02-01
INV-30623 | P2511 | Office fit-out, Heidelberg | 2026-03-10 | Progress claim | 1581.75 | 79.09 | 0 | 1502.66 | 150.27 | 1652.93 | Approved - sent to Xero | 2026-03-01
INV-30624 | P2512 | Warehouse lighting upgrade, Northcote | 2026-03-10 | Progress claim | 1543.4 | 77.17 | 0 | 1466.23 | 146.62 | 1612.85 | Approved - sent to Xero | 2026-03-01
INV-30625 | P2513 | Aged care wing, St Kilda | 2026-03-10 | Progress claim | 4100 | 0 | 0 | 4100 | 410 | 4510 | Approved - sent to Xero | 2026-03-01
INV-30626 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-03-10 | Progress claim | 7750 | 0 | 0 | 7750 | 775 | 8525 | Approved - sent to Xero | 2026-03-01
INV-30627 | P2521 | Aged care wing, Coburg | 2026-03-10 | Progress claim | 17672.25 | 0 | 0 | 17672.25 | 1767.23 | 19439.48 | Approved - sent to Xero | 2026-03-01
INV-30628 | P2526 | School science block, Clayton | 2026-03-10 | Progress claim | 5786.5 | 289.33 | 0 | 5497.17 | 549.72 | 6046.89 | Approved - sent to Xero | 2026-03-01
INV-30629 | P2529 | Apartment common areas, Preston | 2026-03-10 | Progress claim | 2106.25 | 0 | 0 | 2106.25 | 210.63 | 2316.88 | Approved - sent to Xero | 2026-03-01
INV-30630 | P2530 | Gym fit-out, Preston | 2026-03-10 | Progress claim | 30159 | 1507.95 | 0 | 28651.05 | 2865.11 | 31516.16 | Approved - sent to Xero | 2026-03-01
INV-30631 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-03-10 | Progress claim | 8474.7 | 423.74 | 0 | 8050.96 | 805.1 | 8856.06 | Approved - sent to Xero | 2026-03-01
INV-30632 | P2534 | Retail tenancy fit-out, Bayswater | 2026-03-10 | Progress claim | 18282.6 | 914.13 | 0 | 17368.47 | 1736.85 | 19105.32 | Approved - sent to Xero | 2026-03-01
INV-30633 | P2536 | Warehouse lighting upgrade, Preston | 2026-03-10 | Progress claim | 14273.85 | 0 | 0 | 14273.85 | 1427.39 | 15701.24 | Approved - sent to Xero | 2026-03-01
INV-30634 | P2537 | Car park lighting and EV, Ascot Vale | 2026-03-10 | Progress claim | 38097 | 0 | 0 | 38097 | 3809.7 | 41906.7 | Approved - sent to Xero | 2026-03-01
INV-30635 | P2538 | Medical centre electrical, Kew | 2026-03-10 | Progress claim | 8295.6 | 0 | 0 | 8295.6 | 829.56 | 9125.16 | Approved - sent to Xero | 2026-03-01
INV-30636 | P2540 | Aged care wing, Burwood | 2026-03-10 | Progress claim | 27754.45 | 0 | 0 | 27754.45 | 2775.45 | 30529.9 | Approved - sent to Xero | 2026-03-01
INV-30637 | P2541 | Apartment common areas, Clayton | 2026-03-10 | Progress claim | 9894 | 494.7 | 0 | 9399.3 | 939.93 | 10339.23 | Approved - sent to Xero | 2026-03-01
INV-30638 | P2542 | Apartment common areas, Moonee Ponds | 2026-03-10 | Progress claim | 14108.85 | 0 | 0 | 14108.85 | 1410.89 | 15519.74 | Approved - sent to Xero | 2026-03-01
INV-30639 | P2543 | Retail tenancy fit-out, Yarraville | 2026-03-10 | Progress claim | 49649.1 | 0 | 0 | 49649.1 | 4964.91 | 54614.01 | Approved - sent to Xero | 2026-03-01
INV-30640 | P2544 | School science block, St Kilda | 2026-03-10 | Progress claim | 13891.2 | 0 | 0 | 13891.2 | 1389.12 | 15280.32 | Approved - sent to Xero | 2026-03-01
INV-30641 | P2545 | Showroom refurbishment, Hawthorn | 2026-03-10 | Progress claim | 25788.7 | 0 | 0 | 25788.7 | 2578.87 | 28367.57 | Approved - sent to Xero | 2026-03-01
INV-30642 | P2546 | Showroom refurbishment, Malvern | 2026-03-10 | Progress claim | 31083.5 | 0 | 0 | 31083.5 | 3108.35 | 34191.85 | Approved - sent to Xero | 2026-03-01
INV-30643 | P2547 | School science block, Dandenong | 2026-03-10 | Progress claim | 4397.25 | 0 | 0 | 4397.25 | 439.73 | 4836.98 | Approved - sent to Xero | 2026-03-01
INV-30644 | P2548 | School science block, Essendon | 2026-03-10 | Progress claim | 5596.6 | 279.83 | 0 | 5316.77 | 531.68 | 5848.45 | Approved - sent to Xero | 2026-03-01
INV-30645 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-03-10 | Progress claim | 8600 | 0 | 0 | 8600 | 860 | 9460 | Approved - sent to Xero | 2026-03-01
INV-30646 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-03-10 | Progress claim | 1376.95 | 0 | 0 | 1376.95 | 137.7 | 1514.65 | Approved - sent to Xero | 2026-03-01
INV-30647 | P2554 | Showroom refurbishment, Reservoir | 2026-03-10 | Progress claim | 3347.65 | 0 | 0 | 3347.65 | 334.77 | 3682.42 | Approved - sent to Xero | 2026-03-01
INV-30648 | P2511 | Office fit-out, Heidelberg | 2026-03-25 | Progress claim | 527.25 | 26.36 | 0 | 500.89 | 50.09 | 550.98 | Approved - sent to Xero | 2026-03-01
INV-30649 | P2512 | Warehouse lighting upgrade, Northcote | 2026-03-25 | Progress claim | 771.7 | 38.59 | 0 | 733.11 | 73.31 | 806.42 | Approved - sent to Xero | 2026-03-01
INV-30650 | P2513 | Aged care wing, St Kilda | 2026-03-25 | Final claim | 11380 | 0 | 0 | 11380 | 1138 | 12518 | Approved - sent to Xero | 2026-03-01
INV-30651 | P2514 | School science block, Richmond | 2026-03-25 | Progress claim | 7896.2 | 394.81 | 0 | 7501.39 | 750.14 | 8251.53 | Approved - sent to Xero | 2026-03-01
INV-30652 | P2516 | Showroom refurbishment, Werribee | 2026-03-25 | Final claim | 77450 | 3872.5 | 31901.27 | 105478.77 | 10547.88 | 116026.65 | Approved - sent to Xero | 2026-03-01
INV-30653 | P2519 | Car park lighting and EV, Williamstown | 2026-03-25 | Progress claim | 2675 | 133.75 | 0 | 2541.25 | 254.13 | 2795.38 | Approved - sent to Xero | 2026-03-01
INV-30654 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-03-25 | Progress claim | 8565.75 | 0 | 0 | 8565.75 | 856.58 | 9422.33 | Approved - sent to Xero | 2026-03-01
INV-30655 | P2521 | Aged care wing, Coburg | 2026-03-25 | Progress claim | 7080.9 | 0 | 0 | 7080.9 | 708.09 | 7788.99 | Approved - sent to Xero | 2026-03-01
INV-30656 | P2524 | Childcare centre, Preston | 2026-03-25 | Progress claim | 7650 | 382.5 | 0 | 7267.5 | 726.75 | 7994.25 | Approved - sent to Xero | 2026-03-01
INV-30657 | P2526 | School science block, Clayton | 2026-03-25 | Progress claim | 5786.5 | 289.33 | 0 | 5497.17 | 549.72 | 6046.89 | Approved - sent to Xero | 2026-03-01
INV-30658 | P2529 | Apartment common areas, Preston | 2026-03-25 | Final claim | 5350 | 0 | 0 | 5350 | 535 | 5885 | Approved - sent to Xero | 2026-03-01
INV-30659 | P2530 | Gym fit-out, Preston | 2026-03-25 | Progress claim | 18268.55 | 913.43 | 0 | 17355.12 | 1735.51 | 19090.63 | Approved - sent to Xero | 2026-03-01
INV-30660 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-03-25 | Progress claim | 5849.9 | 292.5 | 0 | 5557.4 | 555.74 | 6113.14 | Approved - sent to Xero | 2026-03-01
INV-30661 | P2533 | Office fit-out, Oakleigh | 2026-03-25 | Progress claim | 3111.2 | 155.56 | 0 | 2955.64 | 295.56 | 3251.2 | Approved - sent to Xero | 2026-03-01
INV-30662 | P2534 | Retail tenancy fit-out, Bayswater | 2026-03-25 | Progress claim | 14431.75 | 721.59 | 0 | 13710.16 | 1371.02 | 15081.18 | Approved - sent to Xero | 2026-03-01
INV-30663 | P2536 | Warehouse lighting upgrade, Preston | 2026-03-25 | Progress claim | 16794.6 | 0 | 0 | 16794.6 | 1679.46 | 18474.06 | Approved - sent to Xero | 2026-03-01
INV-30664 | P2537 | Car park lighting and EV, Ascot Vale | 2026-03-25 | Progress claim | 22834.5 | 0 | 0 | 22834.5 | 2283.45 | 25117.95 | Approved - sent to Xero | 2026-03-01
INV-30665 | P2538 | Medical centre electrical, Kew | 2026-03-25 | Progress claim | 11799.8 | 0 | 0 | 11799.8 | 1179.98 | 12979.78 | Approved - sent to Xero | 2026-03-01
INV-30666 | P2539 | Retail tenancy fit-out, Carlton | 2026-03-25 | Progress claim | 26155.3 | 0 | 0 | 26155.3 | 2615.53 | 28770.83 | Approved - sent to Xero | 2026-03-01
INV-30667 | P2540 | Aged care wing, Burwood | 2026-03-25 | Progress claim | 17519.8 | 0 | 0 | 17519.8 | 1751.98 | 19271.78 | Approved - sent to Xero | 2026-03-01
INV-30668 | P2541 | Apartment common areas, Clayton | 2026-03-25 | Progress claim | 18081 | 904.05 | 0 | 17176.95 | 1717.7 | 18894.65 | Approved - sent to Xero | 2026-03-01
INV-30669 | P2542 | Apartment common areas, Moonee Ponds | 2026-03-25 | Progress claim | 18692.15 | 0 | 0 | 18692.15 | 1869.22 | 20561.37 | Approved - sent to Xero | 2026-03-01
INV-30670 | P2543 | Retail tenancy fit-out, Yarraville | 2026-03-25 | Progress claim | 54329.85 | 0 | 0 | 54329.85 | 5432.99 | 59762.84 | Approved - sent to Xero | 2026-03-01
INV-30671 | P2544 | School science block, St Kilda | 2026-03-25 | Progress claim | 13891.2 | 0 | 0 | 13891.2 | 1389.12 | 15280.32 | Approved - sent to Xero | 2026-03-01
INV-30672 | P2545 | Showroom refurbishment, Hawthorn | 2026-03-25 | Progress claim | 23853.5 | 0 | 0 | 23853.5 | 2385.35 | 26238.85 | Approved - sent to Xero | 2026-03-01
INV-30673 | P2546 | Showroom refurbishment, Malvern | 2026-03-25 | Progress claim | 56582.4 | 0 | 0 | 56582.4 | 5658.24 | 62240.64 | Approved - sent to Xero | 2026-03-01
INV-30674 | P2547 | School science block, Dandenong | 2026-03-25 | Progress claim | 13191.75 | 0 | 0 | 13191.75 | 1319.18 | 14510.93 | Approved - sent to Xero | 2026-03-01
INV-30675 | P2548 | School science block, Essendon | 2026-03-25 | Progress claim | 16789.8 | 839.49 | 0 | 15950.31 | 1595.03 | 17545.34 | Approved - sent to Xero | 2026-03-01
INV-30676 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-03-25 | Progress claim | 5514.6 | 0 | 0 | 5514.6 | 551.46 | 6066.06 | Approved - sent to Xero | 2026-03-01
INV-30677 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-03-25 | Progress claim | 1376.95 | 0 | 0 | 1376.95 | 137.7 | 1514.65 | Approved - sent to Xero | 2026-03-01
INV-30678 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-03-25 | Progress claim | 1892.7 | 0 | 0 | 1892.7 | 189.27 | 2081.97 | Approved - sent to Xero | 2026-03-01
INV-30679 | P2552 | Aged care wing, Hawthorn | 2026-03-25 | Progress claim | 2483.7 | 0 | 0 | 2483.7 | 248.37 | 2732.07 | Approved - sent to Xero | 2026-03-01
INV-30680 | P2553 | School science block, Bayswater | 2026-03-25 | Progress claim | 15075 | 753.75 | 0 | 14321.25 | 1432.13 | 15753.38 | Approved - sent to Xero | 2026-03-01
INV-30681 | P2554 | Showroom refurbishment, Reservoir | 2026-03-25 | Progress claim | 10042.95 | 0 | 0 | 10042.95 | 1004.3 | 11047.25 | Approved - sent to Xero | 2026-03-01
INV-30682 | P2521 | Aged care wing, Coburg | 2026-04-10 | Progress claim | 7080.9 | 0 | 0 | 7080.9 | 708.09 | 7788.99 | Approved - sent to Xero | 2026-04-01
INV-30683 | P2524 | Childcare centre, Preston | 2026-04-10 | Progress claim | 4226.4 | 211.32 | 0 | 4015.08 | 401.51 | 4416.59 | Approved - sent to Xero | 2026-04-01
INV-30684 | P2526 | School science block, Clayton | 2026-04-10 | Progress claim | 8679.75 | 433.99 | 0 | 8245.76 | 824.58 | 9070.34 | Approved - sent to Xero | 2026-04-01
INV-30685 | P2530 | Gym fit-out, Preston | 2026-04-10 | Progress claim | 9567.15 | 478.36 | 0 | 9088.79 | 908.88 | 9997.67 | Approved - sent to Xero | 2026-04-01
INV-30686 | P2533 | Office fit-out, Oakleigh | 2026-04-10 | Progress claim | 6222.4 | 311.12 | 0 | 5911.28 | 591.13 | 6502.41 | Approved - sent to Xero | 2026-04-01
INV-30687 | P2536 | Warehouse lighting upgrade, Preston | 2026-04-10 | Progress claim | 20598.4 | 0 | 0 | 20598.4 | 2059.84 | 22658.24 | Approved - sent to Xero | 2026-04-01
INV-30688 | P2537 | Car park lighting and EV, Ascot Vale | 2026-04-10 | Progress claim | 10978.4 | 0 | 0 | 10978.4 | 1097.84 | 12076.24 | Approved - sent to Xero | 2026-04-01
INV-30689 | P2539 | Retail tenancy fit-out, Carlton | 2026-04-10 | Progress claim | 18335.4 | 0 | 0 | 18335.4 | 1833.54 | 20168.94 | Approved - sent to Xero | 2026-04-01
INV-30690 | P2542 | Apartment common areas, Moonee Ponds | 2026-04-10 | Progress claim | 16173.25 | 0 | 0 | 16173.25 | 1617.33 | 17790.58 | Approved - sent to Xero | 2026-04-01
INV-30691 | P2544 | School science block, St Kilda | 2026-04-10 | Progress claim | 6945.6 | 0 | 0 | 6945.6 | 694.56 | 7640.16 | Approved - sent to Xero | 2026-04-01
INV-30692 | P2546 | Showroom refurbishment, Malvern | 2026-04-10 | Progress claim | 56582.4 | 0 | 0 | 56582.4 | 5658.24 | 62240.64 | Approved - sent to Xero | 2026-04-01
INV-30693 | P2547 | School science block, Dandenong | 2026-04-10 | Progress claim | 17589 | 0 | 0 | 17589 | 1758.9 | 19347.9 | Approved - sent to Xero | 2026-04-01
INV-30694 | P2548 | School science block, Essendon | 2026-04-10 | Progress claim | 16789.8 | 839.49 | 0 | 15950.31 | 1595.03 | 17545.34 | Approved - sent to Xero | 2026-04-01
INV-30695 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-04-10 | Progress claim | 2839.05 | 0 | 0 | 2839.05 | 283.91 | 3122.96 | Approved - sent to Xero | 2026-04-01
INV-30696 | P2553 | School science block, Bayswater | 2026-04-10 | Progress claim | 15075 | 753.75 | 0 | 14321.25 | 1432.13 | 15753.38 | Approved - sent to Xero | 2026-04-01
INV-30697 | P2511 | Office fit-out, Heidelberg | 2026-04-25 | Final claim | 24775 | 1238.75 | 10030.02 | 33566.27 | 3356.63 | 36922.9 | Approved - sent to Xero | 2026-04-01
INV-30698 | P2512 | Warehouse lighting upgrade, Northcote | 2026-04-25 | Progress claim | 385.85 | 19.29 | 0 | 366.56 | 36.66 | 403.22 | Approved - sent to Xero | 2026-04-01
INV-30699 | P2514 | School science block, Richmond | 2026-04-25 | Progress claim | 12964.55 | 648.23 | 0 | 12316.32 | 1231.63 | 13547.95 | Approved - sent to Xero | 2026-04-01
INV-30700 | P2519 | Car park lighting and EV, Williamstown | 2026-04-25 | Progress claim | 1437 | 71.85 | 0 | 1365.15 | 136.52 | 1501.67 | Approved - sent to Xero | 2026-04-01
INV-30701 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-04-25 | Progress claim | 6526 | 0 | 0 | 6526 | 652.6 | 7178.6 | Approved - sent to Xero | 2026-04-01
INV-30702 | P2521 | Aged care wing, Coburg | 2026-04-25 | Progress claim | 7080.9 | 0 | 0 | 7080.9 | 708.09 | 7788.99 | Approved - sent to Xero | 2026-04-01
INV-30703 | P2524 | Childcare centre, Preston | 2026-04-25 | Progress claim | 22471.2 | 1123.56 | 0 | 21347.64 | 2134.76 | 23482.4 | Approved - sent to Xero | 2026-04-01
INV-30704 | P2526 | School science block, Clayton | 2026-04-25 | Progress claim | 5786.5 | 289.33 | 0 | 5497.17 | 549.72 | 6046.89 | Approved - sent to Xero | 2026-04-01
INV-30705 | P2527 | Showroom refurbishment, Williamstown | 2026-04-25 | Progress claim | 1613.4 | 80.67 | 0 | 1532.73 | 153.27 | 1686 | Approved - sent to Xero | 2026-04-01
INV-30706 | P2530 | Gym fit-out, Preston | 2026-04-25 | Progress claim | 10971.85 | 548.59 | 0 | 10423.26 | 1042.33 | 11465.59 | Approved - sent to Xero | 2026-04-01
INV-30707 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-04-25 | Progress claim | 10587 | 529.35 | 0 | 10057.65 | 1005.77 | 11063.42 | Approved - sent to Xero | 2026-04-01
INV-30708 | P2533 | Office fit-out, Oakleigh | 2026-04-25 | Progress claim | 9416.8 | 470.84 | 0 | 8945.96 | 894.6 | 9840.56 | Approved - sent to Xero | 2026-04-01
INV-30709 | P2534 | Retail tenancy fit-out, Bayswater | 2026-04-25 | Progress claim | 20204.45 | 1010.22 | 0 | 19194.23 | 1919.42 | 21113.65 | Approved - sent to Xero | 2026-04-01
INV-30710 | P2536 | Warehouse lighting upgrade, Preston | 2026-04-25 | Progress claim | 23372.95 | 0 | 0 | 23372.95 | 2337.3 | 25710.25 | Approved - sent to Xero | 2026-04-01
INV-30711 | P2537 | Car park lighting and EV, Ascot Vale | 2026-04-25 | Progress claim | 5489.2 | 0 | 0 | 5489.2 | 548.92 | 6038.12 | Approved - sent to Xero | 2026-04-01
INV-30712 | P2538 | Medical centre electrical, Kew | 2026-04-25 | Progress claim | 23407.8 | 0 | 0 | 23407.8 | 2340.78 | 25748.58 | Approved - sent to Xero | 2026-04-01
INV-30713 | P2539 | Retail tenancy fit-out, Carlton | 2026-04-25 | Progress claim | 15833.4 | 0 | 0 | 15833.4 | 1583.34 | 17416.74 | Approved - sent to Xero | 2026-04-01
INV-30714 | P2541 | Apartment common areas, Clayton | 2026-04-25 | Progress claim | 44233 | 2211.65 | 0 | 42021.35 | 4202.14 | 46223.49 | Approved - sent to Xero | 2026-04-01
INV-30715 | P2542 | Apartment common areas, Moonee Ponds | 2026-04-25 | Progress claim | 13793.8 | 0 | 0 | 13793.8 | 1379.38 | 15173.18 | Approved - sent to Xero | 2026-04-01
INV-30716 | P2543 | Retail tenancy fit-out, Yarraville | 2026-04-25 | Progress claim | 54813.75 | 0 | 0 | 54813.75 | 5481.38 | 60295.13 | Approved - sent to Xero | 2026-04-01
INV-30717 | P2544 | School science block, St Kilda | 2026-04-25 | Progress claim | 4125 | 0 | 0 | 4125 | 412.5 | 4537.5 | Approved - sent to Xero | 2026-04-01
INV-30718 | P2545 | Showroom refurbishment, Hawthorn | 2026-04-25 | Progress claim | 72257.6 | 0 | 0 | 72257.6 | 7225.76 | 79483.36 | Approved - sent to Xero | 2026-04-01
INV-30719 | P2546 | Showroom refurbishment, Malvern | 2026-04-25 | Progress claim | 69629.7 | 0 | 0 | 69629.7 | 6962.97 | 76592.67 | Approved - sent to Xero | 2026-04-01
INV-30720 | P2547 | School science block, Dandenong | 2026-04-25 | Progress claim | 33196.9 | 0 | 0 | 33196.9 | 3319.69 | 36516.59 | Approved - sent to Xero | 2026-04-01
INV-30721 | P2548 | School science block, Essendon | 2026-04-25 | Progress claim | 22386.4 | 1119.32 | 0 | 21267.08 | 2126.71 | 23393.79 | Approved - sent to Xero | 2026-04-01
INV-30722 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-04-25 | Progress claim | 11029.2 | 0 | 0 | 11029.2 | 1102.92 | 12132.12 | Approved - sent to Xero | 2026-04-01
INV-30723 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-04-25 | Progress claim | 9638.65 | 0 | 0 | 9638.65 | 963.87 | 10602.52 | Approved - sent to Xero | 2026-04-01
INV-30724 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-04-25 | Progress claim | 1892.7 | 0 | 0 | 1892.7 | 189.27 | 2081.97 | Approved - sent to Xero | 2026-04-01
INV-30725 | P2552 | Aged care wing, Hawthorn | 2026-04-25 | Progress claim | 7451.1 | 0 | 0 | 7451.1 | 745.11 | 8196.21 | Approved - sent to Xero | 2026-04-01
INV-30726 | P2553 | School science block, Bayswater | 2026-04-25 | Progress claim | 11492.2 | 574.61 | 0 | 10917.59 | 1091.76 | 12009.35 | Approved - sent to Xero | 2026-04-01
INV-30727 | P2554 | Showroom refurbishment, Reservoir | 2026-04-25 | Progress claim | 26781.2 | 0 | 0 | 26781.2 | 2678.12 | 29459.32 | Approved - sent to Xero | 2026-04-01
INV-30728 | P2514 | School science block, Richmond | 2026-05-10 | Progress claim | 5597.15 | 279.86 | 0 | 5317.29 | 531.73 | 5849.02 | Approved - sent to Xero | 2026-05-01
INV-30729 | P2519 | Car park lighting and EV, Williamstown | 2026-05-10 | Progress claim | 2874 | 143.7 | 0 | 2730.3 | 273.03 | 3003.33 | Approved - sent to Xero | 2026-05-01
INV-30730 | P2521 | Aged care wing, Coburg | 2026-05-10 | Progress claim | 2275.8 | 0 | 0 | 2275.8 | 227.58 | 2503.38 | Approved - sent to Xero | 2026-05-01
INV-30731 | P2523 | Aged care wing, Bayswater | 2026-05-10 | Progress claim | 589.2 | 0 | 0 | 589.2 | 58.92 | 648.12 | Approved - sent to Xero | 2026-05-01
INV-30732 | P2526 | School science block, Clayton | 2026-05-10 | Progress claim | 8679.75 | 433.99 | 0 | 8245.76 | 824.58 | 9070.34 | Approved - sent to Xero | 2026-05-01
INV-30733 | P2527 | Showroom refurbishment, Williamstown | 2026-05-10 | Progress claim | 3226.8 | 161.34 | 0 | 3065.46 | 306.55 | 3372.01 | Approved - sent to Xero | 2026-05-01
INV-30734 | P2530 | Gym fit-out, Preston | 2026-05-10 | Progress claim | 7350 | 367.5 | 0 | 6982.5 | 698.25 | 7680.75 | Approved - sent to Xero | 2026-05-01
INV-30735 | P2533 | Office fit-out, Oakleigh | 2026-05-10 | Progress claim | 5527.8 | 276.39 | 0 | 5251.41 | 525.14 | 5776.55 | Approved - sent to Xero | 2026-05-01
INV-30736 | P2536 | Warehouse lighting upgrade, Preston | 2026-05-10 | Progress claim | 24397.4 | 0 | 0 | 24397.4 | 2439.74 | 26837.14 | Approved - sent to Xero | 2026-05-01
INV-30737 | P2538 | Medical centre electrical, Kew | 2026-05-10 | Progress claim | 7881.25 | 0 | 0 | 7881.25 | 788.13 | 8669.38 | Approved - sent to Xero | 2026-05-01
INV-30738 | P2539 | Retail tenancy fit-out, Carlton | 2026-05-10 | Progress claim | 18455.7 | 0 | 0 | 18455.7 | 1845.57 | 20301.27 | Approved - sent to Xero | 2026-05-01
INV-30739 | P2544 | School science block, St Kilda | 2026-05-10 | Progress claim | 6047.9 | 0 | 0 | 6047.9 | 604.79 | 6652.69 | Approved - sent to Xero | 2026-05-01
INV-30740 | P2545 | Showroom refurbishment, Hawthorn | 2026-05-10 | Progress claim | 46001.05 | 0 | 0 | 46001.05 | 4600.11 | 50601.16 | Approved - sent to Xero | 2026-05-01
INV-30741 | P2546 | Showroom refurbishment, Malvern | 2026-05-10 | Progress claim | 63023.55 | 0 | 0 | 63023.55 | 6302.36 | 69325.91 | Approved - sent to Xero | 2026-05-01
INV-30742 | P2547 | School science block, Dandenong | 2026-05-10 | Progress claim | 53815.1 | 0 | 0 | 53815.1 | 5381.51 | 59196.61 | Approved - sent to Xero | 2026-05-01
INV-30743 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-05-10 | Progress claim | 11029.2 | 0 | 0 | 11029.2 | 1102.92 | 12132.12 | Approved - sent to Xero | 2026-05-01
INV-30744 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-05-10 | Progress claim | 5507.8 | 0 | 0 | 5507.8 | 550.78 | 6058.58 | Approved - sent to Xero | 2026-05-01
INV-30745 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-05-10 | Progress claim | 3785.4 | 0 | 0 | 3785.4 | 378.54 | 4163.94 | Approved - sent to Xero | 2026-05-01
INV-30746 | P2552 | Aged care wing, Hawthorn | 2026-05-10 | Progress claim | 7451.1 | 0 | 0 | 7451.1 | 745.11 | 8196.21 | Approved - sent to Xero | 2026-05-01
INV-30747 | P2553 | School science block, Bayswater | 2026-05-10 | Progress claim | 28458.55 | 1422.93 | 0 | 27035.62 | 2703.56 | 29739.18 | Approved - sent to Xero | 2026-05-01
INV-30748 | P2554 | Showroom refurbishment, Reservoir | 2026-05-10 | Progress claim | 19961 | 0 | 0 | 19961 | 1996.1 | 21957.1 | Approved - sent to Xero | 2026-05-01
INV-30749 | P2512 | Warehouse lighting upgrade, Northcote | 2026-05-25 | Final claim | 11025 | 551.25 | 5668.76 | 16142.51 | 1614.25 | 17756.76 | Approved - sent to Xero | 2026-05-01
INV-30750 | P2514 | School science block, Richmond | 2026-05-25 | Progress claim | 10949.05 | 547.45 | 0 | 10401.6 | 1040.16 | 11441.76 | Approved - sent to Xero | 2026-05-01
INV-30751 | P2519 | Car park lighting and EV, Williamstown | 2026-05-25 | Progress claim | 2874 | 143.7 | 0 | 2730.3 | 273.03 | 3003.33 | Approved - sent to Xero | 2026-05-01
INV-30752 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-05-25 | Progress claim | 6526 | 0 | 0 | 6526 | 652.6 | 7178.6 | Approved - sent to Xero | 2026-05-01
INV-30753 | P2521 | Aged care wing, Coburg | 2026-05-25 | Progress claim | 2844.75 | 0 | 0 | 2844.75 | 284.48 | 3129.23 | Approved - sent to Xero | 2026-05-01
INV-30754 | P2523 | Aged care wing, Bayswater | 2026-05-25 | Progress claim | 5028.4 | 0 | 0 | 5028.4 | 502.84 | 5531.24 | Approved - sent to Xero | 2026-05-01
INV-30755 | P2524 | Childcare centre, Preston | 2026-05-25 | Progress claim | 33602.8 | 1680.14 | 0 | 31922.66 | 3192.27 | 35114.93 | Approved - sent to Xero | 2026-05-01
INV-30756 | P2526 | School science block, Clayton | 2026-05-25 | Progress claim | 5786.5 | 289.33 | 0 | 5497.17 | 549.72 | 6046.89 | Approved - sent to Xero | 2026-05-01
INV-30757 | P2527 | Showroom refurbishment, Williamstown | 2026-05-25 | Progress claim | 2689 | 134.45 | 0 | 2554.55 | 255.46 | 2810.01 | Approved - sent to Xero | 2026-05-01
INV-30758 | P2530 | Gym fit-out, Preston | 2026-05-25 | Progress claim | 4593.75 | 229.69 | 0 | 4364.06 | 436.41 | 4800.47 | Approved - sent to Xero | 2026-05-01
INV-30759 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-05-25 | Progress claim | 9385.25 | 469.26 | 0 | 8915.99 | 891.6 | 9807.59 | Approved - sent to Xero | 2026-05-01
INV-30760 | P2533 | Office fit-out, Oakleigh | 2026-05-25 | Final claim | 32495 | 1624.75 | 11956.26 | 42826.51 | 4282.65 | 47109.16 | Approved - sent to Xero | 2026-05-01
INV-30761 | P2535 | Office fit-out, Preston | 2026-05-25 | Progress claim | 624.75 | 0 | 0 | 624.75 | 62.48 | 687.23 | Approved - sent to Xero | 2026-05-01
INV-30762 | P2536 | Warehouse lighting upgrade, Preston | 2026-05-25 | Progress claim | 34732.15 | 0 | 0 | 34732.15 | 3473.22 | 38205.37 | Approved - sent to Xero | 2026-05-01
INV-30763 | P2538 | Medical centre electrical, Kew | 2026-05-25 | Progress claim | 4866.3 | 0 | 0 | 4866.3 | 486.63 | 5352.93 | Approved - sent to Xero | 2026-05-01
INV-30764 | P2539 | Retail tenancy fit-out, Carlton | 2026-05-25 | Progress claim | 16254.25 | 0 | 0 | 16254.25 | 1625.43 | 17879.68 | Approved - sent to Xero | 2026-05-01
INV-30765 | P2540 | Aged care wing, Burwood | 2026-05-25 | Progress claim | 3189 | 0 | 0 | 3189 | 318.9 | 3507.9 | Approved - sent to Xero | 2026-05-01
INV-30766 | P2541 | Apartment common areas, Clayton | 2026-05-25 | Progress claim | 68658.75 | 3432.94 | 0 | 65225.81 | 6522.58 | 71748.39 | Approved - sent to Xero | 2026-05-01
INV-30767 | P2542 | Apartment common areas, Moonee Ponds | 2026-05-25 | Progress claim | 13749.9 | 0 | 0 | 13749.9 | 1374.99 | 15124.89 | Approved - sent to Xero | 2026-05-01
INV-30768 | P2543 | Retail tenancy fit-out, Yarraville | 2026-05-25 | Progress claim | 8919.45 | 0 | 0 | 8919.45 | 891.95 | 9811.4 | Approved - sent to Xero | 2026-05-01
INV-30769 | P2544 | School science block, St Kilda | 2026-05-25 | Progress claim | 2472.3 | 0 | 0 | 2472.3 | 247.23 | 2719.53 | Approved - sent to Xero | 2026-05-01
INV-30770 | P2545 | Showroom refurbishment, Hawthorn | 2026-05-25 | Progress claim | 35741.15 | 0 | 0 | 35741.15 | 3574.12 | 39315.27 | Approved - sent to Xero | 2026-05-01
INV-30771 | P2546 | Showroom refurbishment, Malvern | 2026-05-25 | Progress claim | 103042.9 | 0 | 0 | 103042.9 | 10304.29 | 113347.19 | Approved - sent to Xero | 2026-05-01
INV-30772 | P2547 | School science block, Dandenong | 2026-05-25 | Progress claim | 53143.95 | 0 | 0 | 53143.95 | 5314.4 | 58458.35 | Approved - sent to Xero | 2026-05-01
INV-30773 | P2548 | School science block, Essendon | 2026-05-25 | Progress claim | 92198.4 | 4609.92 | 0 | 87588.48 | 8758.85 | 96347.33 | Approved - sent to Xero | 2026-05-01
INV-30774 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-05-25 | Progress claim | 11029.2 | 0 | 0 | 11029.2 | 1102.92 | 12132.12 | Approved - sent to Xero | 2026-05-01
INV-30775 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-05-25 | Progress claim | 7242.1 | 0 | 0 | 7242.1 | 724.21 | 7966.31 | Approved - sent to Xero | 2026-05-01
INV-30776 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-05-25 | Progress claim | 7305.45 | 0 | 0 | 7305.45 | 730.55 | 8036 | Approved - sent to Xero | 2026-05-01
INV-30777 | P2552 | Aged care wing, Hawthorn | 2026-05-25 | Progress claim | 10458.25 | 0 | 0 | 10458.25 | 1045.83 | 11504.08 | Approved - sent to Xero | 2026-05-01
INV-30778 | P2553 | School science block, Bayswater | 2026-05-25 | Progress claim | 46013.2 | 2300.66 | 0 | 43712.54 | 4371.25 | 48083.79 | Approved - sent to Xero | 2026-05-01
INV-30779 | P2554 | Showroom refurbishment, Reservoir | 2026-05-25 | Progress claim | 13140.8 | 0 | 0 | 13140.8 | 1314.08 | 14454.88 | Approved - sent to Xero | 2026-05-01
INV-30780 | P2555 | Gym fit-out, Camberwell | 2026-05-25 | Progress claim | 4441.2 | 0 | 0 | 4441.2 | 444.12 | 4885.32 | Approved - sent to Xero | 2026-05-01
INV-30781 | P2556 | Office fit-out, Preston West | 2026-05-25 | Progress claim | 11073.1 | 553.66 | 0 | 10519.44 | 1051.94 | 11571.38 | Approved - sent to Xero | 2026-05-01
INV-30782 | P2514 | School science block, Richmond | 2026-06-10 | Progress claim | 6800 | 340 | 0 | 6460 | 646 | 7106 | Approved - sent to Xero | 2026-06-01
INV-30783 | P2521 | Aged care wing, Coburg | 2026-06-10 | Progress claim | 2275.8 | 0 | 0 | 2275.8 | 227.58 | 2503.38 | Approved - sent to Xero | 2026-06-01
INV-30784 | P2523 | Aged care wing, Bayswater | 2026-06-10 | Progress claim | 5617.6 | 0 | 0 | 5617.6 | 561.76 | 6179.36 | Approved - sent to Xero | 2026-06-01
INV-30785 | P2524 | Childcare centre, Preston | 2026-06-10 | Progress claim | 10075 | 503.75 | 0 | 9571.25 | 957.13 | 10528.38 | Approved - sent to Xero | 2026-06-01
INV-30786 | P2526 | School science block, Clayton | 2026-06-10 | Progress claim | 5786.5 | 289.33 | 0 | 5497.17 | 549.72 | 6046.89 | Approved - sent to Xero | 2026-06-01
INV-30787 | P2535 | Office fit-out, Preston | 2026-06-10 | Progress claim | 1874.25 | 0 | 0 | 1874.25 | 187.43 | 2061.68 | Approved - sent to Xero | 2026-06-01
INV-30788 | P2539 | Retail tenancy fit-out, Carlton | 2026-06-10 | Progress claim | 21946 | 0 | 0 | 21946 | 2194.6 | 24140.6 | Approved - sent to Xero | 2026-06-01
INV-30789 | P2543 | Retail tenancy fit-out, Yarraville | 2026-06-10 | Progress claim | 507.4 | 0 | 0 | 507.4 | 50.74 | 558.14 | Approved - sent to Xero | 2026-06-01
INV-30790 | P2545 | Showroom refurbishment, Hawthorn | 2026-06-10 | Progress claim | 35009.55 | 0 | 0 | 35009.55 | 3500.96 | 38510.51 | Approved - sent to Xero | 2026-06-01
INV-30791 | P2546 | Showroom refurbishment, Malvern | 2026-06-10 | Progress claim | 111075.35 | 0 | 0 | 111075.35 | 11107.54 | 122182.89 | Approved - sent to Xero | 2026-06-01
INV-30792 | P2547 | School science block, Dandenong | 2026-06-10 | Progress claim | 56282.75 | 0 | 0 | 56282.75 | 5628.28 | 61911.03 | Approved - sent to Xero | 2026-06-01
INV-30793 | P2548 | School science block, Essendon | 2026-06-10 | Progress claim | 29641 | 1482.05 | 0 | 28158.95 | 2815.9 | 30974.85 | Approved - sent to Xero | 2026-06-01
INV-30794 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-06-10 | Progress claim | 22544.65 | 0 | 0 | 22544.65 | 2254.47 | 24799.12 | Approved - sent to Xero | 2026-06-01
INV-30795 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-06-10 | Progress claim | 7956.8 | 0 | 0 | 7956.8 | 795.68 | 8752.48 | Approved - sent to Xero | 2026-06-01
INV-30796 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-06-10 | Progress claim | 9538.65 | 0 | 0 | 9538.65 | 953.87 | 10492.52 | Approved - sent to Xero | 2026-06-01
INV-30797 | P2552 | Aged care wing, Hawthorn | 2026-06-10 | Progress claim | 19479.7 | 0 | 0 | 19479.7 | 1947.97 | 21427.67 | Approved - sent to Xero | 2026-06-01
INV-30798 | P2556 | Office fit-out, Preston West | 2026-06-10 | Progress claim | 29883.4 | 1494.17 | 0 | 28389.23 | 2838.92 | 31228.15 | Approved - sent to Xero | 2026-06-01
INV-30799 | P2514 | School science block, Richmond | 2026-06-25 | Final claim | 16090 | 804.5 | 9742.51 | 25028.01 | 2502.8 | 27530.81 | Approved - sent to Xero | 2026-06-01
INV-30800 | P2519 | Car park lighting and EV, Williamstown | 2026-06-25 | Progress claim | 1916 | 95.8 | 0 | 1820.2 | 182.02 | 2002.22 | Approved - sent to Xero | 2026-06-01
INV-30801 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-06-25 | Progress claim | 1631.5 | 0 | 0 | 1631.5 | 163.15 | 1794.65 | Approved - sent to Xero | 2026-06-01
INV-30802 | P2521 | Aged care wing, Coburg | 2026-06-25 | Progress claim | 2275.8 | 0 | 0 | 2275.8 | 227.58 | 2503.38 | Approved - sent to Xero | 2026-06-01
INV-30803 | P2523 | Aged care wing, Bayswater | 2026-06-25 | Progress claim | 1178.4 | 0 | 0 | 1178.4 | 117.84 | 1296.24 | Approved - sent to Xero | 2026-06-01
INV-30804 | P2524 | Childcare centre, Preston | 2026-06-25 | Final claim | 23480 | 1174 | 14191.26 | 36497.26 | 3649.73 | 40146.99 | Approved - sent to Xero | 2026-06-01
INV-30805 | P2526 | School science block, Clayton | 2026-06-25 | Progress claim | 4058.15 | 202.91 | 0 | 3855.24 | 385.52 | 4240.76 | Approved - sent to Xero | 2026-06-01
INV-30806 | P2527 | Showroom refurbishment, Williamstown | 2026-06-25 | Progress claim | 2689 | 134.45 | 0 | 2554.55 | 255.46 | 2810.01 | Approved - sent to Xero | 2026-06-01
INV-30807 | P2530 | Gym fit-out, Preston | 2026-06-25 | Final claim | 26893.75 | 1344.69 | 9377.52 | 34926.58 | 3492.66 | 38419.24 | Approved - sent to Xero | 2026-06-01
INV-30808 | P2532 | Industrial unit power upgrade, Ascot Vale | 2026-06-25 | Final claim | 17365 | 868.25 | 9171.28 | 25668.03 | 2566.8 | 28234.83 | Approved - sent to Xero | 2026-06-01
INV-30809 | P2535 | Office fit-out, Preston | 2026-06-25 | Progress claim | 1249.5 | 0 | 0 | 1249.5 | 124.95 | 1374.45 | Approved - sent to Xero | 2026-06-01
INV-30810 | P2536 | Warehouse lighting upgrade, Preston | 2026-06-25 | Progress claim | 50773.8 | 0 | 0 | 50773.8 | 5077.38 | 55851.18 | Approved - sent to Xero | 2026-06-01
INV-30811 | P2537 | Car park lighting and EV, Ascot Vale | 2026-06-25 | Progress claim | 309.05 | 0 | 0 | 309.05 | 30.91 | 339.96 | Approved - sent to Xero | 2026-06-01
INV-30812 | P2538 | Medical centre electrical, Kew | 2026-06-25 | Progress claim | 1622.1 | 0 | 0 | 1622.1 | 162.21 | 1784.31 | Approved - sent to Xero | 2026-06-01
INV-30813 | P2539 | Retail tenancy fit-out, Carlton | 2026-06-25 | Progress claim | 27564.45 | 0 | 0 | 27564.45 | 2756.45 | 30320.9 | Approved - sent to Xero | 2026-06-01
INV-30814 | P2540 | Aged care wing, Burwood | 2026-06-25 | Final claim | 7175.25 | 0 | 0 | 7175.25 | 717.53 | 7892.78 | Approved - sent to Xero | 2026-06-01
INV-30815 | P2541 | Apartment common areas, Clayton | 2026-06-25 | Progress claim | 77082.2 | 3854.11 | 0 | 73228.09 | 7322.81 | 80550.9 | Approved - sent to Xero | 2026-06-01
INV-30816 | P2543 | Retail tenancy fit-out, Yarraville | 2026-06-25 | Progress claim | 3044.4 | 0 | 0 | 3044.4 | 304.44 | 3348.84 | Approved - sent to Xero | 2026-06-01
INV-30817 | P2544 | School science block, St Kilda | 2026-06-25 | Final claim | 15129.1 | 0 | 0 | 15129.1 | 1512.91 | 16642.01 | Approved - sent to Xero | 2026-06-01
INV-30818 | P2545 | Showroom refurbishment, Hawthorn | 2026-06-25 | Progress claim | 31624.65 | 0 | 0 | 31624.65 | 3162.47 | 34787.12 | Approved - sent to Xero | 2026-06-01
INV-30819 | P2546 | Showroom refurbishment, Malvern | 2026-06-25 | Progress claim | 67993.4 | 0 | 0 | 67993.4 | 6799.34 | 74792.74 | Approved - sent to Xero | 2026-06-01
INV-30820 | P2547 | School science block, Dandenong | 2026-06-25 | Progress claim | 41570.25 | 0 | 0 | 41570.25 | 4157.03 | 45727.28 | Approved - sent to Xero | 2026-06-01
INV-30821 | P2548 | School science block, Essendon | 2026-06-25 | Progress claim | 29641 | 1482.05 | 0 | 28158.95 | 2815.9 | 30974.85 | Approved - sent to Xero | 2026-06-01
INV-30822 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-06-25 | Progress claim | 17030.05 | 0 | 0 | 17030.05 | 1703.01 | 18733.06 | Approved - sent to Xero | 2026-06-01
INV-30823 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-06-25 | Progress claim | 8671.5 | 0 | 0 | 8671.5 | 867.15 | 9538.65 | Approved - sent to Xero | 2026-06-01
INV-30824 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-06-25 | Progress claim | 10933.65 | 0 | 0 | 10933.65 | 1093.37 | 12027.02 | Approved - sent to Xero | 2026-06-01
INV-30825 | P2552 | Aged care wing, Hawthorn | 2026-06-25 | Progress claim | 25494 | 0 | 0 | 25494 | 2549.4 | 28043.4 | Approved - sent to Xero | 2026-06-01
INV-30826 | P2553 | School science block, Bayswater | 2026-06-25 | Progress claim | 118421.65 | 5921.08 | 0 | 112500.57 | 11250.06 | 123750.63 | Approved - sent to Xero | 2026-06-01
INV-30827 | P2554 | Showroom refurbishment, Reservoir | 2026-06-25 | Progress claim | 22559.25 | 0 | 0 | 22559.25 | 2255.93 | 24815.18 | Approved - sent to Xero | 2026-06-01
INV-30828 | P2555 | Gym fit-out, Camberwell | 2026-06-25 | Progress claim | 15938.5 | 0 | 0 | 15938.5 | 1593.85 | 17532.35 | Approved - sent to Xero | 2026-06-01
INV-30829 | P2556 | Office fit-out, Preston West | 2026-06-25 | Progress claim | 33922.5 | 1696.13 | 0 | 32226.37 | 3222.64 | 35449.01 | Approved - sent to Xero | 2026-06-01
INV-30830 | P2523 | Aged care wing, Bayswater | 2026-07-10 | Progress claim | 5514.2 | 0 | 0 | 5514.2 | 551.42 | 6065.62 | Approved - sent to Xero | 2026-07-01
INV-30831 | P2526 | School science block, Clayton | 2026-07-10 | Progress claim | 2329.8 | 116.49 | 0 | 2213.31 | 221.33 | 2434.64 | Approved - sent to Xero | 2026-07-01
INV-30832 | P2534 | Retail tenancy fit-out, Bayswater | 2026-07-10 | Progress claim | 1501.2 | 75.06 | 0 | 1426.14 | 142.61 | 1568.75 | Approved - sent to Xero | 2026-07-01
INV-30833 | P2536 | Warehouse lighting upgrade, Preston | 2026-07-10 | Progress claim | 19283.25 | 0 | 0 | 19283.25 | 1928.33 | 21211.58 | Approved - sent to Xero | 2026-07-01
INV-30834 | P2538 | Medical centre electrical, Kew | 2026-07-10 | Progress claim | 770 | 0 | 0 | 770 | 77 | 847 | Approved - sent to Xero | 2026-07-01
INV-30835 | P2539 | Retail tenancy fit-out, Carlton | 2026-07-10 | Progress claim | 25242.7 | 0 | 0 | 25242.7 | 2524.27 | 27766.97 | Approved - sent to Xero | 2026-07-01
INV-30836 | P2541 | Apartment common areas, Clayton | 2026-07-10 | Progress claim | 23090.45 | 1154.52 | 0 | 21935.93 | 2193.59 | 24129.52 | Approved - sent to Xero | 2026-07-01
INV-30837 | P2545 | Showroom refurbishment, Hawthorn | 2026-07-10 | Progress claim | 34373.1 | 0 | 0 | 34373.1 | 3437.31 | 37810.41 | Approved - sent to Xero | 2026-07-01
INV-30838 | P2547 | School science block, Dandenong | 2026-07-10 | Progress claim | 18778.5 | 0 | 0 | 18778.5 | 1877.85 | 20656.35 | Approved - sent to Xero | 2026-07-01
INV-30839 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-07-10 | Progress claim | 8671.5 | 0 | 0 | 8671.5 | 867.15 | 9538.65 | Approved - sent to Xero | 2026-07-01
INV-30840 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-07-10 | Progress claim | 11041.8 | 0 | 0 | 11041.8 | 1104.18 | 12145.98 | Approved - sent to Xero | 2026-07-01
INV-30841 | P2553 | School science block, Bayswater | 2026-07-10 | Progress claim | 65717.45 | 3285.87 | 0 | 62431.58 | 6243.16 | 68674.74 | Approved - sent to Xero | 2026-07-01
INV-30842 | P2554 | Showroom refurbishment, Reservoir | 2026-07-10 | Progress claim | 12891 | 0 | 0 | 12891 | 1289.1 | 14180.1 | Approved - sent to Xero | 2026-07-01
INV-30843 | P2556 | Office fit-out, Preston West | 2026-07-10 | Progress claim | 44626.45 | 2231.32 | 0 | 42395.13 | 4239.51 | 46634.64 | Approved - sent to Xero | 2026-07-01
INV-30844 | P2519 | Car park lighting and EV, Williamstown | 2026-07-25 | Final claim | 10645 | 532.25 | 5976.27 | 16089.02 | 1608.9 | 17697.92 | Approved - sent to Xero | 2026-07-01
INV-30845 | P2520 | Industrial unit power upgrade, Hawthorn | 2026-07-25 | Final claim | 16315 | 0 | 0 | 16315 | 1631.5 | 17946.5 | Approved - sent to Xero | 2026-07-01
INV-30846 | P2521 | Aged care wing, Coburg | 2026-07-25 | Progress claim | 1137.9 | 0 | 0 | 1137.9 | 113.79 | 1251.69 | Approved - sent to Xero | 2026-07-01
INV-30847 | P2523 | Aged care wing, Bayswater | 2026-07-25 | Progress claim | 5219.6 | 0 | 0 | 5219.6 | 521.96 | 5741.56 | Approved - sent to Xero | 2026-07-01
INV-30848 | P2526 | School science block, Clayton | 2026-07-25 | Progress claim | 2912.25 | 145.61 | 0 | 2766.64 | 276.66 | 3043.3 | Approved - sent to Xero | 2026-07-01
INV-30849 | P2527 | Showroom refurbishment, Williamstown | 2026-07-25 | Final claim | 15365 | 768.25 | 7820.02 | 22416.77 | 2241.68 | 24658.45 | Approved - sent to Xero | 2026-07-01
INV-30850 | P2534 | Retail tenancy fit-out, Bayswater | 2026-07-25 | Progress claim | 3502.8 | 175.14 | 0 | 3327.66 | 332.77 | 3660.43 | Approved - sent to Xero | 2026-07-01
INV-30851 | P2535 | Office fit-out, Preston | 2026-07-25 | Final claim | 4373.25 | 0 | 0 | 4373.25 | 437.33 | 4810.58 | Approved - sent to Xero | 2026-07-01
INV-30852 | P2536 | Warehouse lighting upgrade, Preston | 2026-07-25 | Progress claim | 5857 | 0 | 0 | 5857 | 585.7 | 6442.7 | Approved - sent to Xero | 2026-07-01
INV-30853 | P2537 | Car park lighting and EV, Ascot Vale | 2026-07-25 | Progress claim | 4944.8 | 0 | 0 | 4944.8 | 494.48 | 5439.28 | Approved - sent to Xero | 2026-07-01
INV-30854 | P2538 | Medical centre electrical, Kew | 2026-07-25 | Progress claim | 1078 | 0 | 0 | 1078 | 107.8 | 1185.8 | Approved - sent to Xero | 2026-07-01
INV-30855 | P2539 | Retail tenancy fit-out, Carlton | 2026-07-25 | Progress claim | 22620.4 | 0 | 0 | 22620.4 | 2262.04 | 24882.44 | Approved - sent to Xero | 2026-07-01
INV-30856 | P2541 | Apartment common areas, Clayton | 2026-07-25 | Progress claim | 18201.45 | 910.07 | 0 | 17291.38 | 1729.14 | 19020.52 | Approved - sent to Xero | 2026-07-01
INV-30857 | P2543 | Retail tenancy fit-out, Yarraville | 2026-07-25 | Progress claim | 6088.8 | 0 | 0 | 6088.8 | 608.88 | 6697.68 | Approved - sent to Xero | 2026-07-01
INV-30858 | P2545 | Showroom refurbishment, Hawthorn | 2026-07-25 | Progress claim | 34373.1 | 0 | 0 | 34373.1 | 3437.31 | 37810.41 | Approved - sent to Xero | 2026-07-01
INV-30859 | P2546 | Showroom refurbishment, Malvern | 2026-07-25 | Progress claim | 237812.35 | 0 | 0 | 237812.35 | 23781.24 | 261593.59 | Approved - sent to Xero | 2026-07-01
INV-30860 | P2547 | School science block, Dandenong | 2026-07-25 | Progress claim | 14834.75 | 0 | 0 | 14834.75 | 1483.48 | 16318.23 | Approved - sent to Xero | 2026-07-01
INV-30861 | P2548 | School science block, Essendon | 2026-07-25 | Progress claim | 5928.2 | 296.41 | 0 | 5631.79 | 563.18 | 6194.97 | Approved - sent to Xero | 2026-07-01
INV-30862 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-07-25 | Progress claim | 68945.45 | 0 | 0 | 68945.45 | 6894.55 | 75840 | Approved - sent to Xero | 2026-07-01
INV-30863 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-07-25 | Progress claim | 6937.2 | 0 | 0 | 6937.2 | 693.72 | 7630.92 | Approved - sent to Xero | 2026-07-01
INV-30864 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-07-25 | Progress claim | 8808.6 | 0 | 0 | 8808.6 | 880.86 | 9689.46 | Approved - sent to Xero | 2026-07-01
INV-30865 | P2552 | Aged care wing, Hawthorn | 2026-07-25 | Progress claim | 31508.3 | 0 | 0 | 31508.3 | 3150.83 | 34659.13 | Approved - sent to Xero | 2026-07-01
INV-30866 | P2553 | School science block, Bayswater | 2026-07-25 | Progress claim | 87394.3 | 4369.72 | 0 | 83024.58 | 8302.46 | 91327.04 | Approved - sent to Xero | 2026-07-01
INV-30867 | P2554 | Showroom refurbishment, Reservoir | 2026-07-25 | Progress claim | 10918.25 | 0 | 0 | 10918.25 | 1091.83 | 12010.08 | Approved - sent to Xero | 2026-07-01
INV-30868 | P2555 | Gym fit-out, Camberwell | 2026-07-25 | Progress claim | 27830.1 | 0 | 0 | 27830.1 | 2783.01 | 30613.11 | Approved - sent to Xero | 2026-07-01
INV-30869 | P2556 | Office fit-out, Preston West | 2026-07-25 | Progress claim | 46833.7 | 2341.69 | 0 | 44492.01 | 4449.2 | 48941.21 | Approved - sent to Xero | 2026-07-01
INV-30870 | P2521 | Aged care wing, Coburg | 2026-08-10 | Progress claim | 6075 | 0 | 0 | 6075 | 607.5 | 6682.5 | Approved - sent to Xero | 2026-08-01
INV-30871 | P2534 | Retail tenancy fit-out, Bayswater | 2026-08-10 | Progress claim | 3002.4 | 150.12 | 0 | 2852.28 | 285.23 | 3137.51 | Approved - sent to Xero | 2026-08-01
INV-30872 | P2537 | Car park lighting and EV, Ascot Vale | 2026-08-10 | Progress claim | 618.1 | 0 | 0 | 618.1 | 61.81 | 679.91 | Approved - sent to Xero | 2026-08-01
INV-30873 | P2539 | Retail tenancy fit-out, Carlton | 2026-08-10 | Progress claim | 14306.35 | 0 | 0 | 14306.35 | 1430.64 | 15736.99 | Approved - sent to Xero | 2026-08-01
INV-30874 | P2545 | Showroom refurbishment, Hawthorn | 2026-08-10 | Progress claim | 32908.15 | 0 | 0 | 32908.15 | 3290.82 | 36198.97 | Approved - sent to Xero | 2026-08-01
INV-30875 | P2546 | Showroom refurbishment, Malvern | 2026-08-10 | Progress claim | 110191.4 | 0 | 0 | 110191.4 | 11019.14 | 121210.54 | Approved - sent to Xero | 2026-08-01
INV-30876 | P2547 | School science block, Dandenong | 2026-08-10 | Progress claim | 11867.8 | 0 | 0 | 11867.8 | 1186.78 | 13054.58 | Approved - sent to Xero | 2026-08-01
INV-30877 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-08-10 | Progress claim | 40399.95 | 0 | 0 | 40399.95 | 4040 | 44439.95 | Approved - sent to Xero | 2026-08-01
INV-30878 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-08-10 | Progress claim | 9863.1 | 0 | 0 | 9863.1 | 986.31 | 10849.41 | Approved - sent to Xero | 2026-08-01
INV-30879 | P2553 | School science block, Bayswater | 2026-08-10 | Progress claim | 70320.05 | 3516 | 0 | 66804.05 | 6680.41 | 73484.46 | Approved - sent to Xero | 2026-08-01
INV-30880 | P2555 | Gym fit-out, Camberwell | 2026-08-10 | Progress claim | 12285.9 | 0 | 0 | 12285.9 | 1228.59 | 13514.49 | Approved - sent to Xero | 2026-08-01
INV-30881 | P2556 | Office fit-out, Preston West | 2026-08-10 | Progress claim | 28553.1 | 1427.66 | 0 | 27125.44 | 2712.54 | 29837.98 | Approved - sent to Xero | 2026-08-01
INV-30882 | P2521 | Aged care wing, Coburg | 2026-08-25 | Final claim | 25040 | 0 | 0 | 25040 | 2504 | 27544 | Approved - sent to Xero | 2026-08-01
INV-30883 | P2523 | Aged care wing, Bayswater | 2026-08-25 | Final claim | 7365 | 0 | 0 | 7365 | 736.5 | 8101.5 | Approved - sent to Xero | 2026-08-01
INV-30884 | P2526 | School science block, Clayton | 2026-08-25 | Progress claim | 13919.7 | 695.99 | 0 | 13223.71 | 1322.37 | 14546.08 | Approved - sent to Xero | 2026-08-01
INV-30885 | P2534 | Retail tenancy fit-out, Bayswater | 2026-08-25 | Progress claim | 1501.2 | 75.06 | 0 | 1426.14 | 142.61 | 1568.75 | Approved - sent to Xero | 2026-08-01
INV-30886 | P2536 | Warehouse lighting upgrade, Preston | 2026-08-25 | Progress claim | 1950 | 0 | 0 | 1950 | 195 | 2145 | Approved - sent to Xero | 2026-08-01
INV-30887 | P2537 | Car park lighting and EV, Ascot Vale | 2026-08-25 | Final claim | 8830 | 0 | 0 | 8830 | 883 | 9713 | Approved - sent to Xero | 2026-08-01
INV-30888 | P2538 | Medical centre electrical, Kew | 2026-08-25 | Progress claim | 1078 | 0 | 0 | 1078 | 107.8 | 1185.8 | Approved - sent to Xero | 2026-08-01
INV-30889 | P2539 | Retail tenancy fit-out, Carlton | 2026-08-25 | Progress claim | 5992.3 | 0 | 0 | 5992.3 | 599.23 | 6591.53 | Approved - sent to Xero | 2026-08-01
INV-30890 | P2541 | Apartment common areas, Clayton | 2026-08-25 | Progress claim | 1322.55 | 66.13 | 0 | 1256.42 | 125.64 | 1382.06 | Approved - sent to Xero | 2026-08-01
INV-30891 | P2543 | Retail tenancy fit-out, Yarraville | 2026-08-25 | Final claim | 12685 | 0 | 0 | 12685 | 1268.5 | 13953.5 | Approved - sent to Xero | 2026-08-01
INV-30892 | P2545 | Showroom refurbishment, Hawthorn | 2026-08-25 | Progress claim | 25314.3 | 0 | 0 | 25314.3 | 2531.43 | 27845.73 | Approved - sent to Xero | 2026-08-01
INV-30893 | P2546 | Showroom refurbishment, Malvern | 2026-08-25 | Progress claim | 70884.05 | 0 | 0 | 70884.05 | 7088.41 | 77972.46 | Approved - sent to Xero | 2026-08-01
INV-30894 | P2547 | School science block, Dandenong | 2026-08-25 | Progress claim | 25700.85 | 0 | 0 | 25700.85 | 2570.09 | 28270.94 | Approved - sent to Xero | 2026-08-01
INV-30895 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-08-25 | Progress claim | 23369.9 | 0 | 0 | 23369.9 | 2336.99 | 25706.89 | Approved - sent to Xero | 2026-08-01
INV-30896 | P2550 | Warehouse lighting upgrade, Fitzroy | 2026-08-25 | Progress claim | 1734.3 | 0 | 0 | 1734.3 | 173.43 | 1907.73 | Approved - sent to Xero | 2026-08-01
INV-30897 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-08-25 | Progress claim | 3163.5 | 0 | 0 | 3163.5 | 316.35 | 3479.85 | Approved - sent to Xero | 2026-08-01
INV-30898 | P2553 | School science block, Bayswater | 2026-08-25 | Progress claim | 50848.95 | 2542.45 | 0 | 48306.5 | 4830.65 | 53137.15 | Approved - sent to Xero | 2026-08-01
INV-30899 | P2554 | Showroom refurbishment, Reservoir | 2026-08-25 | Progress claim | 7695.5 | 0 | 0 | 7695.5 | 769.55 | 8465.05 | Approved - sent to Xero | 2026-08-01
INV-30900 | P2555 | Gym fit-out, Camberwell | 2026-08-25 | Progress claim | 7844.7 | 0 | 0 | 7844.7 | 784.47 | 8629.17 | Approved - sent to Xero | 2026-08-01
INV-30901 | P2556 | Office fit-out, Preston West | 2026-08-25 | Progress claim | 17689.25 | 884.46 | 0 | 16804.79 | 1680.48 | 18485.27 | Approved - sent to Xero | 2026-08-01
INV-30902 | P2541 | Apartment common areas, Clayton | 2026-09-10 | Progress claim | 2645.1 | 132.26 | 0 | 2512.84 | 251.28 | 2764.12 | Approved - sent to Xero | 2026-09-01
INV-30903 | P2542 | Apartment common areas, Moonee Ponds | 2026-09-10 | Progress claim | 167.8 | 0 | 0 | 167.8 | 16.78 | 184.58 | Approved - sent to Xero | 2026-09-01
INV-30904 | P2545 | Showroom refurbishment, Hawthorn | 2026-09-10 | Progress claim | 9775.8 | 0 | 0 | 9775.8 | 977.58 | 10753.38 | Approved - sent to Xero | 2026-09-01
INV-30905 | P2546 | Showroom refurbishment, Malvern | 2026-09-10 | Progress claim | 33036.8 | 0 | 0 | 33036.8 | 3303.68 | 36340.48 | Approved - sent to Xero | 2026-09-01
INV-30906 | P2556 | Office fit-out, Preston West | 2026-09-10 | Progress claim | 9443.55 | 472.18 | 0 | 8971.37 | 897.14 | 9868.51 | Approved - sent to Xero | 2026-09-01
INV-30907 | P2526 | School science block, Clayton | 2026-09-25 | Progress claim | 11589.9 | 579.5 | 0 | 11010.4 | 1101.04 | 12111.44 | Approved - sent to Xero | 2026-09-01
INV-30908 | P2534 | Retail tenancy fit-out, Bayswater | 2026-09-25 | Final claim | 11120 | 556 | 5560 | 16124 | 1612.4 | 17736.4 | Approved - sent to Xero | 2026-09-01
INV-30909 | P2538 | Medical centre electrical, Kew | 2026-09-25 | Final claim | 8800 | 0 | 0 | 8800 | 880 | 9680 | Approved - sent to Xero | 2026-09-01
INV-30910 | P2541 | Apartment common areas, Clayton | 2026-09-25 | Progress claim | 2204.25 | 110.21 | 0 | 2094.04 | 209.4 | 2303.44 | Approved - sent to Xero | 2026-09-01
INV-30911 | P2542 | Apartment common areas, Moonee Ponds | 2026-09-25 | Progress claim | 671.2 | 0 | 0 | 671.2 | 67.12 | 738.32 | Approved - sent to Xero | 2026-09-01
INV-30912 | P2545 | Showroom refurbishment, Hawthorn | 2026-09-25 | Progress claim | 6517.2 | 0 | 0 | 6517.2 | 651.72 | 7168.92 | Approved - sent to Xero | 2026-09-01
INV-30913 | P2546 | Showroom refurbishment, Malvern | 2026-09-25 | Progress claim | 32117.7 | 0 | 0 | 32117.7 | 3211.77 | 35329.47 | Approved - sent to Xero | 2026-09-01
INV-30914 | P2547 | School science block, Dandenong | 2026-09-25 | Progress claim | 19321.4 | 0 | 0 | 19321.4 | 1932.14 | 21253.54 | Approved - sent to Xero | 2026-09-01
INV-30915 | P2548 | School science block, Essendon | 2026-09-25 | Progress claim | 1440.6 | 72.03 | 0 | 1368.57 | 136.86 | 1505.43 | Approved - sent to Xero | 2026-09-01
INV-30916 | P2549 | Warehouse lighting upgrade, Box Hill | 2026-09-25 | Progress claim | 58424.75 | 0 | 0 | 58424.75 | 5842.48 | 64267.23 | Approved - sent to Xero | 2026-09-01
INV-30917 | P2551 | Warehouse lighting upgrade, Reservoir | 2026-09-25 | Progress claim | 5272.5 | 0 | 0 | 5272.5 | 527.25 | 5799.75 | Approved - sent to Xero | 2026-09-01
INV-30918 | P2553 | School science block, Bayswater | 2026-09-25 | Progress claim | 44194.05 | 2209.7 | 0 | 41984.35 | 4198.44 | 46182.79 | Approved - sent to Xero | 2026-09-01
INV-30919 | P2555 | Gym fit-out, Camberwell | 2026-09-25 | Progress claim | 13074.5 | 0 | 0 | 13074.5 | 1307.45 | 14381.95 | Approved - sent to Xero | 2026-09-01
INV-30920 | P2556 | Office fit-out, Preston West | 2026-09-25 | Progress claim | 3175 | 158.75 | 0 | 3016.25 | 301.63 | 3317.88 | Approved - sent to Xero | 2026-09-01
Total (follows filters) |  |  |  |  | 11588807.1 | 302435.88 | 180633.95 | 11467005.17 | 1146701.15 | 12613706.32
Formulas:
Month = DATE(YEAR([Claim date]),MONTH([Claim date]),1)

## Claim lines
Claim | Project | Cost centre | Claimed to date % | This claim (ex GST)
INV-30401 | P2511 | Fire detection interface | 85% | 34859.25
INV-30402 | P2512 | Lighting and emergency lighting | 95% | 4845
INV-30402 | P2512 | Power and data outlets | 95% | 14638.2
INV-30402 | P2512 | Fire detection interface | 70% | 19079.2
INV-30403 | P2513 | Mechanical services wiring | 95% | 7248.6
INV-30404 | P2514 | Switchboards and metering | 95% | 9644.85
INV-30404 | P2514 | Containment and cabling | 95% | 4292.1
INV-30404 | P2514 | Lighting and emergency lighting | 50% | 21333.3
INV-30404 | P2514 | Power and data outlets | 45% | 34426.8
INV-30404 | P2514 | Variation V009 | 50% | 10575
INV-30405 | P2515 | Mechanical services wiring | 95% | 3522.4
INV-30405 | P2515 | Testing and commissioning | 40% | 10852
INV-30406 | P2516 | Power and data outlets | 95% | 20977.4
INV-30406 | P2516 | Fire detection interface | 70% | 109876.8
INV-30406 | P2516 | Variation V003 | 50% | 22225
INV-30407 | P2517 | Variation V001 | 50% | 11325
INV-30407 | P2517 | Variation V006 | 50% | 14125
INV-30408 | P2518 | Testing and commissioning | 85% | 10115.2
INV-30408 | P2518 | Variation V011 | 50% | 7525
INV-30409 | P2519 | Switchboards and metering | 90% | 32528.75
INV-30409 | P2519 | Lighting and emergency lighting | 25% | 18301.25
INV-30409 | P2519 | Variation V012 | 50% | 4250
INV-30410 | P2520 | Switchboards and metering | 70% | 37356.25
INV-30410 | P2520 | Fire detection interface | 45% | 56196
INV-30411 | P2521 | Site establishment and temporary power | 60% | 10683.3
INV-30411 | P2521 | Switchboards and metering | 15% | 10307.7
INV-30411 | P2521 | Containment and cabling | 5% | 3291
INV-30412 | P2522 | Switchboards and metering | 95% | 13020.45
INV-30412 | P2522 | Containment and cabling | 95% | 12258.8
INV-30412 | P2522 | Mechanical services wiring | 70% | 23272
INV-30412 | P2522 | Variation V013 | 50% | 4800
INV-30413 | P2523 | Switchboards and metering | 30% | 10693.5
INV-30413 | P2523 | Variation V002 | 50% | 4925
INV-30414 | P2524 | Switchboards and metering | 70% | 30586.4
INV-30414 | P2524 | Containment and cabling | 15% | 24256.95
INV-30414 | P2524 | Power and data outlets | 10% | 8258.8
INV-30415 | P2525 | Switchboards and metering | 95% | 2943.1
INV-30415 | P2525 | Containment and cabling | 95% | 14619.2
INV-30415 | P2525 | Lighting and emergency lighting | 95% | 22635.55
INV-30415 | P2525 | Mechanical services wiring | 90% | 23377.8
INV-30415 | P2525 | Fire detection interface | 90% | 41280
INV-30415 | P2525 | Variation V007 | 50% | 10175
INV-30415 | P2525 | Variation V014 | 50% | 8050
INV-30416 | P2526 | Site establishment and temporary power | 20% | 11318.9
INV-30416 | P2526 | Switchboards and metering | 10% | 11705.9
INV-30417 | P2527 | Switchboards and metering | 30% | 20443.4
INV-30418 | P2528 | Switchboards and metering | 90% | 96185.25
INV-30418 | P2528 | Mechanical services wiring | 10% | 6463.8
INV-30419 | P2529 | Switchboards and metering | 60% | 16792.6
INV-30420 | P2530 | Site establishment and temporary power | 15% | 14088
INV-30421 | P2531 | Site establishment and temporary power | 90% | 47058
INV-30421 | P2531 | Containment and cabling | 15% | 9133.35
INV-30421 | P2531 | Lighting and emergency lighting | 10% | 7589.1
INV-30422 | P2532 | Switchboards and metering | 25% | 25606.5
INV-30423 | P2533 | Switchboards and metering | 20% | 22409.8
INV-30423 | P2533 | Containment and cabling | 5% | 5872.05
INV-30424 | P2536 | Variation V015 | 50% | 6825
INV-30425 | P2512 | Fire detection interface | 85% | 8176.8
INV-30426 | P2514 | Lighting and emergency lighting | 65% | 10666.65
INV-30426 | P2514 | Power and data outlets | 65% | 17213.4
INV-30426 | P2514 | Variation V009 | 100% | 10575
INV-30427 | P2515 | Testing and commissioning | 75% | 9495.5
INV-30428 | P2516 | Fire detection interface | 85% | 41203.8
INV-30428 | P2516 | Variation V003 | 100% | 22225
INV-30428 | P2516 | Variation V021 | 50% | 8450
INV-30428 | P2516 | Variation V024 | 50% | 10400
INV-30429 | P2517 | Testing and commissioning | 10% | 1521.8
INV-30429 | P2517 | Variation V001 | 100% | 11325
INV-30429 | P2517 | Variation V006 | 100% | 14125
INV-30429 | P2517 | Variation V022 | 50% | 10325
INV-30430 | P2519 | Switchboards and metering | 95% | 6505.75
INV-30430 | P2519 | Lighting and emergency lighting | 45% | 14641
INV-30430 | P2519 | Variation V012 | 100% | 4250
INV-30431 | P2520 | Switchboards and metering | 85% | 22413.75
INV-30431 | P2520 | Fire detection interface | 70% | 40140
INV-30432 | P2521 | Site establishment and temporary power | 75% | 5341.65
INV-30432 | P2521 | Switchboards and metering | 30% | 10307.7
INV-30432 | P2521 | Containment and cabling | 10% | 3291
INV-30432 | P2521 | Lighting and emergency lighting | 10% | 5645.4
INV-30433 | P2522 | Mechanical services wiring | 90% | 9308.8
INV-30433 | P2522 | Variation V013 | 100% | 4800
INV-30434 | P2523 | Switchboards and metering | 45% | 10693.5
INV-30434 | P2523 | Power and data outlets | 5% | 3505.9
INV-30434 | P2523 | Variation V002 | 100% | 4925
INV-30435 | P2526 | Site establishment and temporary power | 30% | 11318.9
INV-30435 | P2526 | Switchboards and metering | 20% | 11705.9
INV-30436 | P2527 | Switchboards and metering | 45% | 15332.55
INV-30436 | P2527 | Containment and cabling | 10% | 7131.4
INV-30436 | P2527 | Lighting and emergency lighting | 5% | 6150.65
INV-30437 | P2528 | Switchboards and metering | 95% | 6412.35
INV-30437 | P2528 | Mechanical services wiring | 40% | 19391.4
INV-30437 | P2528 | Fire detection interface | 15% | 23512.05
INV-30438 | P2529 | Switchboards and metering | 90% | 9159.6
INV-30439 | P2530 | Site establishment and temporary power | 25% | 9392
INV-30440 | P2531 | Site establishment and temporary power | 95% | 3137.2
INV-30440 | P2531 | Containment and cabling | 60% | 27400.05
INV-30440 | P2531 | Lighting and emergency lighting | 45% | 26561.85
INV-30440 | P2531 | Power and data outlets | 5% | 1971.1
INV-30441 | P2532 | Switchboards and metering | 45% | 20485.2
INV-30441 | P2532 | Containment and cabling | 10% | 11433.8
INV-30442 | P2535 | Switchboards and metering | 5% | 1967.95
INV-30443 | P2511 | Fire detection interface | 95% | 7746.5
INV-30444 | P2512 | Fire detection interface | 95% | 5451.2
INV-30445 | P2513 | Variation V030 | 50% | 3700
INV-30446 | P2514 | Lighting and emergency lighting | 80% | 10666.65
INV-30446 | P2514 | Power and data outlets | 85% | 17213.4
INV-30447 | P2515 | Testing and commissioning | 95% | 5426
INV-30447 | P2515 | Variation V027 | 50% | 8550
INV-30448 | P2516 | Fire detection interface | 95% | 27469.2
INV-30448 | P2516 | Variation V021 | 100% | 8450
INV-30448 | P2516 | Variation V024 | 100% | 10400
INV-30448 | P2516 | Variation V032 | 50% | 32900
INV-30449 | P2517 | Testing and commissioning | 45% | 5326.3
INV-30449 | P2517 | Variation V022 | 100% | 10325
INV-30450 | P2518 | Switchboards and metering | 100% | 7361.8
INV-30450 | P2518 | Lighting and emergency lighting | 100% | 7811
INV-30450 | P2518 | Testing and commissioning | 100% | 1896.6
INV-30450 | P2518 | Variation V011 | 100% | 7525
INV-30450 | P2518 | Variation V019 | 100% | 15700
INV-30451 | P2519 | Lighting and emergency lighting | 65% | 14641
INV-30452 | P2520 | Switchboards and metering | 95% | 14942.5
INV-30452 | P2520 | Fire detection interface | 90% | 32112
INV-30453 | P2521 | Site establishment and temporary power | 90% | 5341.65
INV-30453 | P2521 | Switchboards and metering | 45% | 10307.7
INV-30453 | P2521 | Containment and cabling | 25% | 9873
INV-30453 | P2521 | Lighting and emergency lighting | 20% | 5645.4
INV-30453 | P2521 | Variation V031 | 50% | 10175
INV-30454 | P2522 | Mechanical services wiring | 95% | 2327.2
INV-30455 | P2523 | Switchboards and metering | 60% | 10693.5
INV-30455 | P2523 | Power and data outlets | 15% | 7011.8
INV-30456 | P2524 | Switchboards and metering | 95% | 19116.5
INV-30456 | P2524 | Containment and cabling | 45% | 48513.9
INV-30456 | P2524 | Power and data outlets | 35% | 20647
INV-30457 | P2525 | Mechanical services wiring | 95% | 1948.15
INV-30457 | P2525 | Fire detection interface | 95% | 2580
INV-30457 | P2525 | Testing and commissioning | 70% | 12267.5
INV-30457 | P2525 | Variation V007 | 100% | 10175
INV-30457 | P2525 | Variation V014 | 100% | 8050
INV-30457 | P2525 | Variation V020 | 50% | 10075
INV-30458 | P2526 | Site establishment and temporary power | 40% | 11318.9
INV-30458 | P2526 | Switchboards and metering | 30% | 11705.9
INV-30458 | P2526 | Lighting and emergency lighting | 5% | 4426.9
INV-30458 | P2526 | Variation V025 | 50% | 9425
INV-30459 | P2527 | Switchboards and metering | 60% | 15332.55
INV-30459 | P2527 | Containment and cabling | 20% | 7131.4
INV-30459 | P2527 | Lighting and emergency lighting | 20% | 18451.95
INV-30460 | P2528 | Mechanical services wiring | 80% | 25855.2
INV-30460 | P2528 | Fire detection interface | 45% | 47024.1
INV-30461 | P2529 | Switchboards and metering | 95% | 1526.6
INV-30461 | P2529 | Mechanical services wiring | 20% | 8218.6
INV-30462 | P2530 | Site establishment and temporary power | 45% | 18784
INV-30462 | P2530 | Switchboards and metering | 10% | 4923.3
INV-30463 | P2531 | Containment and cabling | 95% | 21311.15
INV-30463 | P2531 | Lighting and emergency lighting | 90% | 34150.95
INV-30463 | P2531 | Power and data outlets | 35% | 11826.6
INV-30463 | P2531 | Fire detection interface | 10% | 4342.1
INV-30464 | P2532 | Switchboards and metering | 75% | 30727.8
INV-30464 | P2532 | Containment and cabling | 25% | 17150.7
INV-30465 | P2533 | Switchboards and metering | 70% | 56024.5
INV-30465 | P2533 | Containment and cabling | 35% | 35232.3
INV-30465 | P2533 | Lighting and emergency lighting | 15% | 10476.15
INV-30465 | P2533 | Variation V023 | 50% | 12725
INV-30466 | P2534 | Switchboards and metering | 20% | 17458.6
INV-30467 | P2535 | Switchboards and metering | 10% | 1967.95
INV-30468 | P2536 | Variation V015 | 100% | 6825
INV-30469 | P2538 | Variation V026 | 50% | 1800
INV-30470 | P2511 | Variation V033 | 50% | 12125
INV-30471 | P2514 | Lighting and emergency lighting | 90% | 7111.1
INV-30471 | P2514 | Power and data outlets | 95% | 8606.7
INV-30472 | P2515 | Variation V027 | 100% | 8550
INV-30472 | P2515 | Variation V036 | 50% | 7725
INV-30473 | P2516 | Variation V032 | 100% | 32900
INV-30473 | P2516 | Variation V037 | 50% | 32725
INV-30474 | P2517 | Testing and commissioning | 75% | 4565.4
INV-30475 | P2519 | Lighting and emergency lighting | 85% | 14641
INV-30476 | P2521 | Site establishment and temporary power | 95% | 1780.55
INV-30476 | P2521 | Switchboards and metering | 65% | 13743.6
INV-30476 | P2521 | Containment and cabling | 40% | 9873
INV-30476 | P2521 | Lighting and emergency lighting | 30% | 5645.4
INV-30476 | P2521 | Power and data outlets | 10% | 7050.9
INV-30476 | P2521 | Variation V031 | 100% | 10175
INV-30477 | P2523 | Switchboards and metering | 70% | 7129
INV-30477 | P2523 | Power and data outlets | 30% | 10517.7
INV-30478 | P2525 | Testing and commissioning | 95% | 4381.25
INV-30478 | P2525 | Variation V020 | 100% | 10075
INV-30479 | P2526 | Site establishment and temporary power | 55% | 16978.35
INV-30479 | P2526 | Switchboards and metering | 45% | 17558.85
INV-30479 | P2526 | Lighting and emergency lighting | 15% | 8853.8
INV-30479 | P2526 | Variation V025 | 100% | 9425
INV-30480 | P2532 | Switchboards and metering | 95% | 20485.2
INV-30480 | P2532 | Containment and cabling | 50% | 28584.5
INV-30480 | P2532 | Variation V040 | 50% | 4050
INV-30481 | P2533 | Switchboards and metering | 90% | 22409.8
INV-30481 | P2533 | Containment and cabling | 60% | 29360.25
INV-30481 | P2533 | Lighting and emergency lighting | 40% | 17460.25
INV-30481 | P2533 | Variation V023 | 100% | 12725
INV-30482 | P2534 | Switchboards and metering | 40% | 17458.6
INV-30482 | P2534 | Lighting and emergency lighting | 5% | 3368.6
INV-30483 | P2535 | Switchboards and metering | 25% | 5903.85
INV-30484 | P2511 | Variation V033 | 100% | 12125
INV-30484 | P2511 | Variation V043 | 50% | 5825
INV-30484 | P2511 | Variation V047 | 50% | 3300
INV-30485 | P2512 | Variation V048 | 50% | 3125
INV-30486 | P2513 | Variation V030 | 100% | 3700
INV-30486 | P2513 | Variation V049 | 50% | 3175
INV-30487 | P2514 | Lighting and emergency lighting | 95% | 3555.55
INV-30488 | P2515 | Site establishment and temporary power | 100% | 6434.05
INV-30488 | P2515 | Switchboards and metering | 100% | 4102.05
INV-30488 | P2515 | Lighting and emergency lighting | 100% | 6500.05
INV-30488 | P2515 | Power and data outlets | 100% | 5214.95
INV-30488 | P2515 | Mechanical services wiring | 100% | 3522.4
INV-30488 | P2515 | Testing and commissioning | 100% | 1356.5
INV-30488 | P2515 | Variation V036 | 100% | 7725
INV-30489 | P2516 | Testing and commissioning | 5% | 1470
INV-30489 | P2516 | Variation V037 | 100% | 32725
INV-30489 | P2516 | Variation V041 | 50% | 27100
INV-30490 | P2517 | Testing and commissioning | 95% | 3043.6
INV-30491 | P2519 | Lighting and emergency lighting | 95% | 7320.5
INV-30492 | P2520 | Fire detection interface | 95% | 8028
INV-30492 | P2520 | Variation V052 | 50% | 11200
INV-30493 | P2521 | Switchboards and metering | 80% | 10307.7
INV-30493 | P2521 | Containment and cabling | 60% | 13164
INV-30493 | P2521 | Lighting and emergency lighting | 45% | 8468.1
INV-30493 | P2521 | Power and data outlets | 20% | 7050.9
INV-30493 | P2521 | Mechanical services wiring | 5% | 3540.45
INV-30494 | P2522 | Testing and commissioning | 10% | 705.9
INV-30495 | P2523 | Switchboards and metering | 85% | 10693.5
INV-30495 | P2523 | Power and data outlets | 45% | 10517.7
INV-30496 | P2524 | Containment and cabling | 80% | 56599.55
INV-30496 | P2524 | Power and data outlets | 70% | 28905.8
INV-30496 | P2524 | Mechanical services wiring | 25% | 31925.25
INV-30496 | P2524 | Variation V046 | 50% | 16225
INV-30497 | P2525 | Site establishment and temporary power | 100% | 4116.45
INV-30497 | P2525 | Switchboards and metering | 100% | 2943.1
INV-30497 | P2525 | Containment and cabling | 100% | 1827.4
INV-30497 | P2525 | Lighting and emergency lighting | 100% | 3233.65
INV-30497 | P2525 | Mechanical services wiring | 100% | 1948.15
INV-30497 | P2525 | Fire detection interface | 100% | 2580
INV-30497 | P2525 | Testing and commissioning | 100% | 876.25
INV-30497 | P2525 | Variation V050 | 100% | 14750
INV-30498 | P2526 | Site establishment and temporary power | 65% | 11318.9
INV-30498 | P2526 | Switchboards and metering | 65% | 23411.8
INV-30498 | P2526 | Lighting and emergency lighting | 30% | 13280.7
INV-30499 | P2527 | Switchboards and metering | 90% | 30665.1
INV-30499 | P2527 | Containment and cabling | 50% | 21394.2
INV-30499 | P2527 | Lighting and emergency lighting | 65% | 55355.85
INV-30499 | P2527 | Variation V038 | 50% | 2750
INV-30500 | P2528 | Mechanical services wiring | 95% | 9695.7
INV-30500 | P2528 | Fire detection interface | 95% | 78373.5
INV-30501 | P2529 | Mechanical services wiring | 75% | 22601.15
INV-30502 | P2530 | Site establishment and temporary power | 85% | 37568
INV-30502 | P2530 | Switchboards and metering | 50% | 19693.2
INV-30502 | P2530 | Containment and cabling | 30% | 16553.1
INV-30503 | P2531 | Lighting and emergency lighting | 95% | 3794.55
INV-30503 | P2531 | Power and data outlets | 95% | 23653.2
INV-30503 | P2531 | Fire detection interface | 80% | 30394.7
INV-30503 | P2531 | Variation V035 | 50% | 2950
INV-30504 | P2532 | Containment and cabling | 80% | 34301.4
INV-30504 | P2532 | Lighting and emergency lighting | 5% | 2824.9
INV-30504 | P2532 | Power and data outlets | 10% | 6188.3
INV-30504 | P2532 | Variation V040 | 100% | 4050
INV-30505 | P2533 | Switchboards and metering | 95% | 5602.45
INV-30505 | P2533 | Containment and cabling | 85% | 29360.25
INV-30505 | P2533 | Lighting and emergency lighting | 75% | 24444.35
INV-30506 | P2534 | Switchboards and metering | 60% | 17458.6
INV-30506 | P2534 | Lighting and emergency lighting | 15% | 6737.2
INV-30507 | P2535 | Switchboards and metering | 40% | 5903.85
INV-30507 | P2535 | Lighting and emergency lighting | 10% | 3977.6
INV-30508 | P2536 | Site establishment and temporary power | 5% | 2753.25
INV-30509 | P2537 | Switchboards and metering | 5% | 2592.9
INV-30510 | P2538 | Switchboards and metering | 5% | 681.05
INV-30510 | P2538 | Variation V026 | 100% | 1800
INV-30511 | P2541 | Variation V042 | 50% | 7500
INV-30511 | P2541 | Variation V044 | 50% | 5400
INV-30512 | P2544 | Switchboards and metering | 5% | 3515.1
INV-30513 | P2511 | Testing and commissioning | 5% | 527.25
INV-30513 | P2511 | Variation V043 | 100% | 5825
INV-30513 | P2511 | Variation V047 | 100% | 3300
INV-30514 | P2516 | Testing and commissioning | 30% | 7350
INV-30514 | P2516 | Variation V041 | 100% | 27100
INV-30515 | P2519 | Variation V060 | 50% | 6150
INV-30516 | P2520 | Variation V052 | 100% | 11200
INV-30517 | P2522 | Testing and commissioning | 55% | 3176.55
INV-30518 | P2526 | Site establishment and temporary power | 80% | 16978.35
INV-30518 | P2526 | Switchboards and metering | 80% | 17558.85
INV-30518 | P2526 | Lighting and emergency lighting | 50% | 17707.6
INV-30519 | P2530 | Site establishment and temporary power | 95% | 9392
INV-30519 | P2530 | Switchboards and metering | 75% | 12308.25
INV-30519 | P2530 | Containment and cabling | 60% | 16553.1
INV-30519 | P2530 | Lighting and emergency lighting | 10% | 8701.4
INV-30520 | P2531 | Fire detection interface | 95% | 6513.15
INV-30520 | P2531 | Variation V035 | 100% | 2950
INV-30521 | P2532 | Containment and cabling | 95% | 17150.7
INV-30521 | P2532 | Lighting and emergency lighting | 15% | 5649.8
INV-30521 | P2532 | Power and data outlets | 30% | 12376.6
INV-30522 | P2534 | Switchboards and metering | 80% | 17458.6
INV-30522 | P2534 | Lighting and emergency lighting | 30% | 10105.8
INV-30523 | P2535 | Switchboards and metering | 60% | 7871.8
INV-30523 | P2535 | Lighting and emergency lighting | 35% | 9944
INV-30524 | P2537 | Switchboards and metering | 15% | 5185.8
INV-30525 | P2540 | Switchboards and metering | 5% | 1844.55
INV-30526 | P2541 | Switchboards and metering | 5% | 3298
INV-30526 | P2541 | Variation V042 | 100% | 7500
INV-30526 | P2541 | Variation V044 | 100% | 5400
INV-30527 | P2542 | Switchboards and metering | 5% | 2335.55
INV-30528 | P2544 | Switchboards and metering | 25% | 14060.4
INV-30529 | P2511 | Testing and commissioning | 25% | 2109
INV-30530 | P2512 | Testing and commissioning | 20% | 1543.4
INV-30530 | P2512 | Variation V048 | 100% | 3125
INV-30531 | P2513 | Testing and commissioning | 55% | 3203.2
INV-30531 | P2513 | Variation V049 | 100% | 3175
INV-30532 | P2516 | Testing and commissioning | 65% | 10290
INV-30533 | P2517 | Site establishment and temporary power | 100% | 2649.4
INV-30533 | P2517 | Containment and cabling | 100% | 3018.2
INV-30533 | P2517 | Lighting and emergency lighting | 100% | 2856
INV-30533 | P2517 | Power and data outlets | 100% | 4686.25
INV-30533 | P2517 | Mechanical services wiring | 100% | 3368.25
INV-30533 | P2517 | Fire detection interface | 100% | 4401
INV-30533 | P2517 | Testing and commissioning | 100% | 760.9
INV-30533 | P2517 | Variation V055 | 100% | 11050
INV-30534 | P2519 | Variation V060 | 100% | 6150
INV-30535 | P2520 | Variation V061 | 50% | 5025
INV-30536 | P2521 | Switchboards and metering | 95% | 10307.7
INV-30536 | P2521 | Containment and cabling | 90% | 19746
INV-30536 | P2521 | Lighting and emergency lighting | 75% | 16936.2
INV-30536 | P2521 | Power and data outlets | 55% | 24678.15
INV-30536 | P2521 | Mechanical services wiring | 20% | 10621.35
INV-30536 | P2521 | Variation V058 | 50% | 8500
INV-30537 | P2522 | Testing and commissioning | 90% | 2470.65
INV-30538 | P2523 | Switchboards and metering | 95% | 7129
INV-30538 | P2523 | Power and data outlets | 80% | 24541.3
INV-30539 | P2524 | Containment and cabling | 95% | 24256.95
INV-30539 | P2524 | Power and data outlets | 95% | 20647
INV-30539 | P2524 | Mechanical services wiring | 70% | 57465.45
INV-30539 | P2524 | Variation V046 | 100% | 16225
INV-30540 | P2526 | Site establishment and temporary power | 90% | 11318.9
INV-30540 | P2526 | Switchboards and metering | 90% | 11705.9
INV-30540 | P2526 | Lighting and emergency lighting | 65% | 13280.7
INV-30541 | P2527 | Switchboards and metering | 95% | 5110.85
INV-30541 | P2527 | Containment and cabling | 80% | 21394.2
INV-30541 | P2527 | Lighting and emergency lighting | 95% | 36903.9
INV-30541 | P2527 | Variation V038 | 100% | 2750
INV-30542 | P2528 | Testing and commissioning | 70% | 10197.6
INV-30542 | P2528 | Variation V062 | 50% | 10050
INV-30543 | P2529 | Mechanical services wiring | 95% | 8218.6
INV-30544 | P2530 | Switchboards and metering | 90% | 7384.95
INV-30544 | P2530 | Containment and cabling | 85% | 13794.25
INV-30544 | P2530 | Lighting and emergency lighting | 25% | 13052.1
INV-30544 | P2530 | Mechanical services wiring | 5% | 3189.05
INV-30545 | P2531 | Testing and commissioning | 55% | 4803.15
INV-30546 | P2532 | Lighting and emergency lighting | 35% | 11299.6
INV-30546 | P2532 | Power and data outlets | 55% | 15470.75
INV-30547 | P2533 | Containment and cabling | 95% | 11744.1
INV-30547 | P2533 | Lighting and emergency lighting | 95% | 13968.2
INV-30547 | P2533 | Power and data outlets | 50% | 37006.5
INV-30547 | P2533 | Variation V054 | 50% | 13025
INV-30547 | P2533 | Variation V066 | 50% | 7650
INV-30548 | P2534 | Switchboards and metering | 95% | 13093.95
INV-30548 | P2534 | Lighting and emergency lighting | 50% | 13474.4
INV-30549 | P2535 | Switchboards and metering | 80% | 7871.8
INV-30549 | P2535 | Lighting and emergency lighting | 65% | 11932.8
INV-30550 | P2536 | Site establishment and temporary power | 25% | 11013
INV-30551 | P2537 | Switchboards and metering | 40% | 12964.5
INV-30551 | P2537 | Power and data outlets | 5% | 3183.45
INV-30552 | P2538 | Switchboards and metering | 30% | 3405.25
INV-30553 | P2539 | Switchboards and metering | 5% | 3909.95
INV-30554 | P2540 | Switchboards and metering | 20% | 5533.65
INV-30555 | P2541 | Switchboards and metering | 10% | 3298
INV-30556 | P2542 | Switchboards and metering | 10% | 2335.55
INV-30557 | P2543 | Switchboards and metering | 10% | 13116.3
INV-30557 | P2543 | Variation V064 | 50% | 2850
INV-30558 | P2544 | Switchboards and metering | 60% | 24605.7
INV-30559 | P2546 | Site establishment and temporary power | 5% | 5584.6
INV-30560 | P2548 | Variation V053 | 50% | 4975
INV-30561 | P2549 | Variation V059 | 50% | 9150
INV-30562 | P2551 | Variation V056 | 50% | 1675
INV-30563 | P2512 | Testing and commissioning | 40% | 1543.4
INV-30564 | P2514 | Variation V069 | 50% | 4225
INV-30564 | P2514 | Variation V073 | 50% | 3925
INV-30565 | P2516 | Testing and commissioning | 85% | 5880
INV-30566 | P2523 | Power and data outlets | 90% | 7011.8
INV-30567 | P2526 | Site establishment and temporary power | 95% | 5659.45
INV-30567 | P2526 | Switchboards and metering | 95% | 5852.95
INV-30567 | P2526 | Lighting and emergency lighting | 85% | 17707.6
INV-30567 | P2526 | Mechanical services wiring | 5% | 2893.25
INV-30568 | P2527 | Containment and cabling | 90% | 7131.4
INV-30569 | P2530 | Switchboards and metering | 95% | 2461.65
INV-30569 | P2530 | Containment and cabling | 95% | 5517.7
INV-30569 | P2530 | Lighting and emergency lighting | 45% | 17402.8
INV-30569 | P2530 | Mechanical services wiring | 15% | 6378.1
INV-30570 | P2531 | Testing and commissioning | 95% | 3493.2
INV-30571 | P2532 | Lighting and emergency lighting | 55% | 11299.6
INV-30571 | P2532 | Power and data outlets | 80% | 15470.75
INV-30572 | P2533 | Power and data outlets | 80% | 22203.9
INV-30572 | P2533 | Variation V054 | 100% | 13025
INV-30572 | P2533 | Variation V066 | 100% | 7650
INV-30573 | P2535 | Switchboards and metering | 95% | 5903.85
INV-30573 | P2535 | Lighting and emergency lighting | 90% | 9944
INV-30574 | P2536 | Site establishment and temporary power | 35% | 5506.5
INV-30575 | P2537 | Switchboards and metering | 65% | 12964.5
INV-30575 | P2537 | Power and data outlets | 25% | 12733.8
INV-30576 | P2538 | Switchboards and metering | 45% | 2043.15
INV-30576 | P2538 | Containment and cabling | 5% | 1392.85
INV-30577 | P2539 | Switchboards and metering | 15% | 7819.9
INV-30578 | P2541 | Switchboards and metering | 15% | 3298
INV-30579 | P2542 | Switchboards and metering | 20% | 4671.1
INV-30580 | P2543 | Switchboards and metering | 25% | 19674.45
INV-30580 | P2543 | Variation V064 | 100% | 2850
INV-30581 | P2544 | Switchboards and metering | 95% | 24605.7
INV-30582 | P2546 | Site establishment and temporary power | 10% | 5584.6
INV-30582 | P2546 | Switchboards and metering | 5% | 9957.15
INV-30582 | P2546 | Variation V071 | 50% | 31575
INV-30583 | P2547 | Site establishment and temporary power | 5% | 4397.25
INV-30584 | P2548 | Variation V053 | 100% | 4975
INV-30584 | P2548 | Variation V067 | 50% | 6750
INV-30584 | P2548 | Variation V074 | 50% | 3775
INV-30585 | P2549 | Variation V059 | 100% | 9150
INV-30586 | P2551 | Variation V056 | 100% | 1675
INV-30587 | P2511 | Testing and commissioning | 75% | 5272.5
INV-30588 | P2512 | Testing and commissioning | 60% | 1543.4
INV-30589 | P2513 | Testing and commissioning | 95% | 2329.6
INV-30590 | P2514 | Variation V069 | 100% | 4225
INV-30590 | P2514 | Variation V073 | 100% | 3925
INV-30591 | P2516 | Testing and commissioning | 95% | 2940
INV-30592 | P2519 | Variation V072 | 50% | 2675
INV-30593 | P2520 | Variation V061 | 100% | 5025
INV-30594 | P2521 | Containment and cabling | 95% | 3291
INV-30594 | P2521 | Lighting and emergency lighting | 95% | 11290.8
INV-30594 | P2521 | Power and data outlets | 85% | 21152.7
INV-30594 | P2521 | Mechanical services wiring | 50% | 21242.7
INV-30594 | P2521 | Variation V058 | 100% | 8500
INV-30595 | P2522 | Switchboards and metering | 100% | 4340.15
INV-30595 | P2522 | Containment and cabling | 100% | 3064.7
INV-30595 | P2522 | Mechanical services wiring | 100% | 2327.2
INV-30595 | P2522 | Testing and commissioning | 100% | 705.9
INV-30596 | P2523 | Power and data outlets | 95% | 3505.9
INV-30597 | P2524 | Mechanical services wiring | 95% | 31925.25
INV-30597 | P2524 | Variation V070 | 50% | 7650
INV-30598 | P2526 | Lighting and emergency lighting | 95% | 8853.8
INV-30598 | P2526 | Mechanical services wiring | 10% | 2893.25
INV-30599 | P2527 | Containment and cabling | 95% | 3565.7
INV-30600 | P2528 | Switchboards and metering | 100% | 6412.35
INV-30600 | P2528 | Mechanical services wiring | 100% | 3231.9
INV-30600 | P2528 | Fire detection interface | 100% | 7837.35
INV-30600 | P2528 | Testing and commissioning | 100% | 4370.4
INV-30600 | P2528 | Variation V062 | 100% | 10050
INV-30600 | P2528 | Variation V075 | 100% | 9300
INV-30600 | P2528 | Variation V079 | 100% | 16650
INV-30601 | P2529 | Testing and commissioning | 80% | 2700
INV-30602 | P2530 | Lighting and emergency lighting | 65% | 17402.8
INV-30602 | P2530 | Mechanical services wiring | 35% | 12756.2
INV-30603 | P2531 | Site establishment and temporary power | 100% | 3137.2
INV-30603 | P2531 | Containment and cabling | 100% | 3044.45
INV-30603 | P2531 | Lighting and emergency lighting | 100% | 3794.55
INV-30603 | P2531 | Power and data outlets | 100% | 1971.1
INV-30603 | P2531 | Fire detection interface | 100% | 2171.05
INV-30603 | P2531 | Testing and commissioning | 100% | 436.65
INV-30604 | P2532 | Lighting and emergency lighting | 75% | 11299.6
INV-30604 | P2532 | Power and data outlets | 95% | 9282.45
INV-30605 | P2533 | Power and data outlets | 95% | 11101.95
INV-30606 | P2534 | Lighting and emergency lighting | 85% | 23580.2
INV-30606 | P2534 | Mechanical services wiring | 15% | 8659.05
INV-30607 | P2535 | Lighting and emergency lighting | 95% | 1988.8
INV-30608 | P2536 | Site establishment and temporary power | 50% | 8259.75
INV-30608 | P2536 | Switchboards and metering | 5% | 3007.05
INV-30609 | P2537 | Switchboards and metering | 90% | 12964.5
INV-30609 | P2537 | Power and data outlets | 55% | 19100.7
INV-30609 | P2537 | Mechanical services wiring | 15% | 8233.8
INV-30609 | P2537 | Variation V076 | 50% | 5425
INV-30610 | P2538 | Switchboards and metering | 60% | 2043.15
INV-30610 | P2538 | Containment and cabling | 15% | 2785.7
INV-30611 | P2539 | Switchboards and metering | 25% | 7819.9
INV-30612 | P2540 | Switchboards and metering | 80% | 22134.6
INV-30612 | P2540 | Lighting and emergency lighting | 40% | 13667.2
INV-30612 | P2540 | Fire detection interface | 25% | 7481.5
INV-30613 | P2541 | Switchboards and metering | 30% | 9894
INV-30614 | P2542 | Switchboards and metering | 35% | 7006.65
INV-30615 | P2543 | Switchboards and metering | 45% | 26232.6
INV-30615 | P2543 | Containment and cabling | 10% | 11238.9
INV-30616 | P2544 | Mechanical services wiring | 20% | 9260.8
INV-30617 | P2545 | Containment and cabling | 5% | 3260.65
INV-30617 | P2545 | Variation V081 | 50% | 12600
INV-30618 | P2546 | Site establishment and temporary power | 20% | 11169.2
INV-30618 | P2546 | Switchboards and metering | 10% | 9957.15
INV-30618 | P2546 | Variation V071 | 100% | 31575
INV-30619 | P2547 | Site establishment and temporary power | 10% | 4397.25
INV-30620 | P2548 | Variation V067 | 100% | 6750
INV-30620 | P2548 | Variation V074 | 100% | 3775
INV-30621 | P2549 | Variation V078 | 50% | 8600
INV-30622 | P2551 | Site establishment and temporary power | 5% | 946.35
INV-30623 | P2511 | Testing and commissioning | 90% | 1581.75
INV-30624 | P2512 | Testing and commissioning | 80% | 1543.4
INV-30625 | P2513 | Variation V084 | 50% | 4100
INV-30626 | P2520 | Variation V088 | 50% | 7750
INV-30627 | P2521 | Power and data outlets | 95% | 7050.9
INV-30627 | P2521 | Mechanical services wiring | 65% | 10621.35
INV-30628 | P2526 | Mechanical services wiring | 20% | 5786.5
INV-30629 | P2529 | Testing and commissioning | 95% | 506.25
INV-30629 | P2529 | Variation V086 | 50% | 1600
INV-30630 | P2530 | Lighting and emergency lighting | 85% | 17402.8
INV-30630 | P2530 | Mechanical services wiring | 55% | 12756.2
INV-30631 | P2532 | Lighting and emergency lighting | 90% | 8474.7
INV-30632 | P2534 | Lighting and emergency lighting | 95% | 6737.2
INV-30632 | P2534 | Mechanical services wiring | 35% | 11545.4
INV-30633 | P2536 | Site establishment and temporary power | 65% | 8259.75
INV-30633 | P2536 | Switchboards and metering | 15% | 6014.1
INV-30634 | P2537 | Switchboards and metering | 95% | 2592.9
INV-30634 | P2537 | Power and data outlets | 85% | 19100.7
INV-30634 | P2537 | Mechanical services wiring | 35% | 10978.4
INV-30634 | P2537 | Variation V076 | 100% | 5425
INV-30635 | P2538 | Switchboards and metering | 80% | 2724.2
INV-30635 | P2538 | Containment and cabling | 35% | 5571.4
INV-30636 | P2540 | Switchboards and metering | 95% | 5533.65
INV-30636 | P2540 | Lighting and emergency lighting | 70% | 10250.4
INV-30636 | P2540 | Fire detection interface | 65% | 11970.4
INV-30637 | P2541 | Switchboards and metering | 45% | 9894
INV-30638 | P2542 | Switchboards and metering | 55% | 9342.2
INV-30638 | P2542 | Containment and cabling | 5% | 2291.65
INV-30638 | P2542 | Variation V082 | 50% | 2475
INV-30639 | P2543 | Switchboards and metering | 70% | 32790.75
INV-30639 | P2543 | Containment and cabling | 25% | 16858.35
INV-30640 | P2544 | Mechanical services wiring | 50% | 13891.2
INV-30641 | P2545 | Site establishment and temporary power | 10% | 6667.4
INV-30641 | P2545 | Containment and cabling | 15% | 6521.3
INV-30641 | P2545 | Variation V081 | 100% | 12600
INV-30642 | P2546 | Site establishment and temporary power | 30% | 11169.2
INV-30642 | P2546 | Switchboards and metering | 20% | 19914.3
INV-30643 | P2547 | Site establishment and temporary power | 15% | 4397.25
INV-30644 | P2548 | Switchboards and metering | 5% | 5596.6
INV-30645 | P2549 | Variation V078 | 100% | 8600
INV-30646 | P2550 | Switchboards and metering | 5% | 1376.95
INV-30647 | P2554 | Switchboards and metering | 5% | 3347.65
INV-30648 | P2511 | Testing and commissioning | 95% | 527.25
INV-30649 | P2512 | Testing and commissioning | 90% | 771.7
INV-30650 | P2513 | Switchboards and metering | 100% | 2082.5
INV-30650 | P2513 | Containment and cabling | 100% | 3094.15
INV-30650 | P2513 | Mechanical services wiring | 100% | 1812.15
INV-30650 | P2513 | Testing and commissioning | 100% | 291.2
INV-30650 | P2513 | Variation V084 | 100% | 4100
INV-30651 | P2514 | Testing and commissioning | 20% | 2896.2
INV-30651 | P2514 | Variation V083 | 50% | 5000
INV-30652 | P2516 | Switchboards and metering | 100% | 10763.9
INV-30652 | P2516 | Containment and cabling | 100% | 12542.8
INV-30652 | P2516 | Power and data outlets | 100% | 10488.7
INV-30652 | P2516 | Fire detection interface | 100% | 13734.6
INV-30652 | P2516 | Testing and commissioning | 100% | 1470
INV-30652 | P2516 | Variation V092 | 100% | 28450
INV-30653 | P2519 | Variation V072 | 100% | 2675
INV-30654 | P2520 | Testing and commissioning | 5% | 815.75
INV-30654 | P2520 | Variation V088 | 100% | 7750
INV-30655 | P2521 | Mechanical services wiring | 75% | 7080.9
INV-30656 | P2524 | Variation V070 | 100% | 7650
INV-30657 | P2526 | Mechanical services wiring | 30% | 5786.5
INV-30658 | P2529 | Switchboards and metering | 100% | 1526.6
INV-30658 | P2529 | Mechanical services wiring | 100% | 2054.65
INV-30658 | P2529 | Testing and commissioning | 100% | 168.75
INV-30658 | P2529 | Variation V086 | 100% | 1600
INV-30659 | P2530 | Lighting and emergency lighting | 95% | 8701.4
INV-30659 | P2530 | Mechanical services wiring | 70% | 9567.15
INV-30660 | P2532 | Lighting and emergency lighting | 95% | 2824.9
INV-30660 | P2532 | Variation V094 | 50% | 3025
INV-30661 | P2533 | Testing and commissioning | 20% | 3111.2
INV-30662 | P2534 | Mechanical services wiring | 60% | 14431.75
INV-30663 | P2536 | Site establishment and temporary power | 80% | 8259.75
INV-30663 | P2536 | Switchboards and metering | 25% | 6014.1
INV-30663 | P2536 | Power and data outlets | 5% | 2520.75
INV-30664 | P2537 | Power and data outlets | 95% | 6366.9
INV-30664 | P2537 | Mechanical services wiring | 65% | 16467.6
INV-30665 | P2538 | Switchboards and metering | 90% | 1362.1
INV-30665 | P2538 | Containment and cabling | 55% | 5571.4
INV-30665 | P2538 | Mechanical services wiring | 15% | 4866.3
INV-30666 | P2539 | Switchboards and metering | 55% | 23459.7
INV-30666 | P2539 | Containment and cabling | 5% | 2695.6
INV-30667 | P2540 | Lighting and emergency lighting | 95% | 8542
INV-30667 | P2540 | Fire detection interface | 95% | 8977.8
INV-30668 | P2541 | Switchboards and metering | 65% | 13192
INV-30668 | P2541 | Lighting and emergency lighting | 5% | 4889
INV-30669 | P2542 | Switchboards and metering | 75% | 9342.2
INV-30669 | P2542 | Containment and cabling | 20% | 6874.95
INV-30669 | P2542 | Variation V082 | 100% | 2475
INV-30670 | P2543 | Switchboards and metering | 90% | 26232.6
INV-30670 | P2543 | Containment and cabling | 50% | 28097.25
INV-30671 | P2544 | Mechanical services wiring | 80% | 13891.2
INV-30672 | P2545 | Site establishment and temporary power | 15% | 3333.7
INV-30672 | P2545 | Containment and cabling | 35% | 13042.6
INV-30672 | P2545 | Lighting and emergency lighting | 10% | 7477.2
INV-30673 | P2546 | Site establishment and temporary power | 45% | 16753.8
INV-30673 | P2546 | Switchboards and metering | 40% | 39828.6
INV-30674 | P2547 | Site establishment and temporary power | 30% | 13191.75
INV-30675 | P2548 | Switchboards and metering | 20% | 16789.8
INV-30676 | P2549 | Switchboards and metering | 5% | 5514.6
INV-30677 | P2550 | Switchboards and metering | 10% | 1376.95
INV-30678 | P2551 | Site establishment and temporary power | 15% | 1892.7
INV-30679 | P2552 | Switchboards and metering | 5% | 2483.7
INV-30680 | P2553 | Variation V091 | 50% | 15075
INV-30681 | P2554 | Switchboards and metering | 20% | 10042.95
INV-30682 | P2521 | Mechanical services wiring | 85% | 7080.9
INV-30683 | P2524 | Testing and commissioning | 20% | 4226.4
INV-30684 | P2526 | Mechanical services wiring | 45% | 8679.75
INV-30685 | P2530 | Mechanical services wiring | 85% | 9567.15
INV-30686 | P2533 | Testing and commissioning | 60% | 6222.4
INV-30687 | P2536 | Site establishment and temporary power | 90% | 5506.5
INV-30687 | P2536 | Switchboards and metering | 40% | 9021.15
INV-30687 | P2536 | Power and data outlets | 10% | 2520.75
INV-30687 | P2536 | Variation V097 | 50% | 3550
INV-30688 | P2537 | Mechanical services wiring | 85% | 10978.4
INV-30689 | P2539 | Switchboards and metering | 75% | 15639.8
INV-30689 | P2539 | Containment and cabling | 10% | 2695.6
INV-30690 | P2542 | Switchboards and metering | 90% | 7006.65
INV-30690 | P2542 | Containment and cabling | 40% | 9166.6
INV-30691 | P2544 | Mechanical services wiring | 95% | 6945.6
INV-30692 | P2546 | Site establishment and temporary power | 60% | 16753.8
INV-30692 | P2546 | Switchboards and metering | 60% | 39828.6
INV-30693 | P2547 | Site establishment and temporary power | 50% | 17589
INV-30694 | P2548 | Switchboards and metering | 35% | 16789.8
INV-30695 | P2551 | Site establishment and temporary power | 30% | 2839.05
INV-30696 | P2553 | Variation V091 | 100% | 15075
INV-30697 | P2511 | Site establishment and temporary power | 100% | 2615.95
INV-30697 | P2511 | Switchboards and metering | 100% | 2298.85
INV-30697 | P2511 | Containment and cabling | 100% | 3419.15
INV-30697 | P2511 | Mechanical services wiring | 100% | 4840.55
INV-30697 | P2511 | Fire detection interface | 100% | 3873.25
INV-30697 | P2511 | Testing and commissioning | 100% | 527.25
INV-30697 | P2511 | Variation V102 | 100% | 7200
INV-30698 | P2512 | Testing and commissioning | 95% | 385.85
INV-30699 | P2514 | Testing and commissioning | 75% | 7964.55
INV-30699 | P2514 | Variation V083 | 100% | 5000
INV-30700 | P2519 | Testing and commissioning | 15% | 1437
INV-30701 | P2520 | Testing and commissioning | 45% | 6526
INV-30702 | P2521 | Mechanical services wiring | 95% | 7080.9
INV-30703 | P2524 | Testing and commissioning | 55% | 7396.2
INV-30703 | P2524 | Variation V101 | 50% | 15075
INV-30704 | P2526 | Mechanical services wiring | 55% | 5786.5
INV-30705 | P2527 | Testing and commissioning | 15% | 1613.4
INV-30706 | P2530 | Mechanical services wiring | 95% | 6378.1
INV-30706 | P2530 | Testing and commissioning | 25% | 4593.75
INV-30707 | P2532 | Testing and commissioning | 40% | 4862
INV-30707 | P2532 | Variation V094 | 100% | 3025
INV-30707 | P2532 | Variation V098 | 50% | 2700
INV-30708 | P2533 | Testing and commissioning | 90% | 4666.8
INV-30708 | P2533 | Variation V103 | 50% | 4750
INV-30709 | P2534 | Mechanical services wiring | 95% | 20204.45
INV-30710 | P2536 | Site establishment and temporary power | 95% | 2753.25
INV-30710 | P2536 | Switchboards and metering | 60% | 12028.2
INV-30710 | P2536 | Power and data outlets | 20% | 5041.5
INV-30710 | P2536 | Variation V097 | 100% | 3550
INV-30711 | P2537 | Mechanical services wiring | 95% | 5489.2
INV-30712 | P2538 | Switchboards and metering | 95% | 681.05
INV-30712 | P2538 | Containment and cabling | 90% | 9749.95
INV-30712 | P2538 | Mechanical services wiring | 55% | 12976.8
INV-30713 | P2539 | Switchboards and metering | 85% | 7819.9
INV-30713 | P2539 | Containment and cabling | 20% | 5391.2
INV-30713 | P2539 | Lighting and emergency lighting | 5% | 2622.3
INV-30714 | P2541 | Switchboards and metering | 95% | 19788
INV-30714 | P2541 | Lighting and emergency lighting | 30% | 24445
INV-30715 | P2542 | Switchboards and metering | 95% | 2335.55
INV-30715 | P2542 | Containment and cabling | 65% | 11458.25
INV-30716 | P2543 | Switchboards and metering | 95% | 6558.15
INV-30716 | P2543 | Containment and cabling | 90% | 44955.6
INV-30716 | P2543 | Variation V100 | 50% | 3300
INV-30717 | P2544 | Variation V099 | 50% | 4125
INV-30718 | P2545 | Site establishment and temporary power | 45% | 20002.2
INV-30718 | P2545 | Containment and cabling | 75% | 26085.2
INV-30718 | P2545 | Lighting and emergency lighting | 45% | 26170.2
INV-30719 | P2546 | Site establishment and temporary power | 80% | 22338.4
INV-30719 | P2546 | Switchboards and metering | 80% | 39828.6
INV-30719 | P2546 | Lighting and emergency lighting | 5% | 7462.7
INV-30720 | P2547 | Site establishment and temporary power | 65% | 13191.75
INV-30720 | P2547 | Switchboards and metering | 15% | 11429.85
INV-30720 | P2547 | Containment and cabling | 10% | 8575.3
INV-30721 | P2548 | Switchboards and metering | 55% | 22386.4
INV-30722 | P2549 | Switchboards and metering | 15% | 11029.2
INV-30723 | P2550 | Switchboards and metering | 45% | 9638.65
INV-30724 | P2551 | Site establishment and temporary power | 40% | 1892.7
INV-30725 | P2552 | Switchboards and metering | 20% | 7451.1
INV-30726 | P2553 | Switchboards and metering | 10% | 11492.2
INV-30727 | P2554 | Switchboards and metering | 60% | 26781.2
INV-30728 | P2514 | Testing and commissioning | 90% | 2172.15
INV-30728 | P2514 | Variation V107 | 50% | 3425
INV-30729 | P2519 | Testing and commissioning | 45% | 2874
INV-30730 | P2521 | Testing and commissioning | 20% | 2275.8
INV-30731 | P2523 | Testing and commissioning | 10% | 589.2
INV-30732 | P2526 | Mechanical services wiring | 70% | 8679.75
INV-30733 | P2527 | Testing and commissioning | 45% | 3226.8
INV-30734 | P2530 | Testing and commissioning | 65% | 7350
INV-30735 | P2533 | Testing and commissioning | 95% | 777.8
INV-30735 | P2533 | Variation V103 | 100% | 4750
INV-30736 | P2536 | Switchboards and metering | 75% | 9021.15
INV-30736 | P2536 | Power and data outlets | 35% | 7562.25
INV-30736 | P2536 | Mechanical services wiring | 10% | 7814
INV-30737 | P2538 | Containment and cabling | 95% | 1392.85
INV-30737 | P2538 | Mechanical services wiring | 75% | 6488.4
INV-30738 | P2539 | Switchboards and metering | 95% | 7819.9
INV-30738 | P2539 | Containment and cabling | 30% | 5391.2
INV-30738 | P2539 | Lighting and emergency lighting | 15% | 5244.6
INV-30739 | P2544 | Testing and commissioning | 35% | 1922.9
INV-30739 | P2544 | Variation V099 | 100% | 4125
INV-30740 | P2545 | Site establishment and temporary power | 60% | 10001.1
INV-30740 | P2545 | Containment and cabling | 90% | 9781.95
INV-30740 | P2545 | Lighting and emergency lighting | 70% | 18693
INV-30740 | P2545 | Power and data outlets | 10% | 7525
INV-30741 | P2546 | Site establishment and temporary power | 90% | 11169.2
INV-30741 | P2546 | Switchboards and metering | 95% | 29871.45
INV-30741 | P2546 | Lighting and emergency lighting | 10% | 7462.7
INV-30741 | P2546 | Power and data outlets | 10% | 14520.2
INV-30742 | P2547 | Site establishment and temporary power | 85% | 17589
INV-30742 | P2547 | Switchboards and metering | 35% | 15239.8
INV-30742 | P2547 | Containment and cabling | 30% | 17150.6
INV-30742 | P2547 | Lighting and emergency lighting | 10% | 3835.7
INV-30743 | P2549 | Switchboards and metering | 25% | 11029.2
INV-30744 | P2550 | Switchboards and metering | 65% | 5507.8
INV-30745 | P2551 | Site establishment and temporary power | 60% | 3785.4
INV-30746 | P2552 | Switchboards and metering | 35% | 7451.1
INV-30747 | P2553 | Switchboards and metering | 15% | 5746.1
INV-30747 | P2553 | Containment and cabling | 5% | 6062.45
INV-30747 | P2553 | Variation V108 | 50% | 16650
INV-30748 | P2554 | Switchboards and metering | 85% | 16738.25
INV-30748 | P2554 | Mechanical services wiring | 5% | 3222.75
INV-30749 | P2512 | Switchboards and metering | 100% | 1831.5
INV-30749 | P2512 | Lighting and emergency lighting | 100% | 2422.5
INV-30749 | P2512 | Power and data outlets | 100% | 3659.55
INV-30749 | P2512 | Fire detection interface | 100% | 2725.6
INV-30749 | P2512 | Testing and commissioning | 100% | 385.85
INV-30750 | P2514 | Testing and commissioning | 95% | 724.05
INV-30750 | P2514 | Variation V107 | 100% | 3425
INV-30750 | P2514 | Variation V115 | 50% | 6800
INV-30751 | P2519 | Testing and commissioning | 75% | 2874
INV-30752 | P2520 | Testing and commissioning | 85% | 6526
INV-30753 | P2521 | Testing and commissioning | 45% | 2844.75
INV-30754 | P2523 | Testing and commissioning | 30% | 1178.4
INV-30754 | P2523 | Variation V111 | 50% | 3850
INV-30755 | P2524 | Testing and commissioning | 95% | 8452.8
INV-30755 | P2524 | Variation V101 | 100% | 15075
INV-30755 | P2524 | Variation V105 | 50% | 10075
INV-30756 | P2526 | Mechanical services wiring | 80% | 5786.5
INV-30757 | P2527 | Testing and commissioning | 70% | 2689
INV-30758 | P2530 | Testing and commissioning | 90% | 4593.75
INV-30759 | P2532 | Testing and commissioning | 95% | 6685.25
INV-30759 | P2532 | Variation V098 | 100% | 2700
INV-30760 | P2533 | Switchboards and metering | 100% | 5602.45
INV-30760 | P2533 | Containment and cabling | 100% | 5872.05
INV-30760 | P2533 | Lighting and emergency lighting | 100% | 3492.05
INV-30760 | P2533 | Power and data outlets | 100% | 3700.65
INV-30760 | P2533 | Testing and commissioning | 100% | 777.8
INV-30760 | P2533 | Variation V114 | 100% | 13050
INV-30761 | P2535 | Testing and commissioning | 15% | 624.75
INV-30762 | P2536 | Switchboards and metering | 90% | 9021.15
INV-30762 | P2536 | Power and data outlets | 55% | 10083
INV-30762 | P2536 | Mechanical services wiring | 30% | 15628
INV-30763 | P2538 | Mechanical services wiring | 90% | 4866.3
INV-30764 | P2539 | Containment and cabling | 40% | 5391.2
INV-30764 | P2539 | Lighting and emergency lighting | 30% | 7866.9
INV-30764 | P2539 | Mechanical services wiring | 5% | 2996.15
INV-30765 | P2540 | Testing and commissioning | 60% | 3189
INV-30766 | P2541 | Lighting and emergency lighting | 65% | 34223
INV-30766 | P2541 | Power and data outlets | 25% | 30335.75
INV-30766 | P2541 | Variation V109 | 50% | 4100
INV-30767 | P2542 | Containment and cabling | 95% | 13749.9
INV-30768 | P2543 | Containment and cabling | 95% | 5619.45
INV-30768 | P2543 | Variation V100 | 100% | 3300
INV-30769 | P2544 | Testing and commissioning | 80% | 2472.3
INV-30770 | P2545 | Site establishment and temporary power | 75% | 10001.1
INV-30770 | P2545 | Containment and cabling | 95% | 3260.65
INV-30770 | P2545 | Lighting and emergency lighting | 90% | 14954.4
INV-30770 | P2545 | Power and data outlets | 20% | 7525
INV-30771 | P2546 | Site establishment and temporary power | 95% | 5584.6
INV-30771 | P2546 | Lighting and emergency lighting | 25% | 22388.1
INV-30771 | P2546 | Power and data outlets | 20% | 14520.2
INV-30771 | P2546 | Variation V110 | 50% | 29125
INV-30771 | P2546 | Variation V112 | 50% | 31425
INV-30772 | P2547 | Site establishment and temporary power | 95% | 8794.5
INV-30772 | P2547 | Switchboards and metering | 55% | 15239.8
INV-30772 | P2547 | Containment and cabling | 55% | 21438.25
INV-30772 | P2547 | Lighting and emergency lighting | 30% | 7671.4
INV-30773 | P2548 | Switchboards and metering | 95% | 44772.8
INV-30773 | P2548 | Lighting and emergency lighting | 40% | 47425.6
INV-30774 | P2549 | Switchboards and metering | 35% | 11029.2
INV-30775 | P2550 | Switchboards and metering | 85% | 5507.8
INV-30775 | P2550 | Mechanical services wiring | 5% | 1734.3
INV-30776 | P2551 | Site establishment and temporary power | 75% | 2839.05
INV-30776 | P2551 | Switchboards and metering | 10% | 4466.4
INV-30777 | P2552 | Switchboards and metering | 50% | 7451.1
INV-30777 | P2552 | Mechanical services wiring | 5% | 3007.15
INV-30778 | P2553 | Switchboards and metering | 30% | 17238.3
INV-30778 | P2553 | Containment and cabling | 15% | 12124.9
INV-30778 | P2553 | Variation V108 | 100% | 16650
INV-30779 | P2554 | Switchboards and metering | 95% | 6695.3
INV-30779 | P2554 | Mechanical services wiring | 15% | 6445.5
INV-30780 | P2555 | Switchboards and metering | 10% | 4441.2
INV-30781 | P2556 | Switchboards and metering | 5% | 3698.1
INV-30781 | P2556 | Variation V113 | 50% | 7375
INV-30782 | P2514 | Variation V115 | 100% | 6800
INV-30783 | P2521 | Testing and commissioning | 65% | 2275.8
INV-30784 | P2523 | Testing and commissioning | 60% | 1767.6
INV-30784 | P2523 | Variation V111 | 100% | 3850
INV-30785 | P2524 | Variation V105 | 100% | 10075
INV-30786 | P2526 | Mechanical services wiring | 90% | 5786.5
INV-30787 | P2535 | Testing and commissioning | 60% | 1874.25
INV-30788 | P2539 | Containment and cabling | 55% | 8086.8
INV-30788 | P2539 | Lighting and emergency lighting | 45% | 7866.9
INV-30788 | P2539 | Mechanical services wiring | 15% | 5992.3
INV-30789 | P2543 | Testing and commissioning | 5% | 507.4
INV-30790 | P2545 | Site establishment and temporary power | 90% | 10001.1
INV-30790 | P2545 | Lighting and emergency lighting | 95% | 3738.6
INV-30790 | P2545 | Power and data outlets | 35% | 11287.5
INV-30790 | P2545 | Mechanical services wiring | 15% | 9982.35
INV-30791 | P2546 | Lighting and emergency lighting | 35% | 14925.4
INV-30791 | P2546 | Power and data outlets | 40% | 29040.4
INV-30791 | P2546 | Mechanical services wiring | 5% | 6559.55
INV-30791 | P2546 | Variation V110 | 100% | 29125
INV-30791 | P2546 | Variation V112 | 100% | 31425
INV-30792 | P2547 | Switchboards and metering | 80% | 19049.75
INV-30792 | P2547 | Containment and cabling | 85% | 25725.9
INV-30792 | P2547 | Lighting and emergency lighting | 60% | 11507.1
INV-30793 | P2548 | Lighting and emergency lighting | 65% | 29641
INV-30794 | P2549 | Switchboards and metering | 50% | 16543.8
INV-30794 | P2549 | Containment and cabling | 5% | 6000.85
INV-30795 | P2550 | Switchboards and metering | 95% | 2753.9
INV-30795 | P2550 | Mechanical services wiring | 20% | 5202.9
INV-30796 | P2551 | Site establishment and temporary power | 90% | 2839.05
INV-30796 | P2551 | Switchboards and metering | 25% | 6699.6
INV-30797 | P2552 | Switchboards and metering | 65% | 7451.1
INV-30797 | P2552 | Mechanical services wiring | 25% | 12028.6
INV-30798 | P2556 | Switchboards and metering | 25% | 14792.4
INV-30798 | P2556 | Lighting and emergency lighting | 10% | 7716
INV-30798 | P2556 | Variation V113 | 100% | 7375
INV-30799 | P2514 | Switchboards and metering | 100% | 3214.95
INV-30799 | P2514 | Containment and cabling | 100% | 4292.1
INV-30799 | P2514 | Lighting and emergency lighting | 100% | 3555.55
INV-30799 | P2514 | Power and data outlets | 100% | 4303.35
INV-30799 | P2514 | Testing and commissioning | 100% | 724.05
INV-30800 | P2519 | Testing and commissioning | 95% | 1916
INV-30801 | P2520 | Testing and commissioning | 95% | 1631.5
INV-30802 | P2521 | Testing and commissioning | 85% | 2275.8
INV-30803 | P2523 | Testing and commissioning | 80% | 1178.4
INV-30804 | P2524 | Switchboards and metering | 100% | 3823.3
INV-30804 | P2524 | Containment and cabling | 100% | 8085.65
INV-30804 | P2524 | Power and data outlets | 100% | 4129.4
INV-30804 | P2524 | Mechanical services wiring | 100% | 6385.05
INV-30804 | P2524 | Testing and commissioning | 100% | 1056.6
INV-30805 | P2526 | Mechanical services wiring | 95% | 2893.25
INV-30805 | P2526 | Testing and commissioning | 10% | 1164.9
INV-30806 | P2527 | Testing and commissioning | 95% | 2689
INV-30807 | P2530 | Site establishment and temporary power | 100% | 4696
INV-30807 | P2530 | Switchboards and metering | 100% | 2461.65
INV-30807 | P2530 | Containment and cabling | 100% | 2758.85
INV-30807 | P2530 | Lighting and emergency lighting | 100% | 4350.7
INV-30807 | P2530 | Mechanical services wiring | 100% | 3189.05
INV-30807 | P2530 | Testing and commissioning | 100% | 1837.5
INV-30807 | P2530 | Variation V117 | 100% | 7600
INV-30808 | P2532 | Switchboards and metering | 100% | 5121.3
INV-30808 | P2532 | Containment and cabling | 100% | 5716.9
INV-30808 | P2532 | Lighting and emergency lighting | 100% | 2824.9
INV-30808 | P2532 | Power and data outlets | 100% | 3094.15
INV-30808 | P2532 | Testing and commissioning | 100% | 607.75
INV-30809 | P2535 | Testing and commissioning | 90% | 1249.5
INV-30810 | P2536 | Switchboards and metering | 95% | 3007.05
INV-30810 | P2536 | Power and data outlets | 80% | 12603.75
INV-30810 | P2536 | Mechanical services wiring | 75% | 35163
INV-30811 | P2537 | Testing and commissioning | 5% | 309.05
INV-30812 | P2538 | Mechanical services wiring | 95% | 1622.1
INV-30813 | P2539 | Containment and cabling | 70% | 8086.8
INV-30813 | P2539 | Lighting and emergency lighting | 65% | 10489.2
INV-30813 | P2539 | Mechanical services wiring | 30% | 8988.45
INV-30814 | P2540 | Switchboards and metering | 100% | 1844.55
INV-30814 | P2540 | Lighting and emergency lighting | 100% | 1708.4
INV-30814 | P2540 | Fire detection interface | 100% | 1496.3
INV-30814 | P2540 | Testing and commissioning | 100% | 2126
INV-30815 | P2541 | Lighting and emergency lighting | 90% | 24445
INV-30815 | P2541 | Power and data outlets | 65% | 48537.2
INV-30815 | P2541 | Variation V109 | 100% | 4100
INV-30816 | P2543 | Testing and commissioning | 35% | 3044.4
INV-30817 | P2544 | Switchboards and metering | 100% | 3515.1
INV-30817 | P2544 | Mechanical services wiring | 100% | 2315.2
INV-30817 | P2544 | Testing and commissioning | 100% | 1098.8
INV-30817 | P2544 | Variation V119 | 100% | 5650
INV-30817 | P2544 | Variation V122 | 100% | 2550
INV-30818 | P2545 | Site establishment and temporary power | 95% | 3333.7
INV-30818 | P2545 | Power and data outlets | 55% | 15050
INV-30818 | P2545 | Mechanical services wiring | 30% | 9982.35
INV-30818 | P2545 | Fire detection interface | 5% | 3258.6
INV-30819 | P2546 | Lighting and emergency lighting | 50% | 22388.1
INV-30819 | P2546 | Power and data outlets | 55% | 21780.3
INV-30819 | P2546 | Mechanical services wiring | 15% | 13119.1
INV-30819 | P2546 | Fire detection interface | 5% | 10705.9
INV-30820 | P2547 | Switchboards and metering | 95% | 11429.85
INV-30820 | P2547 | Containment and cabling | 95% | 8575.3
INV-30820 | P2547 | Lighting and emergency lighting | 85% | 9589.25
INV-30820 | P2547 | Mechanical services wiring | 15% | 8900.85
INV-30820 | P2547 | Variation V124 | 50% | 3075
INV-30821 | P2548 | Lighting and emergency lighting | 90% | 29641
INV-30822 | P2549 | Switchboards and metering | 60% | 11029.2
INV-30822 | P2549 | Containment and cabling | 10% | 6000.85
INV-30823 | P2550 | Mechanical services wiring | 45% | 8671.5
INV-30824 | P2551 | Site establishment and temporary power | 95% | 946.35
INV-30824 | P2551 | Switchboards and metering | 45% | 8932.8
INV-30824 | P2551 | Containment and cabling | 5% | 1054.5
INV-30825 | P2552 | Switchboards and metering | 80% | 7451.1
INV-30825 | P2552 | Mechanical services wiring | 55% | 18042.9
INV-30826 | P2553 | Switchboards and metering | 65% | 40222.7
INV-30826 | P2553 | Containment and cabling | 65% | 60624.5
INV-30826 | P2553 | Mechanical services wiring | 15% | 17574.45
INV-30827 | P2554 | Mechanical services wiring | 50% | 22559.25
INV-30828 | P2555 | Switchboards and metering | 40% | 13323.6
INV-30828 | P2555 | Containment and cabling | 5% | 2614.9
INV-30829 | P2556 | Switchboards and metering | 50% | 18490.5
INV-30829 | P2556 | Lighting and emergency lighting | 30% | 15432
INV-30830 | P2523 | Testing and commissioning | 90% | 589.2
INV-30830 | P2523 | Variation V125 | 50% | 4925
INV-30831 | P2526 | Testing and commissioning | 30% | 2329.8
INV-30832 | P2534 | Testing and commissioning | 15% | 1501.2
INV-30833 | P2536 | Power and data outlets | 95% | 7562.25
INV-30833 | P2536 | Mechanical services wiring | 90% | 11721
INV-30834 | P2538 | Testing and commissioning | 25% | 770
INV-30835 | P2539 | Containment and cabling | 80% | 5391.2
INV-30835 | P2539 | Lighting and emergency lighting | 80% | 7866.9
INV-30835 | P2539 | Mechanical services wiring | 50% | 11984.6
INV-30836 | P2541 | Lighting and emergency lighting | 95% | 4889
INV-30836 | P2541 | Power and data outlets | 80% | 18201.45
INV-30837 | P2545 | Power and data outlets | 70% | 11287.5
INV-30837 | P2545 | Mechanical services wiring | 50% | 13309.8
INV-30837 | P2545 | Fire detection interface | 20% | 9775.8
INV-30838 | P2547 | Lighting and emergency lighting | 95% | 3835.7
INV-30838 | P2547 | Mechanical services wiring | 35% | 11867.8
INV-30838 | P2547 | Variation V124 | 100% | 3075
INV-30839 | P2550 | Mechanical services wiring | 70% | 8671.5
INV-30840 | P2551 | Switchboards and metering | 65% | 8932.8
INV-30840 | P2551 | Containment and cabling | 15% | 2109
INV-30841 | P2553 | Switchboards and metering | 80% | 17238.3
INV-30841 | P2553 | Containment and cabling | 85% | 24249.8
INV-30841 | P2553 | Mechanical services wiring | 30% | 17574.45
INV-30841 | P2553 | Fire detection interface | 5% | 6654.9
INV-30842 | P2554 | Mechanical services wiring | 70% | 12891
INV-30843 | P2556 | Switchboards and metering | 80% | 22188.6
INV-30843 | P2556 | Lighting and emergency lighting | 55% | 19290
INV-30843 | P2556 | Power and data outlets | 5% | 3147.85
INV-30844 | P2519 | Switchboards and metering | 100% | 6505.75
INV-30844 | P2519 | Lighting and emergency lighting | 100% | 3660.25
INV-30844 | P2519 | Testing and commissioning | 100% | 479
INV-30845 | P2520 | Switchboards and metering | 100% | 7471.25
INV-30845 | P2520 | Fire detection interface | 100% | 8028
INV-30845 | P2520 | Testing and commissioning | 100% | 815.75
INV-30846 | P2521 | Testing and commissioning | 95% | 1137.9
INV-30847 | P2523 | Testing and commissioning | 95% | 294.6
INV-30847 | P2523 | Variation V125 | 100% | 4925
INV-30848 | P2526 | Testing and commissioning | 55% | 2912.25
INV-30849 | P2527 | Switchboards and metering | 100% | 5110.85
INV-30849 | P2527 | Containment and cabling | 100% | 3565.7
INV-30849 | P2527 | Lighting and emergency lighting | 100% | 6150.65
INV-30849 | P2527 | Testing and commissioning | 100% | 537.8
INV-30850 | P2534 | Testing and commissioning | 50% | 3502.8
INV-30851 | P2535 | Switchboards and metering | 100% | 1967.95
INV-30851 | P2535 | Lighting and emergency lighting | 100% | 1988.8
INV-30851 | P2535 | Testing and commissioning | 100% | 416.5
INV-30852 | P2536 | Mechanical services wiring | 95% | 3907
INV-30852 | P2536 | Variation V127 | 50% | 1950
INV-30853 | P2537 | Testing and commissioning | 85% | 4944.8
INV-30854 | P2538 | Testing and commissioning | 60% | 1078
INV-30855 | P2539 | Containment and cabling | 90% | 5391.2
INV-30855 | P2539 | Lighting and emergency lighting | 90% | 5244.6
INV-30855 | P2539 | Mechanical services wiring | 70% | 11984.6
INV-30856 | P2541 | Power and data outlets | 95% | 18201.45
INV-30857 | P2543 | Testing and commissioning | 95% | 6088.8
INV-30858 | P2545 | Power and data outlets | 85% | 11287.5
INV-30858 | P2545 | Mechanical services wiring | 70% | 13309.8
INV-30858 | P2545 | Fire detection interface | 35% | 9775.8
INV-30859 | P2546 | Lighting and emergency lighting | 80% | 44776.2
INV-30859 | P2546 | Power and data outlets | 90% | 50820.7
INV-30859 | P2546 | Mechanical services wiring | 60% | 59035.95
INV-30859 | P2546 | Fire detection interface | 30% | 53529.5
INV-30859 | P2546 | Variation V128 | 50% | 29650
INV-30860 | P2547 | Mechanical services wiring | 60% | 14834.75
INV-30861 | P2548 | Lighting and emergency lighting | 95% | 5928.2
INV-30862 | P2549 | Switchboards and metering | 85% | 27573
INV-30862 | P2549 | Containment and cabling | 35% | 30004.25
INV-30862 | P2549 | Lighting and emergency lighting | 10% | 11368.2
INV-30863 | P2550 | Mechanical services wiring | 90% | 6937.2
INV-30864 | P2551 | Switchboards and metering | 80% | 6699.6
INV-30864 | P2551 | Containment and cabling | 25% | 2109
INV-30865 | P2552 | Switchboards and metering | 95% | 7451.1
INV-30865 | P2552 | Mechanical services wiring | 95% | 24057.2
INV-30866 | P2553 | Switchboards and metering | 90% | 11492.2
INV-30866 | P2553 | Containment and cabling | 95% | 12124.9
INV-30866 | P2553 | Mechanical services wiring | 50% | 23432.6
INV-30866 | P2553 | Fire detection interface | 25% | 26619.6
INV-30866 | P2553 | Variation V129 | 50% | 13725
INV-30867 | P2554 | Mechanical services wiring | 85% | 9668.25
INV-30867 | P2554 | Variation V126 | 50% | 1250
INV-30868 | P2555 | Switchboards and metering | 85% | 19985.4
INV-30868 | P2555 | Containment and cabling | 20% | 7844.7
INV-30869 | P2556 | Switchboards and metering | 95% | 11094.3
INV-30869 | P2556 | Lighting and emergency lighting | 85% | 23148
INV-30869 | P2556 | Power and data outlets | 25% | 12591.4
INV-30870 | P2521 | Variation V133 | 50% | 6075
INV-30871 | P2534 | Testing and commissioning | 80% | 3002.4
INV-30872 | P2537 | Testing and commissioning | 95% | 618.1
INV-30873 | P2539 | Containment and cabling | 95% | 2695.6
INV-30873 | P2539 | Lighting and emergency lighting | 95% | 2622.3
INV-30873 | P2539 | Mechanical services wiring | 85% | 8988.45
INV-30874 | P2545 | Power and data outlets | 95% | 7525
INV-30874 | P2545 | Mechanical services wiring | 85% | 9982.35
INV-30874 | P2545 | Fire detection interface | 50% | 9775.8
INV-30874 | P2545 | Variation V130 | 50% | 5625
INV-30875 | P2546 | Lighting and emergency lighting | 90% | 14925.4
INV-30875 | P2546 | Power and data outlets | 95% | 7260.1
INV-30875 | P2546 | Mechanical services wiring | 80% | 26238.2
INV-30875 | P2546 | Fire detection interface | 45% | 32117.7
INV-30875 | P2546 | Variation V128 | 100% | 29650
INV-30876 | P2547 | Mechanical services wiring | 80% | 11867.8
INV-30877 | P2549 | Switchboards and metering | 95% | 11029.2
INV-30877 | P2549 | Containment and cabling | 50% | 18002.55
INV-30877 | P2549 | Lighting and emergency lighting | 20% | 11368.2
INV-30878 | P2551 | Switchboards and metering | 95% | 6699.6
INV-30878 | P2551 | Containment and cabling | 40% | 3163.5
INV-30879 | P2553 | Switchboards and metering | 95% | 5746.1
INV-30879 | P2553 | Mechanical services wiring | 65% | 17574.45
INV-30879 | P2553 | Fire detection interface | 50% | 33274.5
INV-30879 | P2553 | Variation V129 | 100% | 13725
INV-30880 | P2555 | Switchboards and metering | 95% | 4441.2
INV-30880 | P2555 | Containment and cabling | 35% | 7844.7
INV-30881 | P2556 | Lighting and emergency lighting | 95% | 7716
INV-30881 | P2556 | Power and data outlets | 55% | 18887.1
INV-30881 | P2556 | Variation V132 | 50% | 1950
INV-30882 | P2521 | Site establishment and temporary power | 100% | 1780.55
INV-30882 | P2521 | Switchboards and metering | 100% | 3435.9
INV-30882 | P2521 | Containment and cabling | 100% | 3291
INV-30882 | P2521 | Lighting and emergency lighting | 100% | 2822.7
INV-30882 | P2521 | Power and data outlets | 100% | 3525.45
INV-30882 | P2521 | Mechanical services wiring | 100% | 3540.45
INV-30882 | P2521 | Testing and commissioning | 100% | 568.95
INV-30882 | P2521 | Variation V133 | 100% | 6075
INV-30883 | P2523 | Switchboards and metering | 100% | 3564.5
INV-30883 | P2523 | Power and data outlets | 100% | 3505.9
INV-30883 | P2523 | Testing and commissioning | 100% | 294.6
INV-30884 | P2526 | Testing and commissioning | 85% | 3494.7
INV-30884 | P2526 | Variation V134 | 50% | 10425
INV-30885 | P2534 | Testing and commissioning | 95% | 1501.2
INV-30886 | P2536 | Variation V127 | 100% | 1950
INV-30887 | P2537 | Switchboards and metering | 100% | 2592.9
INV-30887 | P2537 | Power and data outlets | 100% | 3183.45
INV-30887 | P2537 | Mechanical services wiring | 100% | 2744.6
INV-30887 | P2537 | Testing and commissioning | 100% | 309.05
INV-30888 | P2538 | Testing and commissioning | 95% | 1078
INV-30889 | P2539 | Mechanical services wiring | 95% | 5992.3
INV-30890 | P2541 | Testing and commissioning | 15% | 1322.55
INV-30891 | P2543 | Switchboards and metering | 100% | 6558.15
INV-30891 | P2543 | Containment and cabling | 100% | 5619.45
INV-30891 | P2543 | Testing and commissioning | 100% | 507.4
INV-30892 | P2545 | Mechanical services wiring | 95% | 6654.9
INV-30892 | P2545 | Fire detection interface | 70% | 13034.4
INV-30892 | P2545 | Variation V130 | 100% | 5625
INV-30893 | P2546 | Lighting and emergency lighting | 95% | 7462.7
INV-30893 | P2546 | Mechanical services wiring | 95% | 19678.65
INV-30893 | P2546 | Fire detection interface | 60% | 32117.7
INV-30893 | P2546 | Variation V138 | 50% | 11625
INV-30894 | P2547 | Mechanical services wiring | 95% | 8900.85
INV-30894 | P2547 | Variation V135 | 50% | 10225
INV-30894 | P2547 | Variation V136 | 50% | 6575
INV-30895 | P2549 | Containment and cabling | 60% | 12001.7
INV-30895 | P2549 | Lighting and emergency lighting | 30% | 11368.2
INV-30896 | P2550 | Mechanical services wiring | 95% | 1734.3
INV-30897 | P2551 | Containment and cabling | 55% | 3163.5
INV-30898 | P2553 | Mechanical services wiring | 80% | 17574.45
INV-30898 | P2553 | Fire detection interface | 75% | 33274.5
INV-30899 | P2554 | Mechanical services wiring | 95% | 6445.5
INV-30899 | P2554 | Variation V126 | 100% | 1250
INV-30900 | P2555 | Containment and cabling | 50% | 7844.7
INV-30901 | P2556 | Power and data outlets | 80% | 15739.25
INV-30901 | P2556 | Variation V132 | 100% | 1950
INV-30902 | P2541 | Testing and commissioning | 45% | 2645.1
INV-30903 | P2542 | Testing and commissioning | 5% | 167.8
INV-30904 | P2545 | Fire detection interface | 85% | 9775.8
INV-30905 | P2546 | Fire detection interface | 70% | 21411.8
INV-30905 | P2546 | Variation V138 | 100% | 11625
INV-30906 | P2556 | Power and data outlets | 95% | 9443.55
INV-30907 | P2526 | Testing and commissioning | 95% | 1164.9
INV-30907 | P2526 | Variation V134 | 100% | 10425
INV-30908 | P2534 | Switchboards and metering | 100% | 4364.65
INV-30908 | P2534 | Lighting and emergency lighting | 100% | 3368.6
INV-30908 | P2534 | Mechanical services wiring | 100% | 2886.35
INV-30908 | P2534 | Testing and commissioning | 100% | 500.4
INV-30909 | P2538 | Switchboards and metering | 100% | 681.05
INV-30909 | P2538 | Containment and cabling | 100% | 1392.85
INV-30909 | P2538 | Mechanical services wiring | 100% | 1622.1
INV-30909 | P2538 | Testing and commissioning | 100% | 154
INV-30909 | P2538 | Variation V139 | 100% | 4950
INV-30910 | P2541 | Testing and commissioning | 70% | 2204.25
INV-30911 | P2542 | Testing and commissioning | 25% | 671.2
INV-30912 | P2545 | Fire detection interface | 95% | 6517.2
INV-30913 | P2546 | Fire detection interface | 85% | 32117.7
INV-30914 | P2547 | Testing and commissioning | 20% | 2521.4
INV-30914 | P2547 | Variation V135 | 100% | 10225
INV-30914 | P2547 | Variation V136 | 100% | 6575
INV-30915 | P2548 | Testing and commissioning | 15% | 1440.6
INV-30916 | P2549 | Containment and cabling | 85% | 30004.25
INV-30916 | P2549 | Lighting and emergency lighting | 55% | 28420.5
INV-30917 | P2551 | Containment and cabling | 80% | 5272.5
INV-30918 | P2553 | Mechanical services wiring | 95% | 17574.45
INV-30918 | P2553 | Fire detection interface | 95% | 26619.6
INV-30919 | P2555 | Containment and cabling | 75% | 13074.5
INV-30920 | P2556 | Variation V140 | 50% | 3175
Total (follows filters) |  |  |  | 11588807.1

## Variations
Variation | Project | Project name | Description | Date raised or approved | Value (ex GST) | Status | On old claim spreadsheet | simPRO cost centre created
V001 | P2517 | Aged care wing, Essendon | Additional circuits, level 2 fit-out | 2025-10-01 | 22650 | Approved | N | Y
V002 | P2523 | Aged care wing, Bayswater | Extra power to kitchenette | 2025-10-01 | 9850 | Approved | Y | Y
V003 | P2516 | Showroom refurbishment, Werribee | After-hours work to suit tenant | 2025-10-06 | 44450 | Approved | Y | Y
V004 | P2525 | Medical centre electrical, Mentone | Switchboard upgrade after load review | 2025-10-06 | 18500 | Rejected | n/a | n/a
V005 | P2517 | Aged care wing, Essendon | Relocate sub-board after plan change | 2025-10-08 | 23200 | Rejected | n/a | n/a
V006 | P2517 | Aged care wing, Essendon | Switchboard upgrade after load review | 2025-10-11 | 28250 | Approved | Y | Y
V007 | P2525 | Medical centre electrical, Mentone | Emergency lighting to revised egress | 2025-10-13 | 20350 | Approved | Y | Y
V008 | P2527 | Showroom refurbishment, Williamstown | Door access wiring to revised layout | 2025-10-13 | 8300 | Rejected | n/a | n/a
V009 | P2514 | School science block, Richmond | Emergency lighting to revised egress | 2025-10-15 | 21150 | Approved | Y | Y
V010 | P2516 | Showroom refurbishment, Werribee | Luminaire change to client-selected type | 2025-10-15 | 40800 | Awaiting approval | n/a | n/a
V011 | P2518 | Car park lighting and EV, Heidelberg | Additional circuits, level 2 fit-out | 2025-10-15 | 15050 | Approved | Y | Y
V012 | P2519 | Car park lighting and EV, Williamstown | Luminaire change to client-selected type | 2025-10-18 | 8500 | Approved | Y | Y
V013 | P2522 | Car park lighting and EV, Oakleigh | Additional circuits, level 2 fit-out | 2025-10-19 | 9600 | Approved | Y | Y
V014 | P2525 | Medical centre electrical, Mentone | Extra data points, tenancy 4 | 2025-10-20 | 16100 | Approved | Y | Y
V015 | P2536 | Warehouse lighting upgrade, Preston | After-hours work to suit tenant | 2025-10-23 | 13650 | Approved | Y | Y
V016 | P2516 | Showroom refurbishment, Werribee | Emergency lighting to revised egress | 2025-10-24 | 43250 | Awaiting approval | n/a | n/a
V017 | P2516 | Showroom refurbishment, Werribee | Door access wiring to revised layout | 2025-10-24 | 14900 | Rejected | n/a | n/a
V018 | P2515 | Showroom refurbishment, Preston West | Switchboard upgrade after load review | 2025-11-03 | 13100 | Rejected | n/a | n/a
V019 | P2518 | Car park lighting and EV, Heidelberg | Door access wiring to revised layout | 2025-11-04 | 15700 | Approved | Y | Y
V020 | P2525 | Medical centre electrical, Mentone | Additional EV charger bays | 2025-11-04 | 20150 | Approved | N | Y
V021 | P2516 | Showroom refurbishment, Werribee | Extra power to kitchenette | 2025-11-06 | 16900 | Approved | N | Y
V022 | P2517 | Aged care wing, Essendon | Additional EV charger bays | 2025-11-06 | 20650 | Approved | Y | Y
V023 | P2533 | Office fit-out, Oakleigh | Door access wiring to revised layout | 2025-11-08 | 25450 | Approved | Y | Y
V024 | P2516 | Showroom refurbishment, Werribee | Extra power for server room | 2025-11-10 | 20800 | Approved | Y | Y
V025 | P2526 | School science block, Clayton | Additional circuits, level 2 fit-out | 2025-11-11 | 18850 | Approved | Y | Y
V026 | P2538 | Medical centre electrical, Kew | Emergency lighting to revised egress | 2025-11-13 | 3600 | Approved | N | Y
V027 | P2515 | Showroom refurbishment, Preston West | After-hours work to suit tenant | 2025-11-15 | 17100 | Approved | Y | Y
V028 | P2522 | Car park lighting and EV, Oakleigh | Additional EV charger bays | 2025-11-15 | 5000 | Awaiting approval | n/a | n/a
V029 | P2534 | Retail tenancy fit-out, Bayswater | After-hours work to suit tenant | 2025-11-15 | 9250 | Awaiting approval | n/a | n/a
V030 | P2513 | Aged care wing, St Kilda | Additional EV charger bays | 2025-11-22 | 7400 | Approved | N | Y
V031 | P2521 | Aged care wing, Coburg | Additional circuits, level 2 fit-out | 2025-11-23 | 20350 | Approved | N | Y
V032 | P2516 | Showroom refurbishment, Werribee | Additional EV charger bays | 2025-11-24 | 65800 | Approved | Y | Y
V033 | P2511 | Office fit-out, Heidelberg | After-hours work to suit tenant | 2025-12-01 | 24250 | Approved | Y | Y
V034 | P2530 | Gym fit-out, Preston | Additional EV charger bays | 2025-12-02 | 9800 | Awaiting approval | n/a | n/a
V035 | P2531 | Industrial unit power upgrade, Abbotsford | Luminaire change to client-selected type | 2025-12-02 | 5900 | Approved | Y | Y
V036 | P2515 | Showroom refurbishment, Preston West | Luminaire change to client-selected type | 2025-12-05 | 15450 | Approved | Y | Y
V037 | P2516 | Showroom refurbishment, Werribee | Additional lighting to loading dock | 2025-12-05 | 65450 | Approved | Y | Y
V038 | P2527 | Showroom refurbishment, Williamstown | Extra data points, tenancy 4 | 2025-12-06 | 5500 | Approved | Y | Y
V039 | P2516 | Showroom refurbishment, Werribee | Additional circuits, level 2 fit-out | 2025-12-09 | 53500 | Awaiting approval | n/a | n/a
V040 | P2532 | Industrial unit power upgrade, Ascot Vale | Additional circuits, level 2 fit-out | 2025-12-10 | 8100 | Approved | Y | Y
V041 | P2516 | Showroom refurbishment, Werribee | Extra data points, tenancy 4 | 2025-12-11 | 54200 | Approved | Y | Y
V042 | P2541 | Apartment common areas, Clayton | Emergency lighting to revised egress | 2025-12-11 | 15000 | Approved | Y | Y
V043 | P2511 | Office fit-out, Heidelberg | Additional circuits, level 2 fit-out | 2025-12-12 | 11650 | Approved | Y | Y
V044 | P2541 | Apartment common areas, Clayton | Extra data points, tenancy 4 | 2025-12-13 | 10800 | Approved | Y | Y
V045 | P2528 | Apartment common areas, Bayswater | After-hours work to suit tenant | 2025-12-14 | 17150 | Awaiting approval | n/a | n/a
V046 | P2524 | Childcare centre, Preston | Extra power to kitchenette | 2025-12-16 | 32450 | Approved | Y | Y
V047 | P2511 | Office fit-out, Heidelberg | Relocate sub-board after plan change | 2025-12-18 | 6600 | Approved | Y | Y
V048 | P2512 | Warehouse lighting upgrade, Northcote | Switchboard upgrade after load review | 2025-12-22 | 6250 | Approved | Y | Y
V049 | P2513 | Aged care wing, St Kilda | Additional circuits, level 2 fit-out | 2025-12-22 | 6350 | Approved | Y | Y
V050 | P2525 | Medical centre electrical, Mentone | Relocate sub-board after plan change | 2025-12-22 | 14750 | Approved | N | Y
V051 | P2533 | Office fit-out, Oakleigh | After-hours work to suit tenant | 2025-12-23 | 12350 | Rejected | n/a | n/a
V052 | P2520 | Industrial unit power upgrade, Hawthorn | Extra power to kitchenette | 2025-12-24 | 22400 | Approved | Y | Y
V053 | P2548 | School science block, Essendon | Extra data points, tenancy 4 | 2026-01-01 | 9950 | Approved | N | Y
V054 | P2533 | Office fit-out, Oakleigh | Additional circuits, level 2 fit-out | 2026-01-02 | 26050 | Approved | Y | Y
V055 | P2517 | Aged care wing, Essendon | Door access wiring to revised layout | 2026-01-03 | 11050 | Approved | Y | Y
V056 | P2551 | Warehouse lighting upgrade, Reservoir | Additional EV charger bays | 2026-01-03 | 3350 | Approved | N | Y
V057 | P2530 | Gym fit-out, Preston | Extra data points, tenancy 4 | 2026-01-06 | 22550 | Awaiting approval | n/a | n/a
V058 | P2521 | Aged care wing, Coburg | Door access wiring to revised layout | 2026-01-08 | 17000 | Approved | Y | Y
V059 | P2549 | Warehouse lighting upgrade, Box Hill | Emergency lighting to revised egress | 2026-01-09 | 18300 | Approved | N | Y
V060 | P2519 | Car park lighting and EV, Williamstown | Additional circuits, level 2 fit-out | 2026-01-10 | 12300 | Approved | Y | Y
V061 | P2520 | Industrial unit power upgrade, Hawthorn | After-hours work to suit tenant | 2026-01-13 | 10050 | Approved | Y | Y
V062 | P2528 | Apartment common areas, Bayswater | Extra data points, tenancy 4 | 2026-01-14 | 20100 | Approved | Y | Y
V063 | P2527 | Showroom refurbishment, Williamstown | Additional circuits, level 2 fit-out | 2026-01-18 | 12000 | Rejected | n/a | n/a
V064 | P2543 | Retail tenancy fit-out, Yarraville | Extra power to kitchenette | 2026-01-21 | 5700 | Approved | Y | Y
V065 | P2530 | Gym fit-out, Preston | Emergency lighting to revised egress | 2026-01-23 | 15950 | Awaiting approval | n/a | n/a
V066 | P2533 | Office fit-out, Oakleigh | Luminaire change to client-selected type | 2026-01-23 | 15300 | Approved | Y | Y
V067 | P2548 | School science block, Essendon | Additional circuits, level 2 fit-out | 2026-02-01 | 13500 | Approved | N | Y
V068 | P2514 | School science block, Richmond | Door access wiring to revised layout | 2026-02-03 | 21800 | Awaiting approval | n/a | n/a
V069 | P2514 | School science block, Richmond | Luminaire change to client-selected type | 2026-02-03 | 8450 | Approved | Y | Y
V070 | P2524 | Childcare centre, Preston | Switchboard upgrade after load review | 2026-02-03 | 15300 | Approved | Y | Y
V071 | P2546 | Showroom refurbishment, Malvern | Additional circuits, level 2 fit-out | 2026-02-04 | 63150 | Approved | Y | Y
V072 | P2519 | Car park lighting and EV, Williamstown | Relocate sub-board after plan change | 2026-02-05 | 5350 | Approved | Y | Y
V073 | P2514 | School science block, Richmond | Extra power to kitchenette | 2026-02-07 | 7850 | Approved | N | Y
V074 | P2548 | School science block, Essendon | Luminaire change to client-selected type | 2026-02-08 | 7550 | Approved | Y | Y
V075 | P2528 | Apartment common areas, Bayswater | Luminaire change to client-selected type | 2026-02-09 | 9300 | Approved | Y | Y
V076 | P2537 | Car park lighting and EV, Ascot Vale | After-hours work to suit tenant | 2026-02-13 | 10850 | Approved | Y | Y
V077 | P2544 | School science block, St Kilda | Relocate sub-board after plan change | 2026-02-15 | 7650 | Rejected | n/a | n/a
V078 | P2549 | Warehouse lighting upgrade, Box Hill | Luminaire change to client-selected type | 2026-02-15 | 17200 | Approved | Y | Y
V079 | P2528 | Apartment common areas, Bayswater | Additional EV charger bays | 2026-02-17 | 16650 | Approved | Y | Y
V080 | P2516 | Showroom refurbishment, Werribee | Relocate sub-board after plan change | 2026-02-20 | 24750 | Awaiting approval | n/a | n/a
V081 | P2545 | Showroom refurbishment, Hawthorn | Switchboard upgrade after load review | 2026-02-22 | 25200 | Approved | Y | Y
V082 | P2542 | Apartment common areas, Moonee Ponds | Emergency lighting to revised egress | 2026-03-02 | 4950 | Approved | Y | Y
V083 | P2514 | School science block, Richmond | Extra data points, tenancy 4 | 2026-03-03 | 10000 | Approved | Y | Y
V084 | P2513 | Aged care wing, St Kilda | After-hours work to suit tenant | 2026-03-04 | 8200 | Approved | Y | Y
V085 | P2527 | Showroom refurbishment, Williamstown | Switchboard upgrade after load review | 2026-03-04 | 18150 | Awaiting approval | n/a | n/a
V086 | P2529 | Apartment common areas, Preston | Door access wiring to revised layout | 2026-03-05 | 3200 | Approved | Y | Y
V087 | P2547 | School science block, Dandenong | Switchboard upgrade after load review | 2026-03-06 | 14450 | Awaiting approval | n/a | n/a
V088 | P2520 | Industrial unit power upgrade, Hawthorn | Door access wiring to revised layout | 2026-03-10 | 15500 | Approved | Y | Y
V089 | P2537 | Car park lighting and EV, Ascot Vale | Door access wiring to revised layout | 2026-03-10 | 10750 | Rejected | n/a | n/a
V090 | P2553 | School science block, Bayswater | Relocate sub-board after plan change | 2026-03-16 | 18950 | Awaiting approval | n/a | n/a
V091 | P2553 | School science block, Bayswater | After-hours work to suit tenant | 2026-03-21 | 30150 | Approved | N | Y
V092 | P2516 | Showroom refurbishment, Werribee | Switchboard upgrade after load review | 2026-03-22 | 28450 | Approved | Y | Y
V093 | P2526 | School science block, Clayton | Emergency lighting to revised egress | 2026-03-22 | 22100 | Rejected | n/a | n/a
V094 | P2532 | Industrial unit power upgrade, Ascot Vale | Switchboard upgrade after load review | 2026-03-23 | 6050 | Approved | Y | Y
V095 | P2533 | Office fit-out, Oakleigh | Switchboard upgrade after load review | 2026-04-05 | 9900 | Rejected | n/a | n/a
V096 | P2511 | Office fit-out, Heidelberg | Emergency lighting to revised egress | 2026-04-07 | 22550 | Rejected | n/a | n/a
V097 | P2536 | Warehouse lighting upgrade, Preston | Relocate sub-board after plan change | 2026-04-07 | 7100 | Approved | Y | Y
V098 | P2532 | Industrial unit power upgrade, Ascot Vale | Emergency lighting to revised egress | 2026-04-14 | 5400 | Approved | Y | Y
V099 | P2544 | School science block, St Kilda | Additional EV charger bays | 2026-04-16 | 8250 | Approved | Y | Y
V100 | P2543 | Retail tenancy fit-out, Yarraville | Door access wiring to revised layout | 2026-04-18 | 6600 | Approved | N | Y
V101 | P2524 | Childcare centre, Preston | Additional circuits, level 2 fit-out | 2026-04-20 | 30150 | Approved | N | Y
V102 | P2511 | Office fit-out, Heidelberg | Door access wiring to revised layout | 2026-04-22 | 7200 | Approved | N | Y
V103 | P2533 | Office fit-out, Oakleigh | Additional EV charger bays | 2026-04-22 | 9500 | Approved | Y | Y
V104 | P2553 | School science block, Bayswater | Additional circuits, level 2 fit-out | 2026-04-23 | 25300 | Awaiting approval | n/a | n/a
V105 | P2524 | Childcare centre, Preston | After-hours work to suit tenant | 2026-05-03 | 20150 | Approved | Y | Y
V106 | P2540 | Aged care wing, Burwood | Luminaire change to client-selected type | 2026-05-03 | 3850 | Awaiting approval | n/a | n/a
V107 | P2514 | School science block, Richmond | Relocate sub-board after plan change | 2026-05-08 | 6850 | Approved | N | Y
V108 | P2553 | School science block, Bayswater | Door access wiring to revised layout | 2026-05-10 | 33300 | Approved | Y | Y
V109 | P2541 | Apartment common areas, Clayton | Additional EV charger bays | 2026-05-17 | 8200 | Approved | Y | Y
V110 | P2546 | Showroom refurbishment, Malvern | After-hours work to suit tenant | 2026-05-20 | 58250 | Approved | Y | Y
V111 | P2523 | Aged care wing, Bayswater | Emergency lighting to revised egress | 2026-05-21 | 7700 | Approved | Y | Y
V112 | P2546 | Showroom refurbishment, Malvern | Door access wiring to revised layout | 2026-05-21 | 62850 | Approved | Y | Y
V113 | P2556 | Office fit-out, Preston West | Additional circuits, level 2 fit-out | 2026-05-22 | 14750 | Approved | N | Y
V114 | P2533 | Office fit-out, Oakleigh | Extra data points, tenancy 4 | 2026-05-23 | 13050 | Approved | Y | Y
V115 | P2514 | School science block, Richmond | Additional circuits, level 2 fit-out | 2026-05-24 | 13600 | Approved | Y | Y
V116 | P2546 | Showroom refurbishment, Malvern | Luminaire change to client-selected type | 2026-06-02 | 49600 | Awaiting approval | n/a | n/a
V117 | P2530 | Gym fit-out, Preston | Luminaire change to client-selected type | 2026-06-04 | 7600 | Approved | Y | Y
V118 | P2519 | Car park lighting and EV, Williamstown | Additional EV charger bays | 2026-06-05 | 7300 | Awaiting approval | n/a | n/a
V119 | P2544 | School science block, St Kilda | Luminaire change to client-selected type | 2026-06-10 | 5650 | Approved | Y | Y
V120 | P2524 | Childcare centre, Preston | Extra data points, tenancy 4 | 2026-06-11 | 12950 | Awaiting approval | n/a | n/a
V121 | P2535 | Office fit-out, Preston | Relocate sub-board after plan change | 2026-06-13 | 2500 | Rejected | n/a | n/a
V122 | P2544 | School science block, St Kilda | Switchboard upgrade after load review | 2026-06-15 | 2550 | Approved | Y | Y
V123 | P2553 | School science block, Bayswater | Emergency lighting to revised egress | 2026-06-16 | 23150 | Rejected | n/a | n/a
V124 | P2547 | School science block, Dandenong | Additional EV charger bays | 2026-06-23 | 6150 | Approved | Y | Y
V125 | P2523 | Aged care wing, Bayswater | Relocate sub-board after plan change | 2026-07-02 | 9850 | Approved | Y | Y
V126 | P2554 | Showroom refurbishment, Reservoir | Extra power to kitchenette | 2026-07-12 | 2500 | Approved | Y | Y
V127 | P2536 | Warehouse lighting upgrade, Preston | Extra data points, tenancy 4 | 2026-07-20 | 3900 | Approved | Y | Y
V128 | P2546 | Showroom refurbishment, Malvern | Relocate sub-board after plan change | 2026-07-23 | 59300 | Approved | Y | Y
V129 | P2553 | School science block, Bayswater | Additional EV charger bays | 2026-07-23 | 27450 | Approved | Y | Y
V130 | P2545 | Showroom refurbishment, Hawthorn | Relocate sub-board after plan change | 2026-08-01 | 11250 | Approved | N | Y
V131 | P2538 | Medical centre electrical, Kew | Additional circuits, level 2 fit-out | 2026-08-02 | 3150 | Awaiting approval | n/a | n/a
V132 | P2556 | Office fit-out, Preston West | Additional EV charger bays | 2026-08-03 | 3900 | Approved | Y | Y
V133 | P2521 | Aged care wing, Coburg | After-hours work to suit tenant | 2026-08-04 | 12150 | Approved | N | Y
V134 | P2526 | School science block, Clayton | Additional EV charger bays | 2026-08-10 | 20850 | Approved | Y | Y
V135 | P2547 | School science block, Dandenong | Extra data points, tenancy 4 | 2026-08-13 | 20450 | Approved | Y | Y
V136 | P2547 | School science block, Dandenong | Additional circuits, level 2 fit-out | 2026-08-14 | 13150 | Approved | N | Y
V137 | P2546 | Showroom refurbishment, Malvern | Extra data points, tenancy 4 | 2026-08-19 | 21200 | Awaiting approval | n/a | n/a
V138 | P2546 | Showroom refurbishment, Malvern | Extra power to kitchenette | 2026-08-21 | 23250 | Approved | Y | Y
V139 | P2538 | Medical centre electrical, Kew | Relocate sub-board after plan change | 2026-09-10 | 4950 | Approved | Y | Y
V140 | P2556 | Office fit-out, Preston West | Relocate sub-board after plan change | 2026-09-24 | 6350 | Approved | Y | Y
Total (follows filters) |  |  |  |  | 2417250

## Retention
Project | Project name | Retention rate | Deducted to date | Released to date | Still held | Project status | Next step
P2511 | Office fit-out, Heidelberg | 5% | 20060.02 | 10030.02 | 10030 | Complete | Second release due 2027-04-25
P2512 | Warehouse lighting upgrade, Northcote | 5% | 11337.51 | 5668.76 | 5668.75 | Complete | Second release due 2027-05-25
P2514 | School science block, Richmond | 5% | 19485.01 | 9742.51 | 9742.5 | Complete | Second release due 2027-06-25
P2515 | Showroom refurbishment, Preston West | 5% | 28757.51 | 14378.76 | 14378.75 | Complete | Second release due 2026-12-25
P2516 | Showroom refurbishment, Werribee | 5% | 63802.52 | 31901.27 | 31901.25 | Complete | Second release due 2027-03-25
P2517 | Aged care wing, Essendon | 5% | 25870.01 | 12935.01 | 12935 | Complete | Second release due 2027-01-25
P2518 | Car park lighting and EV, Heidelberg | 5% | 17342.5 | 8671.25 | 8671.25 | Complete | Second release due 2026-11-25
P2519 | Car park lighting and EV, Williamstown | 5% | 11952.52 | 5976.27 | 5976.25 | Complete | Second release due 2027-07-25
P2522 | Car park lighting and EV, Oakleigh | 5% | 10565.01 | 5282.51 | 5282.5 | Complete | Second release due 2027-02-25
P2524 | Childcare centre, Preston | 5% | 28382.51 | 14191.26 | 14191.25 | Complete | Second release due 2027-06-25
P2525 | Medical centre electrical, Mentone | 5% | 21092.5 | 10546.25 | 10546.25 | Complete | Second release due 2026-12-25
P2526 | School science block, Clayton | 5% | 20429.3 | 0 | 20429.3 | Live | Held until practical completion
P2527 | Showroom refurbishment, Williamstown | 5% | 15640.02 | 7820.02 | 7820 | Complete | Second release due 2027-07-25
P2530 | Gym fit-out, Preston | 5% | 18755.02 | 9377.52 | 9377.5 | Complete | Second release due 2027-06-25
P2531 | Industrial unit power upgrade, Abbotsford | 5% | 14850 | 7425 | 7425 | Complete | Second release due 2027-02-25
P2532 | Industrial unit power upgrade, Ascot Vale | 5% | 18342.53 | 9171.28 | 9171.25 | Complete | Second release due 2027-06-25
P2533 | Office fit-out, Oakleigh | 5% | 23912.51 | 11956.26 | 11956.25 | Complete | Second release due 2027-05-25
P2534 | Retail tenancy fit-out, Bayswater | 5% | 11120 | 5560 | 5560 | Complete | Second release due 2027-09-25
P2541 | Apartment common areas, Clayton | 5% | 15550.04 | 0 | 15550.04 | Live | Held until practical completion
P2548 | School science block, Essendon | 5% | 12570.59 | 0 | 12570.59 | Live | Held until practical completion
P2553 | School science block, Bayswater | 5% | 27650.52 | 0 | 27650.52 | Live | Held until practical completion
P2556 | Office fit-out, Preston West | 5% | 11260.02 | 0 | 11260.02 | Live | Held until practical completion
Total (follows filters) |  |  | 448728.17 | 180633.95 | 268094.22

## Xero tie-out
Month | Approved claims | Net (ex GST) | GST | simPRO total (inc GST) | Xero total (inc GST) | Difference | Retention held at month end | Check: net + GST = total
2025-10-01 | 24 | 1059340.73 | 105934.09 | 1165274.82 | 1165274.82 | 0 | 187996.11 | OK
2025-11-01 | 45 | 1386077.48 | 138607.81 | 1524685.29 | 1524685.29 | 0 | 232360.63 | OK
2025-12-01 | 43 | 1353846.21 | 135384.67 | 1489230.88 | 1489230.88 | 0 | 261928.42 | OK
2026-01-01 | 50 | 1019244.79 | 101924.51 | 1121169.3 | 1121169.3 | 0 | 284383.28 | OK
2026-02-01 | 60 | 954021.76 | 95402.25 | 1049424.01 | 1049424.01 | 0 | 291349.87 | OK
2026-03-01 | 59 | 895424.52 | 89542.56 | 984967.08 | 984967.08 | 0 | 273232.75 | OK
2026-04-01 | 46 | 799793.68 | 79979.43 | 879773.11 | 879773.11 | 0 | 276167.02 | OK
2026-05-01 | 54 | 1006003.66 | 100600.44 | 1106604.1 | 1106604.1 | 0 | 278194.91 | OK
2026-06-01 | 48 | 1102417.55 | 110241.85 | 1212659.4 | 1212659.4 | 0 | 257399.61 | OK
2026-07-01 | 40 | 971610.84 | 97161.11 | 1068771.95 | 1068771.95 | 0 | 260005.72 | OK
2026-08-01 | 32 | 644962.48 | 64496.27 | 709458.75 | 709458.75 | 0 | 269363.59 | OK
2026-09-01 | 19 | 274261.47 | 27426.16 | 301687.63 | 301687.63 | 0 | 268094.22 | OK
Total (follows filters) | 520 | 11467005.17 | 1146701.15 | 12613706.32 | 12613706.32 | 0

## WIP 30 Sep 2026
Project | Project name | Contract + approved variations | Cost to date | Forecast cost to complete | % complete (cost to cost) | Earned revenue | Billed to date (ex GST) | Over / (under) billed | Forecast margin | Retention held | Billed less retention held (net invoiced in Xero)
P2526 | School science block, Clayton | 428000 | 325216.92 | 11367.96 | 96.62% | 413544.55 | 408585 | -4959.55 | 21.36% | 20429.3 | 388155.7
P2536 | Warehouse lighting upgrade, Preston | 275950 | 232053.23 | 6122.28 | 97.43% | 268856.73 | 256222.95 | -12633.78 | 13.69% | 0 | 256222.95
P2539 | Retail tenancy fit-out, Carlton | 256000 | 188201.12 | 16935.64 | 91.74% | 234865.2 | 232256 | -2609.2 | 19.87% | 0 | 232256
P2541 | Apartment common areas, Clayton | 327900 | 247143.84 | 11865.14 | 95.42% | 312878.98 | 311000.75 | -1878.23 | 21.01% | 15550.04 | 295450.71
P2542 | Apartment common areas, Moonee Ponds | 100850 | 78633.21 | 4041.83 | 95.11% | 95919.63 | 93705.8 | -2213.83 | 18.02% | 0 | 93705.8
P2545 | Showroom refurbishment, Hawthorn | 471850 | 377961.28 | 21434.28 | 94.63% | 446527.32 | 429398.5 | -17128.82 | 15.36% | 0 | 429398.5
P2546 | Showroom refurbishment, Malvern | 1246800 | 951616.07 | 91969.68 | 91.19% | 1136921.35 | 1148458.2 | 11536.85 | 16.3% | 0 | 1148458.2
P2547 | School science block, Dandenong | 399950 | 325602.66 | 7422.78 | 97.77% | 391035.54 | 372484.75 | -18550.79 | 16.73% | 0 | 372484.75
P2548 | School science block, Essendon | 271100 | 203563.25 | 21895.73 | 90.29% | 244771.79 | 251411.8 | 6640.01 | 16.84% | 12570.59 | 238841.21
P2549 | Warehouse lighting upgrade, Box Hill | 395700 | 250967.58 | 62753.14 | 80% | 316548.65 | 304816.95 | -11731.7 | 20.72% | 0 | 304816.95
P2550 | Warehouse lighting upgrade, Fitzroy | 65500 | 51507.72 | 1507.04 | 97.16% | 63638.04 | 59113.75 | -4524.29 | 19.06% | 0 | 59113.75
P2551 | Warehouse lighting upgrade, Reservoir | 90650 | 76255 | 2715.5 | 96.56% | 87532.89 | 80633.45 | -6899.44 | 12.88% | 0 | 80633.45
P2552 | Aged care wing, Hawthorn | 113800 | 93605.07 | 6145.52 | 93.84% | 106788.91 | 104326.15 | -2462.76 | 12.35% | 0 | 104326.15
P2553 | School science block, Bayswater | 597600 | 475964 | 47910.84 | 90.85% | 542946.64 | 553010.4 | 10063.76 | 12.34% | 27650.52 | 525359.88
P2554 | Showroom refurbishment, Reservoir | 140100 | 106991.45 | 12590.42 | 89.47% | 125349.29 | 127337.6 | 1988.31 | 14.65% | 0 | 127337.6
P2555 | Gym fit-out, Camberwell | 101800 | 60889 | 20721.57 | 74.61% | 75952.17 | 81414.9 | 5462.73 | 19.83% | 0 | 81414.9
P2556 | Office fit-out, Preston West | 245700 | 168698.82 | 19786.2 | 89.5% | 219907.66 | 225200.05 | 5292.39 | 23.29% | 11260.02 | 213940.03
Total (follows filters) |  | 5529250 | 4214870.22 | 367185.55 |  | 5083985.34 | 5039377 | -44608.34 |  | 87460.47

## WIP by month
Month end | Projects open | Contract + approved variations | Billed to date | Earned revenue | Over-billed | Under-billed | Net over / (under) | Check: billed - earned = net
2025-10-31 | 26 | 8696700 | 4277864.45 | 4387786 | 58814.4 | -168735.95 | -109921.55 | OK
2025-11-30 | 28 | 9112200 | 5361456.45 | 5488058.72 | 46370.7 | -172972.97 | -126602.27 | OK
2025-12-31 | 33 | 10707600 | 5747870.45 | 5885893.09 | 46687.18 | -184709.82 | -138022.64 | OK
2026-01-31 | 37 | 11452650 | 6272170.1 | 6447592.25 | 46060.97 | -221483.12 | -175422.15 | OK
2026-02-28 | 37 | 11492550 | 6314608.45 | 6485286.94 | 47184.95 | -217863.44 | -170678.49 | OK
2026-03-31 | 35 | 10179050 | 5670115.85 | 5787016.91 | 60099.35 | -177000.41 | -116901.06 | OK
2026-04-30 | 35 | 10072750 | 6071643.8 | 6205468.31 | 44789.35 | -178613.86 | -133824.51 | OK
2026-05-31 | 33 | 9606450 | 6374675.35 | 6493117.73 | 54004.59 | -172446.97 | -118442.38 | OK
2026-06-30 | 27 | 7684250 | 5512147.6 | 5596932.97 | 52975.36 | -137760.73 | -84785.37 | OK
2026-07-31 | 23 | 6777850 | 5476964.55 | 5531244.37 | 53975.73 | -108255.55 | -54279.82 | OK
2026-08-31 | 19 | 5825900 | 5074334.9 | 5125787.79 | 39658.57 | -91111.46 | -51452.89 | OK
2026-09-30 | 17 | 5529250 | 5039377 | 5083985.34 | 40984.05 | -85592.39 | -44608.34 | OK

## Cost centre list
Cost centre | Xero revenue account (example) | Typical claim basis
Site establishment and temporary power | 4010 Contract revenue: preliminaries | Claimed early, usually 100% by the second claim
Switchboards and metering | 4020 Contract revenue: switchboards | Percentage as boards are built and installed
Containment and cabling | 4030 Contract revenue: containment and cabling | Percentage by level or area
Lighting and emergency lighting | 4040 Contract revenue: lighting | Percentage by level or area
Power and data outlets | 4050 Contract revenue: power and data | Percentage by level or area
Mechanical services wiring | 4060 Contract revenue: mechanical wiring | Percentage as equipment is connected
Fire detection interface | 4070 Contract revenue: fire interface | Percentage, balance on sign-off
Testing and commissioning | 4080 Contract revenue: testing | Held back to the end of the project
Variations | 4090 Contract revenue: variations | Claimed once approved